## 2023-05
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000001 | Project Quality Plan | "Project Quality Plan" | 2023-05-15 | 2023-12-05 |  |  | Soe Myat | 1 | 2
000002 | Project Risk Management Plan | "Project Risk Management Plan" | 2023-05-15 | 2023-06-14 |  |  | Shena | 0 | 1
000003 | BIM Execution Plan (BEP) | "BIM Execution Plan (BEP)" | 2023-05-16 | 2023-07-03 |  |  | Heng Peng | 0 | 1
000004 | Project HSE Plan | "Project HSE Plan" | 2023-05-16 | 2023-07-24 |  |  | Kristnnan | 1 | 2
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2023-05-17 | 2023-06-14 |  |  | Thomas | 1 | 2
000006 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" | 2023-05-17 | 2023-06-12 |  |  | Keith | 1 | 2
000007 | MOBILIZATION PROGRAMME | "MOBILIZATION PROGRAMME " | 2023-05-18 | 2023-06-13 |  |  | Thomas | 0 | 1
000008 | Engineering Deliverable Lists | "Engineering Deliverable Lists" | 2023-05-18 | 2023-11-21 |  |  | Frank/ Franklin | 1 | 2
000009 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | 2023-05-19 | 2023-06-12 |  |  | Keith | 1 | 2
000010 | Vendor Approval for CSA Consultant QP (Tenwit) | "Vendor Approval for CSA Consultant QP (Tenwit)" | 2023-05-19 | 2023-06-12 |  |  | Zora | 0 | 1
000011 | Vendor Approval for Temp ERSS QPD,QPS (Tenwit ) | "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-19 | 2023-06-12 |  |  | Zora | 0 | 1
000012 | Vendor Approval for QECP Consultant (Tenwit ) | "Vendor Approval for QECP Consultant (Tenwit )" | 2023-05-19 | 2023-06-14 |  |  | Zora | 1 | 2
000013 | Vendor Approval for M&E QP (C2D Solutions Pte. LTD ) | "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" | 2023-05-21 | 2024-03-18 |  |  | Freedomer | 0 | 1
000014 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | 2023-06-12 |  |  | Zora | 2 | 3
000015 | CSA Meeting Minutes 0001 | "CSA Meeting Minutes 0001" | 2023-05-23 | 2023-06-12 |  |  | Zora | 0 | 1
000016 | FRP TANK DATA SHEET | "FRP TANK DATA SHEET" | 2023-05-26 | 2023-10-16 |  |  | David | 0 | 1
000017 | CVs of Team Member | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | 2023-05-27 | 2023-06-27 |  |  | Shena | 1 | 2
000018 | Title Block Template (CAD) | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | 2023-05-31 | 2023-06-06 |  |  | REY | 0 | 5
000019 | Vendor Approval for Cable Dectector (JLCD) | "Vendor Approval for Cable Dectector (JLCD)" | 2023-05-31 | 2023-06-16 |  |  | Keith | 1 | 2

## 2023-06
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000006 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" | 2023-06-23 | 2023-06-30 |  |  | Keith | 1 | 2
000012 | Vendor Approval for QECP Consultant (Tenwit ) | "Vendor Approval for QECP Consultant (Tenwit )" | 2023-06-23 | 2023-07-24 |  |  | Zora | 1 | 2
000014 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-06-23 | 2023-07-12 |  |  | Zora | 2 | 3
000018 | Title Block Template (CAD) | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | 2023-06-06 | 2023-06-23 |  |  | REY | 0 | 5
000018 | Title Block Template (CAD) | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | 2023-06-27 | 2023-07-03 |  |  | REY | 0 | 5
000019 | Vendor Approval for Cable Dectector (JLCD) | "Vendor Approval for Cable Dectector (JLCD)" | 2023-06-23 | 2023-06-30 |  |  | Keith | 1 | 2
000020 | HSE Stickers for Machineries and SIC Induction | "HSE Stickers for Machineries and SIC Induction" | 2023-06-05 | 2023-06-14 |  |  | Kristnnan | 0 | 1
000021 | Process & MEICA Meeting Minutes 0001 | "Process & MEICA Meeting Minutes 0001" | 2023-06-11 | 2023-10-18 |  |  | Qili | 0 | 1
000022 | Process & MEICA Meeting Minutes 0002 | "Process & MEICA Meeting Minutes 0002" | 2023-06-11 | 2024-03-18 |  |  | Qili | 0 | 1
000023 | Process & MEICA Meeting Minutes 0003 | "Process & MEICA Meeting Minutes 0003" | 2023-06-11 | 2024-03-18 |  |  | Qili | 0 | 1
000024 | Process & MEICA Meeting Minutes 0004 | "Process & MEICA Meeting Minutes 0004" | 2023-06-11 | 2024-03-18 |  |  | Qili | 0 | 1
000025 | CVs of Team Member | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | 2023-06-12 | 2023-06-20 |  |  | Shena | 1 | 2
000026 | Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD) | "Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD)" | 2023-06-13 | 2023-06-29 |  |  | Bryan | 0 | 1
000027 | C4B Monthly Progress Report Number No.01 (05/23) | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | 2023-06-16 |  |  | Thomas | 2 | 3
000028 | Vendor Approval for THP Package | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | 2023-06-14 | 2023-07-14 |  |  | Joo Kwan | 4 | 5
000029 | CSA Meeting Minutes 0002 | "CSA Meeting Minutes 0002" | 2023-06-16 | 2023-06-28 |  |  | Zora | 0 | 1
000030 | CSA Meeting Minutes 0003 | "CSA Meeting Minutes 0003" | 2023-06-16 | 2023-06-28 |  |  | Zora | 0 | 1
000031 | Engineering Kick Off Meeting Minutes 0001 | "Engineering Kick Off Meeting Minutes 0001" | 2023-06-19 | 2024-03-18 |  |  | Zora | 0 | 1
000032 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | 2023-06-19 | 2023-06-29 |  |  | Anuar | 1 | 2
000033 | C4B HSE Induction Course | "C4B HSE Induction Course" | 2023-06-20 | 2023-07-24 |  |  | Kristnnan | 0 | 1
000034 | Emergency Response Plan | "Emergency Response Plan" | 2023-06-21 | 2023-08-02 |  |  | Kristnnan | 1 | 2
000035 | Project Accident Statistic Board and BCA Board | "Project Accident Statistic Board and BCA Board" | 2023-06-22 | 2023-08-18 |  |  | Kristnnan | 0 | 1
000036 | CSA Meeting Minutes 0004_20230614 | "CSA Meeting Minutes 0004_20230614" | 2023-06-28 | 2023-07-12 |  |  | Zora | 0 | 1
000037 | BIM Bi-Weekly Meeting Minutes 0001_20230614 | "BIM Bi-Weekly Meeting Minutes 0001_20230614" | 2023-06-28 | 2023-07-04 |  |  | Heng Peng | 0 | 1

## 2023-07
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2023-07-13 | 2023-07-31 |  |  | Thomas | 1 | 2
000009 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | 2023-07-03 | 2023-07-12 |  |  | Keith | 1 | 2
000014 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-07-31 | 2023-08-11 |  |  | Zora | 2 | 3
000017 | CVs of Team Member Part 1 (14 Members) | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | 2023-07-12 | 2023-07-25 |  |  | Shena | 1 | 2
000018 | Title Block Template (CAD) | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | 2023-07-04 | 2023-07-03 |  |  | REY | 0 | 5
000025 | CVs of Team Member Part 2 (7 Members) | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | 2023-07-12 | 2023-07-25 |  |  | Shena | 1 | 2
000027 | C4B Monthly Progress Report Number No.01 (05/23) | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-07-04 | 2023-07-13 |  |  | Thomas | 2 | 3
000027 | C4B Monthly Progress Report Number No.01 (05/23) | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-07-14 | 2023-10-18 |  |  | Thomas | 2 | 3
000028 | Vendor Approval for THP Package | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | 2023-07-28 | 2023-08-01 |  |  | Joo Kwan | 4 | 5
000038 | Temporary Utilities for Contractor’s Site Office | "Temporary Utilities for Contractor’s Site Office" | 2023-07-05 | 2023-07-21 |  |  | Yuen Fatt | 0 | 1
000039 | MI-Process & MEICA Meeting Minutes with THP (CAMBI) | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" | 2023-07-05 | 2024-03-18 |  |  | Joo Kwan | 0 | 1
000040 | Request for time extension_Programme of works resubmission | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | 2023-07-06 | 2023-09-22 |  |  | Stanley | 0 | 2
000041 | CSA Meeting Minutes 0004_20230614 | "CSA Meeting Minutes 0004_20230614" | 2023-07-06 | 2023-10-18 |  |  | Zora | 0 | 1
000042 | CVs of Team Members (Part 3) | "CVs of Team Members (Part 3)" | 2023-07-06 | 2023-08-21 |  |  | Shena | 0 | 1
000043 | Presentation Slide for Monthly Progress Meeting No. 01(0523) | "Presentation Slide for Monthly Progress Meeting No. 01(0523)" | 2023-07-07 | 2023-07-13 |  |  | Thomas | 0 | 1
000044 | CVs of Team Members (Part 4) | "CVs of Team Members (Part 4)" | 2023-07-07 | 2023-07-24 |  |  | Shena | 0 | 1
000045 | SITE UTILIZATION PLAN | "SITE UTILIZATION PLAN" | 2023-07-10 | 2023-07-21 |  |  | Edwin | 0 | 1
000045 | SITE OFFICE LAYOUT (Rev1) | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | 2023-07-10 | 2023-07-21 |  |  | Edwin | 1 | 2
000045 | SITE OFFICE LAYOUT (Rev2) | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | 2023-07-26 | 2023-08-02 |  |  | Edwin | 1 | 2
000046 | C4B Monthly Progress Report Number No.02 (06/23) | "C4B Monthly Progress Report Number No.02 (06/23)" | 2023-07-12 | 2023-07-14 |  |  | Thomas | 1 | 2
000046 | C4B Monthly Progress Report Number No.02 (06/23) | "C4B Monthly Progress Report Number No.02 (06/23)" | 2023-07-14 | 2023-10-18 |  |  | Thomas | 1 | 2
000047 | BIM Bi-Weekly Meeting Minutes 0002_20230628 | "BIM Bi-Weekly Meeting Minutes 0002_20230628" | 2023-07-13 | 2023-07-24 |  |  | Heng Peng | 0 | 1
000048 | BS Meeting Minutes 0001_20230706 | "BS Meeting Minutes 0001_20230706" | 2023-07-14 | 2024-02-15 |  |  | Matthew | 0 | 1
000049 | C4B Manpower Deployment Plan | "C4B Manpower Deployment Plan" | 2023-07-14 | 2023-07-24 |  |  | Yi Hao | 0 | 1
000050 | CSA Meeting Minutes 0004_20230705 | "CSA Meeting Minutes 0004_20230705" | 2023-07-14 | 2023-07-24 |  |  | Zora | 0 | 1
000051 | Drawing of Pre-Con Topographical Survey | "Drawing of Pre-Con Topographical Survey" | 2023-07-18 | 2023-08-11 |  |  | REY | 0 | 1
000052 | BIM Bi-Weekly Meeting Minutes 0003_20230712 | "BIM Bi-Weekly Meeting Minutes 0003_20230712" | 2023-07-18 | 2023-07-25 |  |  | Heng Peng | 0 | 1
000053 | CV of Team Member (BIM Authoring Lead) | "CV of Team Member (BIM Authoring Lead)" | 2023-07-19 | 2023-10-23 |  |  | Heng Peng | 1 | 2
000054 | CSA Meeting Minutes 0007_20230712 | "CSA Meeting Minutes 0007_20230712" | 2023-07-24 | 2023-08-10 |  |  | Zora | 0 | 1
000055 | PROGRESS CLAIM NO.1 | "PROGRESS CLAIM NO.1" | 2023-07-24 | 2023-08-30 |  |  | Yi Hao | 0 | 1
000056 | Signboard Sticker for TWRP Main Gate route 3 entrance | "Signboard Sticker for TWRP Main Gate route 3 entrance" | 2023-07-27 | 2023-08-02 |  |  | Dharmen | 0 | 1
000057 | Presentation Slide for Monthly Progress Meeting No. 02(0623) | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" | 2023-07-28 | 2023-08-01 |  |  | Thomas | 0 | 1
000058 | MSRA, SWP for General Civil Works | "MSRA, SWP for General Civil Works" | 2023-07-28 | 2023-08-14 |  |  | Dharmen | 3 | 4

## 2023-08
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000003 | BIM Execution Plan (BEP) | "BIM Execution Plan (BEP)" | 2023-08-21 | 2023-10-20 |  |  | Heng Peng | 5 | 5
000028 | Preliminary design and Vendor Approval | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | 2023-08-02 | 2023-08-31 |  |  | Joo Kwan | 4 | 5
000059 | Vendor Approval of Concrete Supplier-Alliance | "Vendor Approval of Concrete Supplier-Alliance" | 2023-08-01 | 2023-08-10 |  |  | Zora | 0 | 1
000060 | Adjustment of Stage Payment | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | 2023-08-01 | 2023-08-02 |  |  | Yi Hao | 0 | 2
000060 | Adjustment of Stage Payment | "Adjustment of Stage Payment" | 2023-08-02 | 2023-09-15 |  |  | Yi Hao | 0 | 1
000061 | CV of Team Member (CM) | "CV of Team Member (CM)" | 2023-08-03 | 2023-08-11 |  |  | Shena | 0 | 1
000062 | Request for Variable Site Management Team Payment | "Request for Variable Site Management Team Payment" | 2023-08-03 | 2024-01-30 |  |  | Shena | 0 | 1
000063 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" | 2023-08-07 | 2023-08-11 |  |  | Zora | 0 | 1
000063 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" | 2023-08-07 | 2023-08-11 |  |  | Zora | 0 | 1
000064 | Vendor Approval of Concrete Supplier-Pan United | "Vendor Approval of Concrete Supplier-Pan United" | 2023-08-08 | 2023-08-30 |  |  | Zora | 1 | 2
000065 | RFC For HV Routing (from C3B1) to SSN Transformer Room | "RFC For HV Routing (from C3B1) to SSN Transformer Room" | 2023-08-08 | 2024-02-15 |  |  | Freedomer | 0 | 1
000066 | Submission Of BIM Coordination VCM Model (July – 2023) | "Submission Of BIM Coordination VCM Model (July – 2023)" | 2023-08-08 | 2023-08-24 |  |  | Heng Peng | 0 | 1
000067 | Vendor Approval of Rebar Supplier-BRC ASIA LIMITED | "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" | 2023-08-11 | 2023-08-30 |  |  | Zora | 0 | 1
000068 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-08-14 | 2024-03-18 |  |  | Qili | 0 | 1
000068 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-08-14 | 2024-03-18 |  |  | Qili | 0 | 1
000069 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | 2023-08-14 | 2024-03-18 |  |  | Qili | 0 | 1
000069 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | 2023-08-14 | 2024-03-18 |  |  | Qili | 0 | 1
000070 | C4B Monthly Progress Report Number No.03 (07/23) | "C4B Monthly Progress Report Number No.03 (07/23)" | 2023-08-14 | 2023-08-29 |  |  | Thomas | 1 | 2
000071 | Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd. | "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." | 2023-08-15 | 2023-08-30 |  |  | Edwin | 0 | 1
000072 | Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd. | "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | 2023-08-30 |  |  | Edwin | 0 | 1
000073 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" | 2023-08-15 | 2023-08-21 |  |  | Heng Peng | 0 | 1
000073 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" | 2023-08-15 | 2023-08-21 |  |  | Heng Peng | 0 | 1
000074 | Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd | "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" | 2023-08-16 | 2023-08-30 |  |  | Zora | 0 | 1
000075 | CV of Team Member (WSHC) | "CV of Team Member (WSHC)" | 2023-08-22 | 2023-09-25 |  |  | Shena | 0 | 1
000076 | Delegation of Signing Authorities | "Delegation of Signing Authorities" | 2023-08-22 | 2023-09-25 |  |  | Keith | 0 | 1
000077 | Presentation Slide for Monthly Progress Meeting No. 03(0723) | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" | 2023-08-28 | 2023-08-24 |  |  | Thomas | 0 | 1
000078 | Photographic Survey Report for C4B | "Photographic Survey Report for C4B" | 2023-08-24 | 2023-08-30 |  |  | Yuen Fatt | 0 | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-08-31 |  |  | Zora | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-09-07 |  |  | Zora | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-09-07 |  |  | Zora | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-09-07 |  |  | Zora | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-09-07 |  |  | Zora | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-09-07 |  |  | Zora | A1 | 3
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | 2023-09-07 |  |  | Zora | A1 | 3
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-08-24 | 2023-09-07 |  |  | Zora | B1 | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-08-24 | 2023-09-07 |  |  | Zora | B | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-08-24 | 2023-09-07 |  |  | Zora | B | 5
000080 | PAYMENT CLAIM NO.2 | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | 2023-08-25 | 2023-08-30 |  |  | Yi Hao | 0 | 2
000081 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | 2023-08-28 | 2023-09-25 |  |  | Zora | 1 | 2
000082 | BIM Bi-Weekly Meeting Minutes 0006_20230823 | "BIM Bi-Weekly Meeting Minutes 0006_20230823" | 2023-08-28 | 2023-09-06 |  |  | Heng Peng | 0 | 1
000083 | Sidewide Pipe Rack GA and Reactions | "Sidewide Pipe Rack GA and Reactions" | 2023-08-28 | 2023-10-06 |  |  | Zora | 0 | 1
000084 | Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd. | "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | 2023-09-25 |  |  | Zora | 0 | 1
000085 | Concrete Design Mix for ULT Test Pile C50/60 (Alliance) | "Concrete Design Mix for ULT Test Pile C50/60 (Alliance) " | 2023-08-31 | 2023-09-25 |  |  | Zora | 0 | 1
000086 | ECM Plan and Calculation | "ECM Plan and Calculation" | 2023-08-31 | 2023-10-04 |  |  | Yuen Fatt | 0 | 1

## 2023-09
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000002 | Project Risk Management Plan | "Project Risk Management Plan" | 2023-09-05 | 2023-09-13 |  |  | Max/Edwin | 2 | 2
000002 | Project Risk Management Plan | "Project Risk Management Plan" | 2023-09-05 | 2023-09-13 |  |  | Max/Edwin | NA | 1
000004 | Project HSE Plan | "Project HSE Plan" | 2023-09-27 | 2023-10-04 |  |  | Dharmen | 1 | 2
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2023-09-07 | 2023-09-18 |  |  | Thomas | 5.1 | 5
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | 2023-09-26 | 2023-10-03 |  |  | Thomas | 0 | 2
000007 | MOBILIZATION PROGRAMME | "MOBILIZATION PROGRAMME " | 2023-09-13 | 2023-09-20 |  |  | Thomas | NA | 1
000017 | CVs of Team Member Part 1 (14 Members) | "CVs of Team Member Part 1 (14 Members)" | 2023-09-04 | 2023-10-10 |  |  | Shena/ Htet | 2 | 1
000025 | CVs of Team Member Part 2 (7 Members) | "CVs of Team Member Part 2 (7 Members)" | 2023-09-11 | 2024-09-10 |  |  | Shena/ Htet | NA | 1
000034 | Emergency Response Plan | "Emergency Response Plan" | 2023-09-07 | 2023-09-25 |  |  | Dharmen | 1 | 2
000042 | CVs of Team Members (Part 3) | "CVs of Team Members (Part 3)" | 2023-09-04 | 2024-02-01 |  |  | Shena/ Htet | NA | 1
000064 | Vendor Approval of Concrete Supplier-Pan United | "Vendor Approval of Concrete Supplier-Pan United" | 2023-09-22 | 2023-09-25 |  |  | Zora | 1 | 2
000070 | C4B Monthly Progress Report Number No.03 (07/23) | "C4B Monthly Progress Report Number No.03 (07/23)" | 2023-09-25 | 2023-09-27 |  |  | Thomas | 1 | 2
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | 2023-10-17 |  |  | Zora | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | 2023-10-17 |  |  | Zora | 0 | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-09-26 | 2023-10-17 |  |  | Zora | B1 | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-09-26 | 2023-10-17 |  |  | Zora | B | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-09-26 | 2023-10-17 |  |  | Zora | B | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | 2023-10-17 |  |  | Zora | A1 | 3
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | 2023-10-17 |  |  | Zora | A1 | 3
000087 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-09-04 | 2023-09-06 |  |  | Thomas | 0 | 1
000087 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-09-04 | 2023-09-06 |  |  | Thomas | 0 | 1
000088 | Preliminary design and Vendor Approval for SSN Package | "Preliminary design and Vendor Approval for SSN Package" | 2023-09-05 | 2023-09-25 |  |  | Qili | 3 | 4
000089 | Process & MEICA Meeting Minutes 0007_20230718 | "Process & MEICA Meeting Minutes 0007_20230718" | 2023-09-05 | 2024-03-18 |  |  | Qili | 0 | 1
000090 | Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq) | "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | 2023-09-25 |  |  | Qili | 0 | 1
000091 | Cable Detection Report | "Cable Detection Report" | 2023-09-07 | 2023-09-25 |  |  | Yuen Fatt | 0 | 1
000092 | Piping Material Specification | "Piping Material Specification" | 2023-09-08 | 2023-09-25 |  |  | Liying | 3 | 4
000093 | Piperack P&IDs | "Piperack P&IDs" | 2023-09-08 | 2023-11-27 |  |  | Qili | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2023-09-08 | 2023-11-27 |  |  | Qili | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2023-09-08 | 2023-11-27 |  |  | Qili | NA | 1
000094 | Submission Of BIM Coordination VCM Model (Aug – 2023) | "Submission Of BIM Coordination VCM Model (Aug – 2023)" | 2023-09-08 | 2023-09-21 |  |  | Heng Peng | 0 | 1
000095 | BIM Bi-Weekly Meeting Minutes 0007_20230906 | "BIM Bi-Weekly Meeting Minutes 0007_20230906" | 2023-09-11 | 2023-10-03 |  |  | Heng Peng | 0 | 1
000096 | Engineering Calculation Report For Fire Hydrant Pipe | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" | 2023-09-12 | 2023-11-10 |  |  | Darren | 1 | 2
000097 | Engineering Calculation Report For Potable Water Pipe | "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" | 2023-09-12 | 2023-11-10 |  |  | Kyaw Myo | 1 | 2
000098 | C4B Monthly Progress Report Number No.04 (08/23) | "C4B Monthly Progress Report Number No.04 (08/23)" | 2023-09-13 | 2023-09-20 |  |  | Thomas | 1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | 2023-11-27 |  |  | Kyaw Myo | A1 | 2
000100 | Unpriced PO for THP Package (Cambi) | "Unpriced PO for THP Package (Cambi)" | 2023-09-14 | 2023-11-27 |  |  | Joo Kwan | 0 | 1
000101 | Heat Stress Prevention Program | "Heat Stress Prevention Program" | 2023-09-14 | 2023-09-25 |  |  | Dharmen | 0 | 1
000102 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" | 2023-09-18 | 2023-11-21 |  |  | Yibo | 2 | 3
000103 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" | 2023-09-18 | 2023-11-21 |  |  | David | 1 | 2
000104 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-09-19 | 2024-03-18 |  |  | Qili | 0 | 1
000104 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-09-19 | 2024-03-18 |  |  | Qili | 0 | 1
000105 | CV of Team Member (WSHO) | "CV of Team Member (WSHO)" | 2023-09-19 | 2023-10-18 |  |  | Shena | 0 | 1
000106 | Monthly Progress Presentation No. 04 (0823) | "Monthly Progress Presentation No. 04 (0823)" | 2023-09-21 | 2023-09-25 |  |  | Thomas | 0 | 1
000107 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" | 2023-09-25 | 2023-10-16 |  |  | David | 1 | 2
000108 | On-Demand Bond for THP System | "On-Demand Bond for THP System" | 2023-09-27 | 2023-10-02 |  |  | Yi Hao | 0 | 2
000109 | CSA Meeting Minutes 0010_20230802 | "CSA Meeting Minutes 0010_20230802" | 2023-09-27 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2023-09-29 | 2023-10-18 |  |  | Zora | C | 2
000110 | ST606 : SSN Overall Sub-Structure Drawings | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | 2023-10-18 |  |  | Zora | 0 | 1
000111 | PAYMENT CLAIM NO.3 | "PAYMENT CLAIM NO.3" | 2023-09-29 | 2023-10-23 |  |  | Yi Hao | 0 | 1
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | 0 | 1
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | 0 | 1
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | A | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | NA | 1
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | NA | 1
000112 | SSN URA Submission | "SSN URA Submission" | 2023-09-29 | 2023-10-17 |  |  | Zora | NA | 1

## 2023-10
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000002 | Project Risk Management Plan | "Project Risk Management Plan" | 2023-10-30 | 2023-11-07 |  |  | Max | 2 | 2
000002 | Project Risk Management Plan | "Project Risk Management Plan" | 2023-10-30 | 2023-11-07 |  |  | Max | NA | 1
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2023-10-27 | 2023-11-14 |  |  | Krishanthy | 5.1 | 5
000035 | Project Accident Statistic Board and BCA Board | "Project Accident Statistic Board and BCA Board" | 2023-10-13 | 2023-10-23 |  |  | Dharmen | 1 | 1
000060 | Adjustment of Stage Payment | "Adjustment of Stage Payment" | 2023-10-18 | 2023-12-18 |  |  | Yi Hao | 0 | 1
000081 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | 2023-10-05 | 2023-10-18 |  |  | Zora | 1 | 2
000088 | Preliminary design and Vendor Approval for SSN Package | "Preliminary design and Vendor Approval for SSN Package" | 2023-10-05 | 2023-10-23 |  |  | Qili | 3 | 4
000088 | Preliminary design and Vendor Approval for SSN Package | "Preliminary design and Vendor Approval for SSN Package" | 2023-10-31 | 2023-11-08 |  |  | Qili | 3 | 4
000091 | Cable Detection Report | "Cable Detection Report" | 2023-10-06 | 2023-10-18 |  |  | Eng Bee | NA | 1
000098 | C4B Monthly Progress Report Number No.04 (08/23) | "C4B Monthly Progress Report Number No.04 (08/23)" | 2023-10-04 | 2023-10-06 |  |  | Thomas | 1 | 2
000108 | On-Demand Bond for THP System | "On-Demand Bond for THP System" | 2023-10-03 | 2023-10-09 |  |  | Yi Hao | 0 | 2
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 2
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 2
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | A1 | 1
000112 | SSN URA Submission | "SSN URA Submission" | 2023-10-17 | 2023-11-01 |  |  | Zora | NA | 1
000113 | MSRA, SWP for Soil Resistivity Test | "MSRA, SWP for Soil Resistivity Test" | 2023-10-04 | 2023-10-13 |  |  | Yuen Fatt | 0 | 1
000114 | BIM Bi-Weekly Meeting Minutes 0008_20230920 | "BIM Bi-Weekly Meeting Minutes 0008_20230920" | 2023-10-05 | 2023-10-16 |  |  | Heng Peng | 0 | 1
000115 | Project Control Plan | "Project Control Plan" | 2023-10-05 | 2023-10-27 |  |  | Thomas | 1 | 2
000116 | Proposed change of Manufacturer for SSN Aeration blowers | "Proposed change of Manufacturer for SSN Aeration blowers" | 2023-10-06 | 2023-10-25 |  |  | Qili | 0 | 1
000117 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" | 2023-10-06 | 2023-11-28 |  |  | Qili | 1 | 2
000118 | MSRA, SWP for Bored Piling Work | "MSRA, SWP for Bored Piling Work" | 2023-10-06 | 2023-10-18 |  |  | Yuen Fatt | 1 | 2
000119 | MSRA, SWP for Site Set-Up & Associated Works (Seong) | "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | 2023-10-19 |  |  | Yuen Fatt | 0 | 1
000120 | Milestone 1.1 (Sidewide piperack) | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | 2023-10-06 | 2024-03-28 |  |  | Heng Peng | 0 | 2
000121 | Submission Of BIM Coordination VCM Model (Sept – 2023) | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | 2023-10-10 | 2023-10-23 |  |  | Heng Peng | 0 | 2
000122 | MSRA, SWP for Erection of Site Office (Cape) | "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | 2023-10-18 |  |  | Yuen Fatt | 0 | 1
000123 | Traffic Management Plan | "Traffic Management Plan " | 2023-10-10 | 2023-10-18 |  |  | Dharmen | 0 | 1
000124 | Project Execution Plan | "Project Execution Plan" | 2023-10-10 | 2023-10-27 |  |  | Yuen Fatt | 0 | 1
000125 | Vendor Approval of UXO Survey – EXPLOMO | "Vendor Approval of UXO Survey – EXPLOMO" | 2023-10-11 | 2023-10-18 |  |  | Yuen Fatt | 0 | 1
000126 | Process & MEICA Meeting Minutes 0010_20230928 | "Process & MEICA Meeting Minutes 0010_20230928" | 2023-10-12 | 2024-03-18 |  |  | Qili | 0 | 1
000127 | C4B Monthly Progress Report Number No.05 (09/23) | "C4B Monthly Progress Report Number No.05 (09/23)" | 2023-10-14 | 2023-10-27 |  |  | Leslie | 0 | 1
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-10-16 | 2023-11-08 |  |  | Zora | D | 6
000129 | MSRA, SWP for Erection of Site Office (UXO) | "MSRA, SWP for Erection of Site Office (UXO)" | 2023-10-17 | 2023-11-01 |  |  | Yuen Fatt | 0 | 1
000130 | PAYMENT CLAIM NO.4 | "PAYMENT CLAIM NO.4" | 2023-10-18 | 2023-10-23 |  |  | Yi Hao | 0 | 1
000131 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" | 2023-10-18 | 2023-11-17 |  |  | Zora | 0 | 1
000131 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" | 2023-10-18 | 2023-11-17 |  |  | Zora | 0 | 1
000132 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | 2023-10-19 | 2023-11-17 |  |  | Zora | 1 | 2
000133 | THP Equipment List | "THP Equipment List" | 2023-10-20 | 2023-11-27 |  |  | Joo Kwan | 1 | 2
000134 | Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD. | "Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD." | 2023-10-23 | 2023-11-17 |  |  | Yuen Fatt | 0 | 1
000135 | Preliminary Design and Vendor Approval of Blower (Robuschi) | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" | 2023-10-23 | 2023-11-27 |  |  | Yibo | 2 | 3
000136 | Time Lapse Camera Location | "Time Lapse Camera Location" | 2023-10-23 | 2023-12-18 |  |  | Yuen Fatt | 0 | 1
000137 | Monthly Progress Presentation No. 05 (0923) | "Monthly Progress Presentation No. 05 (0923)" | 2023-10-25 | 2023-10-26 |  |  | Thomas | 0 | 1
000138 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-10-25 | 2023-10-26 |  |  | Thomas | 0 | 1
000138 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-10-25 | 2023-10-26 |  |  | Thomas | 0 | 1
000139 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | "Preliminary Design and Vendor Approval of Diffuser (Xylem)" | 2023-10-25 | 2023-12-22 |  |  | Yibo | 1 | 2
000140 | Thermal Hydrolysis Process Presentation | "Thermal Hydrolysis Process Presentation" | 2023-10-25 | 2023-11-27 |  |  | Joo Kwan | 0 | 1
000141 | Process Functional Description | "Process Functional Description" | 2023-10-25 | 2024-01-23 |  |  | Joo Kwan | 3 | 4
000142 | Process Design Basis | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | 2024-01-15 |  |  | Joo Kwan | 3 | 4
000143 | THP Process Flow Diagram | "THP Process Flow Diagram" | 2023-10-26 | 2024-01-23 |  |  | Joo Kwan | B | 3
000143 | THP Process Flow Diagram | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" | 2023-10-26 | 2024-01-23 |  |  | Joo Kwan | 0 | 5
000143 | THP Process Flow Diagram | "THP Process Flow Diagram" | 2023-10-26 | 2024-01-23 |  |  | Joo Kwan | A | 1
000144 | Inspection Test Plan for Earthwork | "Inspection Test Plan for Earthwork" | 2023-10-27 | 2023-11-17 |  |  | Boopathi | 1 | 2
000145 | Inspection Test Plan for Bored piling work | "Inspection Test Plan for Bored piling work" | 2023-10-27 | 2023-11-17 |  |  | Boopathi | 1 | 3
000146 | Inspection Test Plan for Reinforcement work | "Inspection Test Plan for Reinforcement work" | 2023-10-27 | 2023-11-17 |  |  | Boopathi | 1 | 3
000147 | Inspection Test Plan for Concreting Work | "Inspection Test Plan for Concreting Work" | 2023-10-27 | 2023-11-17 |  |  | Boopathi | 1 | 3
000148 | Inspection Test Plan for Formwork | "Inspection Test Plan for Formwork" | 2023-10-27 | 2023-11-17 |  |  | Boopathi | 1 | 2
000149 | Inspection Test Plan for Waterproofing Concrete and Application Work | "Inspection Test Plan for Waterproofing Concrete and Application Work" | 2023-10-27 | 2023-11-17 |  |  | Mohan | 0 | 1
000150 | Inspection Test Plan for Roadwork | "Inspection Test Plan for Roadwork" | 2023-10-27 | 2023-11-17 |  |  | Mohan | 0 | 1
000151 | THP-Electrical Load List | "THP-Electrical Load List" | 2023-10-27 | 2024-02-02 |  |  | Joo Kwan | 2 | 3
000152 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | 2023-10-30 | 2023-11-09 |  |  | Heng Peng | 0 | 1
000152 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | 2023-10-30 | 2023-11-09 |  |  | Heng Peng | 0 | 1
000152 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | 2023-10-30 | 2023-11-09 |  |  | Heng Peng | 0 | 1
000152 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" | 2023-10-30 | 2023-11-09 |  |  | Heng Peng | 0 | 1
000153 | Process & MEICA Meeting Minutes 0011_20231012 | "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-30 | 2024-03-18 |  |  | Qili | 0 | 1
000154 | CV of Team Member (WSHC) | "CV of Team Member (WSHC)" | 2023-10-31 | 2023-12-04 |  |  | Dharmen | 0 | 1
000155 | Professional Indemnity Insurance Letter | "Professional Indemnity Insurance Letter" | 2023-10-31 | 2023-11-07 |  |  | Yi Hao | 0 | 1

## 2023-11
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000028 | Preliminary design and Vendor Approval - THP Package | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | 2023-11-10 | 2023-12-20 |  |  | Joo Kwan | 4 | 5
000046 | C4B Monthly Progress Report Number No.02 (06/23) | "C4B Monthly Progress Report Number No.02 (06/23)" | 2023-11-09 | 2023-11-15 |  |  | Thomas | NA | 1
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-11-07 | 2023-11-21 |  |  | Zora/ HP | A1 | 3
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-11-07 | 2023-11-21 |  |  | Zora/ HP | B1 | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-11-07 | 2023-11-21 |  |  | Zora/ HP | B | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2023-11-07 | 2023-11-21 |  |  | Zora/ HP | B | 5
000079 | ST604 – Overall SSN area Piling Design | "ST604 – Overall SSN area Piling Design" | 2023-11-07 | 2023-11-21 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A | 3
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 2
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | A1 | 2
000112 | SSN URA Submission | "SSN URA Submission" | 2023-11-07 | 2023-11-23 |  |  | Zora/ HP | NA | 1
000115 | Project Control Plan | "Project Control Plan" | 2023-11-10 | 2023-11-15 |  |  | Stanley | 1 | 2
000118 | MSRA, SWP for Bored Piling Work | "MSRA, SWP for Bored Piling Work" | 2023-11-01 | 2023-12-01 |  |  | Yuen Fatt | 1 | 2
000156 | Approval Letter to Commence Works Requiring Earth Control Measure | "Approval Letter to Commence Works Requiring Earth Control Measure" | 2023-11-02 | 2023-11-09 |  |  | Yuen Fatt | 0 | 1
000157 | Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023 | "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" | 2023-11-02 | 2023-12-01 |  |  | Max | 0 | 1
000158 | SSN Electrical Load List | "SSN Electrical Load List" | 2023-11-03 | 2024-04-29 |  |  | Freedomer | 1 | 2
000159 | Haze Management Plan | "Haze Management Plan " | 2023-11-03 | 2023-12-01 |  |  | Dharmen | 0 | 1
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2023-11-03 | 2024-02-16 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2023-11-03 | 2024-02-16 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2023-11-03 | 2024-02-16 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2023-11-03 | 2024-02-16 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | 2023-11-03 | 2024-02-16 |  |  | Freedomer | D | 5
000161 | Submission of Milestone 1.1 Underground Services Model | "Submission of Milestone 1.1 Underground Services Model" | 2023-11-06 | 2024-03-28 |  |  | Nicolas | D | 1
000162 | Submission of Milestone 1.1 Pump Stataion and Blower Area | "Submission of Milestone 1.1 Pump Stataion and Blower Area" && "Submission of Milestone 1.1 Astrea Separator Model" | 2023-11-06 | 2024-03-28 |  |  | Nicolas | 0 | 2
000163 | Submission of Milestone 1.1 Water Tank | "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | 2024-03-28 |  |  | Nicolas | 0 | 1
000164 | Submission of Milestone 1.1 Astrea Separator Model | "Submission of Milestone 1.1 Pump Stataion and Blower Area" && "Submission of Milestone 1.1 Astrea Separator Model" | 2023-11-06 | 2024-03-28 |  |  | Heng Peng/ Muthu | 0 | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-02-16 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-02-16 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-02-16 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-02-16 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | 2024-02-16 |  |  | Freedomer | B | 2
000166 | Inspection Test Plan for Architectural work | "Inspection Test Plan for Architectural work " | 2023-11-06 | 2023-12-07 |  |  | Mohan | 1 | 2
000167 | Inspection Test Plan for Plastering and Painting Work | "Inspection Test Plan for Plastering and Painting Work" | 2023-11-06 | 2023-12-06 |  |  | Mohan | 1 | 2
000168 | Inspection Test Plan for Installation of Raised Access Floor System Work | "Inspection Test Plan for Installation of Raised Access Floor System Work" | 2023-11-06 | 2023-12-06 |  |  | Mohan | 0 | 1
000169 | Inspection Test Plan for Installation of Door and Window Work | "Inspection Test Plan for Installation of Door and Window Work" | 2023-11-06 | 2023-12-12 |  |  | Mohan | 0 | 1
000170 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | 2024-02-14 |  |  | Liying | 2 | 3
000171 | THP Control System Architecture Drawing | "THP Control System Architecture Drawing" | 2023-11-06 | 2023-11-21 |  |  | Zuo Yu | C | 3
000172 | THP Compressed Air Calculation | "THP Compressed Air Calculation" | 2023-11-08 | 2024-01-17 |  |  | Joo Kwan | 2 | 3
000173 | SSN: Plant Drain Hydraulic Profile and calculation | "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2024-01-22 |  |  | Qili | 2 | 3
000173 | SSN: Plant Drain Hydraulic Profile and calculation | "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | 2024-01-22 |  |  | Qili | C | 3
000174 | C4B Monthly Progress Report Number No.06 (10/23) | "C4B Monthly Progress Report Number No.06 (10/23)" | 2023-11-08 | 2023-11-21 |  |  | Thomas | 0 | 1
000175 | Submission Of BIM Coordination VCM Model (Oct – 2023) | "Submission Of BIM Coordination VCM Model (Oct – 2023)" | 2023-11-08 | 2023-11-21 |  |  | Heng Peng | 0 | 1
000176 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | "BIM Bi-Weekly Meeting Minutes 0011_20231101" | 2023-11-09 | 2023-11-14 |  |  | Heng Peng | 0 | 1
000176 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | "BIM Bi-Weekly Meeting Minutes 0011_20231101" | 2023-11-09 | 2023-11-14 |  |  | Heng Peng | 0 | 1
000177 | Data Sheet of Air Compressor | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | 2023-11-09 | 2024-01-22 |  |  | Joo Kwan | 3 | 4
000178 | Data Sheet of Pressure Vessel | "Data Sheet of Pressure Vessel" | 2023-11-10 | 2024-01-18 |  |  | Joo Kwan | 4 | 5
000179 | Data Sheet of PreCoolers | "Data Sheet of PreCoolers" | 2023-11-10 | 2024-01-22 |  |  | Joo Kwan | 1 | 2
000180 | Data Sheet of PGS | "Data Sheet of PGS" | 2023-11-10 | 2024-01-29 |  |  | Joo Kwan | 3 | 4
000181 | Data Sheet of PGC | "Data Sheet of PGC" | 2023-11-10 | 2024-01-29 |  |  | Joo Kwan | 2 | 3
000182 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2023-12-12 |  |  | Zora | A | 3
000182 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2023-12-12 |  |  | Zora | A | 3
000182 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2023-12-12 |  |  | Zora | A | 3
000182 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2023-12-12 |  |  | Zora | A | 3
000182 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2023-12-12 |  |  | Zora | A | 3
000182 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | 2023-12-12 |  |  | Zora | NA | 2
000182 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2024-02-15 |  |  | Zora | A | 3
000182 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2024-02-15 |  |  | Zora | A | 3
000182 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2024-02-15 |  |  | Zora | A | 3
000182 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2023-11-10 | 2024-02-15 |  |  | Zora | A | 3
000182 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | 2024-02-15 |  |  | Zora | NA | 2
000183 | Submission of Milestone 1.1 Electrical Building | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2024-03-28 |  |  | Nicolas | 0 | 1
000183 | Submission of Milestone 1.1 Electrical Building | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2024-03-28 |  |  | Nicolas | 0 | 1
000183 | Submission of Milestone 1.1 Electrical Building | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2024-03-28 |  |  | Nicolas | 0 | 1
000183 | Submission of Milestone 1.1 Electrical Building | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2024-03-28 |  |  | Nicolas | 0 | 1
000183 | Submission of Milestone 1.1 Electrical Building | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | 2024-03-28 |  |  | Nicolas | 0 | 1
000184 | CSA Meeting Minutes 0013_20231019 | "CSA Meeting Minutes 0013_20231019" | 2023-11-14 | 2023-11-23 |  |  | Zora | 0 | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | A | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | A | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | A1 | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | A1 | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | SSN PFD | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000185 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | 2023-11-23 |  |  | Aaron | NA | 1
000186 | Monthly Progress Presentation No. 06 (1023) | "Monthly Progress Presentation No. 06 (1023)" | 2023-11-15 | 2023-11-16 |  |  | Thomas | 0 | 1
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2023-11-15 | 2024-03-12 |  |  | Qili | D | 6
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2023-11-15 | 2024-03-12 |  |  | Qili | D | 6
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2023-11-15 | 2024-03-12 |  |  | Qili | D | 6
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | B | 3
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | B | 3
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | A.1 | 2
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | B | 3
000189 | Plumbing and Sanitary (SSN Area) | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2024-03-12 |  |  | Kyaw Myo | A.2 | 3
000189 | Plumbing and Sanitary (SSN Area) | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2023-11-15 | 2024-03-13 |  |  | Kyaw Myo | A.2 | 4
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | A.1_MS2 | 3
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | A.1_MS2 | 3
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | A.1 | 2
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" | 2023-11-15 | 2023-12-18 |  |  | Kyaw Myo | A | 3
000191 | Electrical Building | "Electrical Building" | 2023-11-17 | 2024-03-28 |  |  | Nicolas | 0 | 1
000192 | Chemical Dosing Area | "Chemical Dosing Area" | 2023-11-17 | 2024-03-28 |  |  | Nicolas | 0 | 1
000193 | Engineering Calculation Report for Fire Hydrant Pipe | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" | 2023-11-17 | 2023-12-18 |  |  | Kyaw Myo | 1 | 2
000194 | Engineering Calculation Report for Potable Water Pipe | "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" | 2023-11-17 | 2023-12-06 |  |  | Emerson | 1 | 2
000195 | Monthly Progress Meeting Minutes 0005_20231017 | "Monthly Progress Meeting Minutes 0005_20231017" | 2023-11-20 | 2023-11-23 |  |  | Thomas | 0 | 1
000196 | Monthly Progress Meeting Minutes 0006_20231114 | "Monthly Progress Meeting Minutes 0006_20231114" | 2023-11-15 | 2023-11-23 |  |  | Thomas | 0 | 1
000197 | THP Overall Single Line Diagram | "THP Overall Single Line Diagram" | 2023-11-21 | 2024-04-29 |  |  | Freedomer | B | 2
000198 | THP Overall Single Line Diagram | "THP Overall Single Line Diagram" | 2023-11-21 | 2024-04-29 |  |  | Freedomer | 0 | 1
000199 | SSN Cable Sizing Calculations | "SSN Cable Sizing Calculations" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | 2 | 3
000200 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | 2023-12-22 |  |  | Freedomer | 2 | 3
000201 | SSN Overall Single Line Diagram | "SSN Overall Single Line Diagram" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | B | 2
000201 | SSN Overall Single Line Diagram | "SSN Overall Single Line Diagram" | 2023-11-23 | 2024-04-29 |  |  | Freedomer | B | 2
000202 | THP Cable List | "THP Cable List" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | 3 | 4
000203 | THP Cable sizing Calculations | "THP Cable sizing Calculations" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | B | 2
000204 | SSN Cable List | "SSN Cable List" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | 3 | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 5
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 5
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 5
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 5
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000205 | Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2023-11-22 | 2024-04-29 |  |  | Freedomer | C | 4
000206 | Preliminary Sizing Calculation for SSN Future OCF System | "Preliminary Sizing Calculation for SSN Future OCF System" | 2023-11-22 | 2024-02-26 |  |  | Qili | 1 | 2
000207 | THP Equipment Sizing Calculation Sheet | "THP Equipment Sizing Calculation Sheet" | 2023-11-22 | 2024-03-07 |  |  | Boon Kee | 0 | 2
000208 | THP Atex Hazardous Area Assessment Report | "THP Atex Hazardous Area Assessment Report" | 2023-11-22 | 2024-05-15 |  |  | Joo Kwan | 1 | 2
000209 | C4B Minutes of Engineering Process & MEICA Meeting No.0012 | "C4B Minutes of Engineering Process & MEICA Meeting No.0012" | 2023-11-24 | 2024-05-21 |  |  | Qili | 0 | 1
000210 | C4B Minutes of SSN Ad Hoc Meeting | "C4B Minutes of SSN Ad Hoc Meeting" | 2023-11-24 | 2024-05-21 |  |  | Qili | 0 | 1
000211 | C4B Minutes of SSN Ad Hoc Meeting | "C4B Minutes of SSN Ad Hoc Meeting" | 2023-11-24 | 2024-05-21 |  |  | Qili | 0 | 1
000212 | THP Equipment Sizing Calculation Sheet | "THP Equipment Sizing Calculation Sheet" | 2023-11-24 | 2023-12-08 |  |  | Boon Kee | 0 | 2
000213 | C4B Minutes of CSA Progress Meeting No.0014 | "C4B Minutes of CSA Progress Meeting No.0014" | 2023-11-27 | 2023-12-13 |  |  | Zora | 0 | 1
000214 | PAYMENT CLAIM NO.5 | "PAYMENT CLAIM NO.5" | 2023-11-27 | 2023-12-06 |  |  | Yi Hao | 0 | 1
000215 | Clarification on Anammox Reactor Design Capacity | "Clarification on Anammox Reactor Design Capacity" | 2023-11-29 | 2024-07-26 |  |  | Franklin | 0 | 1
000216 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | 2023-12-05 |  |  | Boopathi | 1 | 2
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2023-12-04 |  |  | Freedomer | C | 8
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2023-12-04 |  |  | Freedomer | C | 8
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2023-12-04 |  |  | Freedomer | C | 8
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2023-12-04 |  |  | Freedomer | C | 8
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2023-12-04 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2024-02-15 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2024-02-15 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2024-02-15 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2024-02-15 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-11-30 | 2024-02-15 |  |  | Freedomer | C | 8
000219 | Building Services ACMV | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-11-30 | 2023-12-18 |  |  | Kyaw Myo | A.4 | 5
000219 | Building Services ACMV | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-11-30 | 2023-12-18 |  |  | Kyaw Myo | A.4 | 5
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-11-30 | 2023-12-18 |  |  | Kyaw Myo | A.4 | 7
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-11-30 | 2023-12-18 |  |  | Kyaw Myo | A.4 | 7
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2023-11-30 | 2024-05-09 |  |  | Freedomer | B | 2

## 2023-12
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000003 | BIM Execution Plan (BEP) | "BIM Execution Plan (BEP)" | 2023-12-12 | 2024-03-14 |  |  | Heng Peng | 5 | 5
000053 | CV of Team Member (BIM Authoring Lead) | "CV of Team Member (BIM Authoring Lead)" | 2023-12-11 | 2023-12-22 |  |  | Leon | 1 | 2
000117 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" | 2023-12-12 | 2024-01-29 |  |  | Qili | 1 | 2
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2023-12-29 | 2024-02-14 |  |  | Zora | D | 5
000132 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | 2023-12-21 | 2024-01-15 |  |  | Zora | 1 | 2
000135 | Preliminary Design and Vendor Approval of Blower (Aerzen) | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" | 2023-12-26 | 2024-01-29 |  |  | Yibo | 2 | 3
000144 | Inspection Test Plan for Earthwork | "Inspection Test Plan for Earthwork" | 2023-12-21 | 2024-01-15 |  |  | Boopathi | 1 | 2
000145 | Inspection Test Plan for Bored piling work | "Inspection Test Plan for Bored piling work" | 2023-12-21 | 2024-01-15 |  |  | Boopathi | 1 | 3
000146 | Inspection Test Plan for Reinforcement work | "Inspection Test Plan for Reinforcement work" | 2023-12-21 | 2024-01-15 |  |  | Boopathi | 1 | 3
000147 | Inspection Test Plan for Concreting Work | "Inspection Test Plan for Concreting Work" | 2023-12-21 | 2024-01-12 |  |  | Boopathi | 1 | 3
000148 | Inspection Test Plan for Formwork | "Inspection Test Plan for Formwork" | 2023-12-21 | 2024-01-15 |  |  | Mohan | 1 | 2
000216 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-12-12 | 2024-01-12 |  |  | Boopathi | 1 | 2
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | B | 5
000221 | Unpriced PO for Air Compressor System | "Unpriced PO for Air Compressor System" | 2023-12-01 | 2024-01-17 |  |  | Joo Kwan | 0 | 1
000222 | Progressive Cavity Pumps | "Progressive Cavity Pumps" | 2023-12-01 | 2024-03-07 |  |  | Joo Kwan | 0 | 1
000223 | THP Plant Safety Valve | "THP Plant Safety Valve" | 2023-12-01 | 2024-03-07 |  |  | Joo Kwan | 1 | 2
000224 | THP System Control Philosophy | "THP System Control Philosophy" | 2023-12-01 | 2024-01-26 |  |  | Joo Kwan | 1 | 2
000225 | SSN Electrical Building ACMV layout & Schedule | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-12-04 | 2023-12-08 |  |  | Emerson | A.4 | 5
000225 | SSN Electrical Building ACMV layout & Schedule | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-12-04 | 2023-12-08 |  |  | Emerson | A.4 | 5
000225 | SSN Electrical Building ACMV layout & Schedule | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-12-04 | 2023-12-08 |  |  | Emerson | A.4 | 7
000225 | SSN Electrical Building ACMV layout & Schedule | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2023-12-04 | 2023-12-08 |  |  | Emerson | A.4 | 7
000226 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" | 2023-12-05 | 2023-12-13 |  |  | Heng Peng | 0 | 1
000226 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" | 2023-12-05 | 2023-12-13 |  |  | Heng Peng | 0 | 1
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "SSN Power Layout Plan" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | D | 4
000227 | SSN Power Layout Plan | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | 2023-12-05 | 2024-05-07 |  |  | Freedomer | D | 5
000228 | UXO Scanning Report | "UXO Scanning Report" | 2023-12-05 | 2023-12-14 |  |  | Boopathi | 0 | 1
000229 | Preliminary Design and Vendor Approval of Mixer | "Preliminary Design and Vendor Approval of Mixer " | 2023-12-05 | 2024-04-17 |  |  | Yibo | 1 | 2
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2023-12-06 | 2024-03-01 |  |  | Joo Kwan | D | 4
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2023-12-07 | 2023-12-28 |  |  | Zora | A1 | 2
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | 2023-12-28 |  |  | Zora | A1 | 1
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | 2023-12-28 |  |  | Zora | A1 | 1
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2023-12-07 | 2023-12-28 |  |  | Zora | A1 | 2
000232 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" | 2023-12-08 | 2024-02-26 |  |  | Yibo | 2 | 3
000233 | Submission Of BIM Coordination VCM Model (Nov – 2023) | "Submission Of BIM Coordination VCM Model (Nov – 2023)" | 2023-12-08 | 2023-12-26 |  |  | Heng Peng | 0 | 1
000234 | C4B Monthly Progress Report Number No.07 (11/23) | "C4B Monthly Progress Report Number No.07 (11/23)" | 2023-12-11 | 2023-12-18 |  |  | Leslie | 0 | 1
000235 | ULT Test Report of 600mm Dia. Bored Pile | "ULT Test Report of 600mm Dia. Bored Pile " | 2023-12-12 | 2023-12-18 |  |  | Zora | 1 | 2
000235 | ULT Test Report of 600mm Dia. Bored Pile | "ULT Test Report of 600mm Dia. Bored Pile " | 2023-12-22 | 2024-01-16 |  |  | Mohan | 1 | 2
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-12 | 2024-03-20 |  |  | Freedomer | B | 5
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2023-12-12 | 2024-03-20 |  |  | Freedomer | B | 5
000237 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" | 2023-12-12 | 2024-01-24 |  |  | Freedomer | 0 | 1
000238 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | 2024-02-19 |  |  | Liying | 2 | 3
000239 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | 2023-12-14 | 2024-02-19 |  |  | Liying | 1 | 2
000240 | CSA Meeting Minutes 0015_20231116 | "CSA Meeting Minutes 0015_20231116" | 2023-12-14 | 2024-01-25 |  |  | Zora | 0 | 1
000241 | Preliminary design and Vendor Approval – SSN Package (ICA) | "Preliminary design and Vendor Approval – SSN Package (ICA)" | 2023-12-14 | 2024-01-26 |  |  | Zuo Yu | 1 | 2
000242 | THP PLC RIO Component Datasheet | "THP PLC RIO Component Datasheet" | 2023-12-14 | 2024-01-31 |  |  | Zuo Yu | 1 | 2
000243 | THP IO List | "THP IO List" | 2023-12-14 | 2024-01-31 |  |  | Zuo Yu | 1 | 2
000244 | Heat Load Calculation Report for ACMV | "Heat Load Calculation Report for ACMV" | 2023-12-14 | 2024-03-12 |  |  | Kyaw Myo | 0 | 1
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | 2024-02-16 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | 2024-02-16 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | 2024-02-16 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "SSN Earthing Layout Plan" | 2023-12-18 | 2024-02-16 |  |  | Freedomer | A | 1
000246 | THP Layout and Code Compliance | "THP Layout and Code Compliance" | 2023-12-18 | 2024-02-06 |  |  | Lilian | 0 | 1
000247 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | 2024-01-15 |  |  | Mohan | 0 | 1
000247 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | 2024-01-15 |  |  | Mohan | 0 | 1
000247 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | 2024-01-15 |  |  | Mohan | 0 | 1
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A | 1
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2023-12-22 | 2024-01-16 |  |  | Zora | E | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | NA | 1
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | NA | 2
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A | 1
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A | 1
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | NA | 1
000249 | ST602 – ERSS Design < 6m Depth | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | 2024-01-16 |  |  | Zora | NA | 2
000250 | Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI) | "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" | 2023-12-22 | 2024-02-26 |  |  | Yibo | 0 | 1
000251 | C4B SSN PLC/ RIO Panel Component Catalogue | "C4B SSN PLC/ RIO Panel Component Catalogue" | 2023-12-26 | 2024-01-29 |  |  | Zuo Yu | 1 | 2
000252 | Sitewide Piperack Lightning Protection System | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | 2024-02-16 |  |  | Freedomer | A.2 | 5
000252 | Sitewide Piperack Lightning Protection System | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | 2024-02-16 |  |  | Freedomer | A.2 | 5
000253 | Process & MEICA Meeting Minutes 0013_20231123 | "Process & MEICA Meeting Minutes 0013_20231123" | 2023-12-27 | 2024-05-21 |  |  | Qili | 0 | 1
000254 | CV of WSHS | "CV of WSHS" | 2023-12-28 | 2024-02-14 |  |  | Htet Nu | 0 | 1
000255 | Submission of Milestone 1.1 THP MCC Room | "Submission of Milestone 1.1 THP MCC Room" | 2023-12-28 | 2024-03-28 |  |  | Leon | 0 | 1
000256 | On-Demand Bond for SSN | "On-Demand Bond for SSN" | 2023-12-28 | 2024-01-16 |  |  | Yi Hao | 0 | 1
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2023-12-28 | 2024-03-01 |  |  | Boon Kee | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2023-12-28 | 2024-03-01 |  |  | Boon Kee | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2023-12-28 | 2024-03-01 |  |  | Boon Kee | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2023-12-28 | 2024-03-01 |  |  | Boon Kee | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2023-12-28 | 2024-03-01 |  |  | Boon Kee | D | 4

## 2024-01
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000008 | Engineering Deliverable Lists | "Engineering Deliverable Lists" | 2024-01-15 | 2024-08-29 |  |  | Franklin | 1 | 2
000058 | MSRA, SWP for General Civil Works | "MSRA, SWP for General Civil Works" | 2024-01-22 | 2024-02-21 |  |  | Anuar | 3 | 4
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | 2024-01-25 |  |  | Zora | NA | 1
000102 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" | 2024-01-04 | 2024-02-15 |  |  | Yibo | 2 | 3
000145 | Inspection Test Plan for Bored piling work | "Inspection Test Plan for Bored piling work" | 2024-01-29 | 2024-02-21 |  |  | Boopathi | 1 | 3
000146 | Inspection Test Plan for Reinforcement work | "Inspection Test Plan for Reinforcement work" | 2024-01-29 | 2024-02-21 |  |  | Boopathi | 1 | 3
000147 | Inspection Test Plan for Concreting Work | "Inspection Test Plan for Concreting Work" | 2024-01-29 | 2024-02-21 |  |  | Boopathi | 1 | 3
000182 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-01-04 | 2024-02-15 |  |  | Zora | A | 3
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | A1 | 2
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | A1 | 1
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | A1 | 1
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | A1 | 1
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | A1 | 1
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | A1 | 2
000231 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | 2024-02-14 |  |  | Zora/ HP | NA | 1
000258 | Unpriced PO for SSN Package (MattenPlant) | "Unpriced PO for SSN Package (MattenPlant)" | 2024-01-03 | 2024-04-26 |  |  | Yi Hao | 0 | 1
000259 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2024-01-03 | 2024-05-21 |  |  | Qili | 0 | 1
000259 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2024-01-03 | 2024-05-21 |  |  | Qili | 0 | 1
000260 | Milestone 1.1 SSN Overall Area | "Milestone 1.1 SSN Overall Area" | 2024-01-05 | 2024-03-28 |  |  | Nicolas | 0 | 1
000261 | PAYMENT CLAIM NO.6 | "PAYMENT CLAIM NO.6" | 2024-01-08 | 2024-01-30 |  |  | Lilian | 0 | 1
000262 | Tie in Schedule for SSN | "Tie in Schedule for SSN" | 2024-01-08 | 2024-05-27 |  |  | Geno | 0 | 1
000263 | Tie in Schedule for THP | "Tie in Schedule for THP" | 2024-01-09 | 2024-05-27 |  |  | Geno | 0 | 1
000264 | Tie in Schedule for Side wide | "Tie in Schedule for Side wide" | 2024-01-09 | 2024-05-27 |  |  | Geno | 0 | 1
000265 | Notice of Office Relocation | "Notice of Office Relocation" | 2024-01-09 | 2024-05-02 |  |  | Lilian/ Yi Hao | 0 | 1
000266 | Submission Of BIM Coordination VCM Model (Dec – 2023) | "Submission Of BIM Coordination VCM Model (Dec – 2023)" | 2024-01-09 | 2024-01-24 |  |  | Heng Peng | 0 | 1
000267 | CSA Meeting Minutes 0016_20231130 | "CSA Meeting Minutes 0016_20231130" | 2024-01-09 | 2024-01-25 |  |  | Zora | 0 | 1
000268 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" | 2024-01-09 | 2024-01-19 |  |  | Heng Peng | 0 | 1
000268 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" | 2024-01-09 | 2024-01-19 |  |  | Heng Peng | 0 | 1
000269 | P&ID of THP General System [Part 2] | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000269 | P&ID of THP General System [Part 2] | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000269 | P&ID of THP General System [Part 2] | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | 2024-03-01 |  |  | Boon Kee | D | 4
000271 | Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd) | "Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd)" | 2024-01-11 | 2024-01-22 |  |  | Yuen Fatt | 0 | 1
000272 | THP ATEX Zone Drawing | "THP ATEX Zone Drawing" | 2024-01-11 | 2024-05-15 |  |  | Joo Kwan | 0 | 1
000273 | Common Data Environment (CDE) Set-Up and Rollout | "Common Data Environment (CDE) Set-Up and Rollout" | 2024-01-12 | 2024-02-27 |  |  | Heng Peng | 0 | 1
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" | 2024-01-13 | 2024-02-01 |  |  | Zora | 3 | 4
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | B | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-01-13 | 2024-02-14 |  |  | Zora | C | 3
000276 | C4B Monthly Progress Report Number No.08 (12/23) | "C4B Monthly Progress Report Number No.08 (12/23)" | 2024-01-16 | 2024-01-31 |  |  | Leslie | 0 | 1
000277 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-01-16 | 2024-01-22 |  |  | Yuen Fatt | 1 | 2
000278 | THP - Basis of Design Report | "THP - Basis of Design Report" | 2024-01-17 | 2024-03-01 |  |  | Joo Kwan | 0 | 1
000279 | Process & MEICA Meeting Minutes 0016_20240104 | "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-18 | 2024-05-21 |  |  | Qili | 0 | 1
000280 | CV of Team Member (ECO cum ECMO) | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | 2024-01-20 | 2024-02-01 |  |  | Dharmen | 1 | 2
000281 | Sitewide Piperack Earthing System | "Sitewide Piperack Earthing System" | 2024-01-23 | 2024-05-15 |  |  | Freedomer | A | 1
000281 | Sitewide Piperack Earthing System | "Sitewide Piperack Earthing System" | 2024-01-23 | 2024-05-15 |  |  | Freedomer | A | 1
000281 | Sitewide Piperack Earthing System | "Sitewide Piperack Earthing System" | 2024-01-23 | 2024-05-15 |  |  | Freedomer | A | 1
000282 | Assign of Builder License (CES_SDC Pte. Ltd.) | "Assign of Builder License (CES_SDC Pte. Ltd.)" | 2024-01-23 | 2024-05-10 |  |  | Keith | 0 | 1
000283 | Monthly Progress Meeting Minutes 0007_20231219 | "Monthly Progress Meeting Minutes 0007_20231219" | 2024-01-23 | 2024-01-24 |  |  | Thomas | 0 | 1
000284 | IFC of ST604 : Piling design of Minor Structures | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | 2024-02-15 |  |  | Zora | B | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | 2024-02-15 |  |  | Zora | B1 | 5
000284 | IFC of ST604 : Piling design of Minor Structures | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | 2024-02-15 |  |  | Zora | A2 | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | 2024-02-15 |  |  | Zora | B | 5
000285 | Monthly Progress Presentation No. 07 (1123) | "Monthly Progress Presentation No. 07 (1123)" | 2024-01-24 | 2024-01-29 |  |  | Thomas | 0 | 1
000286 | Monthly Progress Presentation No. 08 (1223) | "Monthly Progress Presentation No. 08 (1223)" | 2024-01-24 | 2024-01-25 |  |  | Thomas | 0 | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | A | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | A | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | A | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | A | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | A | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | A | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | 2024-02-21 |  |  | Zora | NA | 1
000288 | PAYMENT CLAIM NO.7 | "PAYMENT CLAIM NO.7" | 2024-01-24 | 2024-02-15 |  |  | Yi Hao | 0 | 1
000289 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2024-01-26 | 2024-04-17 |  |  | Zuo Yu | 1 | 2

## 2024-02
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000088 | Preliminary design and Vendor Approval for SSN Package | "Preliminary design and Vendor Approval for SSN Package" | 2024-02-03 | 2024-04-29 |  |  | Joo kwan | 3 | 4
000092 | Piping Material Specification | "Piping Material Specification" | 2024-02-22 | 2024-04-17 |  |  | Liying | 3 | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-02-24 | 2024-03-05 |  |  | Zora | E | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 3
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-02-24 | 2024-03-05 |  |  | Zora | A.1 | 4
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" | 2024-02-16 | 2024-03-05 |  |  | Zora | 3 | 4
000277 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-02-02 | 2024-02-19 |  |  | Yuen Fatt | 1 | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-15 |  |  | Zora | A1 | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-15 |  |  | Zora | B | 5
000284 | IFC of ST604 : Piling design of Minor Structures | "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-29 |  |  | Zora | B | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-29 |  |  | Zora | A1 | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-29 |  |  | Zora | B1 | 5
000284 | IFC of ST604 : Piling design of Minor Structures | "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-29 |  |  | Zora | A2 | 2
000284 | IFC of ST604 : Piling design of Minor Structures | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-29 |  |  | Zora | B | 5
000284 | IFC of ST604 : Piling design of Minor Structures | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | 2024-02-29 |  |  | Zora | B | 5
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-26 | 2024-02-27 |  |  | Zora | D | 2
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 1
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-28 | 2024-03-20 |  |  | Zora | NA | 1
000290 | Control Valves Data Sheet (THP) | "Control Valves Data Sheet (THP)" | 2024-02-01 | 2024-04-29 |  |  | Joo Kwan | 0 | 1
000291 | Milestone 1.1 THP EICA Silo Area inside Biosolid Building | "Milestone 1.1 THP EICA Silo Area inside Biosolid Building" | 2024-02-01 | 2024-03-28 |  |  | Leon | 0 | 1
000292 | Milestone 1.1 THP Overall & Equipment Layout | "Milestone 1.1 THP Overall & Equipment Layout" | 2024-02-01 | 2024-03-28 |  |  | Leon | 0 | 1
000293 | Milestone 1.1 THP A100 Silo Area inside Biosolid Building | "Milestone 1.1 THP A100 Silo Area inside Biosolid Building" | 2024-02-01 | 2024-03-28 |  |  | Leon | 0 | 1
000294 | Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-02-01 | 2024-03-28 |  |  | Leon | 0 | 1
000295 | Preliminary Design and Vendor Approval of Manway | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" | 2024-02-01 | 2024-04-16 |  |  | David | 1 | 2
000296 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | 2024-02-16 |  |  | Boopathi | 2 | 3
000297 | Pipe Support Standard - General Notes | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 3
000297 | Pipe Support Standard - S01 U-Bolt | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.2 | 3
000297 | Pipe Support Standard - S02 SHOE (DN15 ~ DN450) | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S03 PAD | "Pipe Support Standard - S03 PAD" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.2 | 3
000297 | Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S06 DUMMY PIPE SHEET 1 | "Pipe Support Standard - S06 DUMMY PIPE SHEET 1" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S06 DUMMY PIPE SHEET 2 | "Pipe Support Standard - S06 DUMMY PIPE SHEET 2" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S08 SLIDE STOOL | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S09 TIGHT STOOL | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.2 | 3
000297 | Pipe Support Standard - S11 GUIDE FOR SHOE | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S12 STOPPER FOR SHOE | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S13 BRACKET SUPPORT | "Pipe Support Standard - S13 BRACKET SUPPORT" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1 | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2 | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1 | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2 | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S16 STANCHION | "Pipe Support Standard - S16 STANCHION" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S17 STANCHION (REINFORCED) | "Pipe Support Standard - S17 STANCHION (REINFORCED)" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING | "Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450) | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200) | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A.1 | 2
000297 | Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450) | "Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450)" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000297 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | 2024-05-29 |  |  | Kyaw Myo | A | 1
000298 | Process & MEICA Meeting Minutes 0017_20240118 | "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | 2024-05-21 |  |  | Qili | 0 | 1
000299 | Vendor Approval of MV Cable (Keystone & Polycab) | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | 2024-02-03 | 2024-03-01 |  |  | Freedomer | 3 | 4
000300 | Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024 | "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" | 2024-02-03 | 2024-03-18 |  |  | Max | 0 | 1
000301 | Monthly Progress Meeting Minutes 0008_20240123 | "Monthly Progress Meeting Minutes 0008_20240123" | 2024-02-05 | 2024-02-07 |  |  | Thomas | 0 | 1
000302 | Milestone 1.1 THP Compressed Air System | "Milestone 1.1 THP Compressed Air System" | 2024-02-06 | 2024-03-28 |  |  | Leon | 0 | 1
000303 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-21 |  |  | Zora/ HP | A1 | 1
000303 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-21 |  |  | Zora/ HP | A1 | 1
000303 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-21 |  |  | Zora/ HP | A1 | 1
000303 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-21 |  |  | Zora/ HP | A1 | 1
000303 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-21 |  |  | Zora/ HP | A1 | 1
000303 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | 2024-02-21 |  |  | Zora/ HP | A1 | 1
000304 | Submission Of BIM Coordination VCM Model (Jan–2024) | "Submission Of BIM Coordination VCM Model (Jan–2024)" | 2024-02-06 | 2024-02-22 |  |  | Heng Peng | 0 | 1
000305 | C4B Monthly Progress Report Number No.09 (01 24) | "C4B Monthly Progress Report Number No.09 (01 24)" | 2024-02-08 | 2024-03-08 |  |  | Leslie | 0 | 1
000306 | Payment Claim No. 8 | "Payment Claim No. 8" | 2024-02-08 | 2024-05-10 |  |  | Yi Hao | 0 | 1
000307 | Typical Installation Details for Power | "Typical Installation Details for Power" | 2024-02-13 | 2024-05-13 |  |  | Freedomer | B | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-02-13 | 2024-05-08 |  |  | Freedomer | A | 1
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-02-13 | 2024-05-08 |  |  | Freedomer | C | 3
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-02-13 | 2024-05-08 |  |  | Freedomer | C | 3
000309 | SSN Listing of Interface Points | "SSN Listing of Interface Points" | 2024-02-13 | 2024-05-15 |  |  | Freedomer | B | 2
000310 | Typical Installation Details for Lighting | "Typical Installation Details for Lighting" | 2024-02-13 | 2024-05-13 |  |  | Freedomer | B | 2
000311 | THP Lightning Protection System | "THP Lightning Protection System" | 2024-02-13 | 2024-05-15 |  |  | Freedomer | B | 2
000311 | THP Lightning Protection System | "THP Lightning Protection System" | 2024-02-13 | 2024-05-15 |  |  | Freedomer | B | 2
000312 | CV of Team Member (QA/QC Manager) | "CV of Team Member (QA/QC Manager)" | 2024-02-14 | 2024-02-19 |  |  | Soe Myat | 0 | 1
000313 | Process & MEICA Meeting Minutes 0018_20240201 | "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | 2024-05-21 |  |  | Qili | 0 | 1
000314 | 1st CONSAAS Audit report_2023 | "1st CONSAAS Audit report_2023" | 2024-02-15 | 2024-03-18 |  |  | Dharmen | 0 | 1
000315 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | 2024-02-19 | 2024-04-08 |  |  | Zuo Yu | 1 | 2
000316 | Inspection Test Plan for Structural Steel Work | "Inspection Test Plan for Structural Steel Work" | 2024-02-20 | 2024-08-14 |  |  | Mohan | 0 | 1
000317 | Vendor Approval of CONSAAS Audit (ACE EHS) | "Vendor Approval of CONSAAS Audit (ACE EHS)" | 2024-02-20 | 2024-03-18 |  |  | Dharmen | 0 | 1
000318 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | 2024-03-20 |  |  | Freedomer | 2 | 3
000319 | Monthly Progress Presentation No. 09 (0124) | "Monthly Progress Presentation No. 09 (0124)" | 2024-02-21 | 2024-02-22 |  |  | Thomas | 0 | 1
000320 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" | 2024-02-22 | 2024-03-01 |  |  | Zora | 0 | 1
000320 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" | 2024-02-22 | 2024-03-01 |  |  | Zora | 0 | 1
000321 | THP Listing of Interface Points | "THP Listing of Interface Points" | 2024-02-23 | 2024-05-15 |  |  | Freedomer | 1 | 2
000322 | Process Functional Description | "Process Functional Description" | 2024-02-23 | 2024-03-13 |  |  | Qili | 3 | 4
000323 | Process & MEICA Meeting Minutes 0019_20240215 | "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | 2024-05-21 |  |  | Qili | 0 | 1
000324 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | 2024-02-24 | 2024-07-04 |  |  | Joo Kwan | 0 | 1
000324 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | 2024-02-24 | 2024-07-04 |  |  | Joo Kwan | 0 | 1
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-02-27 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-02-27 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 2
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-02-27 |  |  | Zora | B | 2
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | 2024-02-27 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-29 | 2024-03-20 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-29 | 2024-03-20 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-29 | 2024-03-20 |  |  | Zora | B | 2
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-29 | 2024-03-20 |  |  | Zora | B | 2
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-29 | 2024-03-20 |  |  | Zora | A2 | 4
000326 | Unpriced PO for Transformer (Hitachi) | "Unpriced PO for Transformer (Hitachi)" | 2024-02-26 | 2024-03-20 |  |  | Yi Hao | 1 | 2
000327 | Unpriced PO for Blower (Aerzen) | "Unpriced PO for Blower (Aerzen)" | 2024-02-26 | 2024-05-21 |  |  | Yi Hao | 0 | 1
000328 | Unpriced PO for Diffuser (Xylem) | "Unpriced PO for Diffuser (Xylem)" | 2024-02-26 | 2024-05-21 |  |  | Yi Hao | 0 | 1
000329 | Vendor Approval of SSN Package (ORP Analyser) | "Vendor Approval of SSN Package (ORP Analyser)" | 2024-02-28 | 2024-04-08 |  |  | Low | 0 | 1
000330 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2024-02-28 | 2024-05-09 |  |  | Zuo Yu | 0 | 1
000331 | THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor | "THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor" | 2024-02-28 | 2024-03-20 |  |  | Joo Kwan | 0 | 1
000332 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" | 2024-02-29 | 2024-03-01 |  |  | Yuen Fatt | 0 | 3
000333 | Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd. | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." | 2024-02-29 | 2024-04-16 |  |  | Yuen Fatt | 0 | 1
000334 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | 2024-02-29 | 2024-03-20 |  |  | Freedomer | 3 | 4

## 2024-03
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000003 | BIM Execution Plan (BEP) | "BIM Execution Plan (BEP)" | 2024-03-15 | 2024-03-20 |  |  | Heng Peng | 5 | 5
000028 | Preliminary design and Vendor Approval - THP Package | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" | 2024-03-01 | 2024-04-26 |  |  | Joo Kwan | 4 | 5
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | 2024-05-02 |  |  | Zora | A.2 | 2
000093 | Piperack P&IDs | "Piperack P&IDs" | 2024-03-05 | 2024-04-25 |  |  | Joo kwan | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2024-03-05 | 2024-04-25 |  |  | Joo kwan | E | 6
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 1
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000099 | C4B Sitewide Piping GA Drawing | "C4B Sitewide Piping GA Drawing" | 2024-03-11 | 2024-05-02 |  |  | Kyaw Myo | A1 | 2
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 6
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-03-28 | 2024-05-02 |  |  | Zora | D | 5
000142 | THP Process Design Basis | "Process Design Basis" && "THP Process Design Basis" | 2024-03-20 | 2024-04-26 |  |  | Joo Kwan | 3 | 4
000143 | THP Process Flow Diagram | "THP Process Flow Diagram" | 2024-03-18 | 2024-03-28 |  |  | Joo Kwan | B | 3
000143 | THP Process Flow Diagram | "THP Process Flow Diagram" | 2024-03-18 | 2024-03-28 |  |  | Joo Kwan | B | 2
000151 | THP-Electrical Load List | "THP-Electrical Load List" | 2024-03-28 | 2024-08-23 |  |  | Freedomer | 2 | 3
000171 | THP Control System Architecture Drawing | "THP Control System Architecture Drawing" | 2024-03-13 | 2024-06-13 |  |  | Zuo Yu | C | 3
000178 | Data Sheet of Pressure Vessel | "Data Sheet of Pressure Vessel" | 2024-03-20 | 2024-04-29 |  |  | Joo Kwan | 4 | 5
000179 | Data Sheet of PreCoolers | "Data Sheet of PreCoolers" | 2024-03-19 | 2024-04-29 |  |  | Joo Kwan | 1 | 2
000179 | Data Sheet of PreCoolers | "Data Sheet of PreCoolers" | 2024-03-19 | 2024-04-29 |  |  | Joo Kwan | B | 1
000179 | Data Sheet of PreCoolers | "Data Sheet of PreCoolers" | 2024-03-19 | 2024-04-29 |  |  | Joo Kwan | B | 1
000180 | Data Sheet of PGS | "Data Sheet of PGS" | 2024-03-25 | 2024-05-30 |  |  | Joo Kwan | 3 | 4
000181 | Data Sheet of PGC | "Data Sheet of PGC" | 2024-03-19 | 2024-04-29 |  |  | Joo Kwan | 2 | 3
000207 | THP Equipment Sizing Calculation Sheet | "THP Equipment Sizing Calculation Sheet" | 2024-03-11 | 2024-04-29 |  |  | Joo Kwan | NA | 1
000224 | THP System Control Philosophy | "THP System Control Philosophy" | 2024-03-01 | 2024-04-26 |  |  | Joo Kwan | 1 | 2
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000238 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2024-03-14 | 2024-04-17 |  |  | Liying | 2 | 3
000242 | THP PLC RIO Component Datasheet | "THP PLC RIO Component Datasheet" | 2024-03-11 | 2024-05-15 |  |  | Low | 1 | 2
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 3
000257 | P&ID of THP General System | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 3
000269 | P&ID of THP General System [Part 2] | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000269 | P&ID of THP General System [Part 2] | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000269 | P&ID of THP General System [Part 2] | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000270 | P&ID of THP Train 2 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-03-19 | 2024-04-25 |  |  | Joo Kwan | D | 4
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" | 2024-03-20 | 2024-05-13 |  |  | Zora | 3 | 4
000299 | Vendor Approval of MV Cable (Keystone & Polycab) | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | 2024-03-25 | 2024-05-23 |  |  | Freedomer | 3 | 4
000326 | Unpriced PO for Transformer (Hitachi) | "Unpriced PO for Transformer (Hitachi)" | 2024-03-20 | 2024-04-29 |  |  | Yi Hao | 1 | 2
000332 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" | 2024-03-04 | 2024-04-15 |  |  | Yuen Fatt | 0 | 3
000334 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | 2024-03-26 | 2024-04-29 |  |  | Freedomer | 3 | 4
000335 | Monthly Progress Meeting Minutes 0009_20240220 | "Monthly Progress Meeting Minutes 0009_20240220" | 2024-03-01 | 2024-03-04 |  |  | Thomas | 0 | 1
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | C | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | D | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | B | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | D | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | D | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | B | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | B | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | 2024-03-20 |  |  | Zora | A.1 | 2
000337 | Vendor Approval of cPVC Pipes & Fittings (GF) | "Vendor Approval of cPVC Pipes & Fittings (GF)" | 2024-03-01 | 2024-04-17 |  |  | Liying | 0 | 1
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-03-01 | 2024-03-20 |  |  | Zora | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-03-28 | 2024-05-13 |  |  | Zora | A.4 | 9
000339 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" | 2024-03-05 | 2024-03-05 |  |  | Heng Peng | 0 | 1
000339 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" | 2024-03-05 | 2024-03-05 |  |  | Heng Peng | 0 | 1
000339 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" | 2024-03-05 | 2024-03-05 |  |  | Heng Peng | 0 | 1
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-03-05 | 2024-03-20 |  |  | Zora | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-03-05 | 2024-03-20 |  |  | Zora | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-03-05 | 2024-03-20 |  |  | Zora | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-03-05 | 2024-03-20 |  |  | Zora | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-03-05 | 2024-03-20 |  |  | Zora | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-03-05 | 2024-03-20 |  |  | Zora | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | 2024-03-20 |  |  | Zora | A.1 | 1
000341 | THP UPS Loading List | "THP UPS Loading List" | 2024-03-05 | 2024-03-20 |  |  | Zuo Yu | 4 | 5
000342 | SSN UPS Loading List | "SSN UPS Loading List" | 2024-03-05 | 2024-03-20 |  |  | Zuo Yu | 5 | 6
000343 | CV of Team Member (LEW) | "CV of Team Member (LEW)" | 2024-03-06 | 2024-05-20 |  |  | Yuen Fatt | 0 | 1
000344 | Vendor Approval of SSN Package (Conductivity Analyser) | "Vendor Approval of SSN Package (Conductivity Analyser)" | 2024-03-06 | 2024-05-09 |  |  | Yean Yee | 1 | 2
000345 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | 2024-03-06 | 2024-05-15 |  |  | Yean Yee | 2 | 4
000346 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" | 2024-03-07 | 2024-05-16 |  |  | Yean Yee | 1 | 2
000347 | MSRA, SWP for Time Lapse Camera Steel Pole Erection | "MSRA, SWP for Time Lapse Camera Steel Pole Erection" | 2024-03-08 | 2024-03-20 |  |  | Anuar | 0 | 1
000348 | Submission Of BIM Coordination VCM Model (Feb-2024) | "Submission Of BIM Coordination VCM Model (Feb-2024)" | 2024-03-08 | 2024-03-20 |  |  | Heng Peng | 0 | 1
000349 | THP Lux Calculation and Luminaire Schedule | "THP Lux Calculation and Luminaire Schedule" | 2024-03-08 | 2024-05-07 |  |  | Freedomer | B | 2
000350 | Vendor Approval of SSN Package (pH Analyzer) | "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | 2024-05-14 |  |  | Yean Yee | 1 | 2
000351 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | 2024-03-11 | 2024-03-26 |  |  | Boopathi | 1 | 2
000352 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | 2024-03-12 | 2024-04-17 |  |  | Liying | 1 | 2
000353 | Process & MEICA Meeting Minutes 0020_20240229 | "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | 2024-05-21 |  |  | Qili | 0 | 1
000354 | Incentive / Disincentive Audit Scheme for November 2023 | "Incentive / Disincentive Audit Scheme for November 2023" | 2024-03-12 | 2024-03-18 |  |  | Anuar | 0 | 1
000355 | Incentive / Disincentive Audit Scheme for December 2023 | "Incentive / Disincentive Audit Scheme for December 2023" | 2024-03-12 | 2024-03-18 |  |  | Anuar | 0 | 1
000356 | SSN Transformer Sizing Calculations | "SSN Transformer Sizing Calculations" | 2024-03-12 | 2024-05-20 |  |  | Freedomer | 2 | 3
000357 | Notice of Unforeseeable Underground Obstruction Near Chemical Dosing | "Notice of Unforeseeable Underground Obstruction Near Chemical Dosing" | 2024-03-12 | 2024-05-10 |  |  | Chan | 0 | 1
000358 | C4B Sidestream Nitrogen Removal Process Equipment List | "C4B Sidestream Nitrogen Removal Process Equipment List" | 2024-03-12 | 2024-05-23 |  |  | Joo kwan | 2 | 3
000359 | Vendor Approval of THP Train Instrument | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2024-03-13 | 2024-05-16 |  |  | Zuo Yu | 3 | 4
000360 | SSN PFD | "SSN PFD" | 2024-03-14 | 2024-04-25 |  |  | Qili | D | 6
000360 | SSN PFD | "SSN PFD" | 2024-03-14 | 2024-04-25 |  |  | Qili | D | 6
000360 | SSN PFD | "SSN PFD" | 2024-03-14 | 2024-08-08 |  |  | Joo Kwan | D | 6
000361 | Incentive / Disincentive Audit Scheme for Jan 2024 | "Incentive / Disincentive Audit Scheme for Jan 2024" | 2024-03-14 | 2024-04-02 |  |  | Anuar | 0 | 1
000362 | Incentive / Disincentive Audit Scheme for Feb 2024 | "Incentive / Disincentive Audit Scheme for Feb 2024" | 2024-03-14 | 2024-04-02 |  |  | Anuar | 0 | 1
000363 | Milestone 1.2 - Underground Services | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" | 2024-03-15 | 2024-05-21 |  |  | Leon | 1 | 3
000364 | Milestone 1.2 - SSN Pump Station and Lamella Clarifier | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | 2024-03-15 | 2024-05-21 |  |  | Leon | 1 | 4
000365 | Milestone 1.2 - Sitewide Pipe Rack | "Milestone 1.2 - Sitewide Pipe Rack" | 2024-03-15 | 2024-05-21 |  |  | Leon | 0 | 1
000366 | Milestone 1.2 - SSN Minor Drain | "Milestone 1.2 - SSN Minor Drain" | 2024-03-15 | 2024-05-21 |  |  | Leon | 0 | 1
000367 | Milestone 1.2 - SSN Water Tank | "Milestone 1.2 SSN Water Tank" && "Milestone 1.2 - SSN Water Tank" | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 2
000368 | Milestone 1.2 - SSN Pump Station and Blower | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 5
000369 | Milestone 1.2 - SSN Chemical Dosing Area | "Milestone 1.2 - SSN Chemical Dosing Area " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000370 | Milestone 1.2 - SSN Electrical Building | "Milestone 1.2 - SSN Electrical Building " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000371 | Milestone 1.2 - THP Air Compress System | "Milestone 1.2 - THP Air Compress System " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000372 | Milestone 1.2 - THP Silo Area | "Milestone 1.2 - THP Silo Area " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000373 | Milestone 1.2 - THP Trains | "Milestone 1.2 - THP Trains " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000374 | Milestone 1.2 - THP Drainage | "Milestone 1.2 - THP Drainage " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000375 | Milestone 1.2 - THP Building Service | "Milestone 1.2 - THP Building Service" | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000376 | Milestone 1.2 - THP MCC Room | "Milestone 1.2 - THP MCC Room " | 2024-03-18 | 2024-05-21 |  |  | Leon | 0 | 1
000377 | C4B Monthly Progress Report Number No.10 (02 24) | "C4B Monthly Progress Report Number No.10 (02 24)" | 2024-03-18 | 2024-04-01 |  |  | Leslie | 0 | 1
000378 | Plant Control Narrative | "Plant Control Narrative" | 2024-03-19 | 2024-04-30 |  |  | Joo Kwan | 1 | 3
000379 | Vendor Approval for Waterproof Additive Specialist (CementAID) | "Vendor Approval for Waterproof Additive Specialist (CementAID)" | 2024-03-19 | 2024-03-26 |  |  | Boopathi | 0 | 1
000380 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | 2024-03-26 |  |  | Boopathi | 1 | 3
000381 | Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance) | "Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance)" | 2024-03-20 | 2024-03-26 |  |  | Mohan | 0 | 1
000382 | RFC For SSN Surface Drainage Layout | "RFC For SSN Surface Drainage Layout" | 2024-03-20 | 2024-08-29 |  |  | Zora | 0 | 1
000383 | Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | "Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | 2024-03-20 | 2024-06-21 |  |  | Yi Hao | 0 | 1
000384 | SSN Process Design Calculation | "SSN Process Design Calculation" | 2024-03-20 | 2024-04-25 |  |  | Joo Kwan | 1 | 2
000385 | SSN Process Design Basis | "SSN Process Design Basis" | 2024-03-20 | 2024-04-30 |  |  | Qili | 3 | 4
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | 0 | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | A | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | 0 | 1
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | 2024-05-02 |  |  | Zora | 0 | 1
000387 | Monthly Progress Presentation No. 10 (0224) | "Monthly Progress Presentation No. 10 (0224)" | 2024-03-22 | 2024-03-26 |  |  | Thomas | 0 | 1
000388 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" | 2024-03-22 | 2024-03-26 |  |  | Zora | 0 | 1
000388 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" | 2024-03-22 | 2024-03-26 |  |  | Zora | 0 | 1
000388 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" | 2024-03-22 | 2024-03-26 |  |  | Zora | 0 | 1
000389 | Payment Claim No.9 | "Payment Claim No.9" | 2024-03-23 | 2024-05-10 |  |  | Yi Hao | 0 | 1
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-03-23 | 2024-06-18 |  |  | Yaw Feng | A.1 | 2
000391 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | 2024-08-12 |  |  | Geno | A.2 | 3
000391 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | 2024-08-12 |  |  | Geno | A.2 | 3
000391 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | 2024-08-12 |  |  | Geno | A.2 | 3
000391 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | 2024-08-12 |  |  | Geno | A.2 | 3
000391 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | 2024-08-12 |  |  | Geno | A.2 | 3
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-03-25 | 2024-05-14 |  |  | Zuo Yu | E | 4
000393 | THP Schematic Diagram for Compressed Air System | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000393 | THP Schematic Diagram for Compressed Air System | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | 2024-05-17 |  |  | Freedomer | A | 2
000395 | Air Compressor Motor Outline Drawing | "Air Compressor Motor Outline Drawing " | 2024-03-25 | 2024-05-16 |  |  | Freedomer | B | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-03-25 | 2024-05-02 |  |  | Zora | A.4 | 4
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-03-25 | 2024-05-02 |  |  | Zora/HP | A | 1
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000398 | P&ID for SSN Process | "P&ID for SSN Process" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000399 | P&ID for SSN Chemical Dosing Systems | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-03-26 | 2024-04-30 |  |  | Joo Kwan | D | 5
000399 | P&ID for SSN Chemical Dosing Systems | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-03-26 | 2024-04-30 |  |  | Joo Kwan | D | 5
000399 | P&ID for SSN Chemical Dosing Systems | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-03-26 | 2024-04-30 |  |  | Joo Kwan | D | 5
000399 | P&ID for SSN Chemical Dosing Systems | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-03-26 | 2024-04-30 |  |  | Joo Kwan | D | 5
000399 | P&ID for SSN Chemical Dosing Systems | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-03-26 | 2024-04-30 |  |  | Joo Kwan | D | 5
000399 | P&ID for SSN Chemical Dosing Systems | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-03-26 | 2024-04-30 |  |  | Joo Kwan | D | 5
000400 | P&ID for SSN Plant Water and Instrument Air | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000400 | P&ID for SSN Plant Water and Instrument Air | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2024-03-26 | 2024-05-23 |  |  | Joo Kwan | D | 5
000401 | SSN Control System Architecture Drawing | "SSN Control System Architecture Drawing" | 2024-03-26 | 2024-04-30 |  |  | Zuo Yu | B | 2
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-03-27 | 2024-04-18 |  |  | Zora | A.4 | 9
000403 | SSN Control Philosophy | "SSN Control Philosophy" | 2024-03-27 | 2024-05-23 |  |  | Joo Kwan | 3 | 4
000404 | SSN Chemical Consumption Calculation | "SSN Chemical Consumption Calculation" | 2024-03-28 | 2024-05-23 |  |  | Joo Kwan | 2 | 3
000405 | SSN Chemical Consumption Calculation | "SSN Chemical Consumption Calculation" | 2024-03-28 | 2024-05-30 |  |  | Joo Kwan | 0 | 1
000406 | SSN 22kV MV Power Cable Sizing Calculations | "SSN 22kV MV Power Cable Sizing Calculations" | 2024-03-28 | 2024-05-23 |  |  | Freedomer | 2 | 3
000407 | Basic Design Report of SSN Package | "Basic Design Report of SSN Package" | 2024-03-28 | 2024-05-03 |  |  | Joo Kwan | 2 | 3
000408 | SSN Datasheet & Drawing of Lamella Clarifier | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | 2024-04-29 |  |  | Joo Kwan | 0 | 2
000408 | SSN Datasheet & Drawing of Lamella Clarifier | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | 2024-04-29 |  |  | Joo Kwan | B | 2
000408 | SSN Datasheet & Drawing of Lamella Clarifier | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | 2024-04-29 |  |  | Joo Kwan | B | 2
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | 2024-04-30 |  |  | Joo Kwan | 2 | 3
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | 2024-04-30 |  |  | Joo Kwan | B | 3
000410 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-03-28 | 2024-05-02 |  |  | Aaron/HP | A.2 | 3
000410 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-03-28 | 2024-05-02 |  |  | Aaron/HP | A.2 | 3
000410 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-03-28 | 2024-05-02 |  |  | Aaron/HP | A.2 | 3
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1
000411 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | 2024-05-09 |  |  | Aaron/HP | A | 1

## 2024-04
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000032 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | 2024-04-12 | 2024-06-06 |  |  | Anuar | 1 | 2
000058 | MSRA, SWP for General Civil Works | "MSRA, SWP for General Civil Works" | 2024-04-12 | 2024-06-06 |  |  | Anuar | 3 | 4
000133 | THP Equipment List | "THP Equipment List" | 2024-04-26 | 2024-05-27 |  |  | Joo Kwan | 1 | 2
000141 | Process Functional Description | "Process Functional Description" | 2024-04-02 | 2024-04-26 |  |  | Joo Kwan | 3 | 4
000172 | THP Compressed Air Calculation | "THP Compressed Air Calculation" | 2024-04-19 | 2024-07-26 |  |  | Joo Kwan | 2 | 3
000177 | Data Sheet and Drawing of Air Compressor System | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | 3 | 4
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000177 | Data Sheet and Drawing of Air Compressor System | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | 2024-05-16 |  |  | Joo Kwan | A | 1
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2024-04-25 | 2024-05-27 |  |  | Qili | D | 6
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2024-04-25 | 2024-05-27 |  |  | Qili | D | 6
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2024-04-25 | 2024-05-27 |  |  | Qili | D | 6
000193 | Engineering Calculation Report for Fire Hydrant Pipe | "Engineering Calculation Report for Fire Hydrant Pipe" | 2024-04-04 | 2024-04-26 |  |  | Kyaw Myo | 0 | 1
000239 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | 2024-04-02 | 2024-04-15 |  |  | Liying | 1 | 2
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | D | 4
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | E | 5
000248 | ST601 – ERSS Design < 4m Depth | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-04-15 | 2024-05-20 |  |  | Zora | E | 4
000251 | C4B SSN PLC/ RIO Panel Component Catalogue | "C4B SSN PLC/ RIO Panel Component Catalogue" | 2024-04-08 | 2024-05-15 |  |  | Low | 1 | 2
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | B | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000275 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-04-04 | 2024-05-16 |  |  | Aaron/HP | C | 3
000280 | CV of Team Member (ECO) | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | 2024-04-12 | 2024-06-06 |  |  | Htet Nu | 1 | 2
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-04-18 | 2024-05-21 |  |  | Sithu | D | 2
000287 | Shop Drawings of ST604 : Piling Design of Minor Structures | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-04-18 | 2024-05-21 |  |  | Sithu | D | 1
000289 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2024-04-19 | 2024-05-21 |  |  | Low | 1 | 2
000315 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | 2024-04-15 | 2024-05-15 |  |  | Zuo Yu | 1 | 2
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-04-26 | 2024-05-14 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-04-26 | 2024-05-14 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-04-26 | 2024-05-14 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-04-15 | 2024-06-03 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-04-15 | 2024-06-03 |  |  | Zora | A2 | 4
000325 | IFC of ST605_SSN Piling Layout of Main Water Tanks | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-04-15 | 2024-06-03 |  |  | Zora | A2 | 4
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-25 | 2024-05-14 |  |  | Aaron/HP | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-25 | 2024-05-14 |  |  | Aaron/HP | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-25 | 2024-05-14 |  |  | Aaron/HP | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-25 | 2024-05-14 |  |  | Aaron/HP | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-25 | 2024-05-14 |  |  | Aaron/HP | C | 3
000340 | ST615 – Amendment of ST604 (BCA Submission for Information) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-25 | 2024-05-14 |  |  | Aaron/HP | C | 3
000341 | THP UPS Loading List | "THP UPS Loading List" | 2024-04-19 | 2024-06-18 |  |  | Balaji/ Karthik | 4 | 5
000342 | SSN UPS Loading List | "SSN UPS Loading List" | 2024-04-19 | 2024-06-18 |  |  | Balaji/ Karthik | 5 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-04-19 | 2024-05-02 |  |  | Zora | A.4 | 9
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 3
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 3
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 3
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 3
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 3
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 3
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 1
000412 | ST615 BCA Approved Drawings (Amendment of ST604) | "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | 2024-05-14 |  |  | Aaron/HP | C | 1
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-04-19 |  |  | Zora | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-04-19 |  |  | Zora | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-04-19 |  |  | Zora | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-04-19 |  |  | Zora | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-04-19 |  |  | Zora | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | 2024-04-19 |  |  | Zora | C | 2
000414 | THP GA Drawings | "THP GA Drawings" | 2024-04-02 | 2024-06-05 |  |  | Joo Kwan | C01 | 1
000414 | THP GA Drawings | "THP GA Drawings" | 2024-04-02 | 2024-06-05 |  |  | Joo Kwan | C01 | 1
000414 | THP GA Drawings | "THP GA Drawings" | 2024-04-02 | 2024-06-05 |  |  | Joo Kwan | C01 | 1
000414 | THP GA Drawings | "THP GA Drawings" | 2024-04-02 | 2024-06-05 |  |  | Joo Kwan | C01 | 1
000414 | THP GA Drawings | "THP GA Drawings" | 2024-04-02 | 2024-06-05 |  |  | Joo Kwan | C01 | 1
000415 | SSN Equipment Sizing Calculation | "SSN Equipment Sizing Calculation" | 2024-04-03 | 2024-05-23 |  |  | Joo Kwan | 1 | 2
000416 | SSN Process Hydraulic Calculation & Drawing | "SSN Process Hydraulic Calculation & Drawing" | 2024-04-03 | 2024-06-05 |  |  | Joo Kwan | 2 | 3
000416 | SSN Process Hydraulic Calculation & Drawing | "SSN Process Hydraulic Calculation & Drawing" | 2024-04-03 | 2024-06-05 |  |  | Joo Kwan | C | 3
000417 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | 2024-04-18 |  |  | Zuo Yu | 1 | 2
000418 | SSN Integrated Security management system and plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B_MS2 | 3
000418 | SSN Integrated Security management system and plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B_MS2 | 3
000418 | SSN Integrated Security management system and plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B_MS2 | 3
000418 | SSN Integrated Security management system and plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B_MS2 | 3
000418 | SSN Integrated Security management system and plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B | 2
000418 | SSN Integrated Security management system and plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B | 2
000418 | SSN Integrated Security management system and plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B | 2
000418 | SSN Integrated Security management system and plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-04-04 | 2024-07-18 |  |  | Freedomer | B | 2
000419 | SSN Public Address System | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | 2024-04-04 | 2024-07-04 |  |  | Freedomer | A9 | 3
000419 | SSN Public Address System | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | 2024-04-04 | 2024-07-04 |  |  | Freedomer | A9 | 3
000419 | SSN Public Address System | "SSN Public Address System" | 2024-04-04 | 2024-07-04 |  |  | Freedomer | B | 2
000419 | SSN Public Address System | "SSN Public Address System" | 2024-04-04 | 2024-07-04 |  |  | Freedomer | B | 2
000420 | Monthly Progress Meeting Minutes 0010_20240319 | "Monthly Progress Meeting Minutes 0010_20240319" | 2024-04-04 | 2024-04-05 |  |  | Suresh | 0 | 1
000421 | Data Sheet and Drawing of THP Feed Pump | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" | 2024-04-05 | 2024-06-13 |  |  | Joo Kwan | 2 | 3
000422 | Data Sheet and Drawing of Reactor Feed Pump | "Data Sheet and Drawing of Reactor Feed Pump" | 2024-04-06 | 2024-06-13 |  |  | Joo Kwan | 2 | 3
000423 | Compressed Air System - Anchor Bolts Details & Plinth Details | "Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-04-06 | 2024-05-02 |  |  | Zora | A | 1
000423 | Compressed Air System - Anchor Bolts Details & Plinth Details | "Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-04-05 | 2024-05-02 |  |  | Zora | 1 | 2
000424 | Submission Of BIM Coordination VCM Model (Mar-2024) | "Submission Of BIM Coordination VCM Model (Mar-2024)" | 2024-04-08 | 2024-04-19 |  |  | Heng Peng | 0 | 1
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A2 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A2 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A2 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A.1 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-18 | 2024-05-14 |  |  | Aaron/HP | A2 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-18 | 2024-05-14 |  |  | Aaron/HP | A2 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-18 | 2024-05-14 |  |  | Aaron/HP | A2 | 2
000425 | ST616_Amendment of ST605 (BCA Approved Drawings) | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-18 | 2024-05-14 |  |  | Aaron/HP | A.1 | 2
000426 | ST616 _Amendment of ST605 (IFC Drawings) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A.2 | 3
000426 | ST616 _Amendment of ST605 (IFC Drawings) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A.2 | 3
000426 | ST616 _Amendment of ST605 (IFC Drawings) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-04-08 | 2024-04-17 |  |  | Zora | A.2 | 3
000426 | ST616 _Amendment of ST605 (IFC Drawings) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-04-26 | 2024-05-14 |  |  | Zora | A.2 | 3
000426 | ST616 _Amendment of ST605 (IFC Drawings) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-04-26 | 2024-05-14 |  |  | Zora | A.2 | 3
000426 | ST616 _Amendment of ST605 (IFC Drawings) | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " | 2024-04-26 | 2024-05-14 |  |  | Zora | A.2 | 3
000427 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | 2024-04-08 | 2024-04-22 |  |  | Boopathi | 1 | 2
000427 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | 2024-04-23 | 2024-05-02 |  |  | Boopathi | 1 | 2
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | 0 | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000428 | ST608 - SSN-Shelters (Conceptual Design Submission) | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | 2024-05-02 |  |  | Zora | A | 1
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | 2024-06-05 |  |  | Kyaw Myo | A.2 | 3
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | 2024-06-05 |  |  | Kyaw Myo | A | 1
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | 2024-06-05 |  |  | Kyaw Myo | A | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | 2024-06-05 |  |  | Kyaw Myo | A | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | 2024-06-05 |  |  | Kyaw Myo | A | 1
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | 2024-06-05 |  |  | Kyaw Myo | A | 1
000430 | Piping Special Item List | "Piping Special Item List" | 2024-04-11 | 2024-06-13 |  |  | Liying | 1 | 2
000431 | CV OF TEAM MEMBER (WSHO) | "CV OF TEAM MEMBER (WSHO)" | 2024-04-12 | 2024-06-06 |  |  | Dharmen | 0 | 1
000432 | THP Valve List | "THP Valve List" | 2024-04-12 | 2024-07-26 |  |  | Joo Kwan | 0 | 1
000433 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-04-12 | 2024-05-02 |  |  | Mohan | 1 | 3
000434 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024" | 2024-04-12 | 2024-05-02 |  |  | Mohan | 0 | 1
000435 | Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project) | "Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project)" | 2024-04-13 | 2024-05-10 |  |  | Chan | 0 | 1
000436 | Vendor Approval of SSN Package (TSS Analyser - Optical) | "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | 2024-05-23 |  |  | Yean Yee | 1 | 2
000437 | C4B Monthly Progress Report Number No.11 (03 24) | "C4B Monthly Progress Report Number No.11 (03 24)" | 2024-04-16 | 2024-04-17 |  |  | Krishanthy | 1 | 3
000437 | C4B Monthly Progress Report Number No.11 (03 24) | "C4B Monthly Progress Report Number No.11 (03 24)" | 2024-04-18 | 2024-05-13 |  |  | Krishanthy | 1 | 3
000438 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | 2024-05-23 |  |  | Yean Yee | 3 | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-04-16 | 2024-05-20 |  |  | Freedomer | E | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-04-16 | 2024-05-20 |  |  | Freedomer | D | 4
000440 | SSN Transformer Marshalling Box Schematic Wiring Diagram | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-04-16 | 2024-05-20 |  |  | Freedomer | F | 4
000441 | SSN sample AC/DC/IO circuit diagram | "SSN sample AC/DC/IO circuit diagram" | 2024-04-16 | 2024-07-04 |  |  | Zuo Yu | A | 1
000441 | SSN sample AC/DC/IO circuit diagram | "SSN sample AC/DC/IO circuit diagram" | 2024-04-16 | 2024-07-04 |  |  | Zuo Yu | A | 1
000441 | SSN sample AC/DC/IO circuit diagram | "SSN sample AC/DC/IO circuit diagram" && "SSN IO Sample Schematic Drawing" | 2024-04-16 | 2024-07-04 |  |  | Zuo Yu | B | 2
000442 | Milestone 1.2 - SSN Overall Changes | "Milestone 1.2 - SSN Overall Changes" | 2024-04-17 | 2024-07-05 |  |  | Heng Peng/ Muthu | 0 | 1
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000443 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-17 | 2024-05-13 |  |  | Zora | A | 2
000444 | Reinforcement Bar delivery & Testing Summary -February 2024 | "Reinforcement Bar delivery & Testing Summary -February 2024" | 2024-04-17 | 2024-05-02 |  |  | Mohan | 0 | 1
000445 | Sidewide Piperack Line List | "Sidewide Piperack Line List" && "Line List for Hydrotest (Sitewide PipeRack)" | 2024-04-17 | 2024-07-26 |  |  | Joo Kwan | 0 | 2
000446 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-05-13 |  |  | Zora | 0 | 1
000446 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | 2024-05-13 |  |  | Zora | A | 1
000446 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | 2024-04-19 | 2024-05-13 |  |  | Zora | 0 | 5
000447 | Reinforcement Bar Test Reports -Rebar Size (H10 &H16) | "Reinforcement Bar Test Reports -Rebar Size (H10 &H16)" | 2024-04-22 | 2024-05-02 |  |  | Mohan | 0 | 1
000448 | MSRA,SWP for Bored Piling WLT | "MSRA,SWP for Bored Piling WLT" | 2024-04-24 | 2024-05-02 |  |  | Boopathi | 1 | 2
000449 | Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd) | "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2024-04-25 | 2024-05-02 |  |  | Htet Nu | 0 | 1
000450 | Vendor Approval of ERSS Works (Singlee) | "Vendor Approval of ERSS Works (Singlee)" | 2024-04-25 | 2024-05-02 |  |  | Yuen Fatt | 0 | 1
000451 | Payment Claim No.10 | "Payment Claim No.10" | 2024-04-25 | 2024-05-13 |  |  | Yi Hao | 0 | 1
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000452 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" | 2024-04-26 | 2024-05-20 |  |  | Zora/ HP | A | 2
000453 | Monthly Progress Presentation No. 11 (0324) | "Monthly Progress Presentation No. 11 (0324)" | 2024-04-26 | 2024-05-09 |  |  | Krishanthy | 0 | 1
000454 | Monthly Progress Meeting Minutes 0011_20240423 | "Monthly Progress Meeting Minutes 0011_20240423" | 2024-04-26 | 2024-05-09 |  |  | Krishanthy | 0 | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " && "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | 0 | 2
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000455 | ST610 – Underground Services (BCA Submission File) | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | 2024-05-20 |  |  | Aaron | B | 1
000456 | Inspection and test plan for Compressed Air System | "Inspection and test plan for Compressed Air System" | 2024-04-30 | 2024-07-15 |  |  | Boopathi | 1 | 2
000457 | Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024 | "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" | 2024-04-30 | 2024-06-06 |  |  | Max | 0 | 1
000458 | SSN Transformer Data Sheet | "SSN Transformer Data Sheet" | 2024-04-30 | 2024-05-20 |  |  | Freedomer | 2 | 3
000473 | C4B Monthly Progress Report Number No.12 (04 24) | "C4B Monthly Progress Report Number No.12 (04 24)" | 2024-04-18 | 2024-06-03 |  |  | Krishanthy | 1 | 2

## 2024-05
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000001 | Project Quality Plan | "Project Quality Plan" | 2024-05-13 | 2024-09-10 |  |  | Radha | 1 | 2
000097 | Engineering Calculation Report For Potable Water Pipe | "Engineering Calculation Report For Potable Water Pipe" | 2024-05-30 | 2024-07-09 |  |  | Kyaw Myo | 3 | 3
000120 | Milestone 1.2 Sitewide Pipe Rack | "Milestone 1.2 Sitewide Pipe Rack" | 2024-05-27 | 2024-06-04 |  |  | Nicolas | 1 | 2
000161 | Milestone 1.2 Underground Services | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" | 2024-05-27 | 2024-06-04 |  |  | Nicolas | 1 | 3
000162 | Milestone 1.2 - SSN Pump Station and Blower Area | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | 2024-05-27 | 2024-06-04 |  |  | Nicolas | 0 | 5
000173 | SSN: Plant Drain Hydraulic Profile and calculation | "SSN: Plant Drain Hydraulic Profile and calculation " | 2024-05-06 | 2024-05-30 |  |  | Qili | 2 | 3
000173 | SSN: Plant Drain Hydraulic Profile and calculation | "SSN: Plant Drain Hydraulic Profile and calculation " | 2024-05-06 | 2024-05-30 |  |  | Qili | C | 3
000200 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2024-05-13 | 2024-07-04 |  |  | Freedomer | 2 | 3
000241 | Preliminary design and Vendor Approval – SSN Package (ICA) | "Preliminary design and Vendor Approval – SSN Package (ICA)" | 2024-05-02 | 2024-06-18 |  |  | Balaji/ Karthik | 1 | 2
000244 | Heat Load Calculation Report for ACMV | "Heat Load Calculation Report for ACMV" | 2024-05-14 | 2024-08-14 |  |  | Kyaw Myo | 2 | 2
000318 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-05-21 | 2024-07-04 |  |  | Freedomer | 2 | 3
000334 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | 2024-05-16 | 2024-07-04 |  |  | Freedomer | 3 | 4
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | C | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | D | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | B | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | D | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | D | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | B | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | B | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | A.1 | 2
000336 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | 2024-06-03 |  |  | Zora | B | 1
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-05-20 | 2024-06-06 |  |  | Zora/HP | A.4 | 3
000352 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | 2024-05-10 | 2024-08-06 |  |  | Liying | 1 | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 7
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-05-16 | 2024-06-06 |  |  | Zora/HP | A.4 | 4
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-05-13 | 2024-05-24 |  |  | Zora | A.4 | 9
000407 | Basic Design Report of SSN Package | "Basic Design Report of SSN Package" | 2024-05-23 | 2024-07-04 |  |  | Qili | 2 | 3
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-05-14 | 2024-06-03 |  |  | Aaron/HP | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-05-14 | 2024-06-03 |  |  | Aaron/HP | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-05-14 | 2024-06-03 |  |  | Aaron/HP | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-05-14 | 2024-06-03 |  |  | Aaron/HP | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-05-14 | 2024-06-03 |  |  | Aaron/HP | C | 2
000413 | ST615 Issued for Construction Drawings (Amendment of ST604) | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-05-14 | 2024-06-03 |  |  | Aaron/HP | C | 2
000446 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | 2024-05-31 | 2024-06-10 |  |  | Zora | 0 | 5
000448 | MSRA,SWP for Bored Piling WLT | "MSRA,SWP for Bored Piling WLT" | 2024-05-10 | 2024-05-20 |  |  | Boopathi | 1 | 2
000459 | Vendor Approval of SSN Package (Radar Level Transmitter) | "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | 2024-07-02 |  |  | Zuo Yu | 2 | 3
000460 | Process & MEICA Meeting Minutes 0021_20240328 | "Process & MEICA Meeting Minutes 0021_20240328" | 2024-05-02 | 2024-07-26 |  |  | Qili | 0 | 1
000461 | SSN Overall GA & Equipment Layout Drawings | "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | 0 | 1
000461 | SSN Overall GA & Equipment Layout Drawings | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | 0 | 3
000461 | SSN Overall GA & Equipment Layout Drawings | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | A | 2
000461 | SSN Overall GA & Equipment Layout Drawings | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | A | 3
000461 | SSN Overall GA & Equipment Layout Drawings | "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | 0 | 1
000461 | SSN Overall GA & Equipment Layout Drawings | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | 0 | 2
000461 | SSN Overall GA & Equipment Layout Drawings | "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | 2024-07-26 |  |  | Kyaw Myo | 0 | 1
000462 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | 2024-07-02 |  |  | Yean Yee | 2 | 3
000463 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | 2024-07-02 |  |  | Yean Yee | 2 | 3
000464 | Vendor Approval of SSN Package (Capacitive Level Switches) | "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | 2024-07-02 |  |  | Yean Yee | 2 | 3
000465 | MSRA,SWP for Bored Piling PDA Test | "MSRA,SWP for Bored Piling PDA Test" | 2024-05-07 | 2024-06-12 |  |  | Boopathi | 1 | 2
000466 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | "ST610 – Underground Services (BCA Submission File) " && "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | 2024-05-07 | 2024-05-20 |  |  | Zora | 0 | 2
000467 | Submission Of BIM Coordination VCM Model (Apr-2024) | "Submission Of BIM Coordination VCM Model (Apr-2024)" | 2024-05-08 | 2024-05-21 |  |  | Heng Peng | 0 | 1
000468 | Design for Safety Report 2 | "Design for Safety Report 2" | 2024-05-09 | 2024-06-06 |  |  | Krishanthy | 2 | 4
000469 | Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47) | "Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47)" | 2024-05-10 | 2024-05-20 |  |  | Boopathi | 0 | 1
000470 | Process & MEICA Meeting Minutes 0022_20240425 | "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | 2024-08-14 |  |  | Joo Kwan | 0 | 1
000471 | NEA Waiver Submission of SSN Plant | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2024-05-13 | 2024-05-24 |  |  | Zora | A.2 | 5
000472 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" | 2024-05-17 | 2024-06-03 |  |  | Zora | 0 | 1
000472 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" | 2024-05-17 | 2024-06-03 |  |  | Zora | 0 | 1
000474 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | 2024-07-04 |  |  | Liying | 2 | 3
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-05-18 | 2024-06-03 |  |  | Zora | D | 6
000476 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | 2024-07-02 |  |  | Yean Yee | 1 | 2
000477 | Process & MEICA Meeting Minutes 0023_20240509 | "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-23 | 2024-08-14 |  |  | Joo Kwan | 0 | 1
000478 | Handrail design loading & Testing of THP Train by CAMBI | "Handrail design loading & Testing of THP Train by CAMBI" | 2024-05-23 | 2024-06-03 |  |  | Aaron | 0 | 1
000479 | Proposed change of SS316 Cable Tray within THP Module | "Proposed change of SS316 Cable Tray within THP Module" | 2024-05-23 | 2024-06-18 |  |  | Joo Kwan | 0 | 1
000480 | Proposed change of Carbon loaded GRP Junction Box within THP Module | "Proposed change of Carbon loaded GRP Junction Box within THP Module" | 2024-05-23 | 2024-07-04 |  |  | Joo Kwan | 0 | 1
000481 | Separate Terminal Box for Motor Space Heater | "Separate Terminal Box for Motor Space Heater" | 2024-05-23 | 2024-06-12 |  |  | Joo Kwan | 0 | 1
000482 | Local Control Station with THP Module | "Local Control Station with THP Module" | 2024-05-23 | 2024-06-12 |  |  | Joo Kwan | 0 | 1
000483 | Pressure Instrument Mounting in THP Module | "Pressure Instrument Mounting in THP Module" | 2024-05-23 | 2024-07-04 |  |  | Joo Kwan | 0 | 1
000484 | Pump Color within THP Module | "Pump Color within THP Module" | 2024-05-23 | 2024-08-08 |  |  | Joo Kwan | 0 | 1
000485 | Vendor Approval of Electrical Installer (Cyclect) | "Vendor Approval of Electrical Installer (Cyclect)" | 2024-05-23 | 2024-07-04 |  |  | Yuen Fatt | 0 | 1
000486 | Vendor Approval of ICA Installer Submission (Cyclect) | "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | 2024-07-02 |  |  | Yuen Fatt | 0 | 1
000487 | MSRA & SWP for Mobilization and Demobilization of Machinery | "MSRA & SWP for Mobilization and Demobilization of Machinery" | 2024-05-27 | 2024-06-10 |  |  | Bryan | 0 | 1
000488 | MSRA & SWP for Sheet Piling Work | "MSRA & SWP for Sheet Piling Work" | 2024-05-27 | 2024-06-10 |  |  | Bryan | 0 | 1
000489 | Project Safety Review for ERSS | "Project Safety Review for ERSS" | 2024-05-28 | 2024-06-18 |  |  | Krishanthy | 1 | 2
000490 | Report of DFS (Guide 3) for ERSS | "Report of DFS (Guide 3) for ERSS" | 2024-05-28 | 2024-06-13 |  |  | Krishanthy | 1 | 2
000491 | CV of Team member (Planner) | "CV of Team member (Planner)" | 2024-05-28 | 2024-06-10 |  |  | Htet Nu | 0 | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-05-28 | 2024-08-08 |  |  | Kyaw Myo | A | 1
000493 | Vendor Approval of Testing Laboratory (TUV) | "Vendor Approval of Testing Laboratory (TUV)" | 2024-05-29 | 2024-06-03 |  |  | Boopathi | 0 | 1
000494 | Method Statement for Concrete Temperature Control and Monitoring | "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | 2024-06-10 |  |  | Boopathi | 2 | 3
000495 | Time Lapse Surveys_Apr 24 | "Time Lapse Surveys_Apr 24" | 2024-05-29 | 2024-06-03 |  |  | Yuen Fatt | 0 | 1
000496 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24 | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24" | 2024-05-30 | 2024-08-26 |  |  | Keith | 0 | 1
000497 | General Deviation from ICA G & P Spec | "General Deviation from ICA G & P Spec" | 2024-05-30 | 2024-08-27 |  |  | Low | 0 | 1
000498 | Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115) | "Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115)" | 2024-05-30 | 2024-06-12 |  |  | Radha | 0 | 1
000499 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" | 2024-05-30 | 2024-07-18 |  |  | Joo Kwan | 1 | 2
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | B | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000500 | BCA Approval of ST601 – ERSS < 4m | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | 2024-06-10 |  |  | Zora | C | 1
000501 | Vendor Approval of SSN Package (Thermal Flow Switches) | "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | 2024-07-22 |  |  | Yean Yee | 1 | 2
000502 | Vendor Approval of SSN Package (Pressure Gauges) | "Vendor Approval of SSN Package (Pressure Gauges)" | 2024-05-31 | 2024-07-22 |  |  | Yean Yee | 1 | 2

## 2024-06
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000003 | BIM Execution Plan (BEP) | "BIM Execution Plan (BEP)" | 2024-06-28 | 2024-08-07 |  |  | Heng Peng | 5 | 5
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | 2 | 1
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.1 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 3
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A.2 | 2
000083 | ST603 - Site Wide Pipe Rack Details | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | 2024-07-01 |  |  | Aaron/HP | A | 1
000102 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" | 2024-06-07 | 2024-07-12 |  |  | Yibo | 2 | 3
000120 | Milestone 1.2 Sitewide Pipe Rack | "Milestone 1.2 Sitewide Pipe Rack" | 2024-06-05 | 2024-07-05 |  |  | Nicolas | 1 | 2
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2024-06-12 | 2024-07-01 |  |  | Zora | NA | 1
000135 | Preliminary Design and Vendor Approval of Blower (Aerzen) | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" | 2024-06-25 | 2024-07-31 |  |  | Yibo | 2 | 3
000161 | Milestone 1.2 Underground Services | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" | 2024-06-05 | 2024-07-05 |  |  | Nicolas | 1 | 3
000162 | Milestone 1.2 - SSN Pump Station and Blower Area | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | 2024-06-05 | 2024-07-05 |  |  | Heng Peng/ Muthu | 0 | 5
000163 | Milestone 1.2 SSN Water Tank | "Milestone 1.2 SSN Water Tank" && "Milestone 1.2 - SSN Water Tank" | 2024-06-03 | 2024-07-05 |  |  | Heng Peng/ Muthu | 0 | 2
000164 | Milestone 1.2 SSN Lamella Clarifier | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | 2024-06-04 | 2024-07-05 |  |  | Heng Peng/ Muthu | 1 | 4
000191 | Milestone 1.2 Electrical Building | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | 2024-06-04 | 2024-07-05 |  |  | Heng Peng/ Muthu | 0 | 2
000192 | Milestone 1.2 SSN Chemical Dosing Area | "Milestone 1.2 SSN Chemical Dosing Area" | 2024-06-04 | 2024-07-05 |  |  | Heng Peng/ Muthu | 1 | 1
000199 | SSN Cable Sizing Calculations | "SSN Cable Sizing Calculations" | 2024-06-24 | 2024-08-15 |  |  | Freedomer | 2 | 3
000202 | THP Cable List | "THP Cable List" | 2024-06-12 | 2024-08-16 |  |  | Freedomer | 3 | 4
000203 | THP Cable sizing Calculations | "THP Cable sizing Calculations" | 2024-06-12 | 2024-08-16 |  |  | Freedomer | B | 2
000204 | SSN Cable List | "SSN Cable List" | 2024-06-24 | 2024-08-15 |  |  | Freedomer | 3 | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | 2024-07-31 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | 2024-07-31 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | 2024-07-31 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | 2024-07-31 |  |  | Freedomer | B_endorsed | 3
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | 2024-07-31 |  |  | Freedomer | B_endorsed | 3
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | 2024-07-31 |  |  | Freedomer | B_endorsed | 3
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 3
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-06-21 | 2024-07-01 |  |  | Zora | A.1 | 4
000255 | Milestone 1.2 THP MCC Room | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | 2024-12-05 |  |  | Heng Peng/ Muthu | 1 | 3
000260 | Milestone 1.2 SSN Overall Area | "Milestone 1.2 SSN Overall Area" | 2024-06-11 | 2024-07-05 |  |  | Heng Peng/ Muthu | 0 | 1
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" | 2024-06-06 | 2024-07-05 |  |  | Zora | 3 | 4
000291 | Milestone 1.2 THP EICA Silo Area inside Biosolid Building | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | 2024-07-05 |  |  | Nicolas | 1 | 4
000292 | Milestone 1.2 THP Overall & Equipment Layout | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | 2024-07-05 |  |  | Heng Peng/ Muthu | 0 | 3
000293 | Milestone 1.2 THP A100 Silo Area inside Biosolid Building | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | 2024-07-05 |  |  | Nicolas | 1 | 4
000294 | Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | 2024-07-05 |  |  | Nicolas | 1 | 4
000296 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-06-13 | 2024-06-28 |  |  | Boopathi | 2 | 3
000299 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | 2024-06-07 | 2024-08-15 |  |  | Freedomer | 3 | 4
000302 | Milestone 1.2 THP Compressed Air System | "Milestone 1.2 THP Compressed Air System" | 2024-06-11 | 2024-07-05 |  |  | Nicolas | 0 | 1
000351 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | 2024-06-20 | 2024-06-28 |  |  | Boopathi | 1 | 2
000359 | Vendor Approval of THP Train Instrument (Siemens) | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2024-06-07 | 2024-08-05 |  |  | Zuo Yu | 3 | 4
000360 | SSN PFD | "SSN PFD" | 2024-06-19 | 2024-08-08 |  |  | Joo Kwan | D | 6
000380 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-06-20 | 2024-06-28 |  |  | Mohan | 1 | 3
000383 | Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | "Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | 2024-06-22 | 2024-08-28 |  |  | Theint Theint | 0 | 1
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 3
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-06-26 | 2024-09-17 |  |  | Balaji/ Karthik | E | 4
000423 | Compressed Air System - Anchor Bolts Details & Plinth Details | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-05 | 2024-06-19 |  |  | Zora | B | 2
000423 | Compressed Air System - Anchor Bolts Details & Plinth Details | "Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-05 | 2024-06-19 |  |  | Zora | 1 | 2
000437 | C4B Monthly Progress Report Number No.11 (03 24) | "C4B Monthly Progress Report Number No.11 (03 24)" | 2024-06-11 | 2024-06-18 |  |  | Krishanthy | 1 | 3
000465 | MSRA,SWP for Bored Piling PDA Test | "MSRA,SWP for Bored Piling PDA Test" | 2024-06-19 | 2024-07-01 |  |  | Boopathi | 1 | 2
000466 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | 2024-06-12 | 2024-07-01 |  |  | Aaron | NA | 1
000468 | Design for Safety Report 2 | "Design for Safety Report 2" | 2024-06-07 | 2024-07-05 |  |  | Krishanthy | 2 | 4
000473 | C4B Monthly Progress Report Number No.12 (04 24) | "C4B Monthly Progress Report Number No.12 (04 24)" | 2024-06-11 | 2024-06-18 |  |  | Krishanthy | 1 | 2
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 5
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-06-03 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 5
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-06-07 | 2024-07-01 |  |  | Zora | D | 6
000490 | Report of DFS (Guide 3) for ERSS | "Report of DFS (Guide 3) for ERSS" | 2024-06-19 | 2024-07-12 |  |  | Krishanthy | 1 | 2
000494 | Method Statement for Concrete Temperature Control and Monitoring | "Method Statement for Concrete Temperature Control and Monitoring" | 2024-06-18 | 2024-07-25 |  |  | Boopathi | 2 | 3
000503 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | 2024-06-01 | 2024-07-22 |  |  | Yean Yee | 1 | 2
000504 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | 2024-06-01 | 2024-07-18 |  |  | Liying | 1 | 2
000505 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves) | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves)" | 2024-06-01 | 2024-08-01 |  |  | Liying | 0 | 1
000506 | Payment Claim No.11 | "Payment Claim No.11" | 2024-06-03 | 2024-06-27 |  |  | Yi Hao | 0 | 1
000507 | Blower Pressure Loss Calculation | "Blower Pressure Loss Calculation" | 2024-06-03 | 2024-07-31 |  |  | Joo Kwan | 2 | 3
000508 | Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump] | "Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump]" | 2024-06-04 | 2024-08-16 |  |  | Keith | 0 | 1
000509 | Monthly Progress Meeting Minutes 0012_20240521 | "Monthly Progress Meeting Minutes 0012_20240521" | 2024-06-04 | 2024-06-04 |  |  | Krishanthy | 0 | 1
000510 | Monthly Progress Presentation No. 12 (0424) | "Monthly Progress Presentation No. 12 (0424)" | 2024-06-04 | 2024-06-04 |  |  | Krishanthy | 0 | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | A | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | 1 | 2
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | 0 | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | 0 | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | 0 | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | 0 | 1
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | 2024-07-31 |  |  | Joo Kwan | 0 | 1
000512 | MSRA, SWP for Bored Pile Hacking and Rectification works | "MSRA, SWP for Bored Pile Hacking and Rectification works" | 2024-06-05 | 2024-06-27 |  |  | Radha | 1 | 2
000513 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | 2024-07-22 |  |  | Yean Yee | 3 | 4
000514 | Vendor Approval of SSN Package (Pressure Switch) | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | 2024-07-22 |  |  | Yean Yee | 2 | 3
000515 | Vendor Approval of SSN Package (Temperature Transmitters) | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | 2024-07-22 |  |  | Yean Yee | 2 | 3
000516 | Submission Of BIM Coordination VCM Model (May-2024) | "Submission Of BIM Coordination VCM Model (May-2024)" | 2024-06-07 | 2024-06-22 |  |  | Heng Peng | 0 | 1
000517 | Process & MEICA Meeting Minutes 0024_20240523 | "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | 2024-07-02 |  |  | Joo Kwan | 0 | 1
000518 | MSRA, SWP for Plate Load Test | "MSRA, SWP for Plate Load Test" | 2024-06-10 | 2024-06-27 |  |  | Boopathi | 1 | 2
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000519 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | 2024-07-01 |  |  | Zora/ HP | A | 1
000520 | C4B Monthly Progress Report Number No.13 (05 24) | "C4B Monthly Progress Report Number No.13 (05 24)" | 2024-06-12 | 2024-06-28 |  |  | Leslie | 0 | 1
000521 | Datasheet for Thermal Insulation | "Datasheet for Thermal Insulation" | 2024-06-12 | 2024-08-29 |  |  | David | 0 | 1
000522 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | 2024-06-28 |  |  | Boopathi | 2 | 3
000523 | Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94 | "Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94" | 2024-06-14 | 2024-06-28 |  |  | Boopathi | 0 | 1
000524 | NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source | "NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source " | 2024-06-14 | 2024-08-26 |  |  | Vincent | 0 | 1
000525 | MSRA & SWP of Civil & Structure Work (Substructure) | "MSRA & SWP of Civil & Structure Work (Substructure)" | 2024-06-18 | 2024-07-01 |  |  | Bryan | 0 | 1
000526 | MSRA & SWP of Mobilization & Demobilization of Machinery | "MSRA & SWP of Mobilization & Demobilization of Machinery" | 2024-06-18 | 2024-07-01 |  |  | Bryan | 0 | 1
000527 | THP-Air Compressor's Ducting Layout | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | 2024-08-12 |  |  | Kyaw Myo | A.1 | 3
000527 | THP-Air Compressor's Ducting Layout | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | 2024-08-12 |  |  | Kyaw Myo | A.1 | 3
000527 | THP-Air Compressor's Ducting Layout | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | 2024-08-12 |  |  | Kyaw Myo | A.1 | 3
000528 | Vendor Approval of Communication Cable (Keystone) | "Vendor Approval of Communication Cable (Keystone)" | 2024-06-19 | 2024-08-05 |  |  | Balaji | 0 | 1
000529 | Process & MEICA Meeting Minutes 0025_20240606 | "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | 2024-08-08 |  |  | Joo Kwan | 0 | 1
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 1
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 1
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | C | 2
000530 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | 2024-08-12 |  |  | Zora | A | 1
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | D | 4
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | D | 4
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | D | 4
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | D | 1
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-06-21 | 2024-07-05 |  |  | Zora/ HP | E | 5
000532 | Monthly Concrete Cube Records for Structural works (02 24) | "Monthly Concrete Cube Records for Structural works (02 24)" | 2024-06-25 | 2024-07-05 |  |  | Boopathi | 0 | 1
000533 | Payment Claim No.12 | "Payment Claim No.12" | 2024-06-25 | 2024-06-28 |  |  | Yi Hao | 1 | 2
000533 | Payment Claim No.12 | "Payment Claim No.12" | 2024-06-28 | 2024-11-07 |  |  | Yi Hao | 1 | 2
000534 | SSN Blower P&ID | "SSN Blower P&ID" | 2024-06-26 | 2024-07-31 |  |  | Joo Kwan | 0 | 1
000535 | THP Line List | "THP Line List" | 2024-06-26 | 2024-08-29 |  |  | Joo Kwan | 0 | 1
000536 | IFC of Compressed Air System - Anchor Bolts Details & Plinth Details | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-26 | 2024-07-05 |  |  | Zora/ HP | B | 2
000537 | Design Calculation for Instrument Air Receiver | "Design Calculation for Instrument Air Receiver" | 2024-06-27 | 2024-08-06 |  |  | Yibo | 1 | 2

## 2024-07
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000107 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" | 2024-07-31 | 2024-09-02 |  |  | David | 1 | 2
000141 | Process Functional Description | "Process Functional Description" | 2024-07-28 | 2024-08-29 |  |  | Joo Kwan | 3 | 4
000142 | THP Process Design Basis | "Process Design Basis" && "THP Process Design Basis" | 2024-07-28 | 2024-08-29 |  |  | Joo Kwan | 3 | 4
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2024-07-09 | 2024-10-29 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2024-07-09 | 2024-10-29 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2024-07-09 | 2024-10-29 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2024-07-09 | 2024-10-29 |  |  | Freedomer | B | 2
000165 | SSN-Lux Calculation and luminaire Schedule | "SSN-Lux Calculation and luminaire Schedule" | 2024-07-09 | 2024-10-29 |  |  | Freedomer | B | 2
000171 | THP Control System Architecture Drawing | "THP Control System Architecture Drawing" | 2024-07-29 | 2024-08-30 |  |  | Low | C | 3
000178 | Data Sheet of Pressure Vessel | "Data Sheet of Pressure Vessel" | 2024-07-28 | 2024-08-29 |  |  | Joo Kwan | 4 | 5
000180 | Data Sheet of PGS | "Data Sheet of PGS" | 2024-07-28 | 2024-09-02 |  |  | Joo Kwan | 3 | 4
000200 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2024-07-22 | 2024-10-29 |  |  | Freedomer | 2 | 3
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-07-06 | 2024-08-23 |  |  | Freedomer | C | 4
000222 | Progressive Cavity Pumps | "Progressive Cavity Pumps" | 2024-07-22 | 2024-08-29 |  |  | Joo Kwan | NA | 1
000223 | THP Plant Safety Valve | "THP Plant Safety Valve" | 2024-07-28 | 2024-08-01 |  |  | Joo Kwan | 1 | 2
000224 | THP System Control Philosophy | "THP System Control Philosophy" | 2024-07-30 | 2024-09-24 |  |  | Joo Kwan | NA | 1
000232 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" | 2024-07-29 | 2024-09-02 |  |  | Yibo | 2 | 3
000237 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" | 2024-07-22 | 2024-08-02 |  |  | Freedomer | NA | 1
000243 | THP IO List | "THP IO List" | 2024-07-16 | 2024-09-17 |  |  | Low | 1 | 2
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 3
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 4
000249 | ST602 – ERSS Design < 6m Depth | "ST602 – ERSS Design < 6m Depth" | 2024-07-02 | 2024-07-17 |  |  | Zora | A.1 | 4
000252 | Sitewide Piperack Lightning Protection System | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2024-07-06 | 2024-09-10 |  |  | Freedomer | A.2 | 5
000252 | Sitewide Piperack Lightning Protection System | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2024-07-06 | 2024-09-10 |  |  | Freedomer | A.2 | 5
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" | 2024-07-31 | 2024-08-19 |  |  | Zora | A | 1
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | 2024-07-31 | 2024-08-19 |  |  | Zora | I | 2
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | 2024-07-31 | 2024-08-19 |  |  | Zora | J | 2
000274 | ST612_Typical Railing Design Calculation | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | 2024-07-31 | 2024-08-19 |  |  | Zora | I | 2
000295 | Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE) | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" | 2024-07-31 | 2024-08-29 |  |  | David | 1 | 2
000296 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-07-15 | 2024-08-12 |  |  | Boopathi | 2 | 3
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-07-06 | 2024-10-29 |  |  | Freedomer | C | 3
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-07-06 | 2024-10-29 |  |  | Freedomer | C | 3
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-07-06 | 2024-10-29 |  |  | Freedomer | C | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-07-06 | 2024-10-29 |  |  | Freedomer | C | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-07-06 | 2024-10-29 |  |  | Freedomer | C | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2024-07-06 | 2024-10-29 |  |  | Freedomer | C | 2
000309 | SSN Listing of Interface Points | "SSN Listing of Interface Points" | 2024-07-22 | 2024-10-29 |  |  | Freedomer | B | 2
000315 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | 2024-07-17 | 2024-09-17 |  |  | Balaji/ Karthik | A.C | 1
000318 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-07-22 | 2024-09-24 |  |  | Freedomer | 2 | 3
000322 | Process Functional Description | "Process Functional Description" | 2024-07-23 | 2024-08-29 |  |  | Qili | 3 | 4
000330 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2024-07-17 | 2024-09-17 |  |  | Freedomer | NA | 1
000334 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" | 2024-07-28 | 2024-08-16 |  |  | Freedomer | 3 | 4
000349 | THP Lux Calculation and Luminaire Schedule | "THP Lux Calculation and Luminaire Schedule" | 2024-07-16 | 2024-10-29 |  |  | Freedomer | B | 2
000358 | C4B Sidestream Nitrogen Removal Process Equipment List | "C4B Sidestream Nitrogen Removal Process Equipment List" | 2024-07-24 | 2024-08-29 |  |  | Joo kwan | 2 | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " | 2024-07-04 | 2024-08-12 |  |  | Zora | B | 2
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | 2024-08-12 |  |  | Zora | A | 3
000404 | SSN Chemical Consumption Calculation | "SSN Chemical Consumption Calculation" | 2024-07-28 | 2024-08-29 |  |  | Qili | 2 | 3
000406 | SSN 22kV MV Power Cable Sizing Calculations | "SSN 22kV MV Power Cable Sizing Calculations" | 2024-07-06 | 2024-07-22 |  |  | Freedomer | 2 | 3
000408 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-07-05 | 2024-08-29 |  |  | Qili | 0 | 2
000408 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-07-05 | 2024-08-29 |  |  | Qili | B | 2
000408 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-07-05 | 2024-08-29 |  |  | Qili | B | 2
000408 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-07-05 | 2024-08-29 |  |  | Qili | 0 | 1
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2024-07-05 | 2024-08-29 |  |  | Qili | 2 | 3
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2024-07-05 | 2024-08-29 |  |  | Qili | B | 3
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2024-07-05 | 2024-08-29 |  |  | Qili | B | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | 2024-08-29 |  |  | Kyaw Myo | A.2 | 3
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | 2024-08-29 |  |  | Kyaw Myo | A.1 | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | 2024-08-29 |  |  | Kyaw Myo | A.1 | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | 2024-08-29 |  |  | Kyaw Myo | A.1 | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | 2024-08-29 |  |  | Kyaw Myo | A.1 | 2
000429 | Piping General Arrangement-UG & Plant Drain Manholes | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | 2024-08-29 |  |  | Kyaw Myo | A.1 | 2
000438 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-07-28 | 2024-09-18 |  |  | Yean Yee | 3 | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | E | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | D | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | C | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | C | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | F | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-07-12 | 2024-09-10 |  |  | Freedomer | F | 3
000446 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | 2024-07-16 | 2024-08-16 |  |  | Zora | 0 | 5
000450 | Vendor Approval of ERSS Works (Singlee) | "Vendor Approval of ERSS Works (Singlee)" | 2024-07-09 | 2024-07-17 |  |  | Yuen Fatt | 0 | 1
000456 | Inspection and test plan for Compressed Air System | "Inspection and test plan for Compressed Air System" | 2024-07-22 | 2024-08-20 |  |  | Mohan | 1 | 2
000458 | SSN Transformer Data Sheet | "SSN Transformer Data Sheet" | 2024-07-09 | 2024-09-10 |  |  | Freedomer | 2 | 3
000459 | Vendor Approval of SSN Package (Radar Level Transmitter) | "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-07-30 | 2024-09-18 |  |  | Yean Yee | 2 | 3
000463 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-07-24 | 2024-09-18 |  |  | Yean Yee | 2 | 3
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 5
000475 | IFC of ST610 (Underground Services) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " | 2024-07-11 | 2024-08-21 |  |  | Zora | D | 6
000489 | Project Safety Review for ERSS | "Project Safety Review for ERSS" | 2024-07-09 | 2024-08-12 |  |  | Leslie | 1 | 2
000494 | Method Statement for Concrete Temperature Control and Monitoring | "Method Statement for Concrete Temperature Control and Monitoring" | 2024-07-28 | 2024-08-13 |  |  | Mohan | 2 | 3
000512 | MSRA, SWP for Bored Pile Hacking and Rectification works | "MSRA, SWP for Bored Pile Hacking and Rectification works" | 2024-07-02 | 2024-07-26 |  |  | Boopathi | 1 | 2
000518 | MSRA, SWP for Plate Load Test | "MSRA, SWP for Plate Load Test" | 2024-07-04 | 2024-08-05 |  |  | Mohan | 1 | 2
000522 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-07-04 | 2024-07-17 |  |  | Boopathi | 2 | 3
000522 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-07-22 | 2024-08-12 |  |  | Boopathi | 2 | 3
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 5
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 4
000531 | IFC of ST601 – ERSS < 4m | "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 1
000531 | IFC of ST601 – ERSS < 4m | "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 1
000531 | IFC of ST601 – ERSS < 4m | "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 1
000531 | IFC of ST601 – ERSS < 4m | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " | 2024-07-22 | 2024-08-13 |  |  | Zora/ HP | E | 5
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 1
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000538 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | 2024-07-15 |  |  | Aaron | A | 2
000539 | Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616 | "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" && "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " | 2024-07-02 | 2024-07-15 |  |  | Mohan | 0 | 2
000540 | Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616) | "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " | 2024-07-02 | 2024-07-15 |  |  | Boopathi | 0 | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2024-07-03 | 2024-07-31 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2024-07-03 | 2024-07-31 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2024-07-03 | 2024-07-31 |  |  | Yibo | D | 3
000542 | Process & MEICA Meeting Minutes 0026_20240624 | "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | 2024-08-29 |  |  | Joo Kwan | A | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000543 | Blower Circuit Diagram | "Blower Circuit Diagram" | 2024-07-04 | 2024-10-29 |  |  | Joo Kwan | C | 1
000544 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | 2024-07-04 | 2024-07-16 |  |  | Keith | 0 | 1
000545 | Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615) | "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | 2024-07-04 | 2024-07-17 |  |  | Boopathi | 0 | 1
000546 | Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.) | "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2024-07-05 | 2024-07-18 |  |  | Theint Theint | 0 | 1
000547 | Unpriced PO for Cables (Keystone) | "Unpriced PO for Cables (Keystone)" | 2024-07-08 | 2024-08-05 |  |  | Yi Hao | 0 | 1
000548 | Unpriced PO for Sludge Pump (Netzsch) | "Unpriced PO for Sludge Pump (Netzsch) " && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" | 2024-07-08 | 2024-08-29 |  |  | Yi Hao | 0 | 2
000549 | Unpriced PO for cPVC Pipes (George Fischer) | "Unpriced PO for cPVC Pipes (George Fischer)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" | 2024-07-08 | 2024-08-29 |  |  | Yi Hao | 0 | 2
000550 | Submission Of BIM Coordination VCM Model (Jun-2024) | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" | 2024-07-08 | 2024-07-23 |  |  | Heng Peng | 0 | 3
000551 | MSRA & SWP for Pre-Augering Work | "MSRA & SWP for Pre-Augering Work" | 2024-07-08 | 2024-08-08 |  |  | Bryan | 0 | 1
000552 | C4B Monthly Progress Report Number No.14 (06 24) | "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | 2024-07-09 |  |  | Krishanthy | 1 | 2
000552 | C4B Monthly Progress Report Number No.14 (06 24) | "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-13 | 2024-07-30 |  |  | Leslie | 1 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2024-08-13 |  |  | Qili | 2 | 4
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2024-08-13 |  |  | Qili | 0 | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2024-08-13 |  |  | Qili | 0 | 3
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2024-08-13 |  |  | Qili | A | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | 2024-08-13 |  |  | Qili | A | 2
000554 | SSN UPS and Battery Room Layout | "Milestone 2 SSN Electrical Building" && "SSN UPS and Battery Room Layout" | 2024-07-10 | 2024-09-02 |  |  | Low | A | 2
000555 | SSN Process Non-Process room layout | "Milestone 2 SSN Electrical Building" && "SSN Process Non-Process room layout" | 2024-07-10 | 2024-09-02 |  |  | Low | A | 2
000556 | THP LPS Risk Assessment Report | "THP LPS Risk Assessment Report" | 2024-07-10 | 2024-09-24 |  |  | Freedomer | 2 | 3
000557 | SSN LPS Risk Assessment Report | "SSN LPS Risk Assessment Report" | 2024-07-10 | 2024-09-24 |  |  | Freedomer | 2 | 3
000558 | BIM Bi-Weekly Meeting Minutes 0028_20240626 | "BIM Bi-Weekly Meeting Minutes 0028_20240626" | 2024-07-10 | 2024-08-30 |  |  | Heng Peng | 0 | 1
000559 | Preliminary Design and Vendor Approval for Parabolic Screen | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" | 2024-07-12 | 2024-09-02 |  |  | Yibo | 0 | 3
000560 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" | 2024-07-12 | 2024-08-23 |  |  | David | 1 | 2
000561 | CSA Meeting Minutes 0024,0025,0026_May | "CSA Meeting Minutes 0024,0025,0026_May" | 2024-07-12 | 2024-08-12 |  |  | Zora | 0 | 1
000561 | CSA Meeting Minutes 0024,0025,0026_May | "CSA Meeting Minutes 0024,0025,0026_May" | 2024-07-12 | 2024-08-12 |  |  | Zora | 0 | 1
000561 | CSA Meeting Minutes 0024,0025,0026_May | "CSA Meeting Minutes 0024,0025,0026_May" | 2024-07-12 | 2024-08-12 |  |  | Zora | 0 | 1
000562 | CSA Meeting Minutes 0027,0028_June | "CSA Meeting Minutes 0027,0028_June" | 2024-07-12 | 2024-07-30 |  |  | Zora | 0 | 1
000562 | CSA Meeting Minutes 0027,0028_June | "CSA Meeting Minutes 0027,0028_June" | 2024-07-12 | 2024-07-30 |  |  | Zora | 0 | 1
000563 | Monthly Concrete Cube Records for Structural works (03 24) | "Monthly Concrete Cube Records for Structural works (03 24)" | 2024-07-12 | 2024-08-12 |  |  | Mohan | 0 | 1
000564 | MSRA, SWP for Electrical Work | "MSRA, SWP for Electrical Work" | 2024-07-12 | 2024-09-24 |  |  | Bryan | 0 | 1
000565 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " | 2024-07-13 | 2024-08-23 |  |  | Bryan | 1 | 2
000566 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | 2024-07-13 | 2024-08-06 |  |  | Zuo Yu | 1 | 2
000567 | Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area | "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" && "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " | 2024-07-15 | 2024-08-12 |  |  | Krishanthy | 0 | 2
000568 | Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area | "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " | 2024-07-15 | 2024-08-22 |  |  | Leslie | 0 | 2
000569 | THP Instrument Lists | "THP Instrument Lists" | 2024-07-16 | 2024-09-17 |  |  | Yean Yee | 1 | 2
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-07-16 | 2024-08-21 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000571 | THP MCC Schematic Diagram | "THP SLD" && "THP MCC Schematic Diagram" | 2024-07-16 | 2024-08-23 |  |  | Freedomer | E | 6
000572 | IFC of BSB Silo Area Pump Plinth Details | "IFC of BSB Silo Area Pump Plinth Details " | 2024-07-17 | 2024-08-28 |  |  | Zora | A | 1
000573 | IFC of SSN Electrical Building Transformer Plinth Details | "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | 2024-09-14 |  |  | Zora | A | 1
000574 | Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) | "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2024-07-17 | 2024-08-12 |  |  | Theint Theint | 0 | 1
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000575 | THP MCC Outline Drawing | "THP SLD" && "THP MCC Outline Drawing" | 2024-07-17 | 2024-08-15 |  |  | Freedomer | E | 6
000576 | Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) | "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2024-07-17 | 2024-08-12 |  |  | Theint Theint | 0 | 1
000577 | Vendor Approval for PVC Lining System - (Linabond) | "Vendor Approval for PVC Lining System - (Linabond)" | 2024-07-17 | 2024-08-12 |  |  | Boopathi | 0 | 1
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | B | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000578 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-07-20 | 2024-08-21 |  |  | Zora | C | 3
000579 | SSN PLC I/O List | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | 2024-07-22 | 2024-09-17 |  |  | Balaji/ Karthik | 4 | 5
000580 | THP Cast in Layout Inside Bio-solid Building | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | 2024-10-04 |  |  | Geno | A | 1
000580 | THP Cast in Layout Inside Bio-solid Building | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | 2024-10-04 |  |  | Geno | A | 1
000580 | THP Cast in Layout Inside Bio-solid Building | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | 2024-10-04 |  |  | Geno | A | 1
000580 | THP Cast in Layout Inside Bio-solid Building | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | 2024-10-04 |  |  | Geno | A | 1
000581 | Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2024-07-23 | 2024-08-14 |  |  | Sithu | X | 3
000582 | Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details | "Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details" | 2024-07-23 | 2024-08-13 |  |  | Sithu | A.1 | 1
000583 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | 2024-07-24 | 2024-09-02 |  |  | Balaji/ Karthik | 3 | 4
000584 | Process & MEICA Meeting Minutes 0027_20240704 | "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-24 | 2024-08-29 |  |  | Joo Kwan | 0 | 1
000585 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | 2024-07-25 | 2024-08-12 |  |  | Boopathi | 0 | 1
000585 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | 2024-07-25 | 2024-08-12 |  |  | Boopathi | 0 | 1
000586 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | 2024-07-25 | 2024-08-12 |  |  | Boopathi | 0 | 1
000586 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | 2024-07-25 | 2024-08-12 |  |  | Boopathi | 0 | 1
000587 | Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd. | "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2024-07-25 | 2024-08-12 |  |  | Yuen Fatt | 0 | 1
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 3
000588 | THP URA Submission | "THP URA Submission" | 2024-07-25 | 2024-08-02 |  |  | Zora | A | 3
000589 | Vendor Approval of Earthing System & LPS Material | "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" | 2024-07-26 | 2024-08-05 |  |  | Freedomer | 1 | 2
000590 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-27 | 2024-08-15 |  |  | Freedomer | 2 | 3
000591 | PLant Drain Hydraulic Calculation | "PLant Drain Hydraulic Calculation" | 2024-07-28 | 2024-09-02 |  |  | Joo Kwan | 1 | 2
000592 | Vendor Approval of SS Cable Ladder, Trays and Accessories | "Vendor Approval of SS Cable Ladder, Trays and Accessories" | 2024-07-28 | 2024-08-15 |  |  | Freedomer | 0 | 1
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | 2024-10-09 |  |  | David | 1 | 2
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | 2024-10-09 |  |  | David | 1 | 2
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | 2024-10-09 |  |  | David | 1 | 2
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | 2024-10-09 |  |  | David | 1 | 2
000594 | Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight) | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" | 2024-07-29 | 2024-08-05 |  |  | Yi Hao | 0 | 1
000595 | Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen) | "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | 2024-07-30 | 2024-08-29 |  |  | Yi Hao | 0 | 1
000596 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024" | 2024-07-30 | 2024-10-07 |  |  | Vincent | 0 | 1
000597 | Air Compressor Pressure Loss Calculation | "Air Compressor Pressure Loss Calculation" | 2024-07-30 | 2024-09-04 |  |  | Joo Kwan | 1 | 2
000598 | Underground Cast In Schedule and Details | "Underground Cast In Schedule and Details" | 2024-07-30 | 2024-09-02 |  |  | Kyaw Myo | A | 1
000598 | Underground Cast In Schedule and Details | "Underground Cast In Schedule and Details" | 2024-07-30 | 2024-09-02 |  |  | Kyaw Myo | A | 1
000598 | Underground Cast In Schedule and Details | "Underground Cast In Schedule and Details" | 2024-07-30 | 2024-09-02 |  |  | Kyaw Myo | A | 1
000598 | Underground Cast In Schedule and Details | "Underground Cast In Schedule and Details" | 2024-07-30 | 2024-09-02 |  |  | Kyaw Myo | A | 1
000599 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" | 2024-07-30 | 2024-10-10 |  |  | Balaji/ Karthik | 1 | 2
000600 | Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings | "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2024-07-31 | 2024-09-02 |  |  | Mohan | 0 | 1
000601 | THP Functional Design Specification | "THP Functional Design Specification" | 2024-07-31 | 2024-10-09 |  |  | Joo Kwan | 2 | 3
000602 | THP Alarm List | "THP Alarm List" | 2024-07-31 | 2024-11-08 |  |  | Low | 0 | 1
000603 | SSN Underground Piping Stress Calculation Report | "SSN Underground Piping Stress Calculation Report" | 2024-07-31 | 2024-09-02 |  |  | David | 0 | 1
000631 | Submission Of BIM Coordination VCM Model (Jul-2024) | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" | 2024-07-08 | 2024-08-08 |  |  | Heng Peng | 0 | 3
000653 | Unpriced PO for Hyperbolix Mixer (Entec International) | "Unpriced PO for Hyperbolix Mixer (Entec International)" | 2024-07-08 | 2024-08-29 |  |  | Yi Hao | 0 | 1

## 2024-08
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000092 | Piping Material Specification | "Piping Material Specification" | 2024-08-07 | 2024-09-02 |  |  | Liying | 3 | 4
000093 | Piperack P&IDs | "Piperack P&IDs" | 2024-08-20 | 2024-10-29 |  |  | Qili | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2024-08-20 | 2024-10-29 |  |  | Qili | E | 6
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | 2024-10-01 |  |  | Nicolas | 1 | 4
000143 | THP Process Flow Diagram | "THP Process Flow Diagram" | 2024-08-26 | 2024-10-10 |  |  | Joo Kwan | B | 3
000143 | THP Process Flow Diagram | "THP Process Flow Diagram" | 2024-08-26 | 2024-10-10 |  |  | Joo Kwan | B | 2
000172 | THP Compressed Air Calculation | "THP Compressed Air Calculation" | 2024-08-15 | 2024-11-07 |  |  | Joo Kwan | 2 | 3
000173 | SSN: Plant Drain Hydraulic Profile and calculation | "SSN: Plant Drain Hydraulic Profile and calculation " | 2024-08-07 | 2024-10-09 |  |  | Qili | 2 | 3
000173 | SSN: Plant Drain Hydraulic Profile and calculation | "SSN: Plant Drain Hydraulic Profile and calculation " | 2024-08-07 | 2024-10-09 |  |  | Qili | C | 3
000177 | Data Sheet of Air Compressor System | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | 2024-08-12 | 2024-10-25 |  |  | Joo Kwan | 3 | 4
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | B | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "SSN Power Layout Plan" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | D | 4
000227 | SSN Power Layout Plan | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | 2024-08-13 | 2024-12-14 |  |  | Freedomer | D | 5
000229 | Preliminary Design and Vendor Approval of Mixer | "Preliminary Design and Vendor Approval of Mixer " | 2024-08-20 | 2024-09-02 |  |  | Yibo | 1 | 2
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | B | 5
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | B | 5
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | B | 4
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | B | 4
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | B | 4
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | C | 2
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" | 2024-08-13 | 2024-12-07 |  |  | Freedomer | C | 2
000238 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2024-08-07 | 2024-09-02 |  |  | Liying | 2 | 3
000359 | Vendor Approval of THP Train Instrument (Siemens) | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2024-08-20 | 2024-09-03 |  |  | Yean Yee/ Cambi | 3 | 4
000360 | SSN PFD | "SSN PFD" | 2024-08-29 | 2024-10-09 |  |  | Qili | D | 6
000360 | SSN PFD | "SSN PFD" | 2024-08-29 | 2024-10-09 |  |  | Qili | D | 6
000384 | SSN Process Design Calculation | "SSN Process Design Calculation" | 2024-08-01 | 2024-09-04 |  |  | Joo Kwan | 1 | 2
000385 | SSN Process Design Basis | "SSN Process Design Basis" | 2024-08-02 | 2024-09-04 |  |  | Qili | 3 | 4
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000390 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" | 2024-08-27 | 2024-10-29 |  |  | Balaji/ Karthik | A.1 | 2
000393 | THP Schematic Diagram for Compressed Air System | "THP Schematic Diagram for Compressed Air System" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000393 | THP Schematic Diagram for Compressed Air System | "THP Schematic Diagram for Compressed Air System" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000394 | THP Schematic Diagram for Compressed Air Dryer | "THP Schematic Diagram for Compressed Air Dryer" | 2024-08-13 | 2024-11-08 |  |  | Freedomer | A | 2
000395 | Air Compressor Motor Outline Drawing | "Air Compressor Motor Outline Drawing " | 2024-08-16 | 2024-11-04 |  |  | Freedomer | B | 2
000401 | SSN Control System Architecture Drawing | "SSN Control System Architecture Drawing" | 2024-08-26 | 2024-10-16 |  |  | Low | B | 2
000403 | SSN Control Philosophy | "SSN Control Philosophy" | 2024-08-12 | 2024-09-03 |  |  | Qili | 3 | 4
000415 | SSN Equipment Sizing Calculation | "SSN Equipment Sizing Calculation" | 2024-08-12 | 2024-10-11 |  |  | Qili | 1 | 2
000416 | SSN Process Hydraulic Calculation & Drawing | "SSN Process Hydraulic Calculation & Drawing" | 2024-08-21 | 2024-10-25 |  |  | Qili | 2 | 3
000416 | SSN Process Hydraulic Calculation & Drawing | "SSN Process Hydraulic Calculation & Drawing" | 2024-08-21 | 2024-10-25 |  |  | Qili | C | 3
000417 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-08-15 | 2024-11-08 |  |  | Karthik/ Cambi | 1 | 2
000421 | Data Sheet of THP Feed Pump | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" | 2024-08-12 | 2024-09-10 |  |  | Joo Kwan | 2 | 3
000422 | Data Sheet and Drawing of Reactor Feed Pump | "Data Sheet and Drawing of Reactor Feed Pump" | 2024-08-12 | 2024-09-10 |  |  | Joo Kwan | 2 | 3
000430 | Piping Special Item List | "Piping Special Item List" | 2024-08-01 | 2024-09-02 |  |  | Liying | 1 | 2
000441 | SSN IO Sample Schematic Drawing | "SSN sample AC/DC/IO circuit diagram" && "SSN IO Sample Schematic Drawing" | 2024-08-20 | 2024-10-17 |  |  | Low | B | 2
000441 | SSN IO Sample Schematic Drawing | "SSN IO Sample Schematic Drawing" | 2024-08-20 | 2024-10-17 |  |  | Low | B | 1
000441 | SSN IO Sample Schematic Drawing | "SSN IO Sample Schematic Drawing" | 2024-08-20 | 2024-10-17 |  |  | Low | B | 1
000441 | SSN IO Sample Schematic Drawing | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | 2024-08-20 | 2024-10-17 |  |  | Low | A | 2
000441 | SSN IO Sample Schematic Drawing | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | 2024-08-20 | 2024-10-17 |  |  | Low | A | 2
000441 | SSN IO Sample Schematic Drawing | "SSN IO Sample Schematic Drawing" | 2024-08-20 | 2024-10-17 |  |  | Low | B | 1
000441 | SSN IO Sample Schematic Drawing | "SSN IO Sample Schematic Drawing" | 2024-08-20 | 2024-10-17 |  |  | Low | B | 1
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | 2024-08-28 | 2024-09-22 |  |  | Zora | 0 | 5
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | 2024-09-22 |  |  | Zora | A | 1
000462 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-08-01 | 2024-09-18 |  |  | Yean Yee | 2 | 3
000464 | Vendor Approval of SSN Package (Capacitive Level Switches) | "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-08-01 | 2024-09-18 |  |  | Yean Yee | 2 | 3
000468 | Design for Safety Report 2 | "Design for Safety Report 2" | 2024-08-21 | 2024-09-17 |  |  | Krishanthy | 2 | 4
000502 | Vendor Approval of SSN Package (Pressure Gauges) | "Vendor Approval of SSN Package (Pressure Gauges)" | 2024-08-27 | 2024-11-08 |  |  | Yean Yee | 1 | 2
000515 | Vendor Approval of SSN Package (Temperature Transmitters) | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-08-06 | 2024-09-18 |  |  | Yean Yee | 2 | 3
000534 | SSN Blower P&ID | "SSN Blower P&ID" | 2024-08-15 | 2024-09-06 |  |  | Qili | NA | 1
000544 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | 2024-08-03 | 2024-08-19 |  |  | Yuen Fatt | NA | 1
000566 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | 2024-08-16 | 2024-10-10 |  |  | Balaji/ Karthik | 1 | 2
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 4
000588 | THP URA Submission | "THP URA Submission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 3
000588 | THP URA Submission | "THP URA Submission" | 2024-08-24 | 2024-09-13 |  |  | Zora | A | 3
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | B | 2
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000604 | LVSG Schematic Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | B | 2
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000606 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" | 2024-08-01 | 2024-09-24 |  |  | Freedomer | 1 | 2
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000607 | SSN LVSG 0101AB Outline GA Drawing | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-08-01 | 2024-09-18 |  |  | Freedomer | D | 4
000608 | Unpriced PO for Centrifugal Pump (KSB) | "Unpriced PO for Centrifugal Pump (KSB)" | 2024-08-01 | 2024-08-29 |  |  | Yi Hao | 0 | 1
000609 | Unpriced PO for FRP Tank (Jizhou Zhongyi) | "Unpriced PO for FRP Tank (Jizhou Zhongyi)" | 2024-08-01 | 2024-08-29 |  |  | Yi Hao | 0 | 1
000610 | LPS Sample Materials – U-Clamp Connector | "LPS Sample Materials – U-Clamp Connector" | 2024-08-01 | 2024-08-05 |  |  | Yuen Fatt | 0 | 1
000611 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | 2024-08-02 | 2024-08-19 |  |  | Boopathi | 0 | 2
000611 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | 2024-08-02 | 2024-09-17 |  |  | Boopathi | 0 | 2
000612 | Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings | "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2024-08-02 | 2024-09-02 |  |  | Mohan | 0 | 1
000613 | Payment Claim No.13 | "Payment Claim No.13" | 2024-08-02 | 2024-08-16 |  |  | Yi Hao | 0 | 1
000614 | NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions | "NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions" | 2024-08-02 | 2024-10-07 |  |  | Vincent | 0 | 1
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A.2 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A | 3
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A | 3
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | 2024-08-19 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A.2 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A | 3
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A | 3
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A.3 | 2
000615 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-27 | 2024-09-10 |  |  | Sithu | A.3 | 2
000616 | Strength Calculation for Biomass Separator | "Strength Calculation for Biomass Separator" | 2024-08-05 | 2024-09-02 |  |  | Qili | 0 | 1
000617 | Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024 | "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" | 2024-08-05 | 2024-08-21 |  |  | Max | 0 | 1
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | 2024-09-05 |  |  | Yibo | C | 3
000619 | Bored Piling Pile Eccentricity Reports (ECC 01 to 07) | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" | 2024-08-05 | 2024-08-19 |  |  | Mohan | 0 | 1
000620 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | 2024-08-05 | 2024-08-19 |  |  | Boopathi | 0 | 1
000620 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | 2024-08-05 | 2024-08-19 |  |  | Boopathi | 0 | 1
000621 | SSN Reactor Floor flat Design Memo | "SSN Reactor Floor flat Design Memo" | 2024-08-05 | 2024-08-21 |  |  | Qili | 0 | 1
000622 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-08-06 | 2024-08-15 |  |  | Qili | 0 | 1
000622 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-08-06 | 2024-08-15 |  |  | Joo Kwan | 0 | 1
000623 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | 2024-08-06 | 2024-10-29 |  |  | Radha | 5 | 6
000624 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" | 2024-08-06 | 2024-09-06 |  |  | Mohan | 2 | 3
000625 | FAT Procedure for Air Receiver and Air Dryer (Compressor air system) | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" | 2024-08-06 | 2024-09-04 |  |  | Mohan | 0 | 1
000626 | SSN MV Cable and Pilot Cable Data Sheet and Specification | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | 2024-08-07 | 2024-10-29 |  |  | Freedomer | 1 | 2
000627 | Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024 | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" | 2024-08-07 | 2024-08-19 |  |  | Mohan | 0 | 1
000628 | Monthly Progress Meeting Minutes 0013_20240618 | "Monthly Progress Meeting Minutes 0013_20240618" | 2024-08-07 | 2024-08-12 |  |  | Krishanthy | 0 | 1
000628 | Monthly Progress Meeting Minutes 0013_20240618 | "Monthly Progress Meeting Minutes 0013_20240618" | 2024-08-07 | 2024-08-12 |  |  | Krishanthy | 0 | 1
000629 | Monthly Progress Meeting Minutes 0014_20240723 | "Monthly Progress Meeting Minutes 0014_20240723" | 2024-08-07 | 2024-08-12 |  |  | Krishanthy | 0 | 1
000629 | Monthly Progress Meeting Minutes 0014_20240723 | "Monthly Progress Meeting Minutes 0014_20240723" | 2024-08-07 | 2024-08-12 |  |  | Krishanthy | 0 | 1
000630 | Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | 2024-08-07 | 2024-08-19 |  |  | Mohan | 1 | 2
000631 | Submission Of BIM Coordination VCM Model (Jul-2024) | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" | 2024-08-12 | 2024-08-26 |  |  | Heng Peng | 0 | 3
000632 | MSRA, SWP for Erection, Dismantling and Use of Scaffold | "MSRA, SWP for Erection, Dismantling and Use of Scaffold " | 2024-08-12 | 2024-08-30 |  |  | Bryan | 0 | 1
000633 | MSRA, SWP for Jet Grouting | "MSRA, SWP for Jet Grouting" | 2024-08-12 | 2024-09-02 |  |  | Bryan | 0 | 1
000634 | THP Pump Motor Data Sheet | "THP Pump Motor Data Sheet" | 2024-08-12 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000634 | THP Pump Motor Data Sheet | "THP Pump Motor Data Sheet" | 2024-08-12 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000634 | THP Pump Motor Data Sheet | "THP Pump Motor Data Sheet" | 2024-08-12 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000634 | THP Pump Motor Data Sheet | "THP Pump Motor Data Sheet" | 2024-08-12 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000634 | THP Pump Motor Data Sheet | "THP Pump Motor Data Sheet" | 2024-08-12 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000635 | Data Sheet of Flash Tank Discharge Pump | "Data Sheet of Flash Tank Discharge Pump " | 2024-08-12 | 2024-10-09 |  |  | Joo Kwan | 1 | 2
000636 | Data Sheet of Precooler S2 CIRC Pump | "Data Sheet of Precooler S2 CIRC Pump" | 2024-08-12 | 2024-10-09 |  |  | Joo Kwan | 1 | 2
000637 | Data Sheet of Digester Feed Pump | "Data Sheet of Digester Feed Pump" | 2024-08-12 | 2024-10-09 |  |  | Joo Kwan | 1 | 2
000638 | Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings) | "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-08-13 | 2024-08-19 |  |  | Yuen Fatt | 0 | 1
000639 | SSN Functional Design Specification | "SSN Functional Design Specification" | 2024-08-13 | 2024-10-09 |  |  | Balaji | 1 | 2
000640 | Piping General Arrangement of Air Compressor system | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | 2024-08-13 | 2024-10-09 |  |  | Geno | A.1 | 2
000640 | Piping General Arrangement of Air Compressor system | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | 2024-08-13 | 2024-10-09 |  |  | Geno | A.1 | 2
000641 | BCA Approval of ST612 – Typical Railing | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | 2024-08-30 |  |  | Zora | F | 1
000641 | BCA Approval of ST612 – Typical Railing | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | 2024-08-30 |  |  | Zora | F | 1
000641 | BCA Approval of ST612 – Typical Railing | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | 2024-08-30 |  |  | Zora | F | 1
000641 | BCA Approval of ST612 – Typical Railing | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | 2024-08-30 |  |  | Zora | F | 1
000642 | Inspection Test Plan for HDPE Pipe Installation | "Inspection Test Plan for HDPE Pipe Installation" | 2024-08-13 | 2024-09-24 |  |  | Mohan | 1 | 2
000643 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2024-08-13 | 2024-10-16 |  |  | Mohan | 1 | 3
000644 | THP Lux Simulation Report | "THP Lux Simulation Report" | 2024-08-13 | 2024-09-26 |  |  | Freedomer | 2 | 4
000645 | SSN Lux Simulation Report | "SSN Lux Simulation Report" | 2024-08-13 | 2024-09-26 |  |  | Freedomer | 3 | 4
000646 | Aeration Blower System Architecture Drawing | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" | 2024-08-13 | 2024-08-27 |  |  | Low/ Fox | B | 3
000647 | Waterproofing Concrete Demarcation of SSN Main Water Tank | "Waterproofing Concrete Demarcation of SSN Main Water Tank " | 2024-08-13 | 2024-09-11 |  |  | Sithu | A | 1
000647 | Waterproofing Concrete Demarcation of SSN Main Water Tank | "Waterproofing Concrete Demarcation of SSN Main Water Tank " | 2024-08-13 | 2024-09-11 |  |  | Sithu | A | 1
000648 | Data Sheet of Desuperheater | "Data Sheet of Desuperheater " | 2024-08-12 | 2024-09-03 |  |  | Joo Kwan | 0 | 1
000649 | THP Feed Pump Pressure Loss Calculation | "THP Feed Pump Pressure Loss Calculation" | 2024-08-15 | 2024-10-08 |  |  | Joo Kwan | 0 | 1
000650 | Desuperheater Calculation | "Desuperheater Calculation" | 2024-08-15 | 2024-08-23 |  |  | Joo Kwan | 0 | 1
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2024-08-15 | 2024-10-09 |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2024-08-15 | 2024-10-09 |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2024-08-15 | 2024-10-09 |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2024-08-15 | 2024-10-09 |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2024-08-15 | 2024-10-09 |  |  | Joo Kwan | B | 2
000652 | Process & MEICA Meeting Minutes 0030_20240801 | "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | 2024-09-03 |  |  | Joo Kwan | 0 | 1
000654 | Unpriced PO for Dosing Pump (ProMinent) | "Unpriced PO for Dosing Pump (ProMinent)" | 2024-08-15 | 2024-08-29 |  |  | Yi Hao | 0 | 1
000655 | Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg | "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-08-15 | 2024-09-03 |  |  | Mohan | 0 | 1
000656 | Data Sheet for Steam Sparger Package | "Data Sheet for Steam Sparger Package" | 2024-08-16 | 2024-09-10 |  |  | Joo Kwan | 1 | 2
000657 | Procedure for Welding of Underground HDPE Pipe | "Procedure for Welding of Underground HDPE Pipe" | 2024-08-19 | 2024-09-10 |  |  | Mohan | 0 | 1
000658 | C4B Monthly Progress Report Number No.15 (07 24) | "C4B Monthly Progress Report Number No.15 (07 24)" | 2024-08-19 | 2024-09-06 |  |  | Leslie | 0 | 1
000659 | Sample Board Submission for uPVC Pipe 6” & 4” | "Sample Board Submission for uPVC Pipe 6” & 4” " | 2024-08-19 | 2024-09-26 |  |  | Mohan | 0 | 1
000660 | SSN Control Network Connection Drawing | "SSN Control Network Connection Drawing" | 2024-08-19 | 2024-09-06 |  |  | Low | A | 1
000660 | SSN Control Network Connection Drawing | "SSN Control Network Connection Drawing" | 2024-08-19 | 2024-09-06 |  |  | Low | A | 1
000660 | SSN Control Network Connection Drawing | "SSN Control Network Connection Drawing" | 2024-08-19 | 2024-09-06 |  |  | Low | A | 1
000660 | SSN Control Network Connection Drawing | "SSN Control Network Connection Drawing" | 2024-08-19 | 2024-09-06 |  |  | Low | A | 1
000660 | SSN Control Network Connection Drawing | "SSN Control Network Connection Drawing" | 2024-08-19 | 2024-09-06 |  |  | Low | A | 1
000660 | SSN Control Network Connection Drawing | "SSN Control Network Connection Drawing" | 2024-08-19 | 2024-09-06 |  |  | Low | A | 1
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" | 2024-08-20 | 2024-09-23 |  |  | Kyaw Myo | A.1 | 3
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " | 2024-08-20 | 2024-09-23 |  |  | Kyaw Myo | A.1 | 2
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " | 2024-08-20 | 2024-09-23 |  |  | Kyaw Myo | A.1 | 2
000662 | Flash Tank Discharge Pump Pressure Loss Calculation | "Flash Tank Discharge Pump Pressure Loss Calculation" | 2024-08-20 | 2024-10-09 |  |  | Joo Kwan | 0 | 1
000663 | Precooler S2 Circ Pump Pressure Loss Calculation | "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-08-20 | 2024-10-08 |  |  | Joo Kwan | 0 | 1
000664 | Steam Sparger Calculation | "Steam Sparger Calculation" | 2024-08-20 | 2024-09-10 |  |  | Joo Kwan | 1 | 2
000665 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-08-21 | 2024-09-24 |  |  | Radha | 1 | 2
000666 | Incentive/ Disincentive Audit Scheme for Mar 2024 | "Incentive/ Disincentive Audit Scheme for Mar 2024" | 2024-08-22 | 2024-08-30 |  |  | Samy | 0 | 1
000667 | Incentive/ Disincentive Audit Scheme for Apr 2024 | "Incentive/ Disincentive Audit Scheme for Apr 2024" | 2024-08-22 | 2024-08-30 |  |  | Samy | 0 | 1
000668 | Incentive/ Disincentive Audit Scheme for May 2024 | "Incentive/ Disincentive Audit Scheme for May 2024" | 2024-08-22 | 2024-08-30 |  |  | Samy | 0 | 1
000669 | Incentive/ Disincentive Audit Scheme for Jun 2024 | "Incentive/ Disincentive Audit Scheme for Jun 2024" | 2024-08-22 | 2024-08-30 |  |  | Samy | 0 | 1
000670 | Monthly Concrete Cube Records for Structural works for Apr 2024 | "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " | 2024-08-22 | 2024-08-30 |  |  | Boopathi | 0 | 2
000670 | Monthly Concrete Cube Records for Structural works for May 2024 | "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " | 2024-08-27 |  |  |  | Boopathi | 0 | 2
000671 | Vendor Approval of Surge Diverter | "Vendor Approval of Surge Diverter " | 2024-08-23 | 2024-09-26 |  |  | Freedomer | 1 | 2
000672 | THP Equipment layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | 2024-10-17 |  |  | Geno | A.1 | 3
000672 | THP Equipment layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | 2024-10-17 |  |  | Geno | A.1 | 3
000672 | THP Equipment layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | 2024-10-17 |  |  | Geno | A.1 | 3
000672 | THP Equipment layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | 2024-10-17 |  |  | Geno | A.1 | 3
000672 | THP Equipment layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | 2024-10-17 |  |  | Geno | A.1 | 3
000672 | THP Equipment layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | 2024-10-17 |  |  | Geno | A.1 | 3
000673 | SSN 30 Percent ALMOP Report | "SSN 30 Percent ALMOP Report" | 2024-08-23 | 2024-09-06 |  |  | Qili | 0 | 2
000674 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements " | 2024-08-23 | 2025-11-20 |  |  | Vincent | 0 | 1
000675 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" | 2024-08-23 | 2024-09-10 |  |  | David | 1 | 2
000676 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | 2024-10-29 |  |  | Radha | 2 | 3
000677 | SSN Control Narrative | "SSN Control Narrative" | 2024-08-26 | 2024-10-09 |  |  | Qili | 1 | 2
000678 | THP HAZOP Report | "THP HAZOP Report" | 2024-08-26 | 2024-10-09 |  |  | Joo Kwan | 1 | 2
000679 | Vendor Approval of Electrical Consultant – YHW LLP | "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-26 | 2024-09-26 |  |  | Yuen Fatt | 0 | 1
000680 | Laboratory Test Report on Soil Samples | "Laboratory Test Report on Soil Samples" | 2024-08-27 | 2024-09-17 |  |  | Boopathi | 0 | 1
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 2
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Piping Opening " | 2024-08-28 | 2024-10-16 |  |  | Geno | A.2 | 2
000682 | Plate Load test report | "Plate Load test report " | 2024-08-29 | 2024-09-18 |  |  | Mohan | 1 | 2
000683 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" | 2024-08-29 | 2024-09-10 |  |  | Zora | 0 | 1
000683 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" | 2024-08-29 | 2024-09-10 |  |  | Zora | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000684 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" | 2024-08-29 | 2024-09-10 |  |  | Heng Peng | 0 | 1
000685 | Process & MEICA Meeting Minutes 0031_20240815 | "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | 2024-09-10 |  |  | Joo Kwan | 0 | 1
000686 | Data Sheet of Pressure Relief Valve at Air Receiver | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | 2024-10-17 |  |  | Joo Kwan | 2 | 3
000687 | THP 30 Percent ALMOP Study Report | "THP 30 Percent ALMOP Study Report" | 2024-08-29 | 2024-10-17 |  |  | Joo Kwan | 0 | 1
000688 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | 2024-08-30 | 2024-11-05 |  |  | Radha | 1 | 2
000689 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" | 2024-08-30 | 2024-11-25 |  |  | Radha | 2 | 3
000690 | THP Plant Process Water Hydraulic Calculation | "THP Plant Process Water Hydraulic Calculation" | 2024-08-30 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000691 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " | 2024-08-31 | 2024-10-14 |  |  | Radha | 1 | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 1
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000692 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | 2024-09-11 |  |  | Aaron | A | 2
000693 | Monthly Concrete Cube Records for Structural works for July 2024 | "Monthly Concrete Cube Records for Structural works for July 2024" && "Mock-up Temperature Monitoring Test Reports (Alliance)" | 2024-08-31 | 2024-09-18 |  |  | Boopathi | 0 | 2

## 2024-09
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000003 | BIM Execution Plan (BEP) | "BIM Execution Plan (BEP)" | 2024-09-18 | 2024-10-02 |  |  | Heng Peng | 5 | 5
000016 | FRP TANK DATA SHEET | "FRP TANK DATA SHEET" | 2024-09-20 | 2024-10-14 |  |  | David | 1 | 2
000016 | FRP TANK DATA SHEET | "FRP TANK DATA SHEET" | 2024-09-20 | 2024-10-14 |  |  | David | 1 | 2
000141 | Process Functional Description | "Process Functional Description" | 2024-09-30 | 2024-12-05 |  |  | Joo Kwan | 3 | 4
000180 | Data Sheet of PGS | "Data Sheet of PGS" | 2024-09-30 | 2024-10-29 |  |  | Joo Kwan | 3 | 4
000180 | Data Sheet of PGS | "Data Sheet of PGS" | 2024-09-30 | 2024-10-29 |  |  | Joo Kwan | 0 | 1
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2024-09-28 | 2024-11-25 |  |  | Kyaw Myo | A.1 | 2
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2024-09-28 | 2024-11-25 |  |  | Kyaw Myo | B | 3
000189 | Plumbing and Sanitary (SSN Area) | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2024-09-26 | 2024-11-25 |  |  | Kyaw Myo | A.2 | 4
000208 | THP Atex Hazardous Area Assessment Report | "THP Atex Hazardous Area Assessment Report" | 2024-09-11 | 2024-10-25 |  |  | Joo Kwan | 1 | 2
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-09-03 | 2024-12-06 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-09-03 | 2024-12-06 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-09-03 | 2024-12-06 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-09-03 | 2024-12-06 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-09-03 | 2024-12-06 |  |  | Freedomer | C | 8
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2024-09-26 | 2024-11-25 |  |  | Kyaw Myo | A.4 | 7
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2024-09-26 | 2024-11-25 |  |  | Kyaw Myo | A.4 | 7
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-09-20 | 2024-10-03 |  |  | Zora | B | 1
000474 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-09-06 | 2024-09-12 |  |  | Liying | 2 | 3
000513 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-09-16 | 2024-11-08 |  |  | Yean Yee | 3 | 4
000537 | Design Calculation for Instrument Air Receiver | "Design Calculation for Instrument Air Receiver" | 2024-09-03 | 2024-09-05 |  |  | Yibo | 1 | 2
000560 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" | 2024-09-16 | 2024-09-24 |  |  | David | 1 | 2
000565 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " | 2024-09-05 | 2024-10-03 |  |  | Bryan | 1 | 2
000589 | Vendor Approval of Earthing System & LPS Material (Heng) | "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" | 2024-09-02 | 2024-10-29 |  |  | Freedomer | 1 | 2
000597 | Air Compressor Pressure Loss Calculation | "Air Compressor Pressure Loss Calculation" | 2024-09-30 | 2024-11-05 |  |  | Joo Kwan | 1 | 2
000673 | SSN 30 Percent ALMOP Report | "SSN 30 Percent ALMOP Report" | 2024-09-06 | 2024-10-14 |  |  | Qili | 0 | 2
000694 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" | 2024-09-02 | 2024-10-13 |  |  | Radha | 1 | 2
000695 | Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions | "Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions" | 2024-09-03 | 2025-11-20 |  |  | Vincent | 0 | 1
000696 | Payment Claim No.14 | "Payment Claim No.14" | 2024-09-03 | 2024-10-09 |  |  | Yi Hao | 0 | 1
000697 | Data Sheet for Pre Cooler Cooling Water Control Valve | "Data Sheet for Pre Cooler Cooling Water Control Valve" | 2024-09-03 | 2024-10-14 |  |  | Joo Kwan | 1 | 2
000698 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | 2024-10-13 |  |  | Joo Kwan | 2 | 3
000699 | Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024) | "Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024)" | 2024-09-04 | 2025-02-24 |  |  | Vincent | 0 | 1
000700 | Monthly Progress Meeting Minutes 0015_20240827 | "Monthly Progress Meeting Minutes 0015_20240827" | 2024-09-04 | 2024-09-10 |  |  | Krishanthy | 0 | 1
000701 | Monthly Progress Presentation No. 15 (0824) | "Monthly Progress Presentation No. 15 (0824)" | 2024-09-04 | 2024-09-10 |  |  | Krishanthy | 0 | 1
000702 | Unpriced LOA for Structural Steel Works (Sanhe) | "Unpriced LOA for Structural Steel Works (Sanhe) " | 2024-09-05 | 2024-10-13 |  |  | Yi Hao | 0 | 1
000703 | MSRA for RC Super-Structural Work | "MSRA for RC Super-Structural Work" | 2024-09-05 | 2024-09-26 |  |  | Bryan | 0 | 1
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 3
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 3
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 3
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 3
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 3
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 1
000704 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | 2024-10-02 |  |  | Aaron | A | 1
000705 | Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd. | "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." | 2024-09-06 | 2024-09-26 |  |  | Yuen Fatt | 0 | 1
000706 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | 2024-10-29 |  |  | Radha | 4 | 5
000707 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | 2024-10-29 |  |  | Radha | 2 | 3
000708 | Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2024-09-06 | 2024-11-08 |  |  | Radha | 0 | 1
000709 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2024-09-06 | 2024-11-08 |  |  | Radha | 2 | 3
000710 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2024-09-06 | 2024-11-08 |  |  | Radha | 2 | 3
000711 | Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas) | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" | 2024-09-06 | 2024-10-09 |  |  | Freedomer | 0 | 1
000712 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" | 2024-09-06 | 2024-09-09 |  |  | Radha | 0 | 2
000712 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" | 2024-09-09 | 2024-10-29 |  |  | Radha | 0 | 2
000713 | Bored Piling Pile Eccentricity Reports (ECC 08 to 12) | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" | 2024-09-06 | 2024-09-13 |  |  | Mohan | 0 | 1
000714 | Sample Board Submission for PVC lining System (Linabond) | "Sample Board Submission for PVC lining System (Linabond)" | 2024-09-09 | 2024-09-13 |  |  | Boopathi | 0 | 1
000715 | Datat Sheet for Steel Structure and Painting | "Datat Sheet for Steel Structure and Painting" | 2024-09-09 | 2024-10-09 |  |  | Yuen Fatt | 1 | 2
000716 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | 2024-10-14 |  |  | Jovonne | 2 | 3
000717 | Submission Of BIM Coordination VCM Model (Aug-2024) | "Submission Of BIM Coordination VCM Model (Aug-2024)" | 2024-09-09 | 2024-09-24 |  |  | Heng Peng | 0 | 1
000718 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | 2024-10-29 |  |  | Freedomer | 2 | 3
000719 | Sample Board Submission for Lightning and Earthing System (MTF 0003) | "Sample Board Submission for Lightning and Earthing System (MTF 0003)" | 2024-09-10 | 2024-09-26 |  |  | Mohan | 0 | 1
000720 | Sample Board Submission for Lightning and Earthing System (MTF 0005) | "Sample Board Submission for Lightning and Earthing System (MTF 0005)" | 2024-09-10 | 2024-09-26 |  |  | Mohan | 0 | 1
000721 | Data Sheet for Side Manway | "Data Sheet for Side Manway" | 2024-09-10 | 2024-10-11 |  |  | David | 0 | 1
000722 | MSRA SWP for Operating Forklift | "MSRA SWP for Operating Forklift" | 2024-09-11 | 2024-10-10 |  |  | Bryan | 0 | 1
000723 | Detailed Design Report – SSN PACKAGE | "Detailed Design Report – SSN PACKAGE" | 2024-09-12 | 2024-11-07 |  |  | Qili | 0 | 1
000724 | Mock-up Temperature Monitoring Test Reports (Alliance) | "Monthly Concrete Cube Records for Structural works for July 2024" && "Mock-up Temperature Monitoring Test Reports (Alliance)" | 2024-09-16 | 2024-09-26 |  |  | Radha | 0 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-09-16 | 2024-10-04 |  |  | Qili | 1 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-09-16 | 2024-10-04 |  |  | Qili | 1 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-09-16 | 2024-10-04 |  |  | Qili | 1 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-09-16 | 2024-10-04 |  |  | Qili | 1 | 2
000726 | C4B Monthly Progress Report Number No.16 (08 24) | "C4B Monthly Progress Report Number No.16 (08 24) " | 2024-09-16 | 2024-10-01 |  |  | Leslie | 0 | 1
000727 | NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA | "NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA" | 2024-09-16 | 2025-02-24 |  |  | Vincent | 0 | 1
000728 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-10-14 |  |  | David | 2 | 3
000728 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-10-14 |  |  | David | 2 | 3
000729 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-10-14 |  |  | David | 0 | 2
000729 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-10-14 |  |  | David | 0 | 2
000729 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-12-05 |  |  | Qili | 0 | 2
000729 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | 2024-12-05 |  |  | Qili | 0 | 2
000730 | Vendor Approval of LPS Materials (Skypro_DEHN) | "Vendor Approval of LPS Materials (Skypro_DEHN)" | 2024-09-18 | 2024-10-10 |  |  | Freedomer | 1 | 2
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 6
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2024-09-19 | 2024-11-07 |  |  | Qili | D | 5
000732 | CV of Team member (Construction Manager) | "CV of Team member (Construction Manager)" | 2024-09-20 | 2024-10-14 |  |  | Htet Nu | 0 | 1
000733 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | 2024-11-05 |  |  | Radha | 1 | 2
000734 | Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate | "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " | 2024-09-20 | 2024-11-05 |  |  | Radha | 0 | 1
000735 | Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area | "Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area" | 2024-09-20 | 2025-11-20 |  |  | Vincent | 0 | 1
000736 | Process & MEICA Meeting Minutes 0032_20240829 | "Process & MEICA Meeting Minutes 0032_20240829" | 2024-09-27 | 2024-10-10 |  |  | Joo Kwan | 0 | 1
000737 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" | 2024-09-27 | 2024-10-24 |  |  | Krishanthy | 1 | 3
000738 | Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd) | "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | 2024-10-29 |  |  | Radha | 0 | 1

## 2024-10
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2024-10-19 | 2024-11-04 |  |  | Leslie | 5.1 | 5
000097 | Engineering Calculation Report For Potable Water Pipe | "Engineering Calculation Report For Potable Water Pipe" | 2024-10-17 | 2024-11-25 |  |  | Kyaw Myo | 3 | 3
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | 1 | 4
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.2 | 5
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.2 | 5
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng | A.3 | 2
000128 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2024-10-08 | 2024-10-29 |  |  | Aaron | NA | 1
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | 0 | 2
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | B_endorsed | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | B_endorsed | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | B_endorsed | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | B_endorsed | 3
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | B_endorsed | 3
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | B_endorsed | 3
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A | 1
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A | 1
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A | 1
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A | 1
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A | 1
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 5
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 5
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 5
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 5
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | C | 4
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A.2 | 3
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A.1 | 2
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A.1 | 2
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A.1 | 2
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A.1 | 2
000161 | Milestone 2 Underground Services | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-10-05 | 2024-12-05 |  |  | Heng Peng/ Muthu | A.1 | 2
000187 | Plant Drain and Safety Shower P&ID | "Plant Drain and Safety Shower P&ID" | 2024-10-01 | 2024-10-29 |  |  | Qili | NA | 1
000299 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" | 2024-10-16 | 2024-11-04 |  |  | Freedomer | 3 | 4
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | 2024-12-05 |  |  | Heng Peng | 2 | 3
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A.1 | 2
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A.1 | 2
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A | 1
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A | 1
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A | 1
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A | 1
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A.1 | 3
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A.1 | 3
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-10-18 | 2024-12-05 |  |  | Heng Peng | A.1 | 3
000322 | Process Functional Description | "Process Functional Description" | 2024-10-15 | 2024-12-18 |  |  | Qili | 3 | 4
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | B | 1
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | B | 1
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A | 2
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.2 | 2
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | B | 1
000341 | THP UPS Loading List | "THP UPS Loading List" | 2024-10-22 | 2024-12-18 |  |  | Low | 4 | 5
000345 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | 2024-10-04 | 2024-10-18 |  |  | Yean Yee | 2 | 4
000345 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | 2024-10-18 | 2024-12-03 |  |  | Yean Yee | 2 | 4
000360 | SSN PFD | "SSN PFD" | 2024-10-29 | 2025-01-16 |  |  | Qili | D | 6
000360 | SSN PFD | "SSN PFD" | 2024-10-29 | 2025-01-16 |  |  | Qili | D | 6
000378 | Plant Control Narrative | "Plant Control Narrative" | 2024-10-21 | 2024-12-05 |  |  | Joo Kwan | 1 | 3
000378 | Plant Control Narrative | "Plant Control Narrative" | 2024-10-21 | 2025-10-10 |  |  | Joo Kwan | 1 | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " | 2024-10-11 | 2024-10-29 |  |  | Zora | B | 2
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000386 | ST617 - THP-PF-01, 02 & THP-PR-01 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-10-11 | 2024-10-29 |  |  | Zora | A | 3
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 7
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A.2 | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A | 1
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | A | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2024-10-30 | 2025-01-08 |  |  | Aaron | B | 1
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.2 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 3
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A.2 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | A | 1
000397 | NEA DC submission Set | "NEA DC submission Set " | 2024-10-30 | 2025-01-16 |  |  | Aaron/HP | B | 1
000398 | P&ID for SSN Process | "P&ID for SSN Process" | 2024-10-01 | 2024-10-24 |  |  | Joo Kwan | NA | 1
000399 | P&ID for SSN Process | "P&ID for SSN Process" | 2024-10-01 | 2024-11-07 |  |  | Joo Kwan | NA | 1
000400 | P&ID for SSN Plant Water and Instrument Air | "P&ID for SSN Plant Water and Instrument Air" | 2024-10-01 | 2024-10-29 |  |  | Joo Kwan | NA | 1
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A | 1
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2024-10-16 | 2025-02-13 |  |  | Aaron | A | 1
000403 | SSN Control Philosophy | "SSN Control Philosophy" | 2024-10-03 | 2024-11-07 |  |  | Qili | 3 | 4
000404 | SSN Chemical Consumption Calculation | "SSN Chemical Consumption Calculation" | 2024-10-16 | 2024-11-15 |  |  | Qili | 2 | 3
000418 | SSN Integrated Security management system and Plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B_MS2 | 3
000418 | SSN Integrated Security management system and Plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B_MS2 | 3
000418 | SSN Integrated Security management system and Plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B_MS2 | 3
000418 | SSN Integrated Security management system and Plant CCTV | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B_MS2 | 3
000418 | SSN Integrated Security management system and Plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B | 2
000418 | SSN Integrated Security management system and Plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B | 2
000418 | SSN Integrated Security management system and Plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B | 2
000418 | SSN Integrated Security management system and Plant CCTV | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2024-10-22 | 2025-03-25 |  |  | Karthikeyan | B | 2
000419 | SSN Public Address System | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | 2024-10-18 | 2024-10-29 |  |  | Karthikeyan | A9 | 3
000419 | SSN Public Address System | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | 2024-10-18 | 2024-10-29 |  |  | Karthikeyan | A9 | 3
000419 | SSN Public Address System | "SSN Public Address System" | 2024-10-18 | 2024-10-29 |  |  | Karthikeyan | B | 2
000419 | SSN Public Address System | "SSN Public Address System" | 2024-10-18 | 2024-10-29 |  |  | Karthikeyan | B | 2
000428 | ST608 – SSN Shelters Details | "ST608 – SSN Shelters Details" | 2024-10-22 | 2024-12-18 |  |  | Aaron | CES REPLY SHEET S428 | 1
000438 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-10-18 | 2024-12-03 |  |  | Yean Yee | 3 | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | E | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | D | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | C | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | C | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | F | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-10-16 | 2024-11-07 |  |  | Freedomer | F | 3
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 2
000446 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | 2024-10-29 |  |  | Thet Myo | B | 1
000458 | SSN Transformer Data Sheet | "SSN Transformer Data Sheet" | 2024-10-15 | 2024-11-04 |  |  | Freedomer | 2 | 3
000474 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-10-17 | 2024-11-15 |  |  | Liying | 2 | 3
000475 | IFC of ST610 (Underground Services) | "IFC of ST610 (Underground Services) " | 2024-10-09 | 2024-10-24 |  |  | Zora | NA | 1
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.2 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.2 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2024-10-21 | 2024-12-05 |  |  | Kyaw Myo | C.2 | 2
000507 | Blower Pressure Loss Calculation | "Blower Pressure Loss Calculation" | 2024-10-22 | 2024-11-19 |  |  | Qili | 2 | 3
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-10-25 | 2024-11-24 |  |  | Joo Kwan | 1 | 2
000511 | SSN Blower GA drawings and Data Sheets | "SSN Blower GA drawings and Data Sheets" | 2024-10-25 | 2024-11-24 |  |  | Joo Kwan | B | 1
000556 | THP LPS Risk Assessment Report | "THP LPS Risk Assessment Report" | 2024-10-28 | 2024-12-08 |  |  | Freedomer | 2 | 3
000557 | SSN LPS Risk Assessment Report | "SSN LPS Risk Assessment Report" | 2024-10-24 | 2024-12-08 |  |  | Freedomer | 2 | 3
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-10-03 | 2024-10-29 |  |  | Freedomer | E | 6
000571 | THP SLD | "THP SLD" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | NA | 1
000575 | THP MCC Outline Drawing | "THP MCC Outline Drawing" | 2024-10-01 | 2024-10-03 |  |  | Freedomer | NA | 1
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 4
000588 | THP URA Submission | "THP URA Submission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 3
000588 | THP URA Submission | "THP URA Submission" | 2024-10-09 | 2024-10-29 |  |  | Thet Myo | A | 3
000591 | PLant Drain Hydraulic Calculation | "PLant Drain Hydraulic Calculation" | 2024-10-21 | 2024-11-15 |  |  | Joo Kwan | 1 | 2
000606 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" | 2024-10-28 | 2024-11-24 |  |  | Freedomer | 1 | 2
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-10-22 | 2025-01-13 |  |  | Yibo | C | 3
000624 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" | 2024-10-09 | 2024-10-25 |  |  | Radha | 2 | 3
000630 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | 2024-10-02 | 2024-10-14 |  |  | Radha | 1 | 2
000642 | Inspection Test Plan for HDPE Pipe Installation | "Inspection Test Plan for HDPE Pipe Installation" | 2024-10-01 | 2024-10-25 |  |  | Mohan | 1 | 2
000665 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-10-25 | 2024-11-04 |  |  | Radha | 1 | 2
000671 | Vendor Approval of Surge Diverter | "Vendor Approval of Surge Diverter " | 2024-10-04 | 2024-10-29 |  |  | Freedomer | 1 | 2
000673 | SSN 30 Percent ALMOP Report | "SSN 30 Percent ALMOP Report" | 2024-10-29 | 2024-11-27 |  |  | Qili | 0 | 1
000678 | THP HAZOP Report | "THP HAZOP Report" | 2024-10-28 | 2025-04-08 |  |  | Joo Kwan | 1 | 2
000682 | Plate Load test report | "Plate Load test report " | 2024-10-30 | 2024-11-08 |  |  | Mohan | 1 | 2
000730 | Vendor Approval of LPS Materials (Skypro_DEHN) | "Vendor Approval of LPS Materials (Skypro_DEHN)" | 2024-10-14 | 2024-11-07 |  |  | Freedomer | 1 | 2
000739 | Monthly Progress Meeting Minutes 0016_20240924 | "Monthly Progress Meeting Minutes 0016_20240924" | 2024-10-01 | 2024-10-03 |  |  | Krishanthy | 0 | 1
000740 | Monthly Progress Presentation No. 16 (0924) | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" | 2024-10-01 | 2024-10-03 |  |  | Krishanthy | 0 | 2
000741 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | 2024-11-05 |  |  | Radha | 1 | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | E | 2
000742 | BCA submission of ST608 – SSN Shelters (for Information) | "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | 2024-10-24 |  |  | Thet Myo | 0 | 1
000743 | Payment Claim No.15 | "Payment Claim No.15" | 2024-10-04 | 2024-10-09 |  |  | Theint Theint | 0 | 1
000744 | Vendor Manufacturing Inspection test plan for Side Manway | " Vendor Manufacturing Inspection test plan for Side Manway " | 2024-10-04 | 2024-10-11 |  |  | Radha | 1 | 2
000744 | Vendor Manufacturing Inspection test plan for Side Manway | " Vendor Manufacturing Inspection test plan for Side Manway " | 2024-10-30 | 2024-12-05 |  |  | Radha | 1 | 2
000745 | Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024) | "Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024)" | 2024-10-07 | 2025-02-24 |  |  | Vincent | 0 | 1
000746 | CV of Team member (WSHO) | "CV of Team member (WSHO)" | 2024-10-07 | 2024-11-15 |  |  | Dharmen | 0 | 1
000747 | Mock-up Temperature Monitoring Test Reports - G40 (Pan U) | "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" | 2024-10-08 | 2024-10-14 |  |  | Radha | 0 | 1
000748 | Submission Of BIM Coordination VCM Model (Sept-2024) | "Submission Of BIM Coordination VCM Model (Sept-2024)" | 2024-10-08 | 2024-10-29 |  |  | Heng Peng | 0 | 1
000749 | Bar chair Design for SSN Water Tanks Raft Slabs | "Bar chair Design for SSN Water Tanks Raft Slabs " | 2024-10-09 | 2024-10-14 |  |  | Sithu | 0 | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000750 | BCA approval of ST602 - ERSS Design < 6m | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | 2024-11-08 |  |  | Thet Myo | E | 1
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-10-09 | 2024-10-11 |  |  | David | 0 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-10-09 | 2024-10-11 |  |  | David | A.1 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-10-09 | 2024-10-11 |  |  | David | A.1 | 3
000752 | SSN HAZOP Report | "SSN HAZOP Report" | 2024-10-09 | 2024-11-15 |  |  | Qili | 2 | 3
000753 | SSN- Biomass separator footing detail | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-10-10 | 2024-10-29 |  |  | Thet Myo | H | 4
000753 | SSN- Biomass separator footing detail | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-10-10 | 2024-10-29 |  |  | Thet Myo | F | 4
000754 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | 2024-10-10 | 2025-11-20 |  |  | Vincent | 0 | 1
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2024-11-27 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2024-11-27 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2024-11-27 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2024-11-27 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2024-11-27 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2024-10-11 | 2024-11-27 |  |  | Yibo | 1 | 2
000756 | Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT | "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" | 2024-10-11 | 2024-11-19 |  |  | Radha | 0 | 1
000757 | Mock-up Temperature Monitoring Test Reports – G45 (Pan U) | "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" | 2024-10-11 | 2024-10-24 |  |  | Radha | 0 | 1
000758 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | 2024-10-12 | 2024-11-24 |  |  | Liying | 1 | 2
000759 | Delivery and Storage of Compressor Package at Biosolids Building | "Delivery and Storage of Compressor Package at Biosolids Building " | 2024-10-14 | 2024-10-14 |  |  | Charles | 1 | 3
000759 | Delivery and Storage of Compressor Package at Biosolids Building | "Delivery and Storage of Compressor Package at Biosolids Building " | 2024-10-15 | 2024-10-24 |  |  | Charles | 1 | 3
000759 | Delivery and Storage of Compressor Package at Biosolids Building | "Delivery and Storage of Compressor Package at Biosolids Building " | 2024-10-30 | 2024-12-03 |  |  | Charles | 1 | 3
000760 | Incentive/ Disincentive Audit Scheme for Jul 2024 | "Incentive/ Disincentive Audit Scheme for Jul 2024" | 2024-10-14 | 2024-11-15 |  |  | Samy | 0 | 1
000761 | Incentive/ Disincentive Audit Scheme for Aug 2024 | "Incentive/ Disincentive Audit Scheme for Aug 2024" | 2024-10-14 | 2024-11-15 |  |  | Samy | 0 | 1
000762 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | 2024-10-14 | 2024-10-24 |  |  | Krishanthy | 0 | 1
000762 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | 2024-10-14 | 2024-10-24 |  |  | Krishanthy | 0 | 1
000762 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | 2024-10-14 | 2024-10-24 |  |  | Krishanthy | 0 | 1
000763 | SSN Instrument List | "SSN Instrument List " | 2024-10-15 | 2025-02-13 |  |  | Yean Yee/ Low | 1 | 2
000764 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | 2025-03-25 |  |  | Radha | 1 | 2
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000765 | ST614 - SiteWide Pipe Rack 003 | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | 2024-11-08 |  |  | Thet Myo | A | 1
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | 2024-11-15 |  |  | David | 2 | 2
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | 2024-11-15 |  |  | David | C | 3
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | 2024-11-15 |  |  | David | C | 3
000767 | C4B Monthly Progress Report Number No.17 (09 24) | "C4B Monthly Progress Report Number No.17 (09 24) " | 2024-10-19 | 2024-10-25 |  |  | Leslie | 0 | 1
000768 | Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings | "Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings" | 2024-10-21 | 2025-11-20 |  |  | Vincent | 0 | 1
000769 | SSN Dosing Pump Sizing Calculations | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2025-01-20 |  |  | Qili | 0 | 1
000769 | SSN Dosing Pump Sizing Calculations | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2025-01-20 |  |  | Qili | 0 | 1
000769 | SSN Dosing Pump Sizing Calculations | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2025-01-20 |  |  | Qili | 0 | 1
000769 | SSN Dosing Pump Sizing Calculations | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2025-01-20 |  |  | Qili | 0 | 1
000769 | SSN Dosing Pump Sizing Calculations | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2025-01-20 |  |  | Qili | 0 | 1
000769 | SSN Dosing Pump Sizing Calculations | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | 2025-01-20 |  |  | Qili | 0 | 1
000770 | SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs | "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" | 2024-10-22 | 2024-11-21 |  |  | Sithu | 0 | 1
000771 | Bored Piling Pile Eccentricity Reports (ECC 13 to 18) | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" | 2024-10-22 | 2024-11-04 |  |  | Radha | 1 | 3
000772 | SSN Hazardous Area Assessment Report | "SSN Hazardous Area Assessment Report" | 2024-10-23 | 2025-03-25 |  |  | Qili | 0 | 1
000772 | SSN Hazardous Area Assessment Report | "SSN Hazardous Area Assessment Report" | 2024-10-23 | 2025-03-25 |  |  | Qili | A | 1
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | C | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | C | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | C | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | C | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | A | 1
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | A | 1
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000773 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2024-10-23 | 2024-12-14 |  |  | Thet Myo | D | 2
000774 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | 2024-10-23 | 2024-11-21 |  |  | Mohan | 1 | 2
000775 | MSRA for RC Wall | "MSRA for RC Wall" | 2024-10-23 | 2024-11-15 |  |  | Charles | 1 | 3
000776 | Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works | "Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works " | 2024-10-25 | 2025-08-25 |  |  | Vincent | 0 | 1
000777 | Preliminary Design and Vendor Approval for Spray Nozzles | "Preliminary Design and Vendor Approval for Spray Nozzles " | 2024-10-25 | 2024-11-27 |  |  | Qili | 1 | 2
000778 | SSN Piping Support Plan Layout (Cast-In Supports) | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-10-26 | 2025-04-27 |  |  | Charisse | A | 2
000778 | SSN Piping Support Plan Layout (Cast-In Supports) | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-10-26 | 2025-04-27 |  |  | Charisse | A | 2
000778 | SSN Piping Support Plan Layout (Cast-In Supports) | "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-10-26 | 2025-04-27 |  |  | Charisse | A | 1
000779 | SSN Piping Drawing Index | "SSN Piping Drawing Index" | 2024-10-26 | 2024-11-27 |  |  | Charisse | A | 1
000780 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " | 2024-10-26 | 2024-11-20 |  |  | Yuen Fatt | 0 | 1
000781 | Vendor Approval of Raised Floor – Hemsco Pte. Ltd. | "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " | 2024-10-26 | 2024-11-15 |  |  | Yuen Fatt | 0 | 2
000782 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" | 2024-10-28 | 2024-11-27 |  |  | Radha | 1 | 2
000783 | THP Drawing Index | "THP Drawing Index" | 2024-10-28 | 2024-12-14 |  |  | Geno | A | 1
000783 | THP Drawing Index | "THP Drawing Index" | 2024-10-28 | 2024-12-14 |  |  | Geno | A | 1
000784 | Ring Circulation Pump Drawing | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | 2024-10-28 | 2024-11-27 |  |  | Joo Kwan | B | 2
000784 | Ring Circulation Pump Drawing | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | 2024-10-28 | 2024-11-27 |  |  | Joo Kwan | B | 2
000785 | Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024 | "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-28 | 2024-11-15 |  |  | Max | 0 | 1
000786 | Report of DFS (GUIDE 3) for PIPE RACKS | "Report of DFS (GUIDE 3) for PIPE RACKS" | 2024-10-28 | 2024-12-08 |  |  | Max | 0 | 1
000787 | Report of PROJECT SAFETY REVIEW for PIPE RACKS | "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | 2024-10-28 | 2024-12-18 |  |  | Max | 0 | 1
000788 | Payment Claim No.16 | "Payment Claim No.16" | 2024-10-29 | 2024-11-07 |  |  | Theint Theint | 0 | 1
000789 | THP Underground Piping and Cast in Details | "THP Underground Piping and Cast in Details" | 2024-10-30 | 2024-12-05 |  |  | Geno | A | 1
000789 | THP Underground Piping and Cast in Details | "THP Underground Piping and Cast in Details" | 2024-10-30 | 2024-12-05 |  |  | Geno | A | 1
000790 | Quarterly Safety Review Follow Up on ERSS | "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-10-30 | 2024-11-15 |  |  | Max | 1 | 2
000791 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | 2024-10-31 | 2024-11-15 |  |  | Thet Myo | 0 | 1
000791 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | 2024-10-31 | 2024-11-15 |  |  | Thet Myo | 0 | 1
000792 | Monthly Progress Meeting Minutes 0017_20241023 | "Monthly Progress Meeting Minutes 0017_20241023" | 2024-10-31 | 2024-11-07 |  |  | PCM | 0 | 1
000793 | Monthly Progress Presentation No. 17 (1024) | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" | 2024-10-31 | 2024-11-07 |  |  | PCM | 0 | 2
000794 | Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd) | "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" | 2024-10-31 | 2024-11-25 |  |  | Yuen Fatt | 0 | 1

## 2024-11
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000139 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | "Preliminary Design and Vendor Approval of Diffuser (Xylem)" | 2024-11-06 | 2025-03-04 |  |  | Yibo | 1 | 2
000142 | THP Process Design Basis | "Process Design Basis" && "THP Process Design Basis" | 2024-11-04 | 2025-01-02 |  |  | Joo Kwan | 3 | 4
000170 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2024-11-23 | 2024-12-14 |  |  | Liying | 2 | 3
000177 | Data Sheet of Air Compressor System | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" | 2024-11-06 | 2024-12-05 |  |  | Joo Kwan | 3 | 4
000178 | Data Sheet of Pressure Vessel | "Data Sheet of Pressure Vessel" | 2024-11-22 | 2024-12-05 |  |  | Joo Kwan | 4 | 5
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 3
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 3
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2024-11-13 | 2025-01-16 |  |  | Joo Kwan | D | 4
000293 | Milestone 2 THP A100 Silo Area inside Biosolid Building | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-11-09 | 2024-12-05 |  |  | Heng Peng | 1 | 4
000293 | Milestone 2 THP A100 Silo Area inside Biosolid Building | "Milestone 2 THP A100 Silo Area inside Biosolid Building" | 2024-11-09 | 2024-12-05 |  |  | Heng Peng | A | 1
000293 | Milestone 2 THP A100 Silo Area inside Biosolid Building | "Milestone 2 THP A100 Silo Area inside Biosolid Building" | 2024-11-09 | 2024-12-05 |  |  | Heng Peng | A | 1
000342 | SSN UPS Loading List | "SSN UPS Loading List" | 2024-11-20 | 2024-12-30 |  |  | Low | 5 | 6
000358 | C4B Sidestream Nitrogen Removal Process Equipment List | "C4B Sidestream Nitrogen Removal Process Equipment List" | 2024-11-15 | 2025-03-04 |  |  | Qili | 2 | 3
000385 | SSN Process Design Basis | "SSN Process Design Basis" | 2024-11-04 | 2025-01-09 |  |  | Qili | 3 | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2024-11-19 | 2024-12-18 |  |  | Low | E | 3
000407 | Basic Design Report of SSN Package | "Basic Design Report of SSN Package" | 2024-11-18 | 2025-01-08 |  |  | Qili | 2 | 3
000415 | SSN Equipment Sizing Calculation | "SSN Equipment Sizing Calculation" | 2024-11-18 | 2025-01-08 |  |  | Qili | NA | 1
000436 | Vendor Approval of SSN Package (TSS Analyser - Optical) | "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-11-28 | 2025-03-25 |  |  | Yean Yee | 1 | 2
000463 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-11-09 | 2024-11-24 |  |  | Yean Yee | 2 | 3
000464 | Vendor Approval of SSN Package (Capacitive Level Switches) | "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-11-08 | 2024-11-24 |  |  | Yean Yee | 2 | 3
000468 | Design for Safety Report 2 | "Design for Safety Report 2" | 2024-11-03 | 2024-12-07 |  |  | Leslie | 2 | 4
000504 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | 2024-11-02 | 2024-12-05 |  |  | Liying | 1 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | 2024-11-19 |  |  | Qili | 2 | 4
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | 2024-11-19 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | 2024-11-19 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | 2024-11-19 |  |  | Qili | A | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | 2024-11-19 |  |  | Qili | A | 1
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 3
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | E | 6
000579 | SSN RIO 0201 I/O List | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | 2024-11-06 | 2024-12-18 |  |  | Low | 4 | 5
000583 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | 2024-11-29 | 2025-02-25 |  |  | Balaji/ Karthik | 3 | 4
000599 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" | 2024-11-02 | 2024-12-18 |  |  | Low | 1 | 2
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | B | 2
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | B | 2
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2024-11-21 | 2024-12-30 |  |  | Freedomer | D | 4
000623 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | 2024-11-21 | 2024-12-14 |  |  | Radha | 5 | 6
000624 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" | 2024-11-21 | 2024-12-05 |  |  | Radha | 2 | 3
000635 | Data Sheet of Flash Tank Discharge Pump | "Data Sheet of Flash Tank Discharge Pump " | 2024-11-13 | 2024-12-06 |  |  | Joo Kwan | 1 | 2
000636 | Data Sheet of Precooler S2 CIRC Pump | "Data Sheet of Precooler S2 CIRC Pump" | 2024-11-13 | 2024-06-12 |  |  | Joo Kwan | 1 | 2
000686 | Data Sheet of Pressure Relief Valve at Air Receiver | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-11-07 | 2024-12-05 |  |  | Joo Kwan | 2 | 3
000698 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-11-13 | 2024-12-05 |  |  | Joo Kwan | 2 | 3
000706 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-11-20 | 2024-12-14 |  |  | Radha | 4 | 5
000715 | Datat Sheet for Steel Structure and Painting | "Datat Sheet for Steel Structure and Painting" | 2024-11-16 | 2024-12-08 |  |  | Radha | 1 | 2
000716 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-11-13 | 2024-12-05 |  |  | Jovonne | 2 | 3
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-11-27 | 2024-12-08 |  |  | Prachi | 1 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-11-27 | 2024-12-08 |  |  | Prachi | 1 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-11-27 | 2024-12-08 |  |  | Prachi | 1 | 2
000725 | SSN PC pump sizing calculation | "SSN PC pump sizing calculation " | 2024-11-27 | 2024-12-08 |  |  | Prachi | 1 | 2
000737 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" | 2024-11-07 | 2024-11-28 |  |  | Max | 1 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-11-08 | 2024-12-05 |  |  | David | 0 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-11-08 | 2024-12-05 |  |  | David | A.1 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-11-08 | 2024-12-05 |  |  | David | A.1 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-11-08 | 2025-01-20 |  |  | David | A.1 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-11-08 | 2025-01-20 |  |  | David | A.1 | 3
000775 | MSRA for RC Wall | "MSRA for RC Wall" | 2024-11-26 | 2024-12-18 |  |  | Charles | 1 | 3
000795 | FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver) | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" | 2024-11-01 | 2024-12-05 |  |  | Radha | 0 | 1
000796 | Vendor Approval of EICA Material and Accessories (Cable Gland) | "Vendor Approval of EICA Material and Accessories (Cable Gland)" | 2024-11-02 | 2024-11-24 |  |  | Karthikeyan | 0 | 1
000797 | Preliminary Design and Vendor Approval of Unistrut Support | "Preliminary Design and Vendor Approval of Unistrut Support" | 2024-11-02 | 2024-11-24 |  |  | Karthikeyan | 0 | 1
000798 | GA Drawing for Centrifugal Pump | "GA Drawing for Centrifugal Pump" | 2024-11-04 | 2024-12-05 |  |  | David | B | 2
000798 | GA Drawing for Centrifugal Pump | "GA Drawing for Centrifugal Pump" | 2024-11-04 | 2024-12-05 |  |  | David | B | 2
000799 | Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package | "Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package" | 2024-11-05 | 2024-12-05 |  |  | Prachi | 0 | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000800 | ST618- THP Train 1 & 2 Conceptual | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | 2024-12-07 |  |  | Zora | A | 1
000801 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024) | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024)" | 2024-11-06 | 2025-11-20 |  |  | Vincent | 0 | 1
000802 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" | 2024-11-06 | 2024-12-05 |  |  | Yibo | 2 | 3
000803 | Submission of BIM Coordination VCM Model (Oct 2024) | "Submission of BIM Coordination VCM Model (Oct 2024)" | 2024-11-08 | 2024-11-24 |  |  | Heng Peng | 0 | 1
000804 | C4B Monthly Progress Report Number No.18 (10 24) | "C4B Monthly Progress Report Number No.18 (10 24) " | 2024-11-09 | 2024-12-03 |  |  | Leslie | 0 | 1
000805 | Anchor bolt Details for pipe supports for post drill and Cast-in type | "Anchor bolt Details for pipe supports for post drill and Cast-in type" | 2024-11-11 | 2024-12-03 |  |  | Zora | 0 | 1
000805 | Anchor bolt Details for pipe supports for post drill and Cast-in type | "Anchor bolt Details for pipe supports for post drill and Cast-in type" | 2024-11-11 | 2024-12-03 |  |  | Zora | 0 | 1
000806 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | 2024-11-11 | 2024-12-05 |  |  | Yibo | 1 | 2
000807 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | 2024-11-12 | 2024-11-21 |  |  | Radha | 1 | 2
000808 | Sample board submission for SS Cable ladder, trays & accessories (United U-Li) | "Sample board submission for SS Cable ladder, trays & accessories (United U-Li)" | 2024-11-12 | 2024-11-25 |  |  | Radha | 0 | 1
000809 | SSN Overall Area Layout And Sections | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 5
000809 | SSN Overall Area Layout And Sections | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 7
000809 | SSN Overall Area Layout And Sections | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 4
000809 | SSN Overall Area Layout And Sections | "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000810 | SSN_Shelter 001 Layout and Elevation | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000810 | SSN_Shelter 001 Layout and Elevation | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000811 | SSN_Shelter 002 Layout and Elevation | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000811 | SSN_Shelter 002 Layout and Elevation | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000812 | SSN_Shelter 003 Layout and Elevation | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000812 | SSN_Shelter 003 Layout and Elevation | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | 2024-11-13 | 2024-12-08 |  |  | Thet Myo | A.2 | 3
000813 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | 2024-12-05 |  |  | Radha | 1 | 2
000814 | Monthly Concrete Cube Records for Structural works for August 2024 | "Monthly Concrete Cube Records for Structural works for August 2024" | 2024-11-14 | 2024-12-07 |  |  | N.Kumar | 0 | 1
000815 | MSRA and SWP for Installation of Manway | "MSRA and SWP for Installation of Manway" | 2024-11-15 | 2024-12-05 |  |  | Bryan | 0 | 1
000816 | Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech) | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" | 2024-11-16 | 2024-12-05 |  |  | Low | 0 | 1
000817 | Preliminary Design and Vendor Approval – HDMANN Unistrut Support | "Preliminary Design and Vendor Approval – HDMANN Unistrut Support" | 2024-11-16 | 2024-12-06 |  |  | Karthikeyan | 0 | 1
000818 | MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " | 2024-11-16 | 2024-12-06 |  |  | Bryan | 0 | 1
000819 | THP Layout, Elevations and Section Details | "THP Layout, Elevations and Section Details" && "THP BCA BP Submission" | 2024-11-18 | 2025-01-16 |  |  | Thet Myo | A | 2
000819 | THP Layout, Elevations and Section Details | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2024-11-18 | 2025-01-16 |  |  | Thet Myo | A | 3
000819 | THP Layout, Elevations and Section Details | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2024-11-18 | 2025-01-16 |  |  | Thet Myo | A | 3
000819 | THP Layout, Elevations and Section Details | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2024-11-18 | 2025-01-16 |  |  | Thet Myo | A | 3
000819 | THP Layout, Elevations and Section Details | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2024-11-18 | 2025-01-16 |  |  | Thet Myo | A | 3
000820 | THP Door and Finishes Schedules | "THP Door and Finishes Schedules" | 2024-11-18 | 2024-12-18 |  |  | Anna | A | 1
000821 | THP Corridor & Stair Compartment Waterproofing Details | "THP Corridor & Stair Compartment Waterproofing Details" | 2024-11-18 | 2024-12-21 |  |  | Anna | A | 1
000822 | THP Handrail Layout and Cad Ladder Details | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | 2024-12-07 |  |  | Zora | A | 1
000822 | THP Handrail Layout and Cad Ladder Details | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | 2024-12-07 |  |  | Zora | A | 1
000822 | THP Handrail Layout and Cad Ladder Details | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | 2024-12-07 |  |  | Zora | A | 1
000822 | THP Handrail Layout and Cad Ladder Details | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | 2024-12-07 |  |  | Zora | A | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000823 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | 2025-01-16 |  |  | Thet Myo | D | 1
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000824 | ST617 -THP PLATFORM 01 & 02 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" | 2024-11-19 | 2024-12-07 |  |  | Zora | A | 3
000825 | Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm | "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" | 2024-11-20 | 2024-11-27 |  |  | N.Kumar | 0 | 2
000826 | THP Load Flow Study Report | "THP Load Flow Study Report" | 2024-11-20 | 2024-12-14 |  |  | Freedomer | 1 | 2
000827 | THP Short Circuit Study Report | "THP Short Circuit Study Report" | 2024-11-20 | 2024-12-14 |  |  | Freedomer | 1 | 2
000828 | MSRA and SWP for Delivery of 2000kVA Transformer | "MSRA and SWP for Delivery of 2000kVA Transformer " | 2024-11-21 | 2024-12-05 |  |  | Charles | 1 | 2
000829 | Fire Seal Detail | "Fire Seal Detail" | 2024-11-21 | 2024-12-06 |  |  | Anna | A | 1
000830 | Monthly Concrete Cube Records for Structural works for September 2024 | "Monthly Concrete Cube Records for Structural works for September 2024" | 2024-11-21 | 2024-11-27 |  |  | N.Kumar | 0 | 1
000831 | SSN_CAT Ladder | "SSN_CAT Ladder " | 2024-11-22 | 2024-12-08 |  |  | Anna | D | 3
000832 | SSN Electrical Building Archi Drawing | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | 2024-11-22 | 2024-12-07 |  |  | Anna | A.2 | 3
000832 | SSN Electrical Building Archi Drawing | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | 2024-11-22 | 2024-12-07 |  |  | Anna | A.2 | 3
000832 | SSN Electrical Building Archi Drawing | "SSN Electrical Building Archi Drawing" | 2024-11-22 | 2024-12-07 |  |  | Anna | A | 1
000832 | SSN Electrical Building Archi Drawing | "SSN Electrical Building Archi Drawing" | 2024-11-22 | 2024-12-07 |  |  | Anna | A | 1
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2024-11-22 | 2024-12-07 |  |  | Zora | A.2 | 4
000834 | SSN Railing Layout | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2024-11-22 | 2024-12-07 |  |  | Anna | A.2 | 7
000835 | SSN Pavement Plan | "SSN Pavement Plan" && "C4B SSN Drain Hydraulic Calculation" | 2024-11-22 | 2024-12-08 |  |  | Franklin | A | 2
000836 | SSN Wall Mounted Pipe Support Design | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-11-22 | 2024-12-06 |  |  | Aaron | F | 4
000836 | SSN Wall Mounted Pipe Support Design | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-11-22 | 2024-12-06 |  |  | Aaron | H | 4
000837 | Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" | 2024-11-22 | 2024-12-06 |  |  | Thet Myo | 0 | 5
000838 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | 2024-11-22 | 2024-12-05 |  |  | Joo Kwan | 0 | 1
000838 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | 2024-11-22 | 2024-12-05 |  |  | Joo Kwan | 0 | 1
000839 | MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold | "MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold" | 2024-11-23 | 2024-12-18 |  |  | Bryan | 0 | 1
000840 | MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold | "MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold" | 2024-11-23 | 2024-12-07 |  |  | Bryan | 0 | 1
000841 | MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold | "MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold" | 2024-11-23 | 2024-12-18 |  |  | Bryan | 0 | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000842 | Drawings and PE Calculation of ST619 | "Drawings and PE Calculation of ST619 " | 2024-11-25 | 2024-12-06 |  |  | Thet Myo | A | 1
000843 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | 2024-12-07 |  |  | Thet Myo | A | 1
000843 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | 2024-12-07 |  |  | Thet Myo | A | 1
000843 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | 2024-12-07 |  |  | Thet Myo | A | 1
000844 | THP Courtyard RC Plinth Detail | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-11-25 | 2024-12-07 |  |  | Franklin | G | 5
000844 | THP Courtyard RC Plinth Detail | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-11-25 | 2024-12-07 |  |  | Franklin | G | 5
000844 | THP Courtyard RC Plinth Detail | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-11-25 | 2024-12-07 |  |  | Franklin | G | 5
000845 | THP Courtyard Equipment Anchor Bolt Details | " THP Courtyard Equipment Anchor Bolt Details" | 2024-11-25 | 2024-12-18 |  |  | Thet Myo | A | 1
000845 | THP Courtyard Equipment Anchor Bolt Details | " THP Courtyard Equipment Anchor Bolt Details" | 2024-11-25 | 2024-12-18 |  |  | Thet Myo | A | 1
000846 | Data Sheet for Hyperbolic Mixer | "Data Sheet for Hyperbolic Mixer" | 2024-11-28 | 2024-12-14 |  |  | Yibo | 1 | 2
000847 | SSN Hyperbolic Mixer CFD | "SSN Hyperbolic Mixer CFD" | 2024-11-28 | 2024-12-14 |  |  | Yibo/ Qili | 0 | 1
000848 | Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN) | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" | 2024-11-28 | 2024-12-05 |  |  | Freedomer | 0 | 1
000849 | SSN Load Flow Study Report | "SSN Load Flow Study Report" | 2024-11-28 | 2024-12-14 |  |  | Freedomer | 1 | 2
000850 | SSN Short Circuit Study Report | "SSN Short Circuit Study Report" | 2024-11-28 | 2024-12-14 |  |  | Freedomer | 1 | 2
000851 | CSA Meeting Minutes 0036_14112024 | "CSA Meeting Minutes 0036_14112024" | 2024-11-28 | 2024-12-07 |  |  | Thet Myo | 0 | 1
000852 | Quarterly Safety Review Follow Up on SSN RC Works | "Quarterly Safety Review Follow Up on SSN RC Works" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-11-28 | 2024-12-07 |  |  | Max | 1 | 2
000853 | Vendor approval of SSN Package (Autosampler) | "Vendor approval of SSN Package (Autosampler) " | 2024-11-28 | 2025-03-14 |  |  | Yean Yee | 0 | 1
000854 | Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd. | "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." | 2024-11-28 | 2024-12-07 |  |  | Yuen Fatt | 0 | 1
000855 | Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd. | "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " | 2024-11-28 | 2024-12-05 |  |  | Yuen Fatt | 0 | 2
000856 | 2Hrs Fire rated AAC Blocks | "2Hrs Fire rated AAC Blocks" | 2024-11-29 | 2024-12-06 |  |  | Muthu | 1 | 2
000857 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | 2025-03-25 |  |  | Karthikeyan | 1 | 2
000858 | FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy) | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" | 2024-11-30 | 2024-12-14 |  |  | Radha | 0 | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A.1 | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000859 | SSN Wall Shop Drawing | "SSN Wall Shop Drawing" | 2024-11-30 | 2025-01-16 |  |  | Franklin | A | 1
000860 | SSN-Rain Water Drainage Layout and Detail Design | "SSN-Rain Water Drainage Layout and Detail Design" | 2024-11-30 | 2025-03-04 |  |  | Aaron | A | 1
000860 | SSN-Rain Water Drainage Layout and Detail Design | "SSN-Rain Water Drainage Layout and Detail Design" | 2024-11-30 | 2025-03-04 |  |  | Aaron | A | 1
000860 | SSN-Rain Water Drainage Layout and Detail Design | "SSN-Rain Water Drainage Layout and Detail Design" | 2024-11-30 | 2025-03-04 |  |  | Aaron | A | 1
000861 | THP- Valve Pit, Sump and Kerb Detail | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | 2024-11-30 | 2025-03-21 |  |  | Thet Myo | A | 4
000861 | THP- Valve Pit, Sump and Kerb Detail | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | 2024-11-30 | 2025-03-21 |  |  | Thet Myo | A | 5
000862 | Monthly Progress Presentation No. 18 (1124) | "Monthly Progress Presentation No. 18 (1124)" | 2024-11-30 | 2024-12-05 |  |  | Htet Nu | 0 | 1
000863 | Monthly Progress Meeting Minutes 0018_20241113 | "Monthly Progress Meeting Minutes 0018_20241113" | 2024-11-30 | 2024-12-05 |  |  | Htet Nu | 0 | 1

## 2024-12
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000092 | Piping Material Specification | "Piping Material Specification" | 2024-12-13 | 2025-01-20 |  |  | Liying | 3 | 4
000093 | Piperack P&IDs | "Piperack P&IDs" | 2024-12-06 | 2025-01-16 |  |  | Qili | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2024-12-06 | 2025-01-16 |  |  | Qili | E | 6
000166 | Inspection Test Plan for Architectural work | "Inspection Test Plan for Architectural work " | 2024-12-05 | 2024-12-23 |  |  | N.Kumar | 1 | 2
000167 | Inspection Test Plan for Plastering and Painting Work | "Inspection Test Plan for Plastering and Painting Work" | 2024-12-13 | 2024-12-23 |  |  | N.Kumar | 1 | 2
000219 | Building Services ACMV | "Building Services ACMV" | 2024-12-24 | 2025-02-07 |  |  | Kyaw Myo | A.4 | 4
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2024-12-24 | 2025-02-07 |  |  | Kyaw Myo | A.4 | 7
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2024-12-24 | 2025-02-07 |  |  | Kyaw Myo | A.4 | 7
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-12-10 | 2025-01-17 |  |  | Heng Peng | 1 | 4
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-12-10 | 2025-01-17 |  |  | Heng Peng | A | 3
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-12-10 | 2025-01-17 |  |  | Heng Peng | A | 5
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-12-10 | 2025-01-17 |  |  | Heng Peng | A | 5
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-12-10 | 2025-01-17 |  |  | Heng Peng | A | 3
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | 1 | 4
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A_WD | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A_WD | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A_WD | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A_WD | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A_WD | 1
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | 2025-01-17 |  |  | Heng Peng/ Muthu | A_WD | 1
000344 | Vendor Approval of SSN Package (Conductivity Analyser) | "Vendor Approval of SSN Package (Conductivity Analyser)" | 2024-12-05 | 2025-05-06 |  |  | Yean Yee | 1 | 2
000346 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" | 2024-12-05 | 2025-05-06 |  |  | Yean Yee | 1 | 2
000350 | Vendor Approval of SSN Package (pH Analyzer) | "Vendor Approval of SSN Package (pH Analyzer)" | 2024-12-05 | 2025-05-06 |  |  | Yean Yee | 1 | 2
000356 | SSN Transformer Sizing Calculations | "SSN Transformer Sizing Calculations" | 2024-12-14 | 2025-02-13 |  |  | Freedomer | 2 | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | E | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | D | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | C | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | C | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | D | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | E | 3
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | F | 4
000439 | SSN Transformer Outline Drawing | "SSN Transformer Outline Drawing" | 2024-12-11 | 2025-02-13 |  |  | Freedomer | F | 3
000569 | THP Instrument Lists | "THP Instrument Lists" | 2024-12-13 | 2025-02-13 |  |  | Yean Yee/ Low | 1 | 2
000590 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-12-02 | 2025-01-16 |  |  | Freedomer | 2 | 3
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-12-23 | 2025-04-05 |  |  | Yibo | 1 | 2
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-12-23 | 2025-04-05 |  |  | Yibo | 1 | 2
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-12-23 | 2025-04-05 |  |  | Yibo | 1 | 2
000593 | Progressive Cavity Pump Data Sheet | "Progressive Cavity Pump Data Sheet" | 2024-12-23 | 2025-04-05 |  |  | Yibo | 1 | 2
000626 | SSN MV Cable and Pilot Cable Data Sheet and Specification | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | 2024-12-19 | 2025-01-16 |  |  | Freedomer | 1 | 2
000643 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2024-12-12 | 2025-01-20 |  |  | Mohan | 1 | 3
000676 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-12-26 | 2025-02-03 |  |  | Radha | 2 | 3
000707 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-12-20 | 2025-02-20 |  |  | Radha | 2 | 3
000709 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2024-12-23 | 2025-02-24 |  |  | Radha | 2 | 3
000710 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2024-12-23 | 2025-02-24 |  |  | Radha | 2 | 3
000718 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-12-19 | 2025-02-18 |  |  | Freedomer | 2 | 3
000728 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-12-10 | 2024-12-14 |  |  | David | 2 | 3
000728 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-12-10 | 2024-12-14 |  |  | David | 2 | 3
000728 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-12-20 | 2025-01-09 |  |  | David | 2 | 3
000728 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-12-20 | 2025-01-09 |  |  | David | 2 | 3
000751 | Side Manway Calculation and GA Drawing | "Side Manway Calculation and GA Drawing" | 2024-12-17 | 2025-01-20 |  |  | David | 0 | 3
000752 | SSN HAZOP Report | "SSN HAZOP Report" | 2024-12-10 | 2024-12-14 |  |  | Qili | 2 | 3
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-12-06 | 2024-12-12 |  |  | David | C | 3
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-12-06 | 2024-12-12 |  |  | David | C | 3
000774 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | 2024-12-20 | 2025-02-18 |  |  | Mohan | 1 | 2
000775 | MSRA for RC Wall | "MSRA for RC Wall" | 2024-12-19 | 2025-01-08 |  |  | Charles | 1 | 3
000782 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" | 2024-12-14 | 2025-01-20 |  |  | Radha | 1 | 2
000828 | MSRA and SWP for Delivery of 2000kVA Transformer | "MSRA and SWP for Delivery of 2000kVA Transformer " | 2024-12-11 | 2024-12-30 |  |  | Charles | 1 | 2
000845 | THP Courtyard Equipment Anchor Bolt Details | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-12-06 | 2024-12-06 |  |  | Thet Myo | G | 5
000845 | THP Courtyard Equipment Anchor Bolt Details | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-12-06 | 2024-12-06 |  |  | Thet Myo | G | 5
000845 | THP Courtyard Equipment Anchor Bolt Details | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2024-12-06 | 2024-12-06 |  |  | Thet Myo | G | 5
000845 | THP Courtyard Equipment Anchor Bolt Details | " THP Courtyard Equipment Anchor Bolt Details" | 2024-12-18 | 2025-02-12 |  |  | Franklin | A | 1
000845 | THP Courtyard Equipment Anchor Bolt Details | " THP Courtyard Equipment Anchor Bolt Details" | 2024-12-18 | 2025-02-12 |  |  | Franklin | A | 1
000856 | 2Hrs Fire rated AAC Blocks | "2Hrs Fire rated AAC Blocks" | 2024-12-20 | 2025-01-02 |  |  | Muthu | 1 | 2
000864 | Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd. | "Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd." | 2024-12-02 | 2024-06-12 |  |  | Yuen Fatt | 0 | 1
000865 | Payment Claim No.17 | "Payment Claim No.17" | 2024-12-02 | 2024-12-03 |  |  | Yi Hao | 1 | 2
000865 | Payment Claim No.17 | "Payment Claim No.17" | 2024-12-03 | 2025-01-08 |  |  | Yi Hao | 1 | 2
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | C | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | C | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | D | 4
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | C | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | 2025-02-07 |  |  | Freedomer | B | 3
000868 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | 2025-01-08 |  |  | N.Kumar | 2 | 3
000868 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | 2025-02-17 |  |  | N.Kumar | 2 | 3
000869 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | 2024-12-02 | 2025-01-08 |  |  | N.Kumar | 0 | 2
000869 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | 2024-12-02 | 2025-02-03 |  |  | N.Kumar | 0 | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | 2025-02-07 |  |  | Freedomer | C | 3
000871 | THP Courtyard SCDF Consultation Letter | "THP Courtyard SCDF Consultation Letter" | 2024-12-03 | 2024-11-14 |  |  | Thet Myo | 0 | 1
000872 | Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect) | "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" | 2024-12-04 | 2024-12-14 |  |  | Radha | 0 | 1
000873 | FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " | 2024-12-04 | 2024-12-23 |  |  | Radha | 0 | 1
000874 | SSN Catchpot Sizing Calculation | "SSN Catchpot Sizing Calculation " | 2024-12-04 | 2025-01-08 |  |  | Qili | 2 | 3
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 1
000875 | BCA approval of ST608 - SSN Shelter | "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 1
000875 | BCA approval of ST608 - SSN Shelter | "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 1
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000875 | BCA approval of ST608 - SSN Shelter | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | 2025-01-16 |  |  | Thet Myo | E | 2
000876 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" | 2024-12-05 | 2024-12-23 |  |  | N.Kumar | 1 | 2
000877 | CV of Team Member (CSEM) | "CV of Team Member (CSEM)" | 2024-12-07 | 2025-03-25 |  |  | Htet Nu | 0 | 1
000878 | Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3) | "Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3)" | 2024-12-07 | 2025-09-23 |  |  | Vincent | 0 | 1
000879 | VCM Model Submission | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2024-12-09 | 2024-12-23 |  |  | Heng Peng | 0 | 4
000880 | Sampling Pump Calculation | "Sampling Pump Calculation" | 2024-12-10 | 2025-04-27 |  |  | Qili | 0 | 1
000881 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" | 2024-12-10 | 2025-01-20 |  |  | Radha | 1 | 2
000882 | Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex) | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" | 2024-12-10 | 2024-12-23 |  |  | Freedomer | 0 | 1
000883 | Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) | "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " | 2024-12-10 | 2024-12-23 |  |  | N.Kumar | 0 | 1
000884 | Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) | "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " | 2024-12-11 | 2024-12-23 |  |  | N.Kumar | 0 | 1
000885 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" | 2024-12-11 | 2024-12-14 |  |  | Yuen Fatt | 1 | 2
000885 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" | 2024-12-18 | 2024-12-23 |  |  | Yuen Fatt | 1 | 2
000886 | Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX) | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" | 2024-12-11 | 2025-01-08 |  |  | Karthikeyan | 0 | 1
000887 | Incentive/ Disincentive Audit Scheme for Sept 2024 | "Incentive/ Disincentive Audit Scheme for Sept 2024" | 2024-12-12 | 2024-12-30 |  |  | Samy | 0 | 1
000888 | Incentive/ Disincentive Audit Scheme for Oct 2024 | "Incentive/ Disincentive Audit Scheme for Oct 2024" | 2024-12-12 | 2024-12-30 |  |  | Samy | 0 | 1
000889 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | 2025-01-20 |  |  | Radha | 0 | 2
000889 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | 2025-12-23 |  |  | Radha | 0 | 2
000890 | C4B Monthly Progress Report Number No.19 (11 24) | "C4B Monthly Progress Report Number No.19 (11 24) " | 2024-12-13 | 2025-01-16 |  |  | Leslie | 0 | 1
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | 2025-01-12 |  |  | Liying | B | 2
000892 | CSA Meeting Minutes 0037_28112024 | "CSA Meeting Minutes 0037_28112024" | 2024-12-13 | 2024-12-30 |  |  | Thet Myo | 0 | 1
000893 | Vendor Approval of SSN Package (Rotameter) | "Vendor Approval of SSN Package (Rotameter)" | 2024-12-13 | 2025-03-14 |  |  | Yean Yee | 0 | 1
000894 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | 2024-12-13 | 2025-08-25 |  |  | Vincent | 0 | 1
000895 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | 2024-12-13 | 2024-12-23 |  |  | Dhanapal.S | 1 | 2
000896 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | 2024-12-13 | 2025-01-16 |  |  | Dhanapal.S | 1 | 2
000897 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | 2024-12-13 | 2025-01-16 |  |  | Dhanapal.S | 0 | 2
000898 | MSRA and SWP for Installation of AAC Block Wall | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | 2024-12-13 | 2025-01-08 |  |  | Charles | 0 | 2
000899 | Data Sheet for Blower Discharge Sliencer | "Data Sheet for Blower Discharge Sliencer" | 2024-12-13 | 2025-03-04 |  |  | Yibo | 0 | 1
000900 | Datasheet for Electromagnetic Flowmeter | "Datasheet for Electromagnetic Flowmeter" | 2024-12-13 | 2025-03-25 |  |  | Yean Yee | 1 | 2
000901 | Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh | "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | 2024-12-13 | 2024-12-23 |  |  | N.Kumar | 0 | 1
000902 | Instrument Differential Pressure Switch SAT | "Instrument Differential Pressure Switch SAT" | 2024-12-13 | 2025-02-07 |  |  | Joo Kwan | 0 | 1
000903 | Instrument Pressure Transmitter SAT | "Instrument Pressure Transmitter SAT" | 2024-12-13 | 2025-02-07 |  |  | Joo Kwan | 0 | 1
000904 | Penumatic on/ off Valve SAT | "Penumatic on/ off Valve SAT" | 2024-12-13 | 2025-02-07 |  |  | Joo Kwan | 0 | 1
000905 | Air Compresspor SAT | "Air Compresspor SAT" | 2024-12-13 | 2025-02-07 |  |  | Joo Kwan | 0 | 1
000906 | Air Dryer SAT | "Air Dryer SAT" | 2024-12-13 | 2025-02-07 |  |  | Joo Kwan | 0 | 1
000907 | SSN Harmonics Study Report | "SSN Harmonics Study Report" | 2024-12-16 | 2025-02-18 |  |  | Freedomer | 1 | 2
000908 | THP Harmonics Study Report | "THP Harmonics Study Report" | 2024-12-16 | 2025-02-18 |  |  | Freedomer | 0 | 1
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-01-16 |  |  | Kyaw Myo | A.1 | 2
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-01-16 |  |  | Kyaw Myo | A.2 | 3
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2024-12-16 | 2025-01-16 |  |  | Kyaw Myo | A.1 | 2
000910 | Data Sheet of Auto Lubrication Unit for centrifugal pump | "Data Sheet of Auto Lubrication Unit for centrifugal pump" | 2024-12-17 | 2025-01-20 |  |  | David | 0 | 1
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2024-12-17 | 2025-01-16 |  |  | David | A.1 | 2
000912 | Safety Review Report for SSN Structures | "Safety Review Report for SSN Structures" | 2024-12-18 | 2025-01-16 |  |  | Max | 0 | 1
000913 | FAT report for Earth cable, LV Power cable (Unwitnessed) | "FAT report for Earth cable, LV Power cable (Unwitnessed)" | 2024-12-18 | 2025-02-18 |  |  | Radha | 0 | 1
000914 | Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI) | "Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI)" | 2024-12-18 | 2025-03-18 |  |  | Radha | 0 | 1
000915 | Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) | "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | 2025-03-18 |  |  | Radha | 0 | 1
000916 | THP G2D Plant Hydraulic Network Calculation | "THP G2D Plant Hydraulic Network Calculation" | 2024-12-18 | 2025-04-27 |  |  | Joo Kwan | 0 | 1
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2024-12-18 | 2025-03-04 |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2024-12-18 | 2025-03-04 |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2024-12-18 | 2025-03-04 |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2024-12-18 | 2025-03-04 |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2024-12-18 | 2025-03-04 |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2024-12-18 | 2025-03-04 |  |  | Yibo | B | 2
000918 | Hydraulic Calculation (HOSEREEL) | "Hydraulic Calculation (HOSEREEL)" | 2024-12-18 | 2025-01-24 |  |  | Kyaw Myo | 1 | 2
000919 | CV of Team Member (T&C Manager) | "CV of Team Member (T&C Manager)" | 2024-12-19 | 2024-12-27 |  |  | Htet Nu | 1 | 2
000919 | CV of Team Member (T&C Manager) | "CV of Team Member (T&C Manager)" | 2024-12-27 | 2025-03-21 |  |  | Htet Nu | 1 | 2
000920 | Installation of Cable Container Support System | "Installation of Cable Container Support System" | 2024-12-18 | 2025-12-17 |  |  | Bryan | 0 | 1
000921 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | 2024-12-19 | 2025-03-10 |  |  | Prachi | 1 | 2
000922 | Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) | "Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) " | 2024-12-19 | 2025-02-18 |  |  | Dhanapal.S | 0 | 1
000923 | Sample Board Submission for SS Cable Ladder, Accessories (United U-LI) | "Sample Board Submission for SS Cable Ladder, Accessories (United U-LI)" | 2024-12-19 | 2025-02-18 |  |  | Dhanapal.S | 0 | 1
000924 | Vendor Approval of Ducting - CES_Salcon Sdn Bhd | "Vendor Approval of Ducting - CES_Salcon Sdn Bhd" | 2024-12-20 | 2025-01-09 |  |  | Yuen Fatt | 0 | 1
000925 | PC Pump GA Drawing | "PC Pump GA Drawing " | 2024-12-23 | 2025-04-27 |  |  | David | A | 1
000925 | PC Pump GA Drawing | "PC Pump GA Drawing " | 2024-12-23 | 2025-04-27 |  |  | David | A | 1
000925 | PC Pump GA Drawing | "PC Pump GA Drawing " | 2024-12-23 | 2025-04-27 |  |  | David | A | 1
000925 | PC Pump GA Drawing | "PC Pump GA Drawing " | 2024-12-23 | 2025-04-27 |  |  | David | A | 1
000926 | Vendor Approval - Passive Harmonic Filter | "Vendor Approval - Passive Harmonic Filter" | 2024-12-23 | 2025-01-19 |  |  | Freedomer | 0 | 1
000927 | FAT Report for Cable Ladder 1st Batch (United ULI) | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" | 2024-12-23 | 2025-02-18 |  |  | Dhanapal.S | 0 | 2
000928 | Payment Claim No.18 | "Payment Claim No.18" | 2024-12-24 | 2025-01-08 |  |  | Yi Hao | 0 | 1
000929 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" | 2024-12-24 | 2025-03-11 |  |  | Mohan | 0 | 1
000930 | Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) | "Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) " | 2024-12-26 | 2025-03-11 |  |  | Radha | 0 | 1
000931 | Screen General Arrangement Drawing | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" | 2024-12-27 | 2025-03-04 |  |  | Yibo | B | 3
000932 | O&M manual for Air Dryer and Air Compressor | "O&M manual for Air Dryer and Air Compressor" | 2024-12-27 | 2025-03-10 |  |  | YiBo | 0 | 1
000932 | O&M manual for Air Dryer and Air Compressor | "O&M manual for Air Dryer and Air Compressor" | 2024-12-27 | 2025-03-10 |  |  | YiBo | 0 | 1
000933 | Screen General Arrangement Drawing | "Screen General Arrangement Drawing" | 2024-12-27 | 2025-03-04 |  |  | Yibo | A | 1
000934 | Blower Name Plate Drawing | "Blower Name Plate Drawing " | 2024-12-31 | 2025-04-08 |  |  | Yibo | 0 | 1
000935 | Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" | 2024-12-31 | 2025-02-24 |  |  | N.Kumar | 0 | 1
000936 | FAT Report for Power Cable, Control Cable, MV Cable | "FAT Report for Power Cable, Control Cable, MV Cable" | 2024-12-31 | 2025-01-20 |  |  | Dhanapal.S | 0 | 1
000937 | Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site) | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" | 2024-12-31 | 2025-04-08 |  |  | Mohan | 0 | 1
000938 | Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site) | "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" | 2024-12-31 | 2025-04-08 |  |  | Mohan | 0 | 1

## 2025-01
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000170 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2025-01-21 | 2025-04-27 |  |  | Liying | 2 | 3
000197 | THP Overall Single Line Diagram | "THP Overall Single Line Diagram" | 2025-01-21 | 2025-04-30 |  |  | Freedomer | B | 2
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2025-01-22 | 2025-07-02 |  |  | Muthu | 1 | 4
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2025-01-22 | 2025-07-02 |  |  | Muthu | A | 3
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-01-22 | 2025-07-02 |  |  | Muthu | A | 5
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-01-22 | 2025-07-02 |  |  | Muthu | A | 5
000291 | Milestone 2 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2025-01-22 | 2025-07-02 |  |  | Muthu | A | 3
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | 1 | 4
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000341 | THP UPS Loading List | "THP UPS Loading List" | 2025-01-21 | 2025-05-15 |  |  | Low | 4 | 5
000342 | SSN UPS Loading List | "SSN UPS Loading List" | 2025-01-21 | 2025-03-04 |  |  | Low | 5 | 6
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 3
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 3
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-01-15 | 2025-03-25 |  |  | Low | E | 2
000421 | Data Sheet of THP Feed Pump | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" | 2025-01-26 | 2025-04-27 |  |  | Joo Kwan | 2 | 3
000501 | Vendor Approval of SSN Package (Thermal Flow Switches) | "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2025-01-08 | 2025-05-06 |  |  | Yean Yee | 1 | 2
000503 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | 2025-01-08 | 2025-03-17 |  |  | Yean Yee | 1 | 2
000513 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2025-01-10 | 2025-02-12 |  |  | Yean Yee | 3 | 4
000527 | THP-Air Compressor's Ducting Layout | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2025-01-14 | 2025-01-20 |  |  | Kyaw Myo | A.1 | 3
000527 | THP-Air Compressor's Ducting Layout | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2025-01-14 | 2025-01-20 |  |  | Kyaw Myo | A.1 | 3
000527 | THP-Air Compressor's Ducting Layout | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2025-01-14 | 2025-01-20 |  |  | Kyaw Myo | A.1 | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | B | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | B | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | B | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-01-16 | 2025-03-21 |  |  | Yibo | 0 | 1
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-01-21 | 2025-02-07 |  |  | Freedomer | D | 4
000623 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | 2025-01-16 | 2025-02-18 |  |  | Radha | 5 | 6
000686 | Data Sheet of Pressure Relief Valve at Air Receiver | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2025-01-20 | 2025-04-27 |  |  | Joo Kwan | 2 | 3
000698 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2025-01-20 | 2025-04-27 |  |  | Joo Kwan | 2 | 3
000706 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2025-01-16 | 2025-02-18 |  |  | Radha | 4 | 5
000716 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2025-01-20 | 2025-04-27 |  |  | Jovonne | 2 | 3
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 6
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2025-01-03 | 2025-03-06 |  |  | Qili | D | 5
000752 | SSN HAZOP Report | "SSN HAZOP Report" | 2025-01-20 | 2025-03-13 |  |  | Qili | 2 | 3
000758 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | 2025-01-16 | 2025-01-20 |  |  | Liying | 1 | 2
000777 | Preliminary Design and Vendor Approval for Spray Nozzles | "Preliminary Design and Vendor Approval for Spray Nozzles " | 2025-01-11 | 2025-02-12 |  |  | Qili | 1 | 2
000802 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" | 2025-01-26 | 2025-04-27 |  |  | Yibo | 2 | 3
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | B | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | A | 1
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | A | 1
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | A | 1
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | A | 1
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | A | 1
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | 2025-04-08 |  |  | Liying | A | 1
000939 | QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details) | "QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details)" | 2025-01-02 | 2025-04-27 |  |  | Radha | 0 | 1
000940 | Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating | "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | 2025-01-02 | 2025-04-08 |  |  | Radha | 0 | 1
000941 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | 2025-03-18 |  |  | Radha | 1 | 2
000942 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | 2025-01-02 | 2025-02-12 |  |  | Liying | 1 | 2
000943 | Datasheet for Unistrut Supports | "Datasheet for Unistrut Supports" | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | 0 | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000944 | Drawing Submission for Unistrut EICA Cable tray supports | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | 2025-03-13 |  |  | Karthikeyan | A | 1
000945 | BCA submission of ST611 (Pipe Support More Than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-08 |  |  | Zora | D | 2
000945 | BCA submission of ST611 (Pipe Support More Than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-08 |  |  | Zora | D | 2
000945 | BCA submission of ST611 (Pipe Support More Than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-08 |  |  | Zora | D | 2
000945 | BCA submission of ST611 (Pipe Support More Than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-08 |  |  | Zora | D | 2
000945 | BCA submission of ST611 (Pipe Support More Than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-03 | 2025-01-08 |  |  | Zora | D | 2
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000946 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | 2025-01-12 |  |  | Zora | E | 1
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | C | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | C | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | C | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | C | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 1
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 1
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000947 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | 2025-02-12 |  |  | Zora | D | 2
000948 | Bored Piling Pile Eccentricity Reports (ECC 19 & 20) | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" | 2025-01-03 | 2025-01-12 |  |  | N.Kumar | 0 | 1
000949 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2025-01-03 | 2025-01-24 |  |  | Bryan | 1 | 2
000950 | Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd. | "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2025-01-03 | 2025-01-16 |  |  | Yuen Fatt | 0 | 1
000951 | Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" | 2025-01-04 | 2025-02-03 |  |  | N.Kumar | 0 | 1
000952 | Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024 | "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" | 2025-01-04 | 2025-01-24 |  |  | N.Kumar | 0 | 2
000953 | C4B Knife Gate Valve List & Datasheet | "C4B Knife Gate Valve List & Datasheet" | 2025-01-07 | 2025-04-08 |  |  | Liying | 0 | 1
000954 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | 2025-02-12 |  |  | Liying | 2 | 3
000955 | FAT/MDR Report for Side Manway (9 no;) | "FAT/MDR Report for Side Manway (9 no;)" | 2025-01-07 | 2025-03-25 |  |  | Radha | 0 | 1
000956 | Submission of BIM Coordination VCM Model (Dec 2024) | "Submission of BIM Coordination VCM Model (Dec 2024)" | 2025-01-08 | 2025-01-24 |  |  | Heng Peng | 0 | 1
000957 | CSA Meeting Minutes 0038_12122024 | "CSA Meeting Minutes 0038_12122024" | 2025-01-09 | 2025-01-24 |  |  | Thet Myo | 0 | 1
000958 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch) | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" | 2025-01-09 | 2025-03-25 |  |  | Radha | 0 | 1
000959 | Support design for compressed Air system <2m | "Support design for compressed Air system <2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000959 | Support design for compressed Air system <2m | "Support design for compressed Air system <2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000959 | Support design for compressed Air system <2m | "Support design for compressed Air system <2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000960 | Support design for compressed Air system >2m | "Support design for compressed Air system >2m" && "G2D Pipe Support_Report from QPD" | 2025-01-10 | 2025-02-18 |  |  | Franklin | 1 | 2
000960 | Support design for compressed Air system >2m | "Support design for compressed Air system >2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000960 | Support design for compressed Air system >2m | "Support design for compressed Air system >2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000960 | Support design for compressed Air system >2m | "Support design for compressed Air system >2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000960 | Support design for compressed Air system >2m | "Support design for compressed Air system >2m" | 2025-01-10 | 2025-02-18 |  |  | Franklin | A | 1
000961 | Datasheet for Pressure Transmitter | "Datasheet for Pressure Transmitter" | 2025-01-10 | 2025-02-13 |  |  | Yean Yee | 1 | 2
000962 | FAT report for THP Train 1 (Part-1) | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | 2025-02-20 |  |  | Radha | 3 | 4
000963 | BCA Approval of ST611 (Pipe Support more than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-11 | 2025-02-07 |  |  | Zora | D | 2
000963 | BCA Approval of ST611 (Pipe Support more than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-11 | 2025-02-07 |  |  | Zora | D | 2
000963 | BCA Approval of ST611 (Pipe Support more than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-11 | 2025-02-07 |  |  | Zora | D | 2
000963 | BCA Approval of ST611 (Pipe Support more than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-11 | 2025-02-07 |  |  | Zora | D | 2
000963 | BCA Approval of ST611 (Pipe Support more than 2m) | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" | 2025-01-11 | 2025-02-07 |  |  | Zora | D | 2
000964 | Functional Design Specification (Air Compressor System) | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | 2025-03-04 |  |  | Joo Kwan | 2 | 3
000965 | Process & MEICA Meeting Minutes 0036_21112024 | "Process & MEICA Meeting Minutes 0036_21112024" | 2025-01-11 | 2025-01-16 |  |  | Joo Kwan | 0 | 1
000966 | Process & MEICA Meeting Minutes 0037_05122024 | "Process & MEICA Meeting Minutes 0037_05122024" | 2025-01-11 | 2025-01-16 |  |  | Qili | 0 | 1
000967 | Datasheet for pH Transmitter & Sensor | "Datasheet for pH Transmitter & Sensor " | 2025-01-11 | 2025-02-13 |  |  | Yean Yee | 1 | 2
000968 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | 2025-02-24 |  |  | N.Kumar | 1 | 3
000969 | FAT report for Power cable, Control Cable, Instrument Cable (Witness) | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " | 2025-01-13 | 2025-01-20 |  |  | Dhanapal.S | 0 | 1
000970 | FAT report for SS Unistrut Support, Accessories (HDMANN) | "FAT report for SS Unistrut Support, Accessories (HDMANN) " | 2025-01-13 | 2025-03-02 |  |  | Dhanapal.S | 0 | 1
000971 | FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI) | "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" | 2025-01-13 | 2025-02-18 |  |  | Dhanapal.S | 0 | 1
000972 | FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN) | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" | 2025-01-13 | 2025-02-18 |  |  | Dhanapal.S | 0 | 1
000973 | Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks | "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" | 2025-01-13 | 2025-02-24 |  |  | Franklin | 0 | 1
000974 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | 2025-01-14 | 2025-03-18 |  |  | Radha | 0 | 1
000975 | Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 | "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " | 2025-01-14 | 2025-04-11 |  |  | K. Balaji | 0 | 1
000976 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | 2025-02-20 |  |  | Radha | 2 | 3
000977 | Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd) | "Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd)" | 2025-01-15 | 2025-03-04 |  |  | N.Kumar | 0 | 1
000978 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch) | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch)" | 2025-01-16 | 2025-03-25 |  |  | Mohan | 0 | 1
000979 | Monthly Progress Presentation No. 19 (1224) | "Monthly Progress Presentation No. 19 (1224)" | 2025-01-16 | 2025-01-19 |  |  | Htet Nu | 0 | 1
000980 | Monthly Progress Meeting Minutes 0019_20241217 | "Monthly Progress Meeting Minutes 0019_20241217" | 2025-01-16 | 2025-01-19 |  |  | Htet Nu | 0 | 1
000981 | Final Investigation Report (Incident on Leg Injury) | "Final Investigation Report (Incident on Leg Injury)" | 2025-01-16 | 2025-12-23 |  |  | Dharmen | 0 | 1
000982 | Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond) | "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" | 2025-01-16 | 2025-02-24 |  |  | N.Kumar | 0 | 1
000983 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | 2025-01-16 | 2025-02-20 |  |  | Radha | 1 | 2
000984 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | 2025-01-16 | 2025-01-20 |  |  | Liying | 1 | 2
000985 | Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd | "Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd " | 2025-01-17 | 2025-04-27 |  |  | Mohan | 0 | 1
000986 | C4B Monthly Progress Report Number No.20 (12 24) | "C4B Monthly Progress Report Number No.20 (12 24) " | 2025-01-19 | 2025-02-03 |  |  | Htet Nu | 0 | 1
000987 | MSRA and SWP for Waterproofing Work | "MSRA and SWP for Waterproofing Work" | 2025-01-20 | 2025-02-17 |  |  | Charles | 0 | 1
000988 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | 2025-01-20 | 2025-02-12 |  |  | Qili | 1 | 2
000989 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | 2025-01-24 |  |  | Qili | 1 | 4
000990 | THP Steam Pressure Loss Calculation | "THP Steam Pressure Loss Calculation" && "Process Gas Hydraulic Calculation" | 2025-01-20 | 2025-10-06 |  |  | Prachi | 0 | 2
000991 | SSN Compressed Air Headloss Calculation | "SSN Compressed Air Headloss Calculation" | 2025-01-20 | 2025-10-06 |  |  | Qili | 0 | 1
000992 | Air Compressor On Off Valve Data sheet | "Air Compressor On Off Valve Data sheet" | 2025-01-20 | 2025-02-12 |  |  | Joo Kwan | 0 | 2
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 0 | 3
000994 | Commissioning Plan for THP Air Compressor System | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | 2025-02-03 |  |  | Joo Kwan | 2 | 3
000995 | THP Biosolids PMS Network Architecture Drawing | "THP Biosolids PMS Network Architecture Drawing" | 2025-01-21 | 2025-03-31 |  |  | Balaji | 1 | 2
000996 | THP Drawing Index for Cable Raceway and Room Layout | "THP Drawing Index for Cable Raceway and Room Layout" | 2025-01-21 | 2025-03-13 |  |  | Freedomer | A | 1
000997 | Electrical Documents for THP Train 1 & Train 2 (CAMBI) | "Electrical Documents for THP Train 1 & Train 2 (CAMBI)" | 2025-01-22 | 2025-03-13 |  |  | Radha | 0 | 1
000998 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " | 2025-01-22 | 2025-02-24 |  |  | Radha | 1 | 2
000999 | Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd) | "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" | 2025-01-24 | 2025-02-24 |  |  | N.Kumar | 0 | 1
001000 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | 2025-02-13 |  |  | N.Kumar | 3 | 4
001001 | Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | "Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32)" | 2025-01-24 | 2025-02-20 |  |  | N.Kumar | 0 | 1
001002 | Drawing Index (Building and Services Mech.) | "Drawing Index (Building and Services Mech.)" | 2025-01-26 | 2025-04-27 |  |  | Kyaw Myo | A | 1
001002 | Drawing Index (Building and Services Mech.) | "Drawing Index (Building and Services Mech.)" | 2025-01-26 | 2025-04-27 |  |  | Kyaw Myo | A | 1
001003 | CV of Team member (Senior Planning Engineer) | "CV of Team member (Senior Planning Engineer)" | 2025-01-26 | 2025-02-07 |  |  | Htet Nu | 0 | 1
001004 | FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI) | "FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI)" | 2025-01-26 | 2025-02-18 |  |  | Dhanapal.S | 0 | 1
001005 | Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd) | "Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd)" | 2025-01-26 | 2025-03-02 |  |  | Dhanapal.S | 0 | 1
001006 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | 2025-01-26 | 2025-02-07 |  |  | Joo Kwan | 1 | 2
001007 | Process Gas Hydraulic Calculation | "THP Steam Pressure Loss Calculation" && "Process Gas Hydraulic Calculation" | 2025-01-26 | 2025-10-06 |  |  | Joo Kwan | 0 | 2
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Lintel and Stiffener | "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | 2025-02-17 |  |  | Yuen Fatt | A | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001009 | BCA Submission of ST617 (THP Platforms) | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 1
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001010 | BCA Submission of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-01-26 | 2025-02-20 |  |  | Zora | B | 2
001011 | Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1) | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" | 2025-01-26 | 2025-04-11 |  |  | Dhanapal.S | 0 | 1
001012 | THP Compartmentalization Lighting and Ventilation Fan | "THP Compartmentalization Lighting and Ventilation Fan" | 2025-01-26 | 2025-04-02 |  |  | Freedomer | A | 1
001012 | THP Compartmentalization Lighting and Ventilation Fan | "THP Compartmentalization Lighting and Ventilation Fan" | 2025-01-26 | 2025-04-02 |  |  | Freedomer | A | 1
001013 | FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " | 2025-01-26 | 2025-02-18 |  |  | Dhanapal.S | 0 | 1
001014 | ITP for Lightning Protection System Installation | "ITP for Lightning Protection System Installation" | 2025-01-26 | 2025-03-13 |  |  | Dhanapal.S | 1 | 2

## 2025-02
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000097 | Engineering Calculation Report For Potable Water Pipe | "Engineering Calculation Report For Potable Water Pipe" | 2025-02-18 | 2025-03-25 |  |  | Kyaw Myo | 3 | 3
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | 1 | 4
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.2 | 5
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.2 | 5
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000120 | Milestone 2 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng | A.3 | 2
000151 | THP-Electrical Load List | "THP-Electrical Load List" | 2025-02-10 | 2025-05-05 |  |  | Freedomer | 2 | 3
000158 | SSN Electrical Load List | "SSN Electrical Load List" | 2025-02-10 | 2025-05-05 |  |  | Freedomer | 1 | 2
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-02-18 | 2025-05-06 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-02-18 | 2025-05-06 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2025-02-18 | 2025-05-06 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2025-02-18 | 2025-05-06 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | 2025-02-18 | 2025-05-06 |  |  | Freedomer | D | 5
000189 | SSN Plumbing and Sanitary | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2025-02-24 | 2025-03-25 |  |  | Kyaw Myo | A.2 | 4
000189 | SSN Plumbing and Sanitary | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2025-02-24 | 2025-03-25 |  |  | Kyaw Myo | A.2 | 3
000189 | SSN Plumbing and Sanitary | "SSN Plumbing and Sanitary " | 2025-02-24 | 2025-03-25 |  |  | Kyaw Myo | A.1 | 2
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | 2025-02-21 | 2025-03-18 |  |  | Kyaw Myo | A.1_MS2 | 3
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | 2025-02-21 | 2025-03-18 |  |  | Kyaw Myo | A.1_MS2 | 3
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" | 2025-02-21 | 2025-03-18 |  |  | Kyaw Myo | A.1 | 2
000190 | Hose Reel (SSN Area) | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" | 2025-02-21 | 2025-03-18 |  |  | Kyaw Myo | A | 3
000201 | SSN Overall Single Line Diagram | "SSN Overall Single Line Diagram" | 2025-02-14 | 2025-05-06 |  |  | Freedomer | B | 2
000201 | SSN Overall Single Line Diagram | "SSN Overall Single Line Diagram" | 2025-02-14 | 2025-05-06 |  |  | Freedomer | B | 2
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 5
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000205 | SSN Preliminary Lightning Protection System | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-02-20 | 2025-05-06 |  |  | Freedomer | C | 4
000219 | Building Services ACMV | "Building Services ACMV" | 2025-02-13 | 2025-03-25 |  |  | Kyaw Myo | A.4 | 4
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-02-13 | 2025-03-25 |  |  | Kyaw Myo | A.4 | 7
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-02-13 | 2025-03-25 |  |  | Kyaw Myo | A.4 | 7
000232 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" | 2025-02-28 | 2025-11-24 |  |  | Yibo | 2 | 3
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B_endorsed | 4
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B_endorsed | 3
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B_endorsed | 3
000245 | SSN Earthing Layout Plan | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B_endorsed | 3
000252 | Sitewide Piperack Lightning Protection System | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2025-02-25 | 2025-05-06 |  |  | Freedomer | A.2 | 5
000252 | Sitewide Piperack Lightning Protection System | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" | 2025-02-25 | 2025-05-06 |  |  | Freedomer | A.2 | 5
000255 | Milestone 2 THP MCC Room | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2025-02-26 | 2025-07-02 |  |  | Heng Peng/ Muthu | 1 | 3
000311 | THP Lightning Protection System | "THP Lightning Protection System" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B | 2
000311 | THP Lightning Protection System | "THP Lightning Protection System" | 2025-02-25 | 2025-05-05 |  |  | Freedomer | B | 2
000345 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" | 2025-02-27 | 2025-05-06 |  |  | Yean Yee | 2 | 4
000360 | SSN PFD | "SSN PFD" | 2025-02-27 | 2025-03-13 |  |  | Qili | D | 6
000360 | SSN PFD | "SSN PFD" | 2025-02-27 | 2025-03-13 |  |  | Qili | D | 6
000385 | SSN Process Design Basis | "SSN Process Design Basis" | 2025-02-24 | 2025-03-13 |  |  | Qili | 3 | 4
000406 | SSN 22kV MV Power Cable Sizing Calculations | "SSN 22kV MV Power Cable Sizing Calculations" | 2025-02-19 | 2025-05-06 |  |  | Freedomer | 2 | 3
000438 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2025-02-27 | 2025-05-06 |  |  | Yean Yee | 3 | 4
000459 | Vendor Approval of SSN Package (Radar Level Transmitter) | "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2025-02-27 | 2025-04-11 |  |  | Yean Yee | 2 | 3
000462 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2025-02-27 | 2025-04-11 |  |  | Yean Yee | 2 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 3
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.2 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.1 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.2 | 2
000492 | SSN Cast-in Schedule & Details | "SSN Cast-in Schedule & Details" | 2025-02-26 | 2025-04-28 |  |  | Kyaw Myo | C.2 | 2
000623 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | 2025-02-21 | 2025-04-27 |  |  | Radha | 5 | 6
000639 | SSN Functional Design Specification | "SSN Functional Design Specification" | 2025-02-21 | 2025-03-13 |  |  | Balaji | 1 | 2
000656 | Data Sheet for Steam Sparger Package | "Data Sheet for Steam Sparger Package" | 2025-02-18 | 2025-03-10 |  |  | Joo Kwan | 1 | 2
000676 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2025-02-07 | 2025-02-18 |  |  | Radha | 2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 2
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 3
000681 | Biosolid Building Piping Opening | "Biosolid Building Piping Opening " | 2025-02-18 | 2025-04-27 |  |  | Geno | A.2 | 2
000689 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" | 2025-02-07 | 2025-03-13 |  |  | Radha | 2 | 3
000706 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2025-02-26 | 2025-05-06 |  |  | Dhanapal.S | 4 | 5
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2025-02-18 | 2025-03-11 |  |  | Aaron | A.2 | 4
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2025-02-18 | 2025-03-11 |  |  | Aaron | A | 1
000868 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2025-02-20 | 2025-03-04 |  |  | N.Kumar | 2 | 3
000895 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | 2025-02-14 | 2025-04-27 |  |  | Dhanapal.S | 1 | 2
000918 | Hydraulic Calculation (HOSEREEL) | "Hydraulic Calculation (HOSEREEL)" | 2025-02-19 | 2025-03-18 |  |  | Kyaw Myo | 1 | 2
000949 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2025-02-27 | 2025-04-27 |  |  | Bryan | 1 | 2
000989 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-02-25 | 2025-04-02 |  |  | Qili | 1 | 4
001015 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd. | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." | 2025-02-03 | 2025-02-20 |  |  | Yuen Fatt | 0 | 1
001016 | Payment Claim No.19 | "Payment Claim No.19" | 2025-02-03 | 2025-02-17 |  |  | Yi Hao | 0 | 1
001017 | THP Protected Corridor Fan Control Circuit Diagram | "THP Protected Corridor Fan Control Circuit Diagram" | 2025-02-03 | 2025-04-27 |  |  | Freedomer | A | 1
001018 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | 2025-02-03 | 2025-03-25 |  |  | Mohan | 1 | 2
001019 | WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd | "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | 2025-02-03 | 2025-04-27 |  |  | Mohan | 0 | 1
001020 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | 2025-02-04 | 2025-03-02 |  |  | Dhanapal.S | 1 | 2
001021 | FAT Report for Air Blowers (Aerzen) | "FAT Report for Air Blowers (Aerzen)" | 2025-02-05 | 2025-03-25 |  |  | Radha | 0 | 1
001022 | Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | 2025-02-06 | 2025-02-18 |  |  | N.Kumar | 0 | 1
001023 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | 2025-02-07 | 2025-03-02 |  |  | N.Kumar | 1 | 4
001024 | Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" | 2025-02-07 | 2025-02-18 |  |  | N.Kumar | 0 | 1
001025 | Sample Board Submission for Roof Waterproofing (G-Concept) | "Sample Board Submission for Roof Waterproofing (G-Concept)" | 2025-02-07 | 2025-02-24 |  |  | N.Kumar | 0 | 1
001026 | Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | 2025-02-24 |  |  | Yuen Fatt | C | 5
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | 2025-04-08 |  |  | Freedomer | C | 3
001028 | BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters | "BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters " | 2025-02-07 | 2025-02-18 |  |  | Zora | 0 | 1
001029 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-02-07 | 2025-03-25 |  |  | Radha | 1 | 2
001030 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | 2025-04-27 |  |  | Radha | 1 | 2
001031 | SSN Energy Consumption Computation | " SSN Energy Consumption Computation" | 2025-02-07 | 2025-10-06 |  |  | Qili | 0 | 1
001032 | SSN Aeration Blower Control Philosophy | "SSN Aeration Blower Control Philosophy" | 2025-02-07 | 2025-03-13 |  |  | Qili | 1 | 2
001033 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-02-10 | 2025-02-13 |  |  | Yean Yee | 1 | 2
001034 | Submission of BIM Coordination VCM Model (Jan 2025) | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | 2025-02-10 | 2025-02-20 |  |  | Muthu | 0 | 2
001035 | FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch) | "FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch)" | 2025-02-10 | 2025-03-25 |  |  | Mohan | 0 | 1
001036 | Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | 2025-02-11 | 2025-02-24 |  |  | Dhanapal.S | 0 | 1
001037 | EOT Notice Letter for ST617 & ST619 | "EOT Notice Letter for ST617 & ST619" | 2025-02-11 | 2025-04-27 |  |  | Vincent | 0 | 1
001038 | Unppriced PO for YHW | "Unppriced PO for YHW" | 2025-02-11 | 2025-03-13 |  |  | Yi Hao | 0 | 1
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A.2 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-02-12 | 2025-03-25 |  |  | Kyaw Myo | A | 2
001040 | FAT Report for WSD11-MCC-0101A&B | "FAT Report for WSD11-MCC-0101A&B" | 2025-02-12 | 2025-03-13 |  |  | Dhanapal.S | 1 | 2
001041 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | 2025-02-13 | 2025-02-18 |  |  | Radha | 1 | 2
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001042 | Lintel and Stiffener Shop Drawings | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-02-14 | 2025-03-21 |  |  | Yuen Fatt | C | 4
001043 | Preliminary design and Vendor Approval – Plastic Valves (GF) | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | 2025-02-14 | 2025-04-05 |  |  | Liying | 1 | 2
001044 | MSRA, SWP for Site Wide Pipe Rack Installation | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | 2025-02-16 | 2025-12-17 |  |  | Bryan | 0 | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001045 | BCA Approval of ST619 (THP Pipe Rack) | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" | 2025-02-17 | 2025-02-18 |  |  | Franklin | B | 2
001046 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" | 2025-02-17 | 2025-03-17 |  |  | Jun | 0 | 1
001047 | C4B Monthly Progress Report Number No.21 (01 25) | "C4B Monthly Progress Report Number No.21 (01 25) " | 2025-02-17 | 2025-03-13 |  |  | Leslie | 0 | 1
001048 | Monthly Progress Presentation No. 20 (0125) | "Monthly Progress Presentation No. 20 (0125)" | 2025-02-18 | 2025-02-18 |  |  | Htet Nu | 0 | 1
001049 | Monthly Progress Meeting Minutes 0020_20250122 | "Monthly Progress Meeting Minutes 0020_20250122" | 2025-02-18 | 2025-02-24 |  |  | Htet Nu | 0 | 1
001050 | Shop Drawings for SSN Electrical Building Roof Waterproofing | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | 2025-03-13 |  |  | Yuen Fatt | C | 5
001050 | Shop Drawings for SSN Electrical Building Roof Waterproofing | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | 2025-03-13 |  |  | Yuen Fatt | D | 5
001051 | Data Sheet for Parabolic Screen | "Data Sheet for Parabolic Screen" | 2025-02-18 | 2025-03-04 |  |  | Yibo | 1 | 2
001052 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | 2025-02-18 | 2025-04-08 |  |  | Freedomer | A | 1
001052 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | 2025-02-18 | 2025-04-08 |  |  | Freedomer | A | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001053 | BCA Approval of ST617 (THP Platform 01 & 02) | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | 2025-03-10 |  |  | Zora | B | 1
001054 | Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works | "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" | 2025-02-18 | 2025-02-24 |  |  | N.Kumar | 0 | 1
001055 | Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd) | "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2025-02-18 | 2025-05-06 |  |  | Dhanapal.S | 0 | 1
001056 | Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" | 2025-02-18 | 2025-05-06 |  |  | Dhanapal.S | 0 | 1
001057 | Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" | 2025-02-18 | 2025-05-06 |  |  | Dhanapal.S | 0 | 1
001058 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-03-13 |  |  | Franklin | D | 2
001058 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-03-13 |  |  | Franklin | D | 2
001058 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-03-13 |  |  | Franklin | D | 2
001058 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-03-13 |  |  | Franklin | D | 2
001058 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | 2025-03-13 |  |  | Franklin | 1 | 1
001059 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch) | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch)" | 2025-02-19 | 2025-04-27 |  |  | Mohan | 0 | 1
001060 | Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system | "Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system" | 2025-02-19 | 2025-04-02 |  |  | Radha | 0 | 1
001061 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | 2025-02-20 | 2025-02-25 |  |  | Dhanapal.S | 4 | 5
001062 | Inspection and Test plan for THP air Compressor System Pressure Transmitter | "Inspection and Test plan for THP air Compressor System Pressure Transmitter " | 2025-02-20 | 2025-05-30 |  |  | Dhanapal.S | 0 | 1
001063 | SSN Drawing Index (Cable Tray Layout) | "SSN Drawing Index (Cable Tray Layout)" | 2025-02-21 | 2025-05-06 |  |  | Balaji | A | 1
001064 | SSN Drawing Index (Instrument Layout) | "SSN Drawing Index (Instrument Layout)" | 2025-02-21 | 2025-05-07 |  |  | Balaji | A | 1
001065 | Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton) | "Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton)" | 2025-02-21 | 2025-04-02 |  |  | Radha | 0 | 1
001066 | Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks) | "Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks)" | 2025-02-21 | 2025-04-02 |  |  | David | 0 | 1
001067 | Data Sheet for Steam Sparger G2D Inlet Control Valve | "Data Sheet for Steam Sparger G2D Inlet Control Valve" | 2025-02-21 | 2025-04-28 |  |  | Joo Kwan | 0 | 1
001068 | MSRA, SWP for Box Out Concreting | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | 2025-02-24 | 2025-03-18 |  |  | Charles | 1 | 4
001069 | Unpriced PO for CSEL Pipes (MUSG) | "Unpriced PO for CSEL Pipes (MUSG)" | 2025-02-24 | 2025-03-27 |  |  | Yi Hao | 0 | 1
001070 | Unpriced PO for Cable Raceway (United-U Li) | "Unpriced PO for Cable Raceway (United-U Li) " | 2025-02-24 | 2025-03-13 |  |  | Yi Hao | 0 | 1
001071 | Unpriced PO for Cable Raceway (Jebsen & Jessen) | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" | 2025-02-24 | 2025-03-13 |  |  | Yi Hao | 0 | 1
001072 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | 2025-03-11 |  |  | Leslie | 0 | 1
001072 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | 2025-03-11 |  |  | Leslie | 0 | 1
001072 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | 2025-03-11 |  |  | Leslie | 0 | 1
001073 | THP-Dry Riser System | "THP-Dry Riser System" && "Dry Riser Installation Details" | 2025-02-25 | 2025-03-25 |  |  | Kyaw Myo | A1 | 2
001073 | THP-Dry Riser System | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | 2025-02-25 | 2025-03-25 |  |  | Kyaw Myo | A1 | 4
001073 | THP-Dry Riser System | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | 2025-02-25 | 2025-03-25 |  |  | Kyaw Myo | A | 3
001073 | THP-Dry Riser System | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | 2025-02-25 | 2025-03-25 |  |  | Kyaw Myo | A | 3
001074 | FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch | "FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch" | 2025-02-26 | 2025-05-06 |  |  | Dhanapal.S | 0 | 1
001075 | Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd) | "Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd)" | 2025-02-27 | 2025-04-11 |  |  | N.Kumar | 0 | 1
001076 | Fan Static Load Calculation (SSN Electrical Building) | "Fan Static Load Calculation (SSN Electrical Building)" | 2025-02-27 | 2025-03-25 |  |  | Kyaw Myo | 0 | 1
001077 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-28 | 2025-03-13 |  |  | Franklin | D | 2
001077 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-28 | 2025-03-13 |  |  | Franklin | D | 2
001077 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-28 | 2025-03-13 |  |  | Franklin | D | 2
001077 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-28 | 2025-03-13 |  |  | Franklin | D | 2
001078 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" | 2025-02-28 | 2025-04-06 |  |  | N.Kumar | 1 | 2
001079 | C4B SSN Pressure Reducing Valve Calculations | "C4B SSN Pressure Reducing Valve Calculations" | 2025-02-28 | 2025-04-28 |  |  | Prachi | 0 | 1
001080 | C4B SSN Pressure Reducing Valve Datasheet | "C4B SSN Pressure Reducing Valve Datasheet" | 2025-02-28 | 2025-04-28 |  |  | Prachi | 1 | 2
001225 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | 2025-05-05 |  |  | Leslie | 0 | 1
001225 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | 2025-05-05 |  |  | Leslie | 0 | 1
001225 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | 2025-05-05 |  |  | Leslie | 0 | 1
001225 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | 2025-05-05 |  |  | Leslie | 0 | 1

## 2025-03
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2025-03-14 | 2025-04-15 |  |  | Leslie | 5.1 | 5
000058 | MSRA, SWP for General Civil Works | "MSRA, SWP for General Civil Works" | 2025-03-20 | 2025-05-07 |  |  | Bryan | 3 | 4
000093 | Piperack P&IDs | "Piperack P&IDs" | 2025-03-14 | 2025-04-30 |  |  | Qili | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2025-03-14 | 2025-04-30 |  |  | Qili | E | 6
000178 | Data Sheet of Pressure Vessel | "Data Sheet of Pressure Vessel" | 2025-03-04 | 2025-10-06 |  |  | Joo Kwan | 4 | 5
000181 | Data Sheet of PGC | "Data Sheet of PGC" | 2025-03-06 | 2025-10-06 |  |  | Joo Kwan | 2 | 3
000206 | Preliminary Sizing Calculation for SSN Future OCF System | "Preliminary Sizing Calculation for SSN Future OCF System" | 2025-03-04 | 2025-10-06 |  |  | Qili | 1 | 2
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 5
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 5
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 4
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 4
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 4
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | C | 2
000236 | THP Earthing Layout Plan | "THP Earthing Layout Plan" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | C | 2
000244 | Heat Load Calculation Report for ACMV | "Heat Load Calculation Report for ACMV" | 2025-03-20 | 2025-05-25 |  |  | Kyaw Myo | 2 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 3
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.2 | 3
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S03 PAD" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.2 | 3
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.2 | 3
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000297 | Standard Pipe Support - For All Area | "Standard Pipe Support - For All Area " | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000307 | Typical Installation Details for Power | "Typical Installation Details for Power" | 2025-03-25 | 2025-05-06 |  |  | Freedomer | B | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2025-03-27 | 2025-05-08 |  |  | Freedomer | C | 3
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2025-03-27 | 2025-05-08 |  |  | Freedomer | C | 3
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2025-03-27 | 2025-05-08 |  |  | Freedomer | C | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2025-03-27 | 2025-05-08 |  |  | Freedomer | C | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2025-03-27 | 2025-05-08 |  |  | Freedomer | C | 2
000308 | SSN Single Line Diagram for MOV DB | "SSN Single Line Diagram for MOV DB" | 2025-03-27 | 2025-05-08 |  |  | Freedomer | C | 2
000310 | Typical Installation Details for Lighting | "Typical Installation Details for Lighting" | 2025-03-25 | 2025-05-06 |  |  | Freedomer | B | 2
000322 | Process Functional Description | "Process Functional Description" | 2025-03-04 | 2025-04-28 |  |  | Qili | 3 | 4
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-10 | 2025-03-21 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-03-21 | 2025-06-11 |  |  | Aaron/HP | A.4 | 7
000342 | SSN UPS Loading List | "SSN UPS Loading List" | 2025-03-06 | 2025-05-15 |  |  | Low | 5 | 6
000359 | Vendor Approval of THP Train Instrument (Siemens) | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2025-03-21 | 2025-05-06 |  |  | Yean Yee/ Cambi | 3 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 7
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 7
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.2 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-10 | 2025-03-21 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.2 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-03-21 | 2025-06-11 |  |  | Zora/HP | A.4 | 5
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-03-26 | 2025-05-20 |  |  | Aaron | A.2 | 6
000403 | SSN Control Philosophy | "SSN Control Philosophy" | 2025-03-14 | 2025-05-15 |  |  | Qili | 3 | 4
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2025-03-14 | 2025-07-14 |  |  | Qili | 2 | 3
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2025-03-14 | 2025-07-14 |  |  | Qili | B | 3
000409 | SSN Datasheet & Drawing of Biomass Separator | "SSN Datasheet & Drawing of Biomass Separator " | 2025-03-14 | 2025-07-14 |  |  | Qili | B | 2
000416 | SSN Process Hydraulic Calculation & Drawing | "SSN Process Hydraulic Calculation & Drawing" | 2025-03-24 | 2025-10-06 |  |  | Qili | 2 | 3
000416 | SSN Process Hydraulic Calculation & Drawing | "SSN Process Hydraulic Calculation & Drawing" | 2025-03-24 | 2025-10-06 |  |  | Qili | C | 3
000476 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2025-03-17 | 2025-05-06 |  |  | Yean Yee | 1 | 2
000499 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" | 2025-03-14 | 2025-07-08 |  |  | Joo Kwan | 1 | 2
000513 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2025-03-17 | 2025-05-06 |  |  | Yean Yee | 3 | 4
000514 | Vendor Approval of SSN Package (Pressure Switch) | "Vendor Approval of SSN Package (Pressure Switch)" | 2025-03-17 | 2025-05-06 |  |  | Yean Yee | 2 | 3
000515 | Vendor Approval of SSN Package (Temperature Transmitters) | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2025-03-17 | 2025-05-06 |  |  | Yean Yee | 2 | 3
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 2 | 4
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 0 | 3
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | B | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | B | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | 2025-04-23 |  |  | Qili | A | 1
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 2
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 3
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-03-07 | 2025-05-06 |  |  | Freedomer | E | 6
000579 | SSN RIO 0201 I/O List | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | 2025-03-06 | 2025-05-07 |  |  | Low | 4 | 5
000583 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | 2025-03-19 | 2025-03-25 |  |  | Balaji/ Karthik | 3 | 4
000637 | Data Sheet of Digester Feed Pump | "Data Sheet of Digester Feed Pump" | 2025-03-04 | 2025-10-06 |  |  | Joo Kwan | 1 | 2
000645 | SSN Lux Simulation Report | "SSN Lux Simulation Report" | 2025-03-12 | 2025-05-06 |  |  | Freedomer | 3 | 4
000677 | SSN Control Narrative | "SSN Control Narrative" | 2025-03-24 | 2025-05-15 |  |  | Qili | 1 | 2
000689 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" | 2025-03-14 | 2025-05-07 |  |  | Radha | 2 | 3
000694 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" | 2025-03-27 | 2025-05-19 |  |  | Radha | 1 | 2
000718 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2025-03-07 | 2025-04-27 |  |  | Freedomer | 2 | 3
000733 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2025-03-06 | 2025-03-21 |  |  | Radha | 1 | 2
000741 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2025-03-18 | 2025-04-27 |  |  | Radha | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2025-03-04 | 2025-10-06 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2025-03-04 | 2025-10-06 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2025-03-04 | 2025-10-06 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2025-03-04 | 2025-10-06 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2025-03-04 | 2025-10-06 |  |  | Yibo | 1 | 2
000755 | Data Sheets for Dosing Pumps | "Data Sheets for Dosing Pumps" | 2025-03-04 | 2025-10-06 |  |  | Yibo | 1 | 2
000806 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | 2025-03-20 | 2025-11-24 |  |  | Yibo | 1 | 2
000807 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | 2025-03-12 | 2025-05-05 |  |  | Radha | 1 | 2
000826 | THP Load Flow Study Report | "THP Load Flow Study Report" | 2025-03-25 | 2025-05-06 |  |  | Freedomer | 1 | 2
000827 | THP Short Circuit Study Report | "THP Short Circuit Study Report" | 2025-03-25 | 2025-05-06 |  |  | Freedomer | 1 | 2
000846 | Data Sheet for Hyperbolic Mixer | "Data Sheet for Hyperbolic Mixer" | 2025-03-27 | 2025-04-27 |  |  | Yibo | 1 | 2
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | 2025-03-13 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | D | 4
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | C | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-05-06 |  |  | Freedomer | B | 2
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 3
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-03-28 | 2025-10-01 |  |  | Freedomer | B | 2
000874 | SSN Catchpot Sizing Calculation | "SSN Catchpot Sizing Calculation " | 2025-03-14 | 2025-04-28 |  |  | Qili | 2 | 3
000881 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" | 2025-03-13 | 2025-05-19 |  |  | Radha | 1 | 2
000891 | GA drawing for Metallic Knife Gate Valves | "GA drawing for Metallic Knife Gate Valves " | 2025-03-13 | 2025-04-08 |  |  | Liying | B | 2
000896 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | 2025-03-06 | 2025-04-27 |  |  | Dhanapal.S | 1 | 2
000897 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | 2025-03-11 | 2025-05-05 |  |  | Dhanapal.S | 0 | 2
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.2 | 3
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 2
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" | 2025-03-13 | 2025-04-02 |  |  | Kyaw Myo | A.1 | 3
000954 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-03-27 | 2025-04-11 |  |  | Liying | 2 | 3
000961 | Datasheet for Pressure Transmitter | "Datasheet for Pressure Transmitter" | 2025-03-17 | 2025-05-07 |  |  | Yean Yee | 1 | 2
000968 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-03-10 | 2025-04-14 |  |  | N.Kumar | 1 | 3
000992 | Air Compressor On Off Valve Data sheet | "Air Compressor On Off Valve Data sheet" | 2025-03-07 | 2025-07-08 |  |  | Joo Kwan | 0 | 2
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-03-06 | 2025-03-18 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-03-06 | 2025-03-18 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-03-06 | 2025-03-18 |  |  | Joo Kwan | 1 | 4
000994 | Commissioning Plan for THP Air Compressor System | "Commissioning Plan for THP Air Compressor System" | 2025-03-06 | 2025-03-18 |  |  | Joo Kwan | 2 | 3
000998 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " | 2025-03-10 | 2025-04-11 |  |  | N.Kumar | 1 | 2
001000 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-03-14 | 2025-04-06 |  |  | N.Kumar | 3 | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Block Wall" | 2025-03-21 | 2025-03-28 |  |  | Yuen Fatt | 1 | 1
001014 | ITP for Lightning Protection System Installation | "ITP for Lightning Protection System Installation" | 2025-03-14 | 2025-05-07 |  |  | Dhanapal.S | 1 | 2
001020 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | 2025-03-14 | 2025-05-05 |  |  | Dhanapal.S | 1 | 2
001023 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | 2025-03-10 | 2025-06-11 |  |  | N.Kumar | 1 | 4
001033 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-03-17 | 2025-05-07 |  |  | Yean Yee | 1 | 2
001040 | FAT Report for WSD11-MCC-0101A&B | "FAT Report for WSD11-MCC-0101A&B" | 2025-03-27 | 2025-05-07 |  |  | Dhanapal.S | 1 | 2
001041 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | 2025-03-24 | 2025-05-19 |  |  | Radha | 1 | 2
001061 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | 2025-03-10 | 2025-04-02 |  |  | Dhanapal.S | 4 | 5
001068 | MSRA, SWP for Box Out Concreting | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" | 2025-03-28 | 2025-04-15 |  |  | Kumar | 1 | 4
001081 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | 2025-03-03 | 2025-03-04 |  |  | Joo Kwan | 1 | 2
001081 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | 2025-03-14 | 2025-04-02 |  |  | Joo Kwan | 1 | 2
001082 | Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd. | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2025-03-03 | 2025-04-02 |  |  | Yuen Fatt | 0 | 1
001083 | Ring Circulation Pump Data Sheet | "Ring Circulation Pump Data Sheet" | 2025-03-04 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001084 | Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation | "Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation" | 2025-03-04 | 2025-07-08 |  |  | Joo Kwan | 0 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 3
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | 2025-06-09 |  |  | Franklin | A1 | 1
001085 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-03-04 | 2025-06-09 |  |  | Franklin | X | 2
001086 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch) | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch)" | 2025-03-04 | 2025-04-30 |  |  | Mohan | 0 | 1
001087 | FAT report for Cable Ladder 1st batch (United ULI) | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" | 2025-03-05 | 2025-05-05 |  |  | Dhanapal.S | 0 | 2
001088 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED" | 2025-03-05 | 2025-03-18 |  |  | K. Balaji | 0 | 1
001089 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD " | 2025-03-05 | 2025-03-18 |  |  | K. Balaji | 0 | 1
001090 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES" | 2025-03-05 | 2025-03-18 |  |  | K. Balaji | 0 | 1
001091 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL)" | 2025-03-06 | 2025-03-25 |  |  | Radha | 0 | 1
001092 | Manual Gate Valve Data Sheet (Cambi Supply) | "Manual Gate Valve Data Sheet (Cambi Supply)" | 2025-03-06 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001093 | Manual Ball Valve Data Sheet (Cambi Supply) | "Manual Ball Valve Data Sheet (Cambi Supply)" | 2025-03-06 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001094 | Manual Globe Valve Data Sheet (Cambi Supply) | "Manual Globe Valve Data Sheet (Cambi Supply)" | 2025-03-06 | 2025-07-08 |  |  | Joo Kwan | 0 | 1
001095 | Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) | "Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) " | 2025-03-06 | 2025-05-05 |  |  | Dhanapal.S | 0 | 1
001096 | FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant) | "FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-03-06 | 2025-03-21 |  |  | Radha | 0 | 1
001097 | FAT report for Pressure transmitter (Air compressor) | "FAT report for Pressure transmitter (Air compressor)" | 2025-03-06 | 2025-05-30 |  |  | Dhanapal.S | 0 | 1
001098 | Unpriced PO for HDPE Pipes (AGRU) | "Unpriced PO for HDPE Pipes (AGRU) " | 2025-03-06 | 2025-03-27 |  |  | Yi Hao | 0 | 1
001099 | SSN -RIO PANEL 0001A/0001B- I/O List | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | 2025-04-22 |  |  | Balaji | 2 | 3
001100 | SSN Aeration Blowers I/O List | "SSN Aeration Blowers I/O List" | 2025-03-06 | 2025-04-22 |  |  | Balaji | 1 | 2
001101 | SSN Motor Starting Study Report | "SSN Motor Starting Study Report " | 2025-03-07 | 2025-05-07 |  |  | Freedomer | 0 | 1
001102 | THP Motor Starting Study Report | "THP Motor Starting Study Report " | 2025-03-07 | 2025-05-07 |  |  | Freedomer | 0 | 1
001103 | ON OFF Gate Valve Data Sheet (Cambi Supply) | "ON OFF Gate Valve Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001104 | ON OFF Ball Valve Data Sheet (Cambi Supply) | "ON OFF Ball Valve Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001105 | ON OFF Ball Valve PN25 Data Sheet (Cambi Supply) | "ON OFF Ball Valve PN25 Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001106 | ON OFF Ball Valve PN40 Data Sheet (Cambi Supply) | "ON OFF Ball Valve PN40 Data Sheet (Cambi Supply)" | 2025-03-07 | 2025-10-06 |  |  | Joo Kwan | 0 | 1
001107 | C4B Monthly Progress Report Number No.22 (02 25) | "C4B Monthly Progress Report Number No.22 (02 25) " | 2025-03-10 | 2025-03-27 |  |  | Leslie | 0 | 1
001108 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" | 2025-03-10 | 2025-03-25 |  |  | Karthikeyan | 1 | 2
001109 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" | 2025-03-10 | 2025-03-25 |  |  | Karthikeyan | 1 | 2
001110 | Submission of BIM Coordination VCM Model (Feb 2025) | " Submission of BIM Coordination VCM Model (Feb 2025) " | 2025-03-10 | 2025-03-25 |  |  | Heng Peng | 0 | 1
001111 | Payment Claim No.20 | "Payment Claim No.20" | 2025-03-10 | 2025-04-27 |  |  | Yi Hao | 0 | 1
001112 | SSN PMS Network Architecture Drawings | "SSN PMS Network Architecture Drawings" | 2025-03-10 | 2025-05-07 |  |  | Balaji | 1 | 2
001113 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" | 2025-03-10 | 2025-03-28 |  |  | K. Balaji | 2 | 3
001113 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" | 2025-03-10 | 2025-05-29 |  |  | K. Balaji | 2 | 3
001114 | Shop Drawings for Siphonic System (Fast Flow) | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " | 2025-03-11 | 2025-04-02 |  |  | Yuen Fatt | A | 2
001114 | Shop Drawings for Siphonic System (Fast Flow) | "Shop Drawings for Siphonic System (Fast Flow)" | 2025-03-11 | 2025-04-02 |  |  | Yuen Fatt | A | 1
001115 | Unpriced PO for Cable Support System (Jiangsu HDMann) | "Unpriced PO for Cable Support System (Jiangsu HDMann) " | 2025-03-11 | 2025-04-27 |  |  | Yi Hao | 0 | 1
001116 | FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) | "FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) " | 2025-03-12 | 2025-03-21 |  |  | Radha | 0 | 1
001117 | SSN -RIO PANEL 0202- I/O List | "SSN -RIO PANEL 0202- I/O List" | 2025-03-12 | 2025-04-22 |  |  | Balaji | 1 | 2
001118 | Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain | "Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain" | 2025-03-12 | 2025-07-08 |  |  | Qili | 0 | 1
001119 | THP LTA Submission | "THP LTA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001119 | THP LTA Submission | "THP LTA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001119 | THP LTA Submission | "THP LTA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001119 | THP LTA Submission | "THP LTA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001119 | THP LTA Submission | "THP LTA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001120 | THP PUB Submission | "THP PUB Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001120 | THP PUB Submission | "THP PUB Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001120 | THP PUB Submission | "THP PUB Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001120 | THP PUB Submission | "THP PUB Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001120 | THP PUB Submission | "THP PUB Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001121 | THP NEA Submission | "THP NEA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001121 | THP NEA Submission | "THP NEA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001121 | THP NEA Submission | "THP NEA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001121 | THP NEA Submission | "THP NEA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001121 | THP NEA Submission | "THP NEA Submission" | 2025-03-12 | 2025-06-11 |  |  | Aaron | A | 1
001122 | NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings | "NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings" | 2025-03-13 | 2025-08-25 |  |  | Vincent | 0 | 1
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | 2025-04-27 |  |  | Yibo | B | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | 2025-04-27 |  |  | Yibo | B | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | 2025-04-27 |  |  | Yibo | B | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | 2025-04-27 |  |  | Yibo | B | 2
001124 | Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON) | "Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON)" | 2025-03-14 | 2025-07-08 |  |  | Radha | 0 | 1
001125 | Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen) | "Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen)" | 2025-03-14 | 2025-04-27 |  |  | Qili | 0 | 1
001126 | SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd. | "SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd." | 2025-03-14 | 2025-06-04 |  |  | N.Kumar | 0 | 1
001127 | Datasheet for Differential Pressure Switch (Compressed Air System) | "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2025-03-17 | 2025-07-10 |  |  | Yean Yee | 0 | 1
001128 | Incentive/ Disincentive Audit Scheme for Nov 2024 | "Incentive/ Disincentive Audit Scheme for Nov 2024" | 2025-03-17 | 2025-03-25 |  |  | Samy | 0 | 1
001129 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " | 2025-03-18 | 2025-03-25 |  |  | Yuen Fatt | 0 | 1
001129 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " | 2025-03-18 | 2025-05-06 |  |  | Yuen Fatt | NA | 1
001130 | Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025 | "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" | 2025-03-18 | 2025-03-25 |  |  | Max | 0 | 1
001131 | Safety Review Report for Sitewide Pipe Rack | "Safety Review Report for Sitewide Pipe Rack" | 2025-03-18 | 2025-05-13 |  |  | Max | 1 | 2
001132 | FAT Procedure for LVSG Panels (Sunlight) | "FAT Procedure for LVSG Panels (Sunlight)" | 2025-03-18 | 2025-05-07 |  |  | Radha | 1 | 2
001133 | FAT Procedure for MDB Panels (Sunlight) | " FAT Procedure for MDB Panels (Sunlight)" | 2025-03-18 | 2025-05-21 |  |  | Radha | 0 | 1
001134 | Report of DFS (GUIDE 3) for THP Trains Installation | "Report of DFS (GUIDE 3) for THP Trains Installation" | 2025-03-18 | 2025-05-12 |  |  | Max | 0 | 2
001134 | Report of DFS (GUIDE 3) for THP Trains Installation | "Report of DFS (GUIDE 3) for THP Trains Installation" | 2025-03-18 | 2025-07-17 |  |  | Htet Nu | 0 | 2
001135 | SSN Spray Nozzle datasheet and drawing | "SSN Spray Nozzle datasheet and drawing" | 2025-03-20 | 2025-07-14 |  |  | Qili | A | 1
001135 | SSN Spray Nozzle datasheet and drawing | "SSN Spray Nozzle datasheet and drawing" | 2025-03-20 | 2025-07-14 |  |  | Qili | 0 | 1
001136 | Sitewide Piperack Handrail and Cad Ladder Layout and Details | "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | 2025-03-20 | 2025-05-07 |  |  | Aaron | A | 1
001137 | Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall) | "Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall)" | 2025-03-20 | 2025-05-07 |  |  | Radha | 0 | 1
001138 | FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI) | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" | 2025-03-20 | 2025-05-06 |  |  | Dhanapal.S | 0 | 1
001139 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | 2025-03-20 | 2025-04-05 |  |  | Qili | 1 | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | 2025-05-20 |  |  | Freedomer | B | 2
001141 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | 2025-03-21 | 2025-04-18 |  |  | Balaji | 1 | 2
001142 | SSN -RIO PANEL 0401- I/O List | "SSN -RIO PANEL 0401- I/O List" | 2025-03-21 | 2025-04-22 |  |  | Balaji | 1 | 2
001143 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " | 2025-03-21 | 2025-04-05 |  |  | K. Balaji | 1 | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | 2025-05-16 |  |  | Balaji | B | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | C | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | 2025-04-30 |  |  | Balaji | B | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | C | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | 2025-07-10 |  |  | Balaji | B | 2
001149 | Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance) | "Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance)" | 2025-03-21 | 2025-05-25 |  |  | Dhanapal.S | 0 | 1
001150 | Report of Project Safety Review for THP Trains Installation | "Report of Project Safety Review for THP Trains Installation" | 2025-03-24 | 2025-05-13 |  |  | Max | 2 | 3
001151 | FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch) | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" | 2025-03-24 | 2025-09-02 |  |  | Mohan | 0 | 1
001152 | Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) | "Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) " | 2025-03-24 | 2025-05-09 |  |  | N.Kumar | 0 | 1
001153 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" | 2025-03-24 | 2025-04-28 |  |  | Yibo | 0 | 1
001153 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-03-24 | 2025-04-28 |  |  | Yibo | A | 2
001154 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2025-03-24 | 2025-05-06 |  |  | K. Balaji | 2 | 3
001155 | SSN -RIO PANEL 0203- I/O List | "SSN -RIO PANEL 0203- I/O List " | 2025-03-24 | 2025-04-27 |  |  | Balaji | 1 | 2
001156 | MSRA for Waterproofing Works | "MSRA for Waterproofing Works" | 2025-03-24 | 2025-04-15 |  |  | Bryan | 0 | 1
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | 2025-05-20 |  |  | Freedomer | B | 2
001158 | SSN Protection Coordination Study Report | "SSN Protection Coordination Study Report" | 2025-03-25 | 2025-05-27 |  |  | Freedomer | 0 | 1
001159 | THP Protection Coordination Study Report | "THP Protection Coordination Study Report" | 2025-03-25 | 2025-05-27 |  |  | Freedomer | 0 | 1
001160 | THP UPS DB SLD Drawing | "THP UPS DB SLD Drawing " | 2025-03-25 | 2025-05-15 |  |  | Karthikeyan | A | 1
001160 | THP UPS DB SLD Drawing | "THP UPS DB SLD Drawing " | 2025-03-25 | 2025-05-15 |  |  | Karthikeyan | A | 1
001160 | THP UPS DB SLD Drawing | "THP UPS DB SLD Drawing " | 2025-03-25 | 2025-05-15 |  |  | Karthikeyan | A | 1
001160 | THP UPS DB SLD Drawing | "THP UPS DB SLD Drawing " | 2025-03-25 | 2025-05-15 |  |  | Karthikeyan | A | 1
001160 | THP UPS DB SLD Drawing | "THP UPS DB SLD Drawing " | 2025-03-25 | 2025-05-15 |  |  | Karthikeyan | A | 1
001161 | MSRA and SWP for MEICA OPENING on Block-wall | "MSRA and SWP for MEICA OPENING on Block-wall " | 2025-03-25 | 2025-04-15 |  |  | Charles | 0 | 1
001162 | Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) | "Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) " | 2025-03-25 | 2025-04-15 |  |  | N.Kumar | 0 | 1
001163 | Unpriced PO for Cable Raceway (Jiangsu HDMann) | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" | 2025-03-25 | 2025-05-06 |  |  | Yi Hao | 0 | 1
001164 | Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd) | "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" | 2025-03-25 | 2025-04-15 |  |  | Aaron | 0 | 1
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-03-25 | 2025-04-18 |  |  | Balaji | B | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | A | 1
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | 2025-04-27 |  |  | Balaji | A | 1
001167 | Datasheet for Electromagnetic Flow Meter | "Datasheet for Electromagnetic Flow Meter " | 2025-03-25 | 2025-07-10 |  |  | Yean Yee | 1 | 2
001168 | Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd. | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." | 2025-03-26 | 2025-04-11 |  |  | Yuen Fatt | 0 | 1
001169 | Consent to Potential Acquisition of CES Construction by OKH | "Consent to Potential Acquisition of CES Construction by OKH " | 2025-03-26 | 2025-04-05 |  |  | Shena | 0 | 1
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-04-27 |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-04-27 |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-04-27 |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-04-27 |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-04-27 |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-03-27 | 2025-04-27 |  |  | Qili | 1 | 2
001171 | Datasheet for Level Transmitter | "Datasheet for Level Transmitter" | 2025-03-27 | 2025-07-14 |  |  | Yean Yee | 1 | 2
001172 | Datasheet & GA drawing for sampling pump | "Datasheet & GA drawing for sampling pump" | 2025-03-27 | 2025-05-21 |  |  | David | 1 | 2
001172 | Datasheet & GA drawing for sampling pump | "Datasheet & GA drawing for sampling pump" | 2025-03-27 | 2025-05-21 |  |  | David | B | 2
001173 | Datasheet for Temperature Transmitter | "Datasheet for Temperature Transmitter " | 2025-03-27 | 2025-07-14 |  |  | Yean Yee | 1 | 3
001174 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " | 2025-03-27 | 2025-06-17 |  |  | Dhanapal.S | 0 | 2
001175 | FAT Report for Compressor Pipe support in Bio solid building | " FAT Report for Compressor Pipe support in Bio solid building" | 2025-03-27 | 2025-09-02 |  |  | Mohan | 0 | 1
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | 2025-05-07 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 4
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001177 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | 2025-05-16 |  |  | Balaji | B | 3
001178 | Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI) | "Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI)" | 2025-03-28 | 2025-09-08 |  |  | Mohan | 0 | 1
001222 | Incentive/ Disincentive Audit Scheme for Dec 2024 | "Incentive/ Disincentive Audit Scheme for Dec 2024" | 2025-03-17 | 2025-05-12 |  |  | Samy | 0 | 1
001223 | Incentive/ Disincentive Audit Scheme for Jan 2025 | "Incentive/ Disincentive Audit Scheme for Jan 2025" | 2025-03-17 | 2025-05-12 |  |  | Samy | 0 | 1
001224 | Incentive/ Disincentive Audit Scheme for Feb 2025 | "Incentive/ Disincentive Audit Scheme for Feb 2025" | 2025-03-17 | 2025-05-12 |  |  | Samy | 0 | 1

## 2025-04
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000005 | PROGRAMME OF THE WORKS | "PROGRAMME OF THE WORKS" | 2025-04-16 | 2025-04-27 |  |  | Leslie | 5.1 | 5
000016 | FRP TANK DATA SHEET | "FRP TANK DATA SHEET" | 2025-04-01 | 2025-10-06 |  |  | David | 1 | 2
000016 | FRP TANK DATA SHEET | "FRP TANK DATA SHEET" | 2025-04-01 | 2025-10-06 |  |  | David | 1 | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | 0 | 5
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 3
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | C | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | B | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 2 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 3
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | 0 | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 3
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | D | 5
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | D | 5
000163 | Milestone 2 SSN Water Tank | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | C | 5
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 2
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000163 | Milestone 2 SSN Water Tank | "Milestone 2 SSN Water Tank" | 2025-04-28 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | 1 | 4
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | 0 | 3
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 2 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 2
000202 | THP Cable List | "THP Cable List" | 2025-04-10 | 2025-05-08 |  |  | Freedomer | 3 | 4
000204 | SSN Cable List | "SSN Cable List" | 2025-04-18 | 2025-05-07 |  |  | Freedomer | 3 | 4
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-16 | 2025-05-08 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-16 | 2025-05-08 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-16 | 2025-05-08 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-16 | 2025-05-08 |  |  | Freedomer | B | 5
000217 | THP Power Layout Plan | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-16 | 2025-05-08 |  |  | Freedomer | B | 5
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-17 | 2025-05-08 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-17 | 2025-05-08 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-17 | 2025-05-08 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-17 | 2025-05-08 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-04-17 | 2025-05-08 |  |  | Freedomer | C | 8
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000220 | SSN Distribution Board Single Line Diagram | "SSN Distribution Board Single Line Diagram" | 2025-04-03 | 2025-06-17 |  |  | Freedomer | B | 2
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2025-04-10 | 2025-05-07 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2025-04-10 | 2025-05-07 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | 2025-04-10 | 2025-05-07 |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "SSN Power Layout Plan" | 2025-04-10 | 2025-05-07 |  |  | Freedomer | D | 4
000227 | SSN Power Layout Plan | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | 2025-04-10 | 2025-05-07 |  |  | Freedomer | D | 5
000293 | Milestone 2 THP A100 Silo Area inside Biosolid Building | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2025-04-09 | 2025-07-02 |  |  | Heng Peng | 1 | 4
000302 | Milestone 2 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2025-04-10 | 2025-07-02 |  |  | Heng Peng | 2 | 3
000422 | Data Sheet and Drawing of Reactor Feed Pump | "Data Sheet and Drawing of Reactor Feed Pump" | 2025-04-10 | 2025-10-06 |  |  | Joo Kwan | 2 | 3
000590 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2025-04-09 | 2025-05-08 |  |  | Freedomer | 2 | 3
000644 | THP Lux Simulation Report | "THP Lux Simulation Report" | 2025-04-22 | 2025-05-06 |  |  | Freedomer | 2 | 4
000664 | Steam Sparger Calculation | "Steam Sparger Calculation" | 2025-04-10 | 2025-10-06 |  |  | Joo Kwan | 1 | 2
000688 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | 2025-04-21 | 2025-09-08 |  |  | Radha | 1 | 2
000691 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " | 2025-04-17 | 2025-05-19 |  |  | Radha | 1 | 2
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2025-04-04 | 2025-10-06 |  |  | David | 2 | 2
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2025-04-04 | 2025-10-06 |  |  | David | C | 3
000766 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2025-04-04 | 2025-10-06 |  |  | David | C | 3
000798 | GA Drawing for Centrifugal Pump | "GA Drawing for Centrifugal Pump" | 2025-04-17 |  |  |  | David | B | 2
000798 | GA Drawing for Centrifugal Pump | "GA Drawing for Centrifugal Pump" | 2025-04-17 |  |  |  | David | B | 2
000831 | SSN_CAT Ladder | "SSN_CAT Ladder " | 2025-04-04 | 2025-04-28 |  |  | Anna | D | 3
000831 | SSN_CAT Ladder | "SSN_CAT Ladder " | 2025-04-04 | 2025-04-28 |  |  | Anna | A | 1
000831 | SSN_CAT Ladder | "SSN_CAT Ladder " | 2025-04-04 | 2025-04-28 |  |  | Anna | A | 1
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | 2025-05-06 |  |  | Freedomer | C | 2
000876 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" | 2025-04-11 | 2025-06-09 |  |  | N.Kumar | 1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 1
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 1
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 1
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 1
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 2
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 1
000911 | GA Drawing for FRP Tank | "GA Drawing for FRP Tank" | 2025-04-01 | 2025-10-06 |  |  | David | A.1 | 1
000921 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | 2025-04-01 | 2025-10-06 |  |  | Prachi | 1 | 2
000941 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-04-21 | 2025-05-19 |  |  | Radha | 1 | 2
000968 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-04-23 | 2025-04-28 |  |  | N.Kumar | 1 | 3
000989 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-04-17 | 2025-05-21 |  |  | Qili | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-04-08 | 2025-04-22 |  |  | Joo Kwan | 0 | 3
000995 | THP Biosolids PMS Network Architecture Drawing | "THP Biosolids PMS Network Architecture Drawing" | 2025-04-09 | 2025-05-07 |  |  | Balaji | 1 | 2
001000 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-04-08 | 2025-05-16 |  |  | N.Kumar | 3 | 4
001029 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-04-21 | 2025-05-12 |  |  | Radha | 1 | 2
001051 | Data Sheet for Parabolic Screen | "Data Sheet for Parabolic Screen" | 2025-04-01 | 2025-10-06 |  |  | Yibo | 1 | 2
001051 | Data Sheet for Parabolic Screen | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" | 2025-04-01 | 2025-10-06 |  |  | Yibo | B | 3
001061 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | 2025-04-11 | 2025-05-12 |  |  | Danapal | 4 | 5
001078 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" | 2025-04-09 | 2025-05-27 |  |  | N.Kumar | 1 | 2
001109 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" | 2025-04-18 | 2025-05-06 |  |  | Karthikeyan | 1 | 2
001141 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | 2025-04-30 | 2025-06-04 |  |  | Balaji | 1 | 2
001143 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " | 2025-04-10 | 2025-05-21 |  |  | K. Balaji | 1 | 2
001179 | Datasheet for Pressure Transmitter | "Datasheet for Pressure Transmitter" | 2025-04-01 | 2025-06-11 |  |  | Yean Yee | 1 | 2
001180 | Datasheet for Tuning Fork Level Switch | "Datasheet for Tuning Fork Level Switch " | 2025-04-01 | 2025-06-11 |  |  | Yean Yee | 1 | 2
001181 | Datasheet for Pressure Switch | "Datasheet for Pressure Switch" | 2025-04-01 | 2025-06-11 |  |  | Yean Yee | 2 | 3
001182 | Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe) | "Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe)" | 2025-04-01 | 2025-06-23 |  |  | Liying | 0 | 1
001183 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" | 2025-04-01 | 2025-06-23 |  |  | Liying | 1 | 2
001184 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch) | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch)" | 2025-04-02 | 2025-05-21 |  |  | Mohan | 0 | 1
001185 | FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch) | "FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch)" | 2025-04-02 | 2025-09-02 |  |  | Mohan | 0 | 1
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.4 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.1 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A1 | 1
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-04-02 | 2025-06-11 |  |  | Aaron | A1 | 1
001187 | Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" | 2025-04-03 | 2025-04-15 |  |  | K Balaji | 1 | 2
001187 | Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" | 2025-04-18 | 2025-05-16 |  |  | K Balaji | 1 | 2
001188 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " | 2025-04-03 | 2025-05-30 |  |  | Freedomer | 1 | 2
001189 | Memo-Installation Letter of TMS for Sivacon S8 | "Memo-Installation Letter of TMS for Sivacon S8" | 2025-04-03 | 2025-05-05 |  |  | Freedomer | 0 | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001190 | SSN UPSDB SLD | "SSN UPSDB SLD " | 2025-04-03 | 2025-04-27 |  |  | Balaji | A | 1
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001191 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001192 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001193 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001194 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-04-03 | 2025-05-16 |  |  | Balaji | B | 3
001195 | Manual Butterfly Valve | "Manual Butterfly Valve " | 2025-04-03 | 2025-06-23 |  |  | Liying | 2 | 3
001196 | Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd) | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" | 2025-04-03 | 2025-04-15 |  |  | Kumar | 0 | 1
001197 | MSRA and SWP for Plastering and Skim Coat | "MSRA and SWP for Plastering and Skim Coat " | 2025-04-03 | 2025-05-12 |  |  | Bryan | 0 | 1
001198 | MSRA and SWP for Floor Screeding and Tiles Laying | "MSRA and SWP for Floor Screeding and Tiles Laying " | 2025-04-03 | 2025-05-12 |  |  | Bryan | 0 | 1
001199 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) " | 2025-04-03 | 2025-09-08 |  |  | Mohan | 0 | 1
001200 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" | 2025-04-03 | 2025-05-21 |  |  | David | 1 | 2
001201 | Preliminary design and Vendor Approval – Strainer (Bliss) | "Preliminary design and Vendor Approval – Strainer (Bliss)" | 2025-04-04 | 2025-06-23 |  |  | Liying | 0 | 1
001202 | Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors | "Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors" | 2025-04-04 | 2025-09-23 |  |  | Vincent | 0 | 1
001203 | MSRA, SWP for Door Installation | "MSRA, SWP for Door Installation" | 2025-04-07 | 2025-04-15 |  |  | Bryan | 0 | 1
001204 | Payment Claim No.21 | "Payment Claim No.21" | 2025-04-07 | 2025-04-27 |  |  | Yi Hao | 0 | 1
001205 | Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) | "Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) " | 2025-04-07 | 2025-06-04 |  |  | N. Kumar | 0 | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-04-07 | 2025-06-11 |  |  | Freedomer | A | 1
001207 | MSRA SWP for Concrete Coring | "MSRA SWP for Concrete Coring " | 2025-04-07 | 2025-05-12 |  |  | N Kumar | 1 | 2
001208 | Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614) | "Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614)" | 2025-04-08 | 2025-06-30 |  |  | Aaron | 0 | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 3
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 3
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001209 | Steel Shop Drawings For SSN PR-001 (ST609) | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | 2025-08-04 |  |  | Aaron | A | 1
001210 | Submission of BIM Coordination VCM Model (Mar 2025) | " Submission of BIM Coordination VCM Model (Mar 2025) " | 2025-04-08 | 2025-04-27 |  |  | Heng Peng | 0 | 1
001211 | Unpriced LOA for MEICA installer (Cyclect Engineering) | "Unpriced LOA for MEICA installer (Cyclect Engineering)" | 2025-04-08 | 2025-10-06 |  |  | Yi Hao | 0 | 1
001212 | C4B Monthly Progress Report Number No.23 (03 25) | "C4B Monthly Progress Report Number No.23 (03 25) " | 2025-04-09 | 2025-04-27 |  |  | Leslie | 0 | 1
001213 | Electrical Signal List for THP -MCC-0101A/0101B | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | 2025-04-09 | 2025-04-27 |  |  | Balaji | 0 | 3
001214 | Unpriced LOA for Fire Protection System | "Unpriced LOA for Fire Protection System" | 2025-04-09 | 2025-10-06 |  |  | Yi Hao | 0 | 1
001215 | Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3 | "Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3" | 2025-04-09 | 2025-05-21 |  |  | K Balaji | 0 | 1
001216 | Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 | "Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 " | 2025-04-09 | 2025-10-06 |  |  | K Balaji | 0 | 1
001217 | FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" | 2025-04-10 | 2025-05-12 |  |  | Danapal | 0 | 1
001218 | ON OFF Butterfly Valve Data sheet (OVS) | "ON OFF Butterfly Valve Data sheet (OVS)" | 2025-04-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001219 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2025-04-10 | 2025-05-25 |  |  | Radha | 3 | 4
001220 | Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve | "Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve" | 2025-04-10 | 2025-05-21 |  |  | Radha | 0 | 1
001221 | Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" | 2025-04-11 | 2025-05-09 |  |  | N Kumar | 0 | 1
001226 | THP Courtyard - Valve Pit, Sump and Kerb Detail | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "SWPR _Platform A and B- Cat ladders" | 2025-04-14 | 2025-05-19 |  |  | Aaron | E | 2
001226 | THP Courtyard - Valve Pit, Sump and Kerb Detail | "THP Courtyard - Valve Pit, Sump and Kerb Detail " | 2025-04-14 | 2025-05-19 |  |  | Aaron | B | 2
001227 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" | 2025-04-14 | 2025-05-30 |  |  | Bryan | 1 | 2
001228 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" | 2025-04-16 | 2025-05-07 |  |  | Kumar | 1 | 2
001229 | Datasheet for Tuning Fork Level Switch | "Datasheet for Tuning Fork Level Switch " | 2025-04-16 | 2025-06-11 |  |  | Yean Yee | 1 | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-04-16 | 2025-06-11 |  |  | Balaji | A | 2
001231 | Datasheet for Radar Level Transmitter | "Datasheet for Radar Level Transmitter " | 2025-04-16 | 2025-06-30 |  |  | Yean Yee | 1 | 2
001232 | MSRA & SWP for NDT Activities | "MSRA & SWP for NDT Activities " | 2025-04-17 | 2025-10-06 |  |  | K Balaji | 0 | 1
001233 | SSN ICA Cable List | "SSN ICA Cable List " | 2025-04-17 | 2025-06-11 |  |  | Balaji | 1 | 2
001234 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" | 2025-04-17 | 2025-05-06 |  |  | Danapal | 2 | 3
001234 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" | 2025-04-17 | 2025-05-25 |  |  | Danapal | 2 | 3
001235 | Panel Base Frame Drawing | "Panel Base Frame Drawing" | 2025-04-18 | 2025-06-11 |  |  | Balaji | A | 1
001236 | Epoxy Coating System | "Epoxy Coating System" | 2025-04-18 | 2025-06-04 |  |  | Yuen Fatt | 0 | 1
001237 | Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps) | "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" | 2025-04-21 | 2025-05-05 |  |  | Kumar | 0 | 1
001238 | Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing | "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" | 2025-04-21 | 2025-05-05 |  |  | Kumar | 0 | 1
001239 | Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports) | "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" | 2025-04-21 | 2025-06-04 |  |  | Kumar | 0 | 1
001240 | Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps) | "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" | 2025-04-21 | 2025-05-30 |  |  | Kumar | 0 | 1
001241 | Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024 | "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" | 2025-04-21 | 2025-05-16 |  |  | Kumar | 0 | 1
001242 | Monthly Progress Presentation No. 21 (0225) | "Monthly Progress Presentation No. 21 (0225)" | 2025-04-21 | 2025-05-05 |  |  | Htet Nu | 0 | 1
001243 | Monthly Progress Meeting Minutes 0021_20250226 | "Monthly Progress Meeting Minutes 0021_20250226" | 2025-04-21 | 2025-05-07 |  |  | Htet Nu | 0 | 1
001244 | Monthly Progress Presentation No. 22 (0325) | "Monthly Progress Presentation No. 22 (0325)" | 2025-04-21 | 2025-05-05 |  |  | Htet Nu | 0 | 1
001245 | Monthly Progress Meeting Minutes 0022_20250324 | "Monthly Progress Meeting Minutes 0022_20250324" | 2025-04-21 | 2025-05-07 |  |  | Htet Nu | 0 | 1
001246 | FAT report for MCP panel WSD11-006-MCP-1000 | "FAT report for MCP panel WSD11-006-MCP-1000 " | 2025-04-22 | 2025-06-11 |  |  | Danapal | 0 | 1
001247 | Vendor Approval for THP Electromagnetic Flowmeters | "Vendor Approval for THP Electromagnetic Flowmeters" | 2025-04-22 | 2025-06-30 |  |  | Yean Yee | 0 | 1
001248 | CSA Meeting Minutes 0046_17042025 | "CSA Meeting Minutes 0046_17042025" | 2025-04-22 | 2025-05-30 |  |  | Htet Nu | 0 | 1
001249 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building " | 2025-04-23 | 2025-08-22 |  |  | Vincent | 0 | 1
001250 | FAT report for THP Sludge cooler B Stage 1 | "FAT report for THP Sludge cooler B Stage 1" | 2025-04-24 | 2025-07-02 |  |  | Radha | 1 | 2
001251 | MSRA, SWP for Water Testing of Liquid Retaining Structure | "MSRA, SWP for Water Testing of Liquid Retaining Structure" | 2025-04-24 | 2025-06-02 |  |  | Bryan | 0 | 1
001252 | Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " | 2025-04-25 | 2025-05-25 |  |  | Danapal | 0 | 1
001253 | FAT Report for Control Cable and Power Cables | "FAT Report for Control Cable and Power Cables" | 2025-04-25 | 2025-05-30 |  |  | Danapal | 0 | 1
001254 | THP ICA Cable List | " THP ICA Cable List" | 2025-04-25 | 2025-06-11 |  |  | Karthikeyan | 0 | 1
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 1
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001255 | ST618 WD Response For THP Train Cambi Structures | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-04-25 | 2025-06-11 |  |  | Aaron | C | 2
001256 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" | 2025-04-28 | 2025-07-02 |  |  | Radha | 1 | 2
001257 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" | 2025-04-29 | 2025-08-01 |  |  | Radha | 1 | 2
001258 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) | "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-04-29 | 2025-06-23 |  |  | Radha | 0 | 1
001259 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | 2025-05-30 |  |  | Joo Kwan | 0 | 1
001259 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | 2025-05-30 |  |  | Joo Kwan | 0 | 1
001259 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | 2025-05-30 |  |  | Joo Kwan | 0 | 1
001259 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | 2025-05-30 |  |  | Joo Kwan | 0 | 1
001259 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | 2025-05-30 |  |  | Joo Kwan | 0 | 1
001260 | Inspection and test Plan for fire protection system | "Inspection and test Plan for fire protection system " | 2025-04-30 | 2025-05-30 |  |  | Danapal | 1 | 2
001261 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" | 2025-04-30 | 2025-07-02 |  |  | Radha | 1 | 2

## 2025-05
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000103 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" | 2025-05-30 | 2025-08-01 |  |  | David | 1 | 2
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | 0 | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | B_MS2 | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | B_MS2 | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | B_MS2 | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | B_MS2 | 3
000191 | Milestone 2 SSN Electrical Building | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | B | 3
000191 | Milestone 2 SSN Electrical Building | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | B | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A9 | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A9 | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A.4 | 5
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A.4 | 5
000191 | Milestone 2 SSN Electrical Building | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A.1_MS2 | 3
000191 | Milestone 2 SSN Electrical Building | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A.1_MS2 | 3
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | D | 5
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | D | 5
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | C | 5
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | C | 5
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | C | 5
000191 | Milestone 2 SSN Electrical Building | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | D | 5
000191 | Milestone 2 SSN Electrical Building | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | D | 5
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN UPS and Battery Room Layout" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 2
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Process Non-Process room layout" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 2
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | 0 | 2
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000191 | Milestone 2 SSN Electrical Building | "Milestone 2 SSN Electrical Building" | 2025-05-15 | 2025-09-23 |  |  | Heng Peng/ Muthu | A | 1
000192 | Milestone 2 SSN Chemical Dosing Area | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | 2025-05-15 | 2025-07-02 |  |  | Heng Peng/ Muthu | 0 | 2
000192 | Milestone 2 SSN Chemical Dosing Area | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | 2025-05-15 | 2025-07-02 |  |  | Heng Peng/ Muthu | D | 5
000192 | Milestone 2 SSN Chemical Dosing Area | "Milestone 2 SSN Chemical Dosing Area" | 2025-05-15 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 1
000192 | Milestone 2 SSN Chemical Dosing Area | "Milestone 2 SSN Chemical Dosing Area" | 2025-05-15 | 2025-07-02 |  |  | Heng Peng/ Muthu | A | 1
000199 | SSN Cable Sizing Calculations | "SSN Cable Sizing Calculations" | 2025-05-30 | 2025-07-23 |  |  | Freedomer | 2 | 3
000260 | Milestone 2 SSN Overall Area | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | 2025-05-15 | 2025-07-02 |  |  | Heng Peng/ Muthu | 0 | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | 0 | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A1 | 4
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 4
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 4
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 4
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 2 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-05-09 | 2025-11-14 |  |  | Heng Peng/ Muthu | A.1 | 3
000341 | THP UPS Loading List | "THP UPS Loading List" | 2025-05-27 | 2025-09-11 |  |  | Karthik | 4 | 5
000356 | SSN Transformer Sizing Calculations | "SSN Transformer Sizing Calculations" | 2025-05-30 | 2025-07-23 |  |  | Freedomer | 2 | 3
000514 | Vendor Approval of SSN Package (Pressure Switch) | "Vendor Approval of SSN Package (Pressure Switch)" | 2025-05-20 | 2025-10-01 |  |  | Yean Yee | 2 | 3
000601 | THP Functional Design Specification | "THP Functional Design Specification" | 2025-05-19 | 2025-07-04 |  |  | Joo Kwan | 2 | 3
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 7
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000605 | SSN LVSG 0101AB Single Line Diagram | "SSN LVSG 0101AB Single Line Diagram" | 2025-05-04 | 2025-05-25 |  |  | Freedomer | D | 4
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000618 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2025-05-13 |  |  |  | Yibo | C | 3
000697 | Data Sheet for Pre Cooler Cooling Water Control Valve | "Data Sheet for Pre Cooler Cooling Water Control Valve" | 2025-05-05 |  |  |  | Joo Kwan | 1 | 2
000764 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2025-05-30 | 2025-06-04 |  |  | Radha | 1 | 2
000849 | SSN Load Flow Study Report | "SSN Load Flow Study Report" | 2025-05-04 | 2025-05-30 |  |  | Freedomer | 1 | 2
000850 | SSN Short Circuit Study Report | "SSN Short Circuit Study Report" | 2025-05-30 | 2025-07-23 |  |  | Freedomer | 1 | 2
000931 | Screen General Arrangement Drawing | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" | 2025-05-26 |  |  |  | Yibo | B | 3
000994 | Commissioning Plan for THP Air Compressor System | "Commissioning Plan for THP Air Compressor System" | 2025-05-10 | 2025-06-04 |  |  | Joo Kwan | 2 | 3
001006 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | 2025-05-19 | 2025-07-02 |  |  | Joo Kwan | 1 | 2
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-05-30 | 2025-06-30 |  |  | Freedomer | C | 3
001061 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | 2025-05-02 | 2025-05-12 |  |  | Danapal | 4 | 5
001132 | FAT Procedure for LVSG Panels (Sunlight) | "FAT Procedure for LVSG Panels (Sunlight)" | 2025-05-23 | 2025-07-14 |  |  | Radha | 1 | 2
001139 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | 2025-05-05 |  |  |  | Qili | 1 | 2
001207 | MSRA SWP for Concrete Coring | "MSRA SWP for Concrete Coring " | 2025-05-18 | 2025-06-13 |  |  | N Kumar | 1 | 2
001213 | Electrical Signal List for THP -MCC-0101A/0101B | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | 2025-05-09 | 2025-06-17 |  |  | Balaji | 0 | 3
001262 | Inspection and test Plan and Factory Acceptance Test for Public Address System | "Inspection and test Plan and Factory Acceptance Test for Public Address System" | 2025-05-02 | 2025-05-30 |  |  | Danapal | 1 | 2
001263 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " | 2025-05-02 | 2025-05-30 |  |  | Danapal | 1 | 2
001264 | Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2025-05-02 | 2025-06-30 |  |  | Danapal | 0 | 1
001265 | Application of Novolac Epoxy Coating | "Application of Novolac Epoxy Coating " | 2025-05-04 | 2025-05-30 |  |  | Bryan | 0 | 1
001266 | MSRA for Protection Relay Replacement Works | "MSRA for Protection Relay Replacement Works " | 2025-05-04 | 2025-06-17 |  |  | Bryan | 0 | 1
001267 | Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " | 2025-05-04 | 2025-06-09 |  |  | Kumar | 0 | 1
001268 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" | 2025-05-04 | 2025-05-30 |  |  | Danapal | 1 | 2
001269 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" | 2025-05-04 | 2026-01-30 |  |  | Yibo | 0 | 1
001269 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" | 2025-05-04 | 2026-01-30 |  |  | Yibo | 0 | 1
001270 | Submission of BIM Coordination VCM Model (Apr 2025) | "Submission of BIM Coordination VCM Model (Apr 2025) " | 2025-05-09 | 2025-05-29 |  |  | Heng Peng | 0 | 1
001271 | FAT Report for Discharge Transfer Pumps (KSB) | "FAT Report for Discharge Transfer Pumps (KSB)" | 2025-05-09 | 2025-07-01 |  |  | Radha | 0 | 1
001272 | Final FAT report for THP train 1 & Train 2 Feed pumps | "Final FAT report for THP train 1 & Train 2 Feed pumps" | 2025-05-09 | 2025-07-02 |  |  | Radha | 0 | 1
001273 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen)" | 2025-05-09 | 2025-07-14 |  |  | Radha | 0 | 1
001274 | Preliminary Design and Vendor Approval Document for Steam Equiptment Package | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" | 2025-05-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001275 | HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard | "HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard" | 2025-05-10 | 2025-07-04 |  |  | Joo Kwan | 0 | 1
001276 | THP HWR Bypass Control Valve | "THP HWR Bypass Control Valve" | 2025-05-10 | 2025-05-21 |  |  | Joo Kwan | 0 | 1
001277 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001277 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001277 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001277 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001277 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | 2025-06-23 |  |  | Joo Kwan | 0 | 1
001278 | Issue for Information-Monthly reinforcement steel delivery records for Mar 2024 | "Issue for Information-Monthly reinforcement steel delivery records for Mar 2024" | 2025-05-13 | 2025-05-20 |  |  | Kumar N | 0 | 1
001279 | Issue for Information-Monthly reinforcement steel delivery records for Apr 2024 | "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" | 2025-05-13 | 2025-06-02 |  |  | Kumar N | 0 | 1
001280 | Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024 | "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" | 2025-05-13 | 2025-06-02 |  |  | Kumar N | 0 | 1
001281 | FAT report for THP Sludge cooler D Stage 2 | "FAT report for THP Sludge cooler D Stage 2" | 2025-05-13 | 2025-07-02 |  |  | Radha | 1 | 2
001282 | ST620 Pipe Supports and Duct Supports Redesign | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | 2025-06-11 |  |  | Aaron | E | 1
001282 | ST620 Pipe Supports and Duct Supports Redesign | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | 2025-06-11 |  |  | Aaron | E | 1
001282 | ST620 Pipe Supports and Duct Supports Redesign | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | 2025-06-11 |  |  | Aaron | E | 1
001282 | ST620 Pipe Supports and Duct Supports Redesign | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | 2025-06-11 |  |  | Aaron | E | 1
001282 | ST620 Pipe Supports and Duct Supports Redesign | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | 2025-06-11 |  |  | Aaron | E | 1
001283 | NEW WD from BCA for ST618 - THP Train Cambi Structures | "NEW WD from BCA for ST618 - THP Train Cambi Structures" | 2025-05-13 | 2025-05-21 |  |  | Aaron | NA | 1
001284 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-05-13 | 2025-06-30 |  |  | Aaron | A.1 | 2
001284 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2025-05-13 | 2025-06-30 |  |  | Aaron | E | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001285 | ST608 drawings Connection Details | "ST608 drawings Connection Details" | 2025-05-13 | 2025-08-07 |  |  | Aaron | F | 1
001286 | Unpriced PO for Accessories for Lighting Protection (SkyPRO) | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" | 2025-05-13 | 2025-05-20 |  |  | Yi Hao | 0 | 1
001287 | Unpriced LOA for Electric Hoist (Helmsion Engineering) | "Unpriced LOA for Electric Hoist (Helmsion Engineering) " | 2025-05-13 | 2025-11-21 |  |  | Yi Hao | 0 | 1
001288 | Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) | "Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) " | 2025-05-13 | 2025-09-08 |  |  | Radha | 0 | 1
001289 | Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve | "Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve" | 2025-05-13 | 2025-08-01 |  |  | Radha | 0 | 1
001290 | Payment Claim No.22 | "Payment Claim No.22" | 2025-05-13 | 2025-08-22 |  |  | Yi Hao | 0 | 1
001291 | C4B Monthly Progress Report Number No.24 (04 25) | "C4B Monthly Progress Report Number No.24 (04 25)" | 2025-05-13 | 2025-05-16 |  |  | Htet Nu | 0 | 1
001292 | Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 | "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " | 2025-05-13 | 2025-06-02 |  |  | Kumar | 0 | 1
001293 | Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024 | "Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024" | 2025-05-13 | 2025-06-02 |  |  | Kumar | 0 | 1
001294 | Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025 | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" | 2025-05-14 | 2025-06-02 |  |  | Kumar | 0 | 1
001295 | Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | "Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) " | 2025-05-14 | 2025-06-02 |  |  | Kumar | 0 | 1
001296 | Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories) | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" | 2025-05-15 | 2025-05-25 |  |  | Karthik | 0 | 1
001297 | Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories) | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" | 2025-05-15 | 2025-05-25 |  |  | Karthik | 0 | 1
001298 | Data Sheets for Clean Gas System | " Data Sheets for Clean Gas System" | 2025-05-15 | 2025-05-25 |  |  | Karthik | 0 | 1
001299 | Typical installation drawing for PA & Fire Alarm System | "Typical installation drawing for PA & Fire Alarm System" && "Typical Installation drawing For PA & Fire Alarm" | 2025-05-15 | 2025-05-25 |  |  | Karthik | A | 2
001300 | Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) | "Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) " | 2025-05-15 | 2025-06-09 |  |  | Dhanapal | 0 | 1
001301 | Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance) | "Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance)" | 2025-05-15 | 2025-06-23 |  |  | Dhanapal | 0 | 1
001302 | Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025" | 2025-05-18 | 2025-06-04 |  |  | Kumar | 0 | 1
001303 | FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN) | "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" | 2025-05-18 | 2025-05-29 |  |  | Radha | 0 | 1
001304 | Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | 2025-05-18 | 2025-07-14 |  |  | Radha | 0 | 1
001305 | Panel GA & Wiring drawing for BS Systems | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" | 2025-05-18 | 2025-06-23 |  |  | Karthik | A | 3
001305 | Panel GA & Wiring drawing for BS Systems | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" | 2025-05-18 | 2025-06-23 |  |  | Karthik | A.1 | 3
001305 | Panel GA & Wiring drawing for BS Systems | "Panel GA & Wiring drawing for BS Systems" | 2025-05-18 | 2025-06-23 |  |  | Karthik | A | 1
001305 | Panel GA & Wiring drawing for BS Systems | "Panel GA & Wiring drawing for BS Systems" | 2025-05-18 | 2025-06-23 |  |  | Karthik | A | 1
001305 | Panel GA & Wiring drawing for BS Systems | "Panel GA & Wiring drawing for BS Systems" | 2025-05-18 | 2025-06-23 |  |  | Karthik | A | 1
001306 | Typical Installation drawing For PA & Fire Alarm | "Typical installation drawing for PA & Fire Alarm System" && "Typical Installation drawing For PA & Fire Alarm" | 2025-05-18 | 2025-06-30 |  |  | Karthik | A | 2
001307 | ST609 SSN-PR001 Fabrication Drawing and Model | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-05-18 | 2025-08-05 |  |  | Aaron | NA | 4
001308 | G1 Booster Pump Hydraulics Calculation | "G1 Booster Pump Hydraulics Calculation " | 2025-05-19 | 2025-07-07 |  |  | Joo Kwan | 1 | 2
001309 | G2D Booster Pump Hydraulics Calculation | "G2D Booster Pump Hydraulics Calculation " | 2025-05-19 | 2025-07-07 |  |  | Joo Kwan | 1 | 2
001310 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" | 2025-05-19 | 2025-05-30 |  |  | Joo Kwan | 1 | 2
001311 | H2S Dispersion Simulation And Risk Assessement Report | "H2S Dispersion Simulation And Risk Assessement Report" | 2025-05-19 | 2025-07-02 |  |  | Joo Kwan | 1 | 2
001312 | Revised Design of THP Steel Structure Plinths | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" | 2025-05-19 | 2025-07-10 |  |  | Aaron | F | 2
001312 | Revised Design of THP Steel Structure Plinths | "Revised Design of THP Steel Structure Plinths" | 2025-05-19 | 2025-07-10 |  |  | Aaron | - | 1
001313 | Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter | "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2025-05-20 | 2025-07-14 |  |  | Dhanapal | 0 | 1
001314 | Preliminary Design and Vendor Approval for Solenoid Valve | "Preliminary Design and Vendor Approval for Solenoid Valve " | 2025-05-20 | 2025-06-20 |  |  | Qili | 1 | 2
001315 | FAT Report for THP Sludge Cooler C Stage 2 | "FAT Report for THP Sludge Cooler C Stage 2" | 2025-05-23 | 2025-07-02 |  |  | Radha | 1 | 2
001316 | Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson) | "Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson)" | 2025-05-23 | 2025-09-02 |  |  | Radha | 0 | 1
001317 | SAT Report for WSD11-MCC-0101A&B | "SAT Report for WSD11-MCC-0101A&B" | 2025-05-23 | 2025-07-23 |  |  | Radha | 0 | 1
001318 | O&M Manual for Aeration Blower | "O&M Manual for Aeration Blower" | 2025-05-26 |  |  |  | Yibo | 0 | 1
001319 | Data Sheet and Drawing for Davit Crane | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | 2025-09-23 |  |  | Yibo | B | 2
001319 | Data Sheet and Drawing for Davit Crane | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | 2025-09-23 |  |  | Yibo | B | 2
001319 | Data Sheet and Drawing for Davit Crane | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | 2025-09-23 |  |  | Yibo | 0 | 1
001319 | Data Sheet and Drawing for Davit Crane | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | 2025-09-23 |  |  | Yibo | 0 | 1
001320 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " | 2025-05-26 | 2025-07-31 |  |  | Radha | 1 | 2
001321 | MSRA and SWP for RC Sub & Super-Structural Work (TechGems) | "MSRA and SWP for RC Sub & Super-Structural Work (TechGems)" | 2025-05-26 | 2025-06-20 |  |  | Bryan | 0 | 1
001322 | Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building | "Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building " | 2025-05-27 | 2025-08-11 |  |  | K Balaji | 0 | 1
001323 | FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank) | "FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank)" | 2025-05-28 | 2025-07-02 |  |  | Radha | 0 | 1
001324 | FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps | "FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps" | 2025-05-28 | 2025-07-04 |  |  | Radha | 0 | 1
001325 | Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. | "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " | 2025-05-28 | 2025-06-04 |  |  | Yuen Fatt | 0 | 2
001326 | Siphonic System Schematic and Calculation | "Siphonic System Schematic and Calculation" | 2025-05-28 | 2025-07-09 |  |  | Yuen Fatt | 0 | 1
001327 | Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. | "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " | 2025-05-28 | 2025-06-04 |  |  | Yuen Fatt | 0 | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | A | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001328 | THP ICA GA & Wiring drawings | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-05-28 | 2025-09-02 |  |  | Karthik | B | 2
001329 | Payment Claim No.23 | "Payment Claim No.23" | 2025-05-30 | 2025-06-02 |  |  | Yi Hao | 0 | 1
001330 | THP ICA GA & Wiring Drawings | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | 2025-12-05 |  |  | Karthik | VOID | 9
001331 | Electrical Signal List for SSN -LVSG-0101A/0101B | "Electrical Signal List for SSN -LVSG-0101A/0101B" | 2025-05-30 | 2025-06-17 |  |  | Balaji | 1 | 2
001332 | FAT Report for CSEL piping DN 750mm (2nd batch) | "FAT Report for CSEL piping DN 750mm (2nd batch)" | 2025-05-30 | 2025-09-02 |  |  | Mohan | 0 | 1
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" && " THP Overall Network Diagrams" | 2025-05-30 | 2025-07-16 |  |  | Balaji | A | 3
001333 | SSN Over All Network Archtecture Drawings | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | 2025-05-30 | 2025-07-16 |  |  | Balaji | A | 2
001333 | SSN Over All Network Archtecture Drawings | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" | 2025-05-30 | 2025-07-16 |  |  | Balaji | A | 2
001334 | Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard | "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | 2025-05-30 | 2025-12-29 |  |  | Bryan | 0 | 1
001335 | Memo-Appointment of LEW Representatives | "Memo-Appointment of LEW Representatives" | 2025-05-30 | 2025-06-20 |  |  | Jun | 0 | 1
001336 | FAT Report for Radar Level Transmitter 1st Batch | "FAT Report for Radar Level Transmitter 1st Batch " | 2025-05-30 | 2025-07-14 |  |  | Dhanapal | 1 | 2
001337 | Method Statement & Risk Assessment for Piping Installation at SWPR | "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2025-05-30 | 2025-08-11 |  |  | K Balaji | 1 | 2

## 2025-06
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 1
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 3
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 3
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000230 | P&ID of THP Train 1 | "P&ID of THP Train 1" && "P&ID of THP General System" | 2025-06-17 | 2025-08-28 |  |  | Joo Kwan | D | 4
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " | 2025-06-25 | 2025-10-06 |  |  | Kyaw Myo | A.2 | 3
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2025-06-25 | 2025-10-06 |  |  | Kyaw Myo | A.2 | 3
000297 | Standard Pipe Support - For All Area | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2025-06-25 | 2025-10-06 |  |  | Kyaw Myo | A.2 | 3
000297 | Standard Pipe Support - For All Area | "Standard Pipe Support - For All Area " | 2025-06-25 | 2025-10-06 |  |  | Kyaw Myo | A | 1
000297 | Standard Pipe Support - For All Area | "Standard Pipe Support - For All Area " | 2025-06-25 | 2025-10-06 |  |  | Kyaw Myo | A.1 | 2
000342 | SSN UPS Loading List | "SSN UPS Loading List" | 2025-06-16 | 2025-09-11 |  |  | Low | 5 | 6
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 3
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 3
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 4
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000392 | Compressor Sequencer Panel | "Compressor Sequencer Panel" | 2025-06-16 | 2025-12-09 |  |  | Karthik | E | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-06-06 | 2025-07-17 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-06-06 | 2025-07-17 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-06-06 | 2025-07-17 |  |  | Yibo | D | 3
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-06-06 | 2025-07-17 |  |  | Yibo | B | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-06-06 | 2025-07-17 |  |  | Yibo | B | 2
000541 | Blower Encapsulation GA | "Blower Encapsulation GA" | 2025-06-06 | 2025-07-17 |  |  | Yibo | B | 2
000579 | SSN RIO 0201 I/O List | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | 2025-06-16 | 2025-07-10 |  |  | Balaji | 4 | 5
000583 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" | 2025-06-19 | 2025-07-10 |  |  | Balaji/ Karthik | 3 | 4
000644 | THP Lux Simulation Report | "THP Lux Simulation Report" | 2025-06-20 | 2025-08-04 |  |  | Freedomer | 2 | 4
000645 | SSN Lux Simulation Report | "SSN Lux Simulation Report" | 2025-06-20 | 2025-08-04 |  |  | Freedomer | 3 | 4
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 1
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 1
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 1
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 1
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" | 2025-06-12 |  |  |  | Joo Kwan | B | 1
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000651 | THP PC Pump GA Drawings | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" | 2025-06-12 |  |  |  | Joo Kwan | B | 2
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" | 2025-06-19 | 2025-10-01 |  |  | Kyaw Myo | A.1 | 3
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " | 2025-06-19 | 2025-10-01 |  |  | Kyaw Myo | A.1 | 2
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " | 2025-06-19 | 2025-10-01 |  |  | Kyaw Myo | A.1 | 2
000661 | SSN External Fire Hydrant Layout & Details | "SSN External Fire Hydrant Layout & Details " | 2025-06-19 | 2025-10-01 |  |  | Kyaw Myo | A.1 | 1
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 6
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2025-06-16 | 2025-08-28 |  |  | Qili | D | 5
000802 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" | 2025-06-16 | 2025-11-24 |  |  | Yibo | 2 | 3
000900 | Datasheet for Electromagnetic Flowmeter | "Datasheet for Electromagnetic Flowmeter" | 2025-06-26 | 2025-07-28 |  |  | Yean Yee | 1 | 2
000909 | Pipe Support Standard- SWPR | "Pipe Support Standard- SWPR" | 2025-06-25 | 2025-10-06 |  |  | Kyaw Myo | A.2 | 3
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2025-06-15 |  |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2025-06-15 |  |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2025-06-15 |  |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2025-06-15 |  |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2025-06-15 |  |  |  | Yibo | B | 2
000917 | GA Drawing for Dosing Pump | "GA Drawing for Dosing Pump" | 2025-06-15 |  |  |  | Yibo | B | 2
000942 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | 2025-06-16 | 2025-09-04 |  |  | Liying | 1 | 2
000954 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-06-17 | 2025-07-28 |  |  | Liying | 2 | 3
000964 | Functional Design Specification (Air Compressor System) | "Functional Design Specification (Air Compressor System)" | 2025-06-04 | 2025-07-02 |  |  | Joo Kwan | 2 | 3
000984 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | 2025-06-16 | 2025-06-23 |  |  | Liying | 1 | 2
000988 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | 2025-06-18 | 2026-01-07 |  |  | Qili | 1 | 2
001000 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-06-06 | 2025-07-04 |  |  | N.Kumar | 3 | 4
001030 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-06-18 | 2025-09-08 |  |  | Radha | 1 | 2
001032 | SSN Aeration Blower Control Philosophy | "SSN Aeration Blower Control Philosophy" | 2025-06-04 | 2025-07-02 |  |  | Qili | 1 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | 0 | 1
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A.2 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A.3 | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A | 2
001039 | THP Protected Corridor Area-Building Service (Mechanical) | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | 2025-07-17 |  |  | Kyaw Myo | A | 2
001043 | Preliminary design and Vendor Approval – Plastic Valves (GF) | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | 2025-06-09 | 2025-06-20 |  |  | Liying | 1 | 2
001061 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" | 2025-06-28 | 2025-07-23 |  |  | Danapal | 4 | 5
001099 | SSN -RIO PANEL 0001A/0001B- I/O List | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-06-16 | 2025-07-10 |  |  | Balaji | 2 | 3
001117 | SSN -RIO PANEL 0202- I/O List | "SSN -RIO PANEL 0202- I/O List" | 2025-06-18 | 2025-09-02 |  |  | Balaji | 1 | 2
001131 | Safety Review Report for Sitewide Pipe Rack | "Safety Review Report for Sitewide Pipe Rack" | 2025-06-18 | 2025-07-07 |  |  | Max | 1 | 2
001142 | SSN -RIO PANEL 0401- I/O List | "SSN -RIO PANEL 0401- I/O List" | 2025-06-25 | 2025-09-15 |  |  | Balaji | 1 | 2
001150 | Report of Project Safety Review for THP Trains Installation | "Report of Project Safety Review for THP Trains Installation" | 2025-06-18 | 2025-07-04 |  |  | Max | 2 | 3
001154 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2025-06-04 | 2025-07-08 |  |  | K. Balaji | 2 | 3
001155 | SSN -RIO PANEL 0203- I/O List | "SSN -RIO PANEL 0203- I/O List " | 2025-06-25 | 2025-09-02 |  |  | Balaji | 1 | 2
001228 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" | 2025-06-27 | 2025-07-04 |  |  | Kumar | 1 | 2
001234 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" | 2025-06-06 | 2025-07-04 |  |  | Danapal | 2 | 3
001331 | Electrical Signal List for SSN -LVSG-0101A/0101B | "Electrical Signal List for SSN -LVSG-0101A/0101B" | 2025-06-09 | 2025-06-30 |  |  | Balaji | 1 | 2
001338 | Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox) | "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-06-03 | 2025-07-16 |  |  | Dhanapal | 1 | 2
001339 | Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter | "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2025-06-03 | 2025-07-17 |  |  | Radha | 0 | 2
001340 | Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox) | "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2025-06-03 | 2025-07-20 |  |  | Radha | 1 | 2
001341 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | 2025-06-03 | 2025-08-01 |  |  | Dhanapal | 2 | 3
001342 | FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" | 2025-06-03 | 2025-06-20 |  |  | Dhanapal | 0 | 1
001343 | Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" | 2025-06-04 | 2025-08-04 |  |  | Dhanapal | 0 | 1
001344 | Vendor Manufacturing Inspection Test Plan for Parabolic Screen | "Vendor Manufacturing Inspection Test Plan for Parabolic Screen" | 2025-06-04 | 2025-07-14 |  |  | Dhanapal | 0 | 1
001345 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 |  |  |  | Yibo | 0 | 1
001345 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 |  |  |  | Yibo | 0 | 1
001345 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 |  |  |  | Yibo | 0 | 1
001345 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 |  |  |  | Yibo | 0 | 1
001345 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 |  |  |  | Yibo | 0 | 1
001345 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 |  |  |  | Yibo | 0 | 1
001346 | Crane Calculation for Davit Crane 1and 2 | "Crane Calculation for Davit Crane 1and 2" | 2025-06-06 | 2026-02-27 |  |  | Yibo | 0 | 1
001346 | Crane Calculation for Davit Crane 1and 2 | "Crane Calculation for Davit Crane 1and 2" | 2025-06-06 | 2026-02-27 |  |  | Yibo | 0 | 1
001347 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | 2025-08-28 |  |  | Yibo | B | 2
001347 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | 2025-08-28 |  |  | Yibo | B | 2
001347 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | 2025-08-28 |  |  | Yibo | 0 | 1
001347 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | 2025-08-28 |  |  | Yibo | 0 | 1
001348 | Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) | "Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) " | 2025-06-06 | 2025-07-28 |  |  | Kumar | 0 | 1
001349 | Submission of BIM Coordination VCM Model (May 2025) | "Submission of BIM Coordination VCM Model (May 2025) " | 2025-06-09 | 2025-06-30 |  |  | Heng Peng | 0 | 1
001350 | Electrical Signal List for MCC - TYPICAL | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " | 2025-06-10 |  |  |  | Freedomer | 1 | 2
001351 | Hookup Drawing for PIT at Air Receiver | "Hookup Drawing for PIT at Air Receiver " | 2025-06-10 | 2025-12-09 |  |  | Yean Yee | A | 1
001352 | Hook up Drawing for PDSH - CAS | "Hook up Drawing for PDSH - CAS" && "Hook-up drawing for PDSH for CAS (THP)" | 2025-06-10 | 2025-12-09 |  |  | Yean Yee | B | 2
001353 | Vendor Approval of SSN Package - Magnetic Level Gauge | "Vendor Approval of SSN Package - Magnetic Level Gauge" | 2025-06-10 | 2025-09-23 |  |  | Yean Yee | 1 | 2
001354 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 2024 to April 2025 | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 2024 to April 2025" | 2025-06-11 | 2025-08-25 |  |  | Htet Nu | 0 | 1
001355 | C4B Monthly Progress Report Number No.25 (05 25) | "C4B Monthly Progress Report Number No.25 (05 25)" | 2025-06-12 | 2025-07-20 |  |  | Htet Nu | 0 | 1
001356 | Waterproofing Shop Drawing Submission | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | 2025-07-02 |  |  | Yuen Fatt | D | 5
001356 | Waterproofing Shop Drawing Submission | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | 2025-07-02 |  |  | Yuen Fatt | A | 2
001356 | Waterproofing Shop Drawing Submission | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | 2025-07-02 |  |  | Yuen Fatt | C | 5
001356 | Waterproofing Shop Drawing Submission | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | 2025-07-11 |  |  | Yuen Fatt | D | 5
001356 | Waterproofing Shop Drawing Submission | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | 2025-06-12 | 2025-07-11 |  |  | Yuen Fatt | C | 5
001356 | Waterproofing Shop Drawing Submission | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | 2025-06-12 | 2025-07-11 |  |  | Yuen Fatt | C | 4
001357 | Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter | "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2025-06-12 | 2025-07-14 |  |  | Radha | 0 | 2
001358 | FAT Report for Spray Nozzles | "FAT Report for Spray Nozzles" | 2025-06-12 | 2025-07-23 |  |  | Radha | 0 | 1
001359 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " | 2025-06-12 | 2025-07-14 |  |  | Dhanapal | 2 | 3
001360 | Sample Board Submission for ACMV Sample Materials (Pho Meng Engineering) | "Sample Board Submission for ACMV Sample Materials (Pho Meng Engineering) " | 2025-06-12 | 2025-07-08 |  |  | Dhanapal | 0 | 1
001361 | FAT report for THP Train 1 (Pulper module, Reactor 1 to 4 module, Upper platform module) | "FAT report for THP Train 1 (Pulper module, Reactor 1 to 4 module, Upper platform module)" | 2025-06-12 | 2025-12-23 |  |  | Dhanapal | 0 | 1
001362 | FAT report for THP Train 2 (Pulper module, Upper platform module) (ICA) | "FAT report for THP Train 2 (Pulper module, Upper platform module) (ICA)" | 2025-06-12 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001363 | Revised Design of THP Steel Structure Plinths (Rev F) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-06-12 | 2025-07-20 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev F) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-06-12 | 2025-07-20 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev F) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-06-12 | 2025-07-20 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev F) | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" | 2025-06-12 | 2025-07-20 |  |  | Aaron | F | 2
001364 | ST609-SSN-PR002 PE Endorsed Fabrication Drawings | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-06-12 | 2025-09-26 |  |  | Aaron | NA | 4
001365 | ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-06-12 | 2025-09-26 |  |  | Aaron | NA | 4
001366 | ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-06-12 | 2025-09-26 |  |  | Aaron | NA | 4
001367 | Raised Floor Shop Drawings submission (Momentum) | "Raised Floor Shop Drawings submission (Momentum)" | 2025-06-12 | 2025-07-02 |  |  | Yuen Fatt | B | 2
001367 | Raised Floor Shop Drawings submission (Momentum) | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | 2025-06-12 | 2025-07-02 |  |  | Yuen Fatt | C | 5
001368 | Vendor Approval for Active Harmonic Filter (DANFOSS) | "Vendor Approval for Active Harmonic Filter (DANFOSS)" | 2025-06-12 | 2025-07-04 |  |  | Freedomer | 1 | 2
001369 | Electrical As Built Drawing List | "Electrical As Built Drawing List" | 2025-06-12 | 2025-07-23 |  |  | Freedomer | 0 | 1
001370 | General Arrangement for TCI Flow Control valve | "General Arrangement for TCI Flow Control valve" | 2025-06-12 |  |  |  | Joo Kwan | A | 1
001371 | General Arrangement for DC Partial Bypass Line Flow Control Valve | "General Arrangement for DC Partial Bypass Line Flow Control Valve" | 2025-06-12 |  |  |  | Joo Kwan | A | 1
001372 | General Arrangement for Lamella Clarifier Flow Control Valve | "General Arrangement for Lamella Clarifier Flow Control Valve" | 2025-06-12 |  |  |  | Joo Kwan | A | 1
001373 | General Arrangement for IRIS Diaphragm Flow Control Valve | "General Arrangement for IRIS Diaphragm Flow Control Valve" | 2025-06-12 |  |  |  | Joo Kwan | A | 1
001374 | GA Drawing for Static Screen - Plinth Opening & Seal plate | "GA Drawing for Static Screen - Plinth Opening & Seal plate" | 2025-06-16 |  |  |  | Joo Kwan | A | 1
001375 | G1 Booster Pump Data Sheet | "G1 Booster Pump Data Sheet" | 2025-06-16 | 2025-07-08 |  |  | Joo Kwan | 1 | 2
001376 | GA for SSN G2D PRV | "GA for SSN G2D PRV" | 2025-06-16 |  |  |  | Joo Kwan | A | 1
001377 | Hook-up Drawing for Pressure Transmitter (HS) | "Hook-up Drawing for Pressure Transmitter (HS)" | 2025-06-16 | 2025-12-10 |  |  | Yean Yee | A | 1
001378 | Data sheet for Autosampler | "Data sheet for Autosampler" | 2025-06-16 | 2025-10-24 |  |  | Yean Yee | 0 | 1
001379 | Data sheet for Capacitive Level Switch | "Data sheet for Capacitive Level Switch" | 2025-06-16 | 2025-11-05 |  |  | Yean Yee | 0 | 1
001380 | Datasheet for Thermal Mass Flowmeter | "Datasheet for Thermal Mass Flowmeter" | 2025-06-16 | 2025-09-24 |  |  | Yean Yee | 0 | 1
001381 | G2D Booster Pump Data Sheet | "G2D Booster Pump Data Sheet" | 2025-06-16 | 2025-07-08 |  |  | Joo Kwan | 1 | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | 2025-07-16 |  |  | Karthik | B | 2
001383 | GA for Bypass Control Valve 1 | "GA for Bypass Control Valve 1" | 2025-06-16 |  |  |  | Joo Kwan | 0 | 1
001384 | GA for Bypass Control Valve 2 | "GA for Bypass Control Valve 2" | 2025-06-16 |  |  |  | Joo Kwan | 0 | 1
001385 | FAT report-THP train 1 & 2 flash tank discharge pumps, reactor feed pumps typical test report | "FAT report-THP train 1 & 2 flash tank discharge pumps, reactor feed pumps typical test report" | 2025-06-16 | 2025-09-08 |  |  | Radha | 0 | 1
001386 | FAT Report for SS Pipes in Sitewide Pipe rack (Cyclect - 4th batch) | "FAT Report for SS Pipes in Sitewide Pipe rack (Cyclect - 4th batch)" | 2025-06-18 | 2025-09-02 |  |  | Mohan | 0 | 1
001387 | Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation) | "Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation)" | 2025-06-18 | 2025-07-14 |  |  | Mohan | 0 | 1
001388 | Project Safety Review Report for THP Installation | "Project Safety Review Report for THP Installation" | 2025-06-18 | 2025-08-25 |  |  | Max | 0 | 1
001389 | FAT Report for Top Manway (900x900mm & 400x400mm) | "FAT Report for Top Manway (900x900mm & 400x400mm) " | 2025-06-18 | 2025-09-02 |  |  | Radha | 0 | 1
001390 | Electrical Signal List for SSN -MCC-1001A/1001B | "Electrical Signal List for SSN -MCC-1001A/1001B " | 2025-06-18 | 2025-07-16 |  |  | Balaji | 0 | 1
001391 | Trust Block Calculation Report for Fire Hydrant | "Trust Block Calculation Report for Fire Hydrant " && "Thrust Block Calculation Report for Fire Hydrant " | 2025-06-19 | 2025-06-30 |  |  | Kyaw Myo | 0 | 2
001392 | Laser Scanning Method of Statement | "Laser Scanning Method of Statement " | 2025-06-19 |  |  |  | Muthu | 0 | 1
001393 | THP Protected Corridor Lux Simulation Report | "THP Protected Corridor Lux Simulation Report" | 2025-06-20 | 2025-08-11 |  |  | Freedomer | 0 | 1
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 1
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 1
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 1
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001394 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | 2025-07-28 |  |  | Aaron | A | 4
001395 | Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector | "Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector" | 2025-06-23 | 2025-07-14 |  |  | Dhanapal | 0 | 1
001396 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | 2025-06-23 | 2025-07-14 |  |  | Dhanapal | 0 | 2
001397 | FAT Report for Progressive Cavity Pumps (NETZSCH) | "FAT Report for Progressive Cavity Pumps (NETZSCH)" | 2025-06-23 | 2025-07-23 |  |  | Dhanapal | 0 | 1
001398 | MSRA, SWP for fire protection services | "MSRA, SWP for fire protection services " | 2025-06-23 | 2025-08-06 |  |  | Bryan | 2 | 3
001399 | MSRA SWP for Wet blasting Linabond Works | "MSRA SWP for Wet blasting Linabond Works" | 2025-06-23 | 2025-06-30 |  |  | Bryan | 0 | 1
001400 | CSA Meeting Minutes 0047 & 0048_15052025 and10062025 | "CSA Meeting Minutes 0047 & 0048_15052025 and10062025" | 2025-06-23 | 2025-07-04 |  |  | Htet Nu | 0 | 1
001400 | CSA Meeting Minutes 0047 & 0048_15052025 and10062025 | "CSA Meeting Minutes 0047 & 0048_15052025 and10062025" | 2025-06-23 | 2025-07-04 |  |  | Htet Nu | 0 | 1
001401 | Vendor Approval for Lighting and Small Power Material (Hong An) | "Vendor Approval for Lighting and Small Power Material (Hong An)" | 2025-06-23 | 2025-07-20 |  |  | Jun | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-06-23 | 2025-07-31 |  |  | Karthikeyan | 1 | 4
001403 | FAT Report for Chemical Dosing Pumps (PROMINENT) | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-06-23 | 2025-08-01 |  |  | Radha | 3 | 4
001404 | Unpriced PO for Flow Control Valve for TCI & DC Stream (KSB) | "Unpriced PO for Flow Control Valve for TCI & DC Stream (KSB)" | 2025-06-23 | 2025-07-31 |  |  | Yihao | 0 | 1
001405 | Unpriced PO for Air Flow Control Valve (Emile Egger) (Effektiv) | "Unpriced PO for Air Flow Control Valve (Emile Egger) (Effektiv)" | 2025-06-23 | 2025-11-24 |  |  | Yihao | 0 | 1
001406 | Datasheet for Temperature Transmitter | "Datasheet for Temperature Transmitter" | 2025-06-25 | 2025-10-06 |  |  | Yean Yee | 0 | 1
001407 | Steam Safety Relief Valve Datasheet | "Steam Safety Relief Valve Datasheet" | 2025-06-25 | 2025-07-08 |  |  | Joo Kwan | 1 | 2
001408 | Steam Strainer Data Sheet | "Steam Strainer Data Sheet" | 2025-06-25 | 2025-07-08 |  |  | Joo Kwan | 0 | 1
001409 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting and Installation Works at SSN Electrical Building | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting and Installation Works at SSN Electrical Building" | 2025-06-26 | 2025-08-20 |  |  | Jun | 0 | 1
001410 | Hook-up Drawing for Pressure Switch (Cambi Loose Items) | "Hook-up Drawing for Pressure Switch (Cambi Loose Items)" | 2025-06-26 | 2025-12-09 |  |  | Yean Yee | A | 1
001410 | Hook-up Drawing for Pressure Switch (Cambi Loose Items) | "Hook-up Drawing for Pressure Switch (Cambi Loose Items)" | 2025-06-26 | 2025-12-09 |  |  | Yean Yee | A | 1
001411 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | 2025-12-09 |  |  | Yean Yee | A | 1
001411 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | 2025-12-09 |  |  | Yean Yee | A | 1
001411 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | 2025-12-09 |  |  | Yean Yee | A | 1
001411 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | 2025-12-09 |  |  | Yean Yee | A | 1
001412 | Payment Claim No.24 | " Payment Claim No.24" | 2025-06-27 | 2025-07-08 |  |  | Yihao | 0 | 1
001413 | ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission | "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" | 2025-06-27 | 2025-08-07 |  |  | Kumar | 0 | 1
001414 | Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction) | "Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction)" | 2025-06-27 | 2025-07-04 |  |  | Kumar | 0 | 1
001415 | Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd) | "Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd)" | 2025-06-27 | 2025-07-28 |  |  | Kumar | 0 | 1
001416 | Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report | "Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report " | 2025-06-27 | 2025-07-14 |  |  | Kumar | 0 | 1
001417 | Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack | "Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack" | 2025-06-28 | 2025-08-11 |  |  | K Balaji | 1 | 2

## 2025-07
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000189 | SSN Plumbing and Sanitary | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2025-07-15 |  |  |  | Kyaw Myo | A.2 | 4
000189 | SSN Plumbing and Sanitary | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " | 2025-07-15 |  |  |  | Kyaw Myo | A.2 | 3
000189 | SSN Plumbing and Sanitary | "SSN Plumbing and Sanitary " | 2025-07-15 |  |  |  | Kyaw Myo | A.1 | 2
000202 | THP Cable List | "THP Cable List" | 2025-07-21 | 2025-09-02 |  |  | Freedomer | 3 | 4
000204 | SSN Cable List | "SSN Cable List" | 2025-07-11 | 2025-07-23 |  |  | Freedomer | 3 | 4
000219 | Building Services ACMV | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-07-15 | 2025-09-08 |  |  | Kyaw Myo | A.4 | 5
000219 | Building Services ACMV | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-07-15 | 2025-09-08 |  |  | Kyaw Myo | A.4 | 5
000219 | Building Services ACMV | "Building Services ACMV" | 2025-07-15 | 2025-09-08 |  |  | Kyaw Myo | A.4 | 4
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-07-15 | 2025-09-08 |  |  | Kyaw Myo | A.4 | 7
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-07-15 | 2025-09-08 |  |  | Kyaw Myo | A.4 | 7
000321 | THP Listing of Interface Points | "THP Listing of Interface Points" | 2025-07-21 | 2025-10-01 |  |  | Freedomer | 1 | 2
000360 | SSN PFD | "SSN PFD" | 2025-07-14 | 2025-09-17 |  |  | Qili | D | 6
000360 | SSN PFD | "SSN PFD" | 2025-07-14 | 2025-09-17 |  |  | Qili | D | 6
000556 | THP LPS Risk Assessment Report | "THP LPS Risk Assessment Report" | 2025-07-07 | 2025-09-02 |  |  | Freedomer | 2 | 3
000557 | SSN LPS Risk Assessment Report | "SSN LPS Risk Assessment Report" | 2025-07-07 | 2025-09-02 |  |  | Freedomer | 2 | 3
000623 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | 2025-07-03 | 2025-09-15 |  |  | Radha | 5 | 6
000675 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" | 2025-07-02 | 2025-11-24 |  |  | David | 1 | 2
000706 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2025-07-03 | 2025-10-01 |  |  | Dhanapal.S | 4 | 5
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 3
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 7
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000866 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-07-01 | 2025-10-06 |  |  | Freedomer | D | 4
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 3
000870 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-07-24 | 2026-01-02 |  |  | Freedomer | C | 2
000874 | SSN Catchpot Sizing Calculation | "SSN Catchpot Sizing Calculation " | 2025-07-14 | 2025-09-17 |  |  | Qili | 2 | 3
001018 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | 2025-07-03 | 2025-12-23 |  |  | Mohan | 1 | 2
001080 | C4B SSN Pressure Reducing Valve Datasheet | "C4B SSN Pressure Reducing Valve Datasheet" | 2025-07-07 |  |  |  | Prachi | 1 | 2
001100 | SSN Aeration Blowers I/O List | "SSN Aeration Blowers I/O List" | 2025-07-11 | 2025-09-23 |  |  | Balaji | 1 | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-07-07 | 2026-01-30 |  |  | Yibo | B | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-07-07 | 2026-01-30 |  |  | Yibo | B | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-07-07 | 2026-01-30 |  |  | Yibo | B | 2
001123 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-07-07 | 2026-01-30 |  |  | Yibo | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001140 | SSN MDB-1001A.B SLD, Schem and GA Drawings | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-07-21 | 2025-09-23 |  |  | Freedomer | B | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001147 | SSN RIO 0201 GA & Wiring Diagram | "SSN RIO 0201 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | C | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001148 | SSN RIO 0202 GA & Wiring Diagram | "SSN RIO 0202 GA & Wiring Diagram" | 2025-07-29 | 2025-12-11 |  |  | Balaji | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001157 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-07-21 | 2025-09-04 |  |  | Freedomer | B | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-07-07 |  |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-07-07 |  |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-07-07 |  |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-07-07 |  |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-07-07 |  |  |  | Qili | 1 | 2
001170 | SSN FCV Calculation and Datasheet | "SSN FCV Calculation and Datasheet" | 2025-07-07 |  |  |  | Qili | 1 | 2
001174 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " | 2025-07-10 | 2025-07-17 |  |  | Dhanapal.S | 0 | 2
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-07-11 | 2025-10-01 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-07-10 | 2025-09-23 |  |  | Balaji | B | 3
001183 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" | 2025-07-22 | 2025-08-01 |  |  | Liying | 1 | 2
001188 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " | 2025-07-22 | 2025-10-01 |  |  | Freedomer | 1 | 2
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-07-08 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-07-11 | 2025-09-23 |  |  | Balaji | B | 3
001200 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" | 2025-07-02 | 2026-01-07 |  |  | David | 1 | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-07-08 | 2025-10-01 |  |  | Freedomer | C | 2
001218 | ON OFF Butterfly Valve Data sheet (OVS) | "ON OFF Butterfly Valve Data sheet (OVS)" | 2025-07-11 | 2025-09-04 |  |  | Joo Kwan | 1 | 1
001219 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2025-07-02 | 2025-08-06 |  |  | Radha | 3 | 4
001231 | Datasheet for Radar Level Transmitter | "Datasheet for Radar Level Transmitter " | 2025-07-22 | 2025-08-06 |  |  | Yean Yee | 1 | 2
001260 | Inspection and test Plan for fire protection system | "Inspection and test Plan for fire protection system " | 2025-07-04 | 2025-12-29 |  |  | Danapal | 1 | 2
001262 | Inspection and test Plan and Factory Acceptance Test for Public Address System | "Inspection and test Plan and Factory Acceptance Test for Public Address System" | 2025-07-05 |  |  |  | Danapal | 1 | 2
001263 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " | 2025-07-07 | 2025-12-29 |  |  | Danapal | 1 | 2
001268 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" | 2025-07-05 | 2025-09-23 |  |  | Danapal | 1 | 2
001309 | G2D Booster Pump Hydraulics Calculation | "G2D Booster Pump Hydraulics Calculation " | 2025-07-28 |  |  |  | Joo Kwan | 1 | 2
001310 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" | 2025-07-15 |  |  |  | Joo Kwan | 1 | 2
001311 | H2S Dispersion Simulation And Risk Assessement Report | "H2S Dispersion Simulation And Risk Assessement Report" | 2025-07-28 | 2025-09-24 |  |  | Joo Kwan | 1 | 2
001314 | Preliminary Design and Vendor Approval for Solenoid Valve | "Preliminary Design and Vendor Approval for Solenoid Valve " | 2025-07-28 |  |  |  | Joo Kwan | 1 | 2
001336 | FAT Report for Radar Level Transmitter 1st Batch | "FAT Report for Radar Level Transmitter 1st Batch " | 2025-07-22 | 2025-08-06 |  |  | Dhanapal | 1 | 2
001356 | Waterproofing Shop Drawing Submission | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-07-30 | 2025-08-04 |  |  | Yuen Fatt | C | 5
001356 | Waterproofing Shop Drawing Submission | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-07-30 | 2025-08-04 |  |  | Yuen Fatt | D | 5
001356 | Waterproofing Shop Drawing Submission | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | 2025-07-30 | 2025-08-04 |  |  | Yuen Fatt | C | 5
001356 | Waterproofing Shop Drawing Submission | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | 2025-07-30 | 2025-08-04 |  |  | Yuen Fatt | C | 4
001359 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " | 2025-07-22 | 2025-10-10 |  |  | Dhanapal | 2 | 3
001367 | Raised Floor Shop Drawings submission (Momentum) | "Raised Floor Shop Drawings submission (Momentum)" | 2025-07-24 | 2025-08-01 |  |  | Yuen Fatt | B | 2
001367 | Raised Floor Shop Drawings submission (Momentum) | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | 2025-07-24 | 2025-08-01 |  |  | Yuen Fatt | C | 5
001391 | Thrust Block Calculation Report for Fire Hydrant | "Trust Block Calculation Report for Fire Hydrant " && "Thrust Block Calculation Report for Fire Hydrant " | 2025-07-11 | 2025-12-29 |  |  | Kyaw Myo | 0 | 2
001418 | Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement | "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | 2025-07-01 | 2025-07-28 |  |  | Aaron | NA | 4
001419 | Project Safety Review for SSN Steel Structure and MEICA Equipment Installation | "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" | 2025-07-01 | 2025-07-16 |  |  | Max | 1 | 2
001420 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2025-07-01 | 2025-07-14 |  |  | Max | 1 | 2
001420 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | "Quarterly Safety Review Follow Up on SSN RC Works" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2025-07-01 | 2025-07-14 |  |  | Max | 1 | 2
001420 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2025-07-01 | 2025-07-14 |  |  | Max | 0 | 1
001420 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2025-07-01 | 2025-07-14 |  |  | Max | 0 | 1
001421 | C4B ST621 (Site Wide Pipe Rack) - BCA WD | "C4B ST621 (Site Wide Pipe Rack) - BCA WD" | 2025-07-01 | 2025-07-28 |  |  | Aaron | NA | 1
001422 | FAT Report for Parabolic Screen | "FAT Report for Parabolic Screen" | 2025-07-02 | 2025-09-08 |  |  | Radha | 0 | 1
001423 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 5th batch) | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 5th batch)" | 2025-07-02 | 2025-09-02 |  |  | Mohan | 0 | 1
001424 | Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services) | "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2025-07-02 | 2025-08-19 |  |  | Radha | 0 | 1
001425 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services) | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2025-07-02 | 2025-08-19 |  |  | Radha | 0 | 1
001426 | Sample board Submission for PA Conduit ,Saddle,Junction box | "Sample board Submission for PA Conduit ,Saddle,Junction box" | 2025-07-02 | 2025-08-19 |  |  | Dhanapal | 0 | 1
001427 | Vendor Manufacturing Inspection test plan for Pressure Gauges | "Vendor Manufacturing Inspection test plan for Pressure Gauges " | 2025-07-02 | 2025-07-14 |  |  | Dhanapal | 0 | 1
001428 | Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik | "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" | 2025-07-02 |  |  |  | Yuen Fatt | 0 | 2
001429 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025" | 2025-07-02 | 2025-07-17 |  |  | Kumar | 0 | 1
001430 | THP RIO Panel 002A I/O List | "THP RIO Panel 002A I/O List" | 2025-07-02 | 2025-10-24 |  |  | Karthikeyan | 0 | 1
001431 | Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik | "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" | 2025-07-03 |  |  |  | Yuen Fatt | 0 | 2
001432 | Vendor Approval for Distribution Boards (ZPA) | "Vendor Approval for Distribution Boards (ZPA)" | 2025-07-04 | 2025-07-17 |  |  | Freedomer | 1 | 2
001433 | Material Submission - Steel Structure Base Plate Grouting (Sanhe) | "Material Submission - Steel Structure Base Plate Grouting (Sanhe)" | 2025-07-04 | 2025-07-17 |  |  | Kumar | 0 | 1
001434 | VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD. | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." | 2025-07-04 | 2025-07-14 |  |  | Yuen Fatt | 0 | 1
001435 | Material and Test Certificate EN10204-3.1 For Butterfly Valves (OVS-Heaton) | "Material and Test Certificate EN10204-3.1 For Butterfly Valves (OVS-Heaton)" | 2025-07-05 | 2025-09-08 |  |  | Mohan | 0 | 1
001436 | Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe) | "Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe)" && "Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe)" | 2025-07-05 | 2025-07-28 |  |  | Kumar | 0 | 2
001437 | Vendor Approval for Distribution Boards (GSM) | "Vendor Approval for Distribution Boards (GSM)" | 2025-07-07 | 2025-07-17 |  |  | Freedomer | 1 | 2
001438 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | 2025-07-07 | 2025-09-02 |  |  | Freedomer | 2 | 3
001439 | FAT report for LVSG Panels (Sunlight) | "FAT report for LVSG Panels (Sunlight)" | 2025-07-07 | 2025-07-17 |  |  | Dhanapal | 0 | 1
001440 | THP RIO Panel 0101 I/O List | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | 2025-07-07 | 2025-08-06 |  |  | Karthikeyan | 0 | 3
001441 | FAT Report for SSN Flow Control Valve (KSB) | "FAT Report for SSN Flow Control Valve (KSB)" | 2025-07-07 | 2025-08-01 |  |  | Mohan | 0 | 1
001442 | THP RIO Panel 001A-I/O list | "THP RIO Panel 001A-I/O list" | 2025-07-07 | 2025-10-07 |  |  | Karthikeyan | 0 | 1
001443 | THP RIO Panel 001B-I/O list | "THP RIO Panel 001B-I/O list" | 2025-07-07 | 2025-10-07 |  |  | Karthikeyan | 0 | 1
001444 | THP RIO Panel 002B-I/O list | "THP RIO Panel 002B-I/O list" | 2025-07-07 | 2025-10-24 |  |  | Karthikeyan | 0 | 1
001445 | GA for G2D Booster Pump | "GA for G2D Booster Pump" | 2025-07-07 |  |  |  | Joo Kwan | A | 1
001446 | Vendor Manufacturing Inspection Test Plan for pH Analyser | "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2025-07-08 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001447 | Factory Acceptance Test Report for pH Analyser | "Factory Acceptance Test Report for pH Analyser" | 2025-07-08 | 2025-07-11 |  |  | Dhanapal | 0 | 1
001448 | FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight) | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" | 2025-07-08 | 2025-07-17 |  |  | Dhanapal | 0 | 1
001449 | Site Acceptance Test Procedure for 22KV HV Cable | "Site Acceptance Test Procedure for 22KV HV Cable" | 2025-07-08 | 2025-07-23 |  |  | Dhanapal | 0 | 1
001450 | Inspection and Test Plan for Cable Laying, Installation, Testing and Termination | "Inspection and Test Plan for Cable Laying, Installation, Testing and Termination " | 2025-07-08 | 2025-07-23 |  |  | Dhanapal | 0 | 1
001451 | FAT Report for G2D Water Pressure Reducing Valve (Pipeline-Elite) | "FAT Report for G2D Water Pressure Reducing Valve (Pipeline-Elite)" | 2025-07-08 | 2025-09-02 |  |  | Mohan | 0 | 1
001452 | VCM Submission for 2025-06 | "VCM Submission for 2025-06" | 2025-07-08 | 2025-07-30 |  |  | Heng Peng | 0 | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001453 | SSN RIO - 203 GA & Wiring Diagram | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | 2025-11-10 |  |  | Balaji | C | 1
001454 | Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " | 2025-07-09 | 2025-08-07 |  |  | Kumar | 1 | 2
001455 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps (ZPA) | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps (ZPA)" | 2025-07-09 | 2025-09-02 |  |  | Freedomer | 0 | 1
001456 | Steam Motorized Valve Data Sheet | " Steam Motorized Valve Data Sheet" | 2025-07-10 | 2025-09-04 |  |  | Mohan | 0 | 1
001457 | FAT Report for THP Flow Control Valve (KSB) | " FAT Report for THP Flow Control Valve (KSB)" | 2025-07-10 | 2025-08-01 |  |  | Mohan | 0 | 1
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-07-11 | 2025-08-01 |  |  | Aaron | A.5 | 7
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Typical Railing Details" | 2025-07-11 | 2025-08-01 |  |  | Aaron | A | 2
001459 | Valve Chamber Design for SSN- Portable Water Line | "Valve Chamber Design for SSN- Portable Water Line" | 2025-07-10 | 2025-09-17 |  |  | Aaron | NA | 2
001460 | ST611 Pipe Supports Redesign | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | 2025-10-23 |  |  | Aaron | A | 2
001460 | ST611 Pipe Supports Redesign | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | 2025-10-23 |  |  | Aaron | A | 2
001460 | ST611 Pipe Supports Redesign | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | 2025-10-23 |  |  | Aaron | A | 2
001460 | ST611 Pipe Supports Redesign | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | 2025-10-23 |  |  | Aaron | A | 2
001461 | Issue for Information - Monthly Concrete Cube Records for Structural Works for May 2025 | "Issue for Information - Monthly Concrete Cube Records for Structural Works for May 2025" | 2025-07-11 | 2025-08-05 |  |  | Kumar | 0 | 1
001462 | Updated Drawings ST607 - SSN Water Tank | " Updated Drawings ST607 - SSN Water Tank" | 2025-07-11 | 2025-10-23 |  |  | Aaron | - | 1
001463 | Vendor Manufacturing Inspection Test Plan for Conductive Analyser | "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" && "Factory Acceptance Test Report for Pressure Gauges" | 2025-07-11 | 2025-08-15 |  |  | Dhanapal | 0 | 2
001464 | FAT Report for EQ Tank Transfer Pumps (KSB) | " FAT Report for EQ Tank Transfer Pumps (KSB)" | 2025-07-11 | 2025-08-11 |  |  | Mohan | 0 | 1
001465 | Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser | "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | 2025-07-11 | 2025-10-01 |  |  | Dhanapal | 0 | 1
001466 | Factory Acceptance Test Report for Conductivity Analyser | " Factory Acceptance Test Report for Conductivity Analyser" | 2025-07-11 | 2025-08-26 |  |  | Dhanapal | 0 | 1
001467 | Electrical Signal List for SSN -MCC-0102A/0102B | "Electrical Signal List for SSN -MCC-0102A/0102B " | 2025-07-11 | 2025-07-16 |  |  | Karthikeyan | 0 | 1
001467 | Electrical Signal List for SSN -MCC-0102A/0102B | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " | 2025-07-25 | 2025-10-01 |  |  | Karthikeyan | 1 | 2
001468 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | 2025-12-09 |  |  | Balaji | A | 1
001468 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | 2025-12-09 |  |  | Balaji | A | 1
001468 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | 2025-12-09 |  |  | Balaji | A | 1
001468 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | 2025-12-09 |  |  | Balaji | A | 1
001468 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | 2025-12-09 |  |  | Balaji | A | 1
001468 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | 2025-12-09 |  |  | Balaji | A | 1
001469 | Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical | "Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical" | 2025-07-11 | 2025-08-15 |  |  | Dhanapal | 0 | 1
001470 | Preliminary design and Vendor Approval for Strainer (Spirax) | " Preliminary design and Vendor Approval for Strainer (Spirax)" | 2025-07-11 | 2025-08-01 |  |  | Liying | 0 | 1
001471 | C4B Monthly Progress Report Number No.26 (06 25) | "C4B Monthly Progress Report Number No.26 (06 25)" | 2025-07-12 | 2025-08-04 |  |  | Htet Nu | 0 | 1
001472 | Vendor Manufacturing Inspection Test Plan for Temperature Transmitters | "Vendor Manufacturing Inspection Test Plan for Temperature Transmitters" | 2025-07-14 | 2025-10-06 |  |  | Dhanapal | 0 | 1
001473 | GA for G1 Booster Pump | "GA for G1 Booster Pump" | 2025-07-14 |  |  |  | Joo Kwan | A | 1
001474 | Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter | " Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter" | 2025-07-14 | 2025-10-06 |  |  | Dhanapal | 0 | 1
001475 | Factory Acceptance Test Report for Thermal Flow/Mass Flowmeter | " Factory Acceptance Test Report for Thermal Flow/Mass Flowmeter" | 2025-07-14 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001476 | Factory Acceptance Test Report for Pressure Gauges | "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" && "Factory Acceptance Test Report for Pressure Gauges" | 2025-07-14 | 2025-10-15 |  |  | Dhanapal | 0 | 2
001477 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New Biosolids Building | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New Biosolids Building" | 2025-07-15 | 2025-08-22 |  |  | Vincent | 0 | 1
001478 | Factory Acceptance Test Report for Capacitive Level Switch/Leak Detector | " Factory Acceptance Test Report for Capacitive Level Switch/Leak Detector" | 2025-07-16 | 2025-12-10 |  |  | Dhanapal | 0 | 1
001479 | Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN) | "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | 2025-07-16 | 2025-10-24 |  |  | Dhanapal | 0 | 2
001480 | Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN) | "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | 2025-07-16 | 2025-12-09 |  |  | Dhanapal | 0 | 2
001481 | Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN) | "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" && "SAT Procedure for LVSG Panels (Sunlight)" | 2025-07-16 | 2025-11-05 |  |  | Dhanapal | 0 | 2
001482 | Shop Drawing for Cat Ladder Details ST617 THP-PF-01 _ QPD design drawing | "Shop Drawing for Cat Ladder Details ST617 THP-PF-01 _ QPD design drawing" | 2025-07-16 | 2025-08-12 |  |  | Aaron | C | 1
001483 | Aluminum Railing (Mock-up) Drawing | "Aluminum Railing (Mock-up) Drawing" | 2025-07-16 | 2025-08-14 |  |  | Aaron | NA | 1
001484 | Vendor Manufacturing Inspection Test Plan for Pressure Transmitters (SSN) | "Vendor Manufacturing Inspection Test Plan for Pressure Transmitters (SSN)" | 2025-07-16 | 2025-10-23 |  |  | Dhanapal | 0 | 1
001485 | Incentive/ Disincentive Audit Scheme for Mar 2025 | "Incentive/ Disincentive Audit Scheme for Mar 2025" | 2025-07-17 | 2025-09-11 |  |  | Malon | 0 | 1
001486 | Incentive/ Disincentive Audit Scheme for Apr 2025 | "Incentive/ Disincentive Audit Scheme for Apr 2025" | 2025-07-17 | 2025-09-11 |  |  | Malon | 0 | 1
001487 | Incentive/ Disincentive Audit Scheme for May 2025 | "Incentive/ Disincentive Audit Scheme for May 2025" | 2025-07-17 | 2025-09-11 |  |  | Malon | 0 | 1
001488 | Incentive/ Disincentive Audit Scheme for Jun 2025 | "Incentive/ Disincentive Audit Scheme for Jun 2025" | 2025-07-17 | 2025-09-11 |  |  | Malon | 0 | 1
001489 | Factory Acceptance Test Report for Auto Sampler | "Factory Acceptance Test Report for Auto Sampler" | 2025-07-21 | 2025-10-24 |  |  | Dhanapal | 0 | 1
001490 | Factory Acceptance Test Report for TSS Analyser - Optical | "Factory Acceptance Test Report for TSS Analyser - Optical" | 2025-07-21 | 2025-08-26 |  |  | Dhanapal | 0 | 1
001491 | Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand | "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" | 2025-07-21 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001492 | Inspection Test Plan for Transformer | "Inspection Test Plan for Transformer" | 2025-07-21 | 2025-08-01 |  |  | Dhanapal | 0 | 1
001493 | FAT Report for Desuperheater (Cambi) | "FAT Report for Desuperheater (Cambi)" | 2025-07-21 | 2025-11-23 |  |  | Radha | 0 | 1
001494 | Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) | "Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) " | 2025-07-21 | 2025-08-01 |  |  | Dhanapal | 0 | 1
001495 | Hydro Test Pack and Golden Weld Joint Procedure for Steam High Pressure Line | "Hydro Test Pack and Golden Weld Joint Procedure for Steam High Pressure Line" | 2025-07-21 | 2025-09-08 |  |  | Mohan | 0 | 1
001496 | Datasheet for Conductivity Analyser | "Datasheet for Conductivity Analyser" | 2025-07-22 | 2025-08-15 |  |  | Yean Yee | 0 | 1
001497 | Preliminary design and Vendor Approval - Strainer (Asahi, Agru) | "Preliminary design and Vendor Approval - Strainer (Asahi, Agru)" | 2025-07-22 | 2025-08-01 |  |  | Liying | 0 | 1
001498 | ST617 THP-PF-02 Shop Drawing Submission | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-07-22 | 2025-12-10 |  |  | Aaron | A.5 | 3
001499 | MSRA, SWP for Waterproofing Works (Electrical Building Roof) | "MSRA, SWP for Waterproofing Works (Electrical Building Roof)" | 2025-07-22 | 2025-08-01 |  |  | Bryan | 0 | 1
001500 | Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser) | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001501 | Unpriced PO for Radar Level Transmitter (Endress & Hauser) | "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001502 | Unpriced PO for Tuning Fork Level Switch (Endress & Hauser) | "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001503 | Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser) | "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001504 | Unpriced PO for Capacitive Level Switch (IFM) | "Unpriced PO for Capacitive Level Switch (IFM)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001505 | Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser) | "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001506 | Unpriced PO for Pressure Gauge (Baumer) | "Unpriced PO for Pressure Gauge (Baumer) " | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001507 | Unpriced PO for Conductive Level Switch (Endress & Hauser) | "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001508 | Unpriced PO for Pressure Transmitter (Endress & Hauser) | "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001509 | Unpriced PO for Pressure Transmitter (Emerson) | "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001510 | Unpriced PO for Pressure Transmitter (Emerson) | "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001511 | Unpriced PO for Temperature Transmitter (Endress & Hauser) | "Unpriced PO for Temperature Transmitter (Endress & Hauser)" | 2025-07-22 | 2025-07-31 |  |  | Caeden | 0 | 1
001512 | Unpriced PO for Knife Gate Valve (Jash Engineering) | "Unpriced PO for Knife Gate Valve (Jash Engineering)" | 2025-07-22 | 2025-11-24 |  |  | Caeden | 0 | 1
001513 | Unpriced PO for Ball Valve (OVS Engineering) | "Unpriced PO for Ball Valve (OVS Engineering)" | 2025-07-22 | 2025-11-04 |  |  | Caeden | 0 | 1
001514 | Unpriced PO for Non-return Check Valve (Breen International) | "Unpriced PO for Non-return Check Valve (Breen International)" | 2025-07-22 | 2025-11-24 |  |  | Caeden | 0 | 1
001515 | Unpriced PO for Metallic Butterfly Valve (OVS Engineering) | "Unpriced PO for Metallic Butterfly Valve (OVS Engineering)" | 2025-07-22 | 2025-11-24 |  |  | Caeden | 0 | 1
001516 | Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore) | "Unpriced PO for Sludge Pump (Netzsch) " && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" | 2025-07-22 | 2025-11-24 |  |  | Caeden | 0 | 2
001517 | Unpriced PO for SS Auto Ball Valve (OVS Engineering) | "Unpriced PO for cPVC Pipes (George Fischer)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" | 2025-07-22 | 2025-11-24 |  |  | Caeden | 0 | 2
001518 | Unpriced PO for Manual Ball Valve (OVS Engineering) | "Unpriced PO for Manual Ball Valve (OVS Engineering) " | 2025-07-22 | 2025-11-24 |  |  | Caeden | 0 | 1
001519 | Piping Valve List & Datasheet – Plastic Valve (GF) | "Piping Valve List & Datasheet – Plastic Valve (GF)" | 2025-07-22 | 2025-09-04 |  |  | Liying | 0 | 1
001520 | Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN) | "Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN)" | 2025-07-22 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001521 | Inspection Test Plan for Low Voltage Switchgear | "Inspection Test Plan for Low Voltage Switchgear" | 2025-07-22 | 2025-08-01 |  |  | Dhanapal | 0 | 1
001522 | Inspection Test Plan for CSEL Pipe Installation | "Inspection Test Plan for CSEL Pipe Installation" | 2025-07-23 | 2025-09-08 |  |  | Mohan | 0 | 1
001523 | Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118 | "Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118" | 2025-07-23 | 2025-08-01 |  |  | Dhanapal | 0 | 1
001524 | DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" | 2025-07-24 | 2025-08-01 |  |  | Htet Nu | 0 | 1
001525 | SSN Electrical building L2, Column C2A PE Endorsement | "SSN Electrical building L2, Column C2A PE Endorsement" | 2025-07-24 | 2025-08-12 |  |  | Aaron | A | 1
001526 | THP 1&2 Building Services DB SLD | "THP 1&2 Building Services DB SLD" | 2025-07-24 | 2025-09-15 |  |  | Freedomer | A | 1
001526 | THP 1&2 Building Services DB SLD | "THP 1&2 Building Services DB SLD" | 2025-07-24 | 2025-09-15 |  |  | Freedomer | A | 1
001527 | Material Submission – ARDEX 320 – Liquid Concrete Hardener and Dustproofer (Raised Floor Installations, Momentum Construction) | "Material Submission – ARDEX 320 – Liquid Concrete Hardener and Dustproofer (Raised Floor Installations, Momentum Construction)" | 2025-07-24 | 2025-08-01 |  |  | Kumar | 0 | 1
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 4
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | 2025-07-24 | 2025-09-24 |  |  | Aaron | A.6 | 4
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A | 1
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A | 1
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | 2025-09-24 |  |  | Aaron | A | 2
001529 | ST603_SWPR01&02 fabrication drawing | "ST603_SWPR01&02 fabrication drawing" && "ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed)" | 2025-07-24 | 2026-01-02 |  |  | Aaron | NA | 2
001530 | Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | 2025-07-24 | 2025-08-25 |  |  | Aaron | C | 4
001531 | ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed) | "ST603_SWPR01&02 fabrication drawing" && "ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed)" | 2025-07-24 | 2025-09-15 |  |  | Aaron | NA | 2
001532 | MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works | "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" | 2025-07-28 | 2025-09-15 |  |  | Bryan | 0 | 1
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | 0 | 1
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 2
001533 | BCA Approval of ST618 (THP Train_Cambi Structures) | "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | 2026-01-02 |  |  | Aaron | C | 1
001534 | Material Submission for HV Plug and Transformer Termination Kit | "Material Submission for HV Plug and Transformer Termination Kit " | 2025-07-29 | 2025-09-03 |  |  | Mohan | 0 | 1
001535 | Datasheet for TSS Analyser | "Datasheet for TSS Analyser" | 2025-07-29 | 2025-08-15 |  |  | Yean Yee | 0 | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 1
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001536 | SSN RIO - 0401 GA & Wiring Diagram | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | 2025-11-13 |  |  | Balaji | B | 4
001537 | Factory Acceptance Test Report for Public Address System | "Factory Acceptance Test Report for Public Address System" | 2025-07-30 | 2025-09-23 |  |  | Dhanapal | 0 | 1
001538 | Factory Acceptance Test Report for Pressure Transmitters (SSN) | "Factory Acceptance Test Report for Pressure Transmitters (SSN)" | 2025-07-30 | 2025-10-23 |  |  | Dhanapal | 0 | 1
001539 | Factory Acceptance Test Report for Clean Gas System Panel | "Factory Acceptance Test Report for Clean Gas System Panel" | 2025-07-30 | 2025-10-27 |  |  | Dhanapal | 0 | 1
001540 | Factory Acceptance Test Report for PH Analyser | "Factory Acceptance Test Report for PH Analyser" | 2025-07-30 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001541 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect-6th Batch) | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect-6th Batch) " | 2025-07-30 | 2025-09-08 |  |  | Mohan | 0 | 1
001542 | Factory Acceptance Test Report for Dissolved Oxygen Analyser | "Factory Acceptance Test Report for Dissolved Oxygen Analyser" | 2025-07-30 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001543 | Sample Board Submission for 50x50 SS316 Trunking | "Sample Board Submission for 50x50 SS316 Trunking" | 2025-07-30 |  |  |  | Mohan | 0 | 1
001544 | MSRA and SWP for SSN Tanks Openings Top Shelter Canvas Cover Installation | "MSRA and SWP for SSN Tanks Openings Top Shelter Canvas Cover Installation" | 2025-07-30 | 2025-08-25 |  |  | Bryan | 0 | 1
001545 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" | 2025-07-31 | 2025-12-09 |  |  | Dhanapal | 1 | 2

## 2025-08
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-08-04 | 2025-09-02 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-08-04 | 2025-09-02 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2025-08-04 | 2025-09-02 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2025-08-04 | 2025-09-02 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | 2025-08-04 | 2025-09-02 |  |  | Freedomer | D | 5
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | C | 8
000274 | ST612_Typical Railing | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | 2025-08-13 | 2025-09-08 |  |  | Aaron | I | 2
000274 | ST612_Typical Railing | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | 2025-08-13 | 2025-09-08 |  |  | Aaron | J | 2
000274 | ST612_Typical Railing | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " | 2025-08-13 | 2025-09-08 |  |  | Aaron | I | 2
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-08-12 | 2025-10-14 |  |  | Aaron/HP | A.4 | 7
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-08-12 | 2025-10-13 |  |  | Zora/HP | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-08-19 | 2025-10-13 |  |  | Aaron | A.2 | 6
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 2 | 4
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 3
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 2
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 1
000553 | Data Sheet, Drawing and Calculation of SSN Diffuser | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-08-22 | 2025-10-06 |  |  | Qili | 0 | 2
000579 | SSN RIO 0201 I/O List | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " | 2025-08-19 | 2025-09-15 |  |  | Balaji | 4 | 5
000601 | THP Functional Design Specification | "THP Functional Design Specification" | 2025-08-12 | 2025-10-08 |  |  | Joo Kwan | 2 | 3
000831 | SSN_CAT Ladder | "SSN_CAT Ladder " | 2025-08-19 | 2025-10-15 |  |  | Anna | D | 3
000831 | SSN_CAT Ladder | "SSN_CAT Ladder " | 2025-08-19 | 2025-10-15 |  |  | Anna | C | 1
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2025-08-19 | 2025-09-24 |  |  | Aaron | A.2 | 4
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2025-08-19 | 2025-09-24 |  |  | Aaron | A.2 | 2
000844 | THP Courtyard RC Plinth Detail | "THP Courtyard RC Plinth Detail" | 2025-08-22 | 2025-09-17 |  |  | Aaron | NA | 1
000867 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | C | 3
000964 | Functional Design Specification (Air Compressor System) | "Functional Design Specification (Air Compressor System)" | 2025-08-12 | 2025-10-08 |  |  | Joo Kwan | 2 | 3
000967 | Datasheet for pH Transmitter & Sensor | "Datasheet for pH Transmitter & Sensor " | 2025-08-15 | 2025-11-26 |  |  | Yean Yee | 1 | 2
000989 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-08-25 |  |  |  | Joo Kwan | 1 | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 3
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001008 | Shop Drawings for Block Wall | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" | 2025-08-13 | 2025-09-15 |  |  | Yuen Fatt | C | 4
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001027 | THP-MCC-0001AB MCC Drawings | "THP-MCC-0001AB MCC Drawings" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | C | 3
001099 | SSN -RIO PANEL 0001A/0001B- I/O List | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-08-19 | 2025-09-23 |  |  | Balaji | 2 | 3
001108 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" | 2025-08-22 |  |  |  | Karthikeyan | 1 | 2
001112 | SSN PMS Network Architecture Drawings | "SSN PMS Network Architecture Drawings" | 2025-08-07 | 2025-10-23 |  |  | Balaji | 1 | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001144 | SSN ECCP-1000- GA & Wiring Diagram | "SSN ECCP-1000- GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | B | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001145 | SSN RIO 0001A GA & Wiring Diagram | "SSN RIO 0001A GA & Wiring Diagram" | 2025-08-19 | 2025-10-01 |  |  | Balaji | C | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001146 | SSN RIO 0001B GA & Wiring Diagram | "SSN RIO 0001B GA & Wiring Diagram" | 2025-08-19 | 2025-10-08 |  |  | Balaji | B | 2
001154 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2025-08-12 | 2026-01-05 |  |  | K. Balaji | 2 | 3
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001165 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2025-08-22 | 2025-12-09 |  |  | Balaji | B | 2
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-08-07 | 2025-10-30 |  |  | Balaji | B | 3
001195 | Manual Butterfly Valve | "Manual Butterfly Valve " | 2025-08-06 | 2025-09-04 |  |  | Liying | 2 | 3
001219 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2025-08-19 | 2025-08-28 |  |  | Radha | 3 | 4
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-08-22 | 2025-09-02 |  |  | Balaji | A | 2
001257 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" | 2025-08-25 | 2025-12-23 |  |  | Radha | 1 | 2
001308 | G1 Booster Pump Hydraulics Calculation | "G1 Booster Pump Hydraulics Calculation " | 2025-08-25 |  |  |  | Joo Kwan | 1 | 2
001312 | Revised Design of THP Steel Structure Plinths | "Revised Design of THP Steel Structure Plinths" | 2025-08-22 | 2025-09-17 |  |  | Aaron | NA | 1
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" | 2025-08-25 | 2025-10-01 |  |  | Balaji | C | 2
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" | 2025-08-25 | 2025-10-01 |  |  | Balaji | C | 2
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" | 2025-08-25 | 2025-10-01 |  |  | Balaji | C | 2
001338 | Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox) | "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-08-21 | 2025-09-02 |  |  | Dhanapal | 1 | 2
001340 | Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox) | "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2025-08-25 | 2025-09-02 |  |  | Radha | 1 | 2
001341 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | 2025-08-27 | 2025-09-02 |  |  | Dhanapal | 2 | 3
001356 | Waterproofing Shop Drawing Submission | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-08-27 | 2025-10-06 |  |  | Yuen Fatt | C | 5
001356 | Waterproofing Shop Drawing Submission | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-08-27 | 2025-10-06 |  |  | Yuen Fatt | D | 5
001356 | Waterproofing Shop Drawing Submission | "Waterproofing Shop Drawing Submission " && "Raised Floor Shop Drawings submission (Momentum)" | 2025-08-27 | 2025-10-06 |  |  | Yuen Fatt | C | 5
001356 | Waterproofing Shop Drawing Submission | "Waterproofing Shop Drawing Submission " && "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" | 2025-08-27 | 2025-10-06 |  |  | Yuen Fatt | C | 4
001363 | Revised Design of THP Steel Structure Plinths (Rev G) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-08-22 | 2025-09-24 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev G) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-08-22 | 2025-09-24 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev G) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-08-22 | 2025-09-24 |  |  | Aaron | G | 5
001368 | Vendor Approval for Active Harmonic Filter (DANFOSS) | "Vendor Approval for Active Harmonic Filter (DANFOSS)" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | 1 | 2
001375 | G1 Booster Pump Data Sheet | "G1 Booster Pump Data Sheet" | 2025-08-25 | 2025-09-08 |  |  | Joo Kwan | 1 | 2
001381 | G2D Booster Pump Data Sheet | "G2D Booster Pump Data Sheet" | 2025-08-22 | 2025-09-08 |  |  | Joo Kwan | 1 | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001382 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-08-13 | 2025-09-02 |  |  | Karthik | B | 2
001401 | Vendor Approval for Lighting and Small Power Material (Hong An) | "Vendor Approval for Lighting and Small Power Material (Hong An)" | 2025-08-14 | 2025-09-03 |  |  | Jun | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-08-27 | 2025-10-22 |  |  | Karthikeyan | 1 | 4
001417 | Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack | "Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack" | 2025-08-29 | 2025-12-29 |  |  | K Balaji | 1 | 2
001432 | Vendor Approval for Distribution Boards (ZPA) | "Vendor Approval for Distribution Boards (ZPA)" | 2025-08-21 | 2025-10-01 |  |  | Freedomer | 1 | 2
001454 | Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " | 2025-08-18 | 2025-10-13 |  |  | Kumar | 1 | 2
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-08-13 | 2025-08-15 |  |  | Aaron | A.5 | 7
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | 2025-08-15 |  |  | Aaron | A.5 | 2
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | 2025-08-15 |  |  | Aaron | A.5 | 2
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | 2025-08-15 |  |  | Aaron | A.5 | 2
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-08-22 | 2025-08-28 |  |  | Aaron | A.5 | 7
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" | 2025-08-22 | 2025-08-28 |  |  | Aaron | A.5 | 2
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" | 2025-08-22 | 2025-08-28 |  |  | Aaron | A.5 | 2
001458 | Railing Shop Drawing For Electrical Building | " Railing Shop Drawing For Electrical Building" | 2025-08-22 | 2025-08-28 |  |  | Aaron | A.5 | 2
001500 | Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser) | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001501 | Unpriced PO for Radar Level Transmitter (Endress & Hauser) | "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2025-08-22 | 2025-12-05 |  |  | Caeden | 0 | 1
001502 | Unpriced PO for Tuning Fork Level Switch (Endress & Hauser) | "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001503 | Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser) | "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001504 | Unpriced PO for Capacitive Level Switch (IFM) | "Unpriced PO for Capacitive Level Switch (IFM)" | 2025-08-01 | 2025-12-05 |  |  | Caeden | 0 | 1
001505 | Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser) | "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001506 | Unpriced PO for Pressure Gauge (Baumer) | "Unpriced PO for Pressure Gauge (Baumer) " | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001507 | Unpriced PO for Conductive Level Switch (Endress & Hauser) | "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001508 | Unpriced PO for Pressure Transmitter (Endress & Hauser) | "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001509 | Unpriced PO for Pressure Transmitter (Emerson) | "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-08-01 | 2025-08-11 |  |  | Caeden | 0 | 1
001510 | Unpriced PO for Pressure Transmitter (Emerson) | "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-08-01 | 2025-12-15 |  |  | Caeden | 0 | 1
001511 | Unpriced PO for Temperature Transmitter (Endress & Hauser) | "Unpriced PO for Temperature Transmitter (Endress & Hauser)" | 2025-08-01 | 2025-08-05 |  |  | Caeden | 1 | 1
001546 | CV of Team Member (QA/QC Manager) | "CV of Team Member (QA/QC Manager)" | 2025-08-01 | 2026-01-16 |  |  | Htet Nu | 0 | 1
001547 | THP Overall Network Diagrams | "SSN Over All Network Archtecture Drawings" && " THP Overall Network Diagrams" | 2025-08-01 | 2025-09-23 |  |  | Balaji | A | 3
001547 | THP Overall Network Diagrams | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" | 2025-08-01 | 2025-09-23 |  |  | Balaji | B | 3
001547 | THP Overall Network Diagrams | " THP Overall Network Diagrams" | 2025-08-01 | 2025-09-23 |  |  | Balaji | B | 2
001548 | Shop Drawing for ST608 (SH001,002,003, CR001, PR003)_PE Endorsed | "Shop Drawing for ST608 (SH001,002,003, CR001, PR003)_PE Endorsed" | 2025-08-01 | 2025-10-27 |  |  | Aaron | 0 | 1
001549 | Vendor Approval of Building Management System (BMS) (Willowglen) | "Vendor Approval of Building Management System (BMS) (Willowglen)" | 2025-08-04 | 2025-09-11 |  |  | Mr Low | 2 | 3
001550 | Vendor Approval of PMS Network Interface Panel (Vector InfoTech) | "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" | 2025-08-04 | 2025-08-14 |  |  | Mr Low | 0 | 1
001551 | Datasheet for Dissolved Oxygen Analyser | "Datasheet for Dissolved Oxygen Analyser " | 2025-08-04 | 2025-10-01 |  |  | Yean Yee | 0 | 1
001552 | Datasheet for Pressure Gauge | "Datasheet for Pressure Gauge" | 2025-08-04 | 2025-11-05 |  |  | Yean Yee | 0 | 1
001553 | FAT Report for SS Pipe in THP-HS Line (Cyclect) | "FAT Report for SS Pipe in THP-HS Line (Cyclect)" | 2025-08-04 | 2025-09-08 |  |  | Radha | 0 | 1
001554 | SAT Procedure for LVSG Panels (Sunlight) | "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" && "SAT Procedure for LVSG Panels (Sunlight)" | 2025-08-04 | 2025-08-26 |  |  | Dhanapal | 0 | 2
001555 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for G1 Booster Pumps (KSB) | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for G1 Booster Pumps (KSB)" | 2025-08-05 | 2025-09-08 |  |  | Mohan | 0 | 1
001556 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for G2D Booster Pumps (KSB) | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for G2D Booster Pumps (KSB)" | 2025-08-05 | 2025-09-08 |  |  | Mohan | 0 | 1
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 4
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 4
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 4
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 4
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 4
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 4
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001557 | LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001558 | LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 3
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A | 3
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001559 | SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | A_To withdraw | 1
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | 2025-08-20 |  |  | Freedomer | B | 2
001561 | Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi) | "Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi)" | 2025-08-05 | 2025-09-02 |  |  | Dhanapal | 0 | 1
001562 | Certificate of Proper Installation for LVSG Panels (Sunlight) | "Certificate of Proper Installation for LVSG Panels (Sunlight)" | 2025-08-05 | 2025-09-02 |  |  | Dhanapal | 0 | 1
001563 | Certificate of Proper Installation for WSD11-MCC-0101A&B (Sunlight) | "Certificate of Proper Installation for WSD11-MCC-0101A&B (Sunlight) " | 2025-08-05 | 2025-09-02 |  |  | Dhanapal | 0 | 1
001564 | Factory Acceptance Test Report for Fire Alarm System | "Factory Acceptance Test Report for Fire Alarm System " | 2025-08-05 | 2025-10-22 |  |  | Dhanapal | 1 | 2
001565 | SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | "SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi)" | 2025-08-05 | 2025-10-01 |  |  | Dhanapal | 1 | 2
001566 | Notice for Extension of Time and Cost for Interface Work at C4A THP Courtyard Reinforced Concrete Ground Slab - (THP Train 1 and Train 2) | "Notice for Extension of Time and Cost for Interface Work at C4A THP Courtyard Reinforced Concrete Ground Slab - (THP Train 1 and Train 2)" | 2025-08-06 | 2025-09-23 |  |  | Vincent | 0 | 1
001567 | Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd | "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" | 2025-08-06 | 2025-08-26 |  |  | Yuen Fatt | 0 | 1
001568 | Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636 | "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-08-06 | 2025-10-06 |  |  | Kumar | 0 | 1
001569 | Payment Claim No.25 | "Payment Claim No.25" | 2025-08-07 | 2025-08-22 |  |  | YiHao | 0 | 1
001570 | FAT Report for Manual Knife Gate Valves - Batch 1 (Jash) | "FAT Report for Manual Knife Gate Valves - Batch 1 (Jash)" | 2025-08-07 | 2025-09-02 |  |  | Mohan | 0 | 1
001571 | Test Report 2.2 for Manual Plastic Valves | "Test Report 2.2 for Manual Plastic Valves " && "FAT Report for CSEL Piping (3rd Batch) " | 2025-08-07 | 2025-09-08 |  |  | Mohan | 0 | 2
001572 | THP Courtyard Sump Design (Updates) | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | 2025-08-07 | 2025-08-25 |  |  | Aaron | A | 5
001572 | THP Courtyard Sump Design (Updates) | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | 2025-08-07 | 2025-08-25 |  |  | Aaron | A | 4
001573 | MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground) | "MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground)" && "MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) " | 2025-08-09 | 2025-12-29 |  |  | Bryan | 0 | 2
001574 | VCM Submission for 2025-07 | "VCM Submission for 2025-07" | 2025-08-11 | 2025-08-27 |  |  | Heng Peng | 0 | 1
001575 | Notice for Extension of Time and Cost for Additional Aluminium Handrails QAQC requirements (NOC REF: C4B-006_AUG_2024) | "Notice for Extension of Time and Cost for Additional Aluminium Handrails QAQC requirements (NOC REF: C4B-006_AUG_2024)" | 2025-08-11 | 2025-09-23 |  |  | Vincent | 0 | 1
001576 | Vendor Approval for Insulation Material & Cladding Sheet – STHP & HS | "Vendor Approval for Insulation Material & Cladding Sheet – STHP & HS" | 2025-08-12 | 2025-11-24 |  |  | Jun | 0 | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001577 | BCA Approval of ST621 (Site Wide Pipe Rack) | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | 2025-09-25 |  |  | Aaron | A | 1
001578 | SSN Aeration Line Automatic Condensate Drain Valve | "SSN Aeration Line Automatic Condensate Drain Valve" | 2025-08-12 |  |  |  | Joo Kwan | 0 | 1
001579 | FAT Report for CSEL Piping (3rd Batch) | "Test Report 2.2 for Manual Plastic Valves " && "FAT Report for CSEL Piping (3rd Batch) " | 2025-08-12 | 2025-09-08 |  |  | Mohan | 0 | 2
001580 | FAT Report for IA Line from THP to SWPR (SS Spools) | "FAT Report for IA Line from THP to SWPR (SS Spools)" | 2025-08-12 | 2025-09-08 |  |  | Mohan | 0 | 1
001581 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | 2025-08-12 | 2025-09-26 |  |  | Dhanapal | 2 | 3
001582 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | 2025-08-12 | 2025-08-15 |  |  | Htet Nu | 0 | 1
001582 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | 2025-08-12 | 2025-08-15 |  |  | Htet Nu | 0 | 1
001582 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | 2025-08-12 | 2025-08-15 |  |  | Htet Nu | 0 | 1
001583 | FAT Report for SWPR Pipe's Guide Supports | "FAT Report for SWPR Pipe's Guide Supports " | 2025-08-12 | 2025-09-08 |  |  | Mohan | 0 | 1
001584 | Notice For Extension of Time And Cost For Delay Of Vessel Stratford 138 IMO 9305491 Due To Force Majeure And Fire | "Notice For Extension of Time And Cost For Delay Of Vessel Stratford 138 IMO 9305491 Due To Force Majeure And Fire" | 2025-08-13 | 2025-10-15 |  |  | Vincent | 0 | 1
001585 | MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) | "MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground)" && "MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) " | 2025-08-13 | 2025-12-29 |  |  | Bryan | 0 | 2
001586 | SWPR _Platform A and B- Cat ladders | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "SWPR _Platform A and B- Cat ladders" | 2025-08-13 | 2025-10-14 |  |  | Aaron | E | 2
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001587 | ST619 THP-PR01 (PE endorsed drawing) | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | 2025-10-27 |  |  | Aaron | A.3 | 1
001588 | SSN Equipment Loading and Equipment Plinth Layout | "SSN Equipment Loading and Equipment Plinth Layout" | 2025-08-13 | 2025-10-06 |  |  | Aaron | A | 1
001589 | Shop Drawing for Typical Railing Details | "Shop Drawing for Typical Railing Details" | 2025-08-13 | 2025-09-23 |  |  | Aaron | A | 1
001589 | Shop Drawing for Typical Railing Details | "Shop Drawing for Typical Railing Details" | 2025-08-13 | 2025-09-23 |  |  | Aaron | A | 1
001589 | Shop Drawing for Typical Railing Details | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Typical Railing Details" | 2025-08-13 | 2025-09-23 |  |  | Aaron | A | 2
001590 | Material Test Report EN 10204-3.1 for Manual Ball Valves (OVS-Heaton) | "Material Test Report EN 10204-3.1 for Manual Ball Valves (OVS-Heaton)" | 2025-08-13 | 2025-09-08 |  |  | Mohan | 0 | 1
001591 | 80% THP ALMOP Report | "80% THP ALMOP Report" | 2025-08-14 |  |  |  | Joo Kwan | 0 | 1
001592 | Factory Acceptance Test Report for Temperature Transmitters | "Factory Acceptance Test Report for Temperature Transmitters" | 2025-08-14 | 2025-10-06 |  |  | Dhanapal | 0 | 1
001593 | Factory Acceptance Test Report for Tuning Fork Level Switches | "Factory Acceptance Test Report for Tuning Fork Level Switches " | 2025-08-14 | 2025-11-05 |  |  | Dhanapal | 0 | 1
001594 | C4B Monthly Progress Report Number No.27 (07 25) | "C4B Monthly Progress Report Number No.27 (07 25)" | 2025-08-15 | 2025-08-30 |  |  | Htet Nu | 0 | 1
001595 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) (3rd Batch) | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) (3rd Batch)" | 2025-08-15 | 2025-09-08 |  |  | Mohan | 0 | 1
001596 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Jun 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Jun 2025" | 2025-08-15 | 2025-08-26 |  |  | Kumar | 0 | 1
001597 | Notice for Extension of Time and Cost for Delay Due To Relay Modification of SSN 22KV Incoming Feeder From C3B1 HVSG | "Notice for Extension of Time and Cost for Delay Due To Relay Modification of SSN 22KV Incoming Feeder From C3B1 HVSG" | 2025-08-15 | 2025-10-15 |  |  | Vincent | 0 | 1
001598 | Factory Acceptance Test Report for Thermal Flow Switch | "Factory Acceptance Test Report for Thermal Flow Switch" | 2025-08-17 | 2025-10-23 |  |  | Dhanapal | 0 | 1
001599 | Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) | "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) " | 2025-08-17 | 2025-10-23 |  |  | Dhanapal | 0 | 1
001600 | QA/QC Report for Air Conditioning System | "QA/QC Report for Air Conditioning System" | 2025-08-19 | 2025-10-10 |  |  | Mohan | 1 | 2
001601 | QA/QC Report for Mechanical Ventilation Fan | "QA/QC Report for Mechanical Ventilation Fan" | 2025-08-19 | 2025-10-10 |  |  | Mohan | 1 | 2
001602 | FAT Report for Manual Knife Gate Valves Batch 2 (Jash) | "FAT Report for Manual Knife Gate Valves Batch 2 (Jash)" | 2025-08-19 | 2025-09-02 |  |  | Mohan | 0 | 1
001603 | ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " | 2025-08-19 | 2025-10-27 |  |  | Kumar | 0 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | 2025-09-04 |  |  | Yuen Fatt | A | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | 2025-09-04 |  |  | Yuen Fatt | A | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | 2025-09-04 |  |  | Yuen Fatt | A | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | 2025-09-04 |  |  | Yuen Fatt | A | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | 2025-09-04 |  |  | Yuen Fatt | A | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | 2025-09-04 |  |  | Yuen Fatt | A | 1
001605 | ST609 Inspection Reports | "ST609 Inspection Reports" | 2025-08-19 | 2025-10-13 |  |  | Radha | 0 | 1
001606 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | "Test Procedure for Pull & Push Load Test - Aluminium Handrail" | 2025-08-19 | 2025-09-24 |  |  | Radha | 2 | 3
001607 | Inspection Test Plan for Distribution Panels (MDBs) | " Inspection Test Plan for Distribution Panels (MDBs)" | 2025-08-22 | 2025-09-15 |  |  | Dhanapal | 0 | 1
001608 | ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" | 2025-08-20 | 2025-10-27 |  |  | Radha | 0 | 1
001609 | THP Fire alarm devices interface with C4A Fire Alarm panel | " THP Fire alarm devices interface with C4A Fire Alarm panel" | 2025-08-22 | 2025-10-22 |  |  | Karthik | A | 1
001610 | G2D Water Hydraulic Pressure Loss Calculation | "G2D Water Hydraulic Pressure Loss Calculation" | 2025-08-22 |  |  |  | Qili | 0 | 1
001611 | Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) | "Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) " | 2025-08-22 | 2025-12-05 |  |  | Caedan | 0 | 1
001612 | Unpriced PO for Thermal Flow Switch (Endress & Hauser) | "Unpriced PO for Thermal Flow Switch (Endress & Hauser) " | 2025-08-22 | 2025-12-05 |  |  | Caedan | 0 | 1
001613 | Unpriced PO for Pressure Switch (IFM) | "Unpriced PO for Pressure Switch (IFM) " | 2025-08-22 | 2025-12-05 |  |  | Caedan | 0 | 1
001614 | Unpriced PO for Rotameter (Krohne) | "Unpriced PO for Rotameter (Krohne) " | 2025-08-22 | 2025-12-05 |  |  | Caedan | 0 | 1
001615 | Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng) | "Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng)" && "Unpriced PO for Valve for Condensate System (Spirax Sarco)" | 2025-08-22 | 2025-11-24 |  |  | Caedan | 0 | 2
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.5 | 3
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A | 2
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001616 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | 2025-10-01 |  |  | Aaron | A.1 | 1
001617 | Piping Special Item - Metallic Strainer (Spirax Sarco) | "Piping Special Item - Metallic Strainer (Spirax Sarco)" | 2025-08-25 | 2025-10-22 |  |  | Liying | 0 | 1
001618 | Piping Special Item - Plastic Strainer (Asahi/ Argu) | "Piping Special Item - Plastic Strainer (Asahi/ Argu)" | 2025-08-25 | 2025-10-22 |  |  | Liying | 0 | 1
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | 2025-11-10 |  |  | David Li | C | 3
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | 2025-11-10 |  |  | David Li | C | 3
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | 2025-11-10 |  |  | David Li | D | 3
001620 | C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026) | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" | 2025-08-25 | 2025-10-01 |  |  | Htet Nu | 0 | 1
001621 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | 2025-08-25 | 2025-09-26 |  |  | Dhanapal | 0 | 3
001622 | ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission | "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2025-08-25 | 2025-10-24 |  |  | Radha | 0 | 1
001623 | SSN Chemical Dosing Platform Design | "SSN Chemical Dosing Platform Design" | 2025-08-25 | 2025-12-02 |  |  | Aaron | A | 1
001623 | SSN Chemical Dosing Platform Design | "SSN Chemical Dosing Platform Design" | 2025-08-25 | 2025-12-02 |  |  | Aaron | A | 1
001623 | SSN Chemical Dosing Platform Design | "SSN Chemical Dosing Platform Design" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-08-25 | 2025-12-02 |  |  | Aaron | A.1 | 2
001624 | Operation and Maintenance Manual for Parabolic Screen | "Operation and Maintenance Manual for Parabolic Screen" | 2025-08-25 |  |  |  | Yibo | 0 | 1
001625 | SSN Rain Water Drainage Layout and Detail Design | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2025-08-26 | 2025-11-10 |  |  | Aaron | A.2 | 7
001625 | SSN Rain Water Drainage Layout and Detail Design | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2025-08-26 | 2025-11-10 |  |  | Aaron | A.2 | 7
001625 | SSN Rain Water Drainage Layout and Detail Design | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2025-08-26 | 2025-11-10 |  |  | Aaron | A.2 | 7
001626 | Material Submission for Waterproofing (Pro-Werkze Pte Ltd) | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" | 2025-08-26 | 2025-09-17 |  |  | Kumar | 0 | 1
001627 | CV of Team Member (WSHO) | "CV of Team Member (WSHO)" | 2025-08-26 | 2025-09-11 |  |  | Htet Nu | 0 | 1
001628 | SAT Report for WST02-LVSG-0101A & WST02-LVSG-0101B | "SAT Report for WST02-LVSG-0101A & WST02-LVSG-0101B" | 2025-08-27 | 2025-10-01 |  |  | Dhanapal | 0 | 1
001629 | ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission | "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2025-08-27 | 2025-10-29 |  |  | Radha | 0 | 1
001630 | Unpriced PO for Building Management System (Willowglen) | "Unpriced PO for Building Management System (Willowglen)" | 2025-08-27 |  |  |  | Caeden | 0 | 1
001631 | Vendor Information of BD Flowmeter | "Vendor Information of BD Flowmeter " | 2025-08-27 | 2025-10-30 |  |  | Yean Yee | 0 | 1
001632 | SSN Instrument Hookup Drawing for Electromagnetic FIT | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | 2025-12-10 |  |  | Yean Yee | A | 1
001632 | SSN Instrument Hookup Drawing for Electromagnetic FIT | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | 2025-12-10 |  |  | Yean Yee | A | 1
001632 | SSN Instrument Hookup Drawing for Electromagnetic FIT | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | 2025-12-10 |  |  | Yean Yee | A | 1
001632 | SSN Instrument Hookup Drawing for Electromagnetic FIT | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | 2025-12-10 |  |  | Yean Yee | A | 1
001632 | SSN Instrument Hookup Drawing for Electromagnetic FIT | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | 2025-12-10 |  |  | Yean Yee | A | 1
001633 | Cable List for RIO-0101 | "Cable List for RIO-0101" | 2025-08-27 | 2025-12-10 |  |  | Karthik | 0 | 1
001634 | Cable List for RIO-002A | "Cable List for RIO-002A" | 2025-08-27 | 2025-12-10 |  |  | Karthik | 0 | 1
001635 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" | 2025-08-28 | 2025-10-01 |  |  | Dhanapal | 1 | 2
001636 | Testing Check List (Process) | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-08-29 | 2025-10-01 |  |  | Joo Kwan | VOID | 9
001637 | Commissioning Plan for EQ Tank and Lamella Clarifier | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-08-29 | 2025-09-08 |  |  | Joo Kwan | VOID | 9
001638 | Commissioning Plan for THP Train | "Commissioning Plan for THP Train" | 2025-08-29 | 2025-09-04 |  |  | Joo Kwan | 0 | 1
001639 | Factory Acceptance Test Report for Conductive Probe Level Switches | "Factory Acceptance Test Report for Conductive Probe Level Switches" | 2025-08-29 | 2025-11-14 |  |  | Dhanapal | 0 | 1
001640 | HDG Grating Clamp Details | "HDG Grating Clamp Details" | 2025-08-29 | 2025-10-23 |  |  | Aaron | C | 1
001641 | THP Silo Crossover Platform Pipe Support | "THP Silo Crossover Platform Pipe Support" | 2025-08-29 | 2025-09-17 |  |  | Aaron | F | 1
001641 | THP Silo Crossover Platform Pipe Support | "THP Silo Crossover Platform Pipe Support" | 2025-08-29 | 2025-09-17 |  |  | Aaron | E | 1
001641 | THP Silo Crossover Platform Pipe Support | "THP Silo Crossover Platform Pipe Support" | 2025-08-29 | 2025-09-17 |  |  | Aaron | F | 1

## 2025-09
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000161 | Milestone 3 Underground Services | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | 2025-09-29 | 2026-01-27 |  |  | Heng Peng/ Muthu | 0 | 2
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | 2025-09-11 | 2025-12-29 |  |  | Kyaw Myo | B | 3
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" | 2025-09-11 | 2025-12-29 |  |  | Kyaw Myo | B | 3
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2025-09-11 | 2025-12-29 |  |  | Kyaw Myo | B | 1
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2025-09-11 | 2025-12-29 |  |  | Kyaw Myo | B | 1
000188 | Fire Alarm-Gas Suppression | "Fire Alarm-Gas Suppression" | 2025-09-11 | 2025-12-29 |  |  | Kyaw Myo | B | 3
000507 | Blower Pressure Loss Calculation | "Blower Pressure Loss Calculation" | 2025-09-10 | 2026-02-23 |  |  | Qili | 2 | 3
000643 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2025-09-25 | 2025-10-06 |  |  | Mohan | 1 | 3
000857 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2025-09-15 | 2025-12-02 |  |  | Karthikeyan | 1 | 2
000861 | THP- Valve Pit, Sump and Kerb Detail | "THP- Valve Pit, Sump and Kerb Detail" | 2025-09-15 | 2025-09-25 |  |  | Thet Myo | NA | 1
001150 | Report of Project Safety Review for THP Trains Installation | "Report of Project Safety Review for THP Trains Installation" | 2025-09-03 | 2025-10-14 |  |  | Max | 2 | 3
001180 | Datasheet for Tuning Fork Level Switch | "Datasheet for Tuning Fork Level Switch " | 2025-09-10 | 2025-12-02 |  |  | Yean Yee | 1 | 2
001181 | Datasheet for Pressure Switch | "Datasheet for Pressure Switch" | 2025-09-10 | 2025-12-02 |  |  | Yean Yee | 2 | 3
001226 | THP Courtyard - Valve Pit, Sump and Kerb Detail | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | 2025-09-15 | 2025-10-15 |  |  | Aaron | A | 5
001226 | THP Courtyard - Valve Pit, Sump and Kerb Detail | "THP Courtyard - Valve Pit, Sump and Kerb Detail " | 2025-09-15 | 2025-10-15 |  |  | Aaron | B | 2
001341 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | 2025-09-17 | 2025-12-23 |  |  | Dhanapal | 2 | 3
001347 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-09-29 |  |  |  | Yibo | B | 2
001347 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-09-29 |  |  |  | Yibo | B | 2
001363 | Revised Design of THP Steel Structure Plinths (Rev G) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-09-24 | 2026-01-12 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev G) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-09-24 | 2026-01-12 |  |  | Aaron | G | 5
001363 | Revised Design of THP Steel Structure Plinths (Rev G) | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" | 2025-09-24 | 2026-01-12 |  |  | Aaron | G | 5
001403 | FAT Report for Chemical Dosing Pumps (PROMINENT) | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-09-09 | 2025-11-10 |  |  | Radha | 3 | 4
001419 | Project Safety Review for SSN Steel Structure and MEICA Equipment Installation | "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" | 2025-09-03 | 2025-10-06 |  |  | Max | 1 | 2
001549 | Vendor Approval of Building Management System (BMS) (Willowglen) | "Vendor Approval of Building Management System (BMS) (Willowglen)" | 2025-09-29 | 2025-11-14 |  |  | Mr Low | 2 | 3
001572 | THP Courtyard Sump Design (Updates) | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | 2025-09-15 | 2025-09-24 |  |  | Aaron | A | 5
001572 | THP Courtyard Sump Design (Updates) | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | 2025-09-15 | 2025-09-24 |  |  | Aaron | A | 4
001581 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | 2025-09-30 | 2025-10-02 |  |  | Dhanapal | 2 | 3
001642 | GA drawing for Sampling Sink | "GA drawing for Sampling Sink" | 2025-09-01 |  |  |  | David | A | 1
001643 | SAT Report for WST02-MCC-1001A & WST02-MCC-1001B | "SAT Report for WST02-MCC-1001A & WST02-MCC-1001B" | 2025-09-01 | 2025-10-01 |  |  | Dhanapal | 0 | 1
001644 | Load Test Reports for Top Manway (Aluminium Hatch) | "Load Test Reports for Top Manway (Aluminium Hatch)" | 2025-09-01 |  |  |  | Kumar | 0 | 1
001645 | Part 2 Further Notice For Extension Of Time and Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | "Part 2 Further Notice For Extension Of Time and Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG" | 2025-09-02 | 2025-10-15 |  |  | Vincent | 0 | 1
001646 | RFC for LVSG and MCC Panel to Directly Sit on the Floor Instead of Concrete Base | "RFC for LVSG and MCC Panel to Directly Sit on the Floor Instead of Concrete Base" | 2025-09-03 | 2025-10-06 |  |  | Freedomer | 0 | 1
001647 | Payment Claim No.26 | "Payment Claim No.26" | 2025-09-03 | 2025-09-23 |  |  | Yi Hao | 0 | 1
001648 | THP G2D Pressure Reducing Valve Data Sheet | "THP G2D Pressure Reducing Valve Data Sheet" | 2025-09-04 | 2025-10-22 |  |  | Joo Kwan | 0 | 1
001649 | Solenoid Valve Data Sheet | "Solenoid Valve Data Sheet" | 2025-09-04 | 2025-10-22 |  |  | Joo Kwan | 1 | 2
001650 | Vendor Manufacturing Inspection Test Plan for Rotameter | "Vendor Manufacturing Inspection Test Plan for Rotameter " && "FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight)" | 2025-09-04 | 2025-12-10 |  |  | Dhanapal | 0 | 2
001651 | FAT Report for RIO Mock Up Panel | "FAT Report for RIO Mock Up Panel " | 2025-09-04 | 2025-12-10 |  |  | Dhanapal | 0 | 1
001652 | FAT Report for PLC Mock Up Panel | "FAT Report for PLC Mock Up Panel " | 2025-09-04 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001653 | FAT Report for FFOTP Mock Up Panel | "FAT Report for FFOTP Mock Up Panel" | 2025-09-04 | 2025-12-09 |  |  | Dhanapal | 0 | 1
001654 | ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission | "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | 2025-09-04 | 2025-10-29 |  |  | Kumar | 0 | 1
001655 | FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight) | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" | 2025-09-08 | 2025-10-06 |  |  | Dhanapal | 0 | 1
001656 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | "Shop Drawing for SWPR-03 Platform A&B Cat ladder" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-09-08 | 2025-10-23 |  |  | Aaron | A.3 | 3
001656 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-09-08 | 2025-10-23 |  |  | Aaron | A.1 | 2
001656 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | "SSN Chemical Dosing Platform Design" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-09-08 | 2025-10-23 |  |  | Aaron | A.1 | 2
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001657 | Chemical Cabinet - GA drawing | "Chemical Cabinet - GA drawing" | 2025-09-08 |  |  |  | David | A | 1
001658 | Vendor Manufacturing Inspection Test Plan & FAT Procedure for Flange Adaptors (Synchong Hoe) | "Vendor Manufacturing Inspection Test Plan & FAT Procedure for Flange Adaptors (Synchong Hoe)" | 2025-09-08 | 2025-12-23 |  |  | Mohan | 0 | 1
001659 | VCM Submission for 2025-08 | "VCM Submission for 2025-08" | 2025-09-08 | 2025-10-01 |  |  | Heng Peng | 0 | 1
001660 | Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe) | "Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe)" && "Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe)" | 2025-09-09 | 2025-10-24 |  |  | Kumar | 0 | 2
001661 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Jul 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Jul 2025" | 2025-09-09 | 2025-10-10 |  |  | Kumar | 0 | 1
001662 | Factory Acceptance Test Report for Rotameter | "Factory Acceptance Test Report for Rotameter" | 2025-09-09 | 2025-12-10 |  |  | Dhanapal | 0 | 1
001663 | Unpriced PO for Raised Floor (Momentum Construction) | "Unpriced PO for Raised Floor (Momentum Construction)" | 2025-09-09 | 2025-12-05 |  |  | Caedan | 0 | 1
001664 | Unpriced PO for Automatic Waste Water Sampler (Endress & Hauser) | "Unpriced PO for Automatic Waste Water Sampler (Endress & Hauser)" | 2025-09-09 | 2025-12-05 |  |  | Caedan | 0 | 1
001665 | Unpriced PO for Control Panels (Fox Singapore) | "Unpriced PO for Control Panels (Fox Singapore)" | 2025-09-09 | 2025-10-27 |  |  | Caedan | 0 | 1
001666 | Unpriced PO for PMS Panel (Vector Infotech) | "Unpriced PO for PMS Panel (Vector Infotech)" | 2025-09-09 | 2025-10-27 |  |  | Caedan | 0 | 1
001667 | FAT Report for THP Area Pipe Supports | "FAT Report for THP Area Pipe Supports" | 2025-09-10 | 2025-12-23 |  |  | Mohan | 0 | 1
001668 | Master Control for THP | "Master Control for THP" | 2025-09-10 | 2025-12-15 |  |  | Joo Kwan | 0 | 1
001669 | FAT Report for SWPR Pipe Guide Supports | "FAT Report for SWPR Pipe Guide Supports" | 2025-09-10 | 2025-12-23 |  |  | Mohan | 0 | 1
001670 | FAT Report for SWPR SS 316L Pipes | "FAT Report for SWPR SS 316L Pipes" | 2025-09-10 | 2025-12-23 |  |  | Mohan | 0 | 1
001671 | FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight) | "FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight)" | 2025-09-10 | 2026-02-02 |  |  | Dhanapal | 0 | 1
001672 | Datasheet for Rotameter | "Datasheet for Rotameter" | 2025-09-10 | 2025-11-05 |  |  | Yean Yee | 0 | 1
001673 | Datasheet for Conductive Level Switch | "Datasheet for Conductive Level Switch" | 2025-09-10 | 2025-11-13 |  |  | Yean Yee | 0 | 1
001674 | SSN Instrument Hookup Drawing for Temperature Transmitter | "SSN Instrument Hookup Drawing for Temperature Transmitter" | 2025-09-10 | 2025-12-10 |  |  | Yean Yee | A | 1
001675 | SSN Instrument Hookup Drawing for Radar Level Transmitter | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | 2025-09-10 | 2025-12-10 |  |  | Yean Yee | A | 1
001675 | SSN Instrument Hookup Drawing for Radar Level Transmitter | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | 2025-09-10 | 2025-12-10 |  |  | Yean Yee | A | 1
001675 | SSN Instrument Hookup Drawing for Radar Level Transmitter | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | 2025-09-10 | 2025-12-10 |  |  | Yean Yee | A | 1
001676 | 80% SSN ALMOP Report | "80% SSN ALMOP Report" | 2025-09-11 |  |  |  | Joo Kwan | 0 | 1
001677 | Sample Board Submission for 40W Floodling Lighting | "Sample Board Submission for 40W Floodling Lighting" | 2025-09-12 | 2025-09-26 |  |  | Dhanapal | 0 | 1
001678 | FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH) | "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" && "FAT Report for Diffuser System (Xylem)" | 2025-09-12 | 2025-12-15 |  |  | Mohan | 1 | 3
001679 | ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" | 2025-09-15 | 2025-10-29 |  |  | Kumar | 0 | 1
001680 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B" | 2025-09-16 | 2025-10-06 |  |  | Dhanapal | 0 | 1
001681 | C4B Monthly Progress Report Number No.28 (08 25) | "C4B Monthly Progress Report Number No.28 (08 25)" | 2025-09-16 | 2025-09-26 |  |  | Htet Nu | 0 | 1
001682 | Annex E - ST601 & ST602 ERSS | "Annex E - ST601 & ST602 ERSS" | 2025-09-17 | 2025-10-06 |  |  | Aaron | NA | 1
001683 | FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight) | "FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight)" | 2025-09-18 | 2025-10-06 |  |  | Dhanapal | 0 | 1
001684 | FAT Report for Diffuser System (Xylem) | "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" && "FAT Report for Diffuser System (Xylem)" | 2025-09-22 | 2025-10-06 |  |  | Mohan | 1 | 3
001685 | Datasheet for Thermal Flow Switch | "Datasheet for Thermal Flow Switch" | 2025-09-23 | 2025-10-23 |  |  | Yean Yee | 1 | 2
001686 | Request for Deferment of Liquidated Damages – Contract Milestone 4 (CM4: Pre-Commissioning Test for Digestion Pre-treatment Facility, Sidestream Nitrogen Removal Facility and Pipe Rack) (5 Oct 2025) | "Request for Deferment of Liquidated Damages – Contract Milestone 4 (CM4: Pre-Commissioning Test for Digestion Pre-treatment Facility, Sidestream Nitrogen Removal Facility and Pipe Rack) (5 Oct 2025) " | 2025-09-23 | 2025-10-15 |  |  | Vincent | 0 | 1
001687 | Hookup Drawing -Thermal Flow Switch | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | 2025-12-10 |  |  | Yean Yee | A | 1
001687 | Hookup Drawing -Thermal Flow Switch | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | 2025-12-10 |  |  | Yean Yee | A | 1
001687 | Hookup Drawing -Thermal Flow Switch | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | 2025-12-10 |  |  | Yean Yee | A | 1
001687 | Hookup Drawing -Thermal Flow Switch | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | 2025-12-10 |  |  | Yean Yee | A | 1
001687 | Hookup Drawing -Thermal Flow Switch | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | 2025-12-10 |  |  | Yean Yee | A | 1
001688 | Notice for Extension of Time and Cost for Delays in Site Wide Pipe Rack Approvals for ST 603-621 Submissions Amongst Other Delays | "Notice for Extension of Time and Cost for Delays in Site Wide Pipe Rack Approvals for ST 603-621 Submissions Amongst Other Delays" | 2025-09-23 | 2026-02-24 |  |  | Vincent | 0 | 1
001689 | FAT Report for Manual Knife Gate Valves - Batch 3 (JASH) | "FAT Report for Manual Knife Gate Valves - Batch 3 (JASH)" | 2025-09-24 | 2026-01-30 |  |  | Danny | 0 | 1
001690 | Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd. | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." | 2025-09-24 | 2025-10-13 |  |  | Yuen Fatt | 0 | 1
001691 | Hookup Drawing - Hydrostatic Level Switch | "Hookup Drawing - Hydrostatic Level Switch" | 2025-09-24 | 2025-12-11 |  |  | Yean Yee | A | 1
001691 | Hookup Drawing - Hydrostatic Level Switch | "Hookup Drawing - Hydrostatic Level Switch" | 2025-09-24 | 2025-12-11 |  |  | Yean Yee | A | 1
001691 | Hookup Drawing - Hydrostatic Level Switch | "Hookup Drawing - Hydrostatic Level Switch" | 2025-09-24 | 2025-12-11 |  |  | Yean Yee | A | 1
001692 | Datasheet for Pressure Transmitter (SSN) | "Datasheet for Pressure Transmitter (SSN)" | 2025-09-24 | 2025-10-23 |  |  | Yean Yee | 0 | 1
001693 | Hookup Drawing for Pressure Transmitter | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | 2025-12-10 |  |  | Yean Yee | A | 1
001693 | Hookup Drawing for Pressure Transmitter | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | 2025-12-10 |  |  | Yean Yee | A | 1
001693 | Hookup Drawing for Pressure Transmitter | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | 2025-12-10 |  |  | Yean Yee | A | 1
001693 | Hookup Drawing for Pressure Transmitter | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | 2025-12-10 |  |  | Yean Yee | A | 1
001694 | Datasheet for Pressure Switch (SSN) | "Datasheet for Pressure Switch (SSN)" | 2025-09-24 | 2025-12-15 |  |  | Yean Yee | 0 | 1
001695 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | 2025-09-25 | 2026-01-07 |  |  | Mohan | 1 | 3
001696 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | 2025-09-25 | 2025-10-01 |  |  | Mohan | 1 | 3
001697 | FAT Report for Actuated Ball Valves (OVS/Rotork) | "FAT Report for Actuated Ball Valves (OVS/Rotork)" | 2025-09-25 | 2026-01-07 |  |  | Mohan | 1 | 2
001698 | Shop drawing for Cat ladders at SSN Area and Electrical Building | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-09-26 | 2025-11-10 |  |  | Aaron | A.5 | 7
001698 | Shop drawing for Cat ladders at SSN Area and Electrical Building | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-09-26 | 2025-11-10 |  |  | Aaron | A.5 | 3
001698 | Shop drawing for Cat ladders at SSN Area and Electrical Building | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-09-26 | 2025-11-10 |  |  | Aaron | A.5 | 3
001698 | Shop drawing for Cat ladders at SSN Area and Electrical Building | "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-09-26 | 2025-11-10 |  |  | Aaron | A.5 | 3
001699 | ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" | 2025-09-26 | 2025-10-13 |  |  | Kumar | 0 | 1
001700 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-09-29 | 2025-10-14 |  |  | Aaron | A | 2
001700 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-09-29 | 2025-10-14 |  |  | Aaron | A.5 | 3
001700 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-09-29 | 2025-10-14 |  |  | Aaron | A.5 | 7
001701 | THP PMS Panel GA and Wiring Diagram | "THP PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001701 | THP PMS Panel GA and Wiring Diagram | "THP PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001701 | THP PMS Panel GA and Wiring Diagram | "THP PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001701 | THP PMS Panel GA and Wiring Diagram | "THP PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001701 | THP PMS Panel GA and Wiring Diagram | "THP PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001702 | SSN PMS Panel GA and Wiring Diagram | "SSN PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001702 | SSN PMS Panel GA and Wiring Diagram | "SSN PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001702 | SSN PMS Panel GA and Wiring Diagram | "SSN PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001702 | SSN PMS Panel GA and Wiring Diagram | "SSN PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001702 | SSN PMS Panel GA and Wiring Diagram | "SSN PMS Panel GA and Wiring Diagram" | 2025-09-29 | 2025-10-07 |  |  | Balaji | A | 1
001703 | SP Item - Flange Adaptor (Synchong Hoe) | "SP Item - Flange Adaptor (Synchong Hoe)" | 2025-09-29 |  |  |  | Liying | 0 | 1
001704 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss) | " Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss)" | 2025-09-29 | 2025-10-15 |  |  | Dhanapal | 0 | 1
001705 | Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN) | " Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN)" | 2025-09-30 | 2025-12-11 |  |  | Dhanapal | 0 | 1
001706 | FAT Report for Clamp Shoe Support, Stopper Support In Site Wide Pipe Rack | "FAT Report for Clamp Shoe Support, Stopper Support In Site Wide Pipe Rack" | 2025-09-30 | 2026-01-30 |  |  | Mohan | 0 | 1
001707 | FAT Report for Clamp Shoe Support in Site Wide Pipe Rack | "FAT Report for Clamp Shoe Support in Site Wide Pipe Rack" | 2025-09-30 | 2026-01-30 |  |  | Mohan | 0 | 1
001708 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025 | " Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025" | 2025-09-30 | 2025-10-13 |  |  | Kumar | 0 | 1
001709 | Unpriced PO for PDB & LCP (GSM) | "Unpriced PO for PDB & LCP (GSM) " | 2025-09-30 | 2025-12-11 |  |  | Caedan | 0 | 1
001710 | Unpriced PO for Earthing Material (Heng Hardware) | "Unpriced PO for Earthing Material (Heng Hardware) " | 2025-09-30 | 2025-11-05 |  |  | Caedan | 0 | 1
001711 | Unpriced PO for Power and Lighting Material (Hong An Engineering) | "Unpriced PO for Power and Lighting Material (Hong An Engineering)" | 2025-09-30 | 2025-11-10 |  |  | Caedan | 0 | 1
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "Testing Check List (Process)" && "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 2
001712 | T&C Check List | "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 1
001712 | T&C Check List | "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 1
001712 | T&C Check List | "T&C Check List " | 2025-09-30 | 2025-12-24 |  |  | Joo Kwan | 0 | 1
001713 | Data Sheet for SSN Sludge Comparment Mixing Nozzle | "Data Sheet for SSN Sludge Comparment Mixing Nozzle" | 2025-09-30 |  |  |  | Joo Kwan | 0 | 1
001714 | Commissioning Plan for Steam Line | "Commissioning Plan for Steam Line" | 2025-09-30 | 2026-01-06 |  |  | Joo Kwan | 0 | 1
001715 | Data Sheet for THP IA Pressure Reducing Valve | "Data Sheet for THP IA Pressure Reducing Valve " | 2025-09-30 | 2025-10-21 |  |  | Joo Kwan | 0 | 1
001716 | Extension of Time – CM4 Milestone | "Extension of Time – CM4 Milestone " | 2025-09-30 |  |  |  | Vincent | 0 | 1

## 2025-10
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000120 | Milestone 3 Sitewide Pipe Rack | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2025-10-08 | 2026-01-30 |  |  | Heng Peng | 1 | 4
000120 | Milestone 3 Sitewide Pipe Rack | "Milestone 3 Sitewide Pipe Rack" | 2025-10-08 | 2026-01-30 |  |  | Heng Peng | A | 1
000120 | Milestone 3 Sitewide Pipe Rack | "Milestone 3 Sitewide Pipe Rack" | 2025-10-08 | 2026-01-30 |  |  | Heng Peng | A | 1
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | 0 | 5
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 3
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | C | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | B | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000162 | Milestone 3 - SSN Pump Station and Blower Area | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | 2025-10-27 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 3
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | 1 | 4
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | 0 | 3
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000164 | Milestone 3 SSN Pump Station and Lamella Clarifier | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | A | 2
000219 | Building Services ACMV | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-10-29 | 2025-12-29 |  |  | Kyaw Myo | A.4 | 5
000219 | Building Services ACMV | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-10-29 | 2025-12-29 |  |  | Kyaw Myo | A.4 | 5
000219 | Building Services ACMV | "Building Services ACMV" | 2025-10-29 | 2025-12-29 |  |  | Kyaw Myo | A.4 | 4
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-10-29 | 2025-12-29 |  |  | Kyaw Myo | A.4 | 7
000219 | Building Services ACMV | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" | 2025-10-29 | 2025-12-29 |  |  | Kyaw Myo | A.4 | 7
000255 | Milestone 3 THP MCC Room | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2025-10-31 | 2026-02-23 |  |  | Heng Peng/ Muthu | 1 | 3
000260 | Milestone 3 SSN Overall Area | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | 2025-10-31 | 2026-01-27 |  |  | Heng Peng/ Muthu | 0 | 2
000291 | Milestone 3 THP EICA Silo Area inside Biosolid Building | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2025-10-28 | 2026-02-24 |  |  | Muthu | 1 | 4
000291 | Milestone 3 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2025-10-28 | 2026-02-24 |  |  | Muthu | A | 3
000291 | Milestone 3 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-10-28 | 2026-02-24 |  |  | Muthu | A | 5
000291 | Milestone 3 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-10-28 | 2026-02-24 |  |  | Muthu | A | 5
000291 | Milestone 3 THP EICA Silo Area inside Biosolid Building | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2025-10-28 | 2026-02-24 |  |  | Muthu | A | 3
000293 | Milestone 3 THP A100 Silo Area inside Biosolid Building | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2025-10-31 | 2026-02-20 |  |  | Heng Peng | 1 | 4
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | 1 | 4
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000294 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng/ Muthu | A | 2
000302 | Milestone 3 THP Compressed Air System | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2025-10-27 | 2026-02-23 |  |  | Heng Peng | 2 | 3
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 2
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Schematic Diagram" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 3
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" && "THP MCC Outline Drawing" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 5
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000570 | THP SLD | "THP SLD" | 2025-10-23 | 2026-02-02 |  |  | Freedomer | E | 6
000623 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " | 2025-10-08 | 2026-02-20 |  |  | Dhanapal | 5 | 6
000707 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2025-10-08 | 2026-02-20 |  |  | Radha | 2 | 3
000709 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2025-10-09 |  |  |  | Dhanapal | 2 | 3
000710 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2025-10-09 | 2026-02-20 |  |  | Dhanapal | 2 | 3
000763 | SSN Instrument List | "SSN Instrument List " | 2025-10-27 | 2026-01-26 |  |  | Yean Yee/ Low | 1 | 2
000813 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2025-10-23 | 2025-12-23 |  |  | Radha | 1 | 2
001167 | Datasheet for Electromagnetic Flow Meter | "Datasheet for Electromagnetic Flow Meter " | 2025-10-16 | 2025-11-27 |  |  | Yean Yee | 1 | 2
001171 | Datasheet for Level Transmitter | "Datasheet for Level Transmitter" | 2025-10-16 | 2025-11-05 |  |  | Yean Yee | 1 | 2
001172 | Datasheet & GA drawing for sampling pump | "Datasheet & GA drawing for sampling pump" | 2025-10-18 |  |  |  | David | 1 | 2
001172 | Datasheet & GA drawing for sampling pump | "Datasheet & GA drawing for sampling pump" | 2025-10-18 |  |  |  | David | B | 2
001173 | Datasheet for Temperature Transmitter | "Datasheet for Temperature Transmitter " | 2025-10-27 | 2025-12-09 |  |  | Yean Yee | 1 | 3
001179 | Datasheet for Pressure Transmitter | "Datasheet for Pressure Transmitter" | 2025-10-16 | 2025-12-02 |  |  | Yean Yee | 1 | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001206 | LCS GA and Schematic Drawing | "LCS GA and Schematic Drawing" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | C | 2
001219 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2025-10-07 | 2025-12-05 |  |  | Mohan | 3 | 4
001233 | SSN ICA Cable List | "SSN ICA Cable List " | 2025-10-28 | 2026-01-26 |  |  | Balaji | 1 | 2
001320 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " | 2025-10-01 |  |  |  | Radha | 1 | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 2
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 1
001328 | THP ICA GA & Wiring drawings | "THP ICA GA & Wiring drawings" | 2025-10-28 | 2025-10-12 |  |  | Balaji | B | 1
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" | 2025-10-27 | 2025-11-26 |  |  | Balaji | C | 2
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" | 2025-10-27 | 2025-11-26 |  |  | Balaji | C | 2
001333 | SSN Over All Network Archtecture Drawings | "SSN Over All Network Archtecture Drawings" | 2025-10-27 | 2025-11-26 |  |  | Balaji | C | 2
001407 | Steam Safety Relief Valve Datasheet | "Steam Safety Relief Valve Datasheet" | 2025-10-23 | 2026-01-07 |  |  | Joo Kwan | 1 | 2
001437 | Vendor Approval for Distribution Boards (GSM) | "Vendor Approval for Distribution Boards (GSM)" | 2025-10-01 | 2025-10-15 |  |  | Freedomer | 1 | 2
001438 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | 2025-10-01 | 2025-10-15 |  |  | Freedomer | 2 | 3
001547 | THP Overall Network Diagrams | "SSN Over All Network Archtecture Drawings" && " THP Overall Network Diagrams" | 2025-10-28 | 2025-11-26 |  |  | Balaji | A | 3
001547 | THP Overall Network Diagrams | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" | 2025-10-28 | 2025-11-26 |  |  | Balaji | B | 3
001547 | THP Overall Network Diagrams | " THP Overall Network Diagrams" | 2025-10-28 | 2025-11-26 |  |  | Balaji | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001560 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-10-01 | 2026-02-20 |  |  | Freedomer | B | 2
001581 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | 2025-10-06 | 2026-02-02 |  |  | Dhanapal | 2 | 3
001600 | QA/QC Report for Air Conditioning System | "QA/QC Report for Air Conditioning System" | 2025-10-13 |  |  |  | Mohan | 1 | 2
001601 | QA/QC Report for Mechanical Ventilation Fan | "QA/QC Report for Mechanical Ventilation Fan" | 2025-10-13 |  |  |  | Mohan | 1 | 2
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-10-18 |  |  |  | David Li | C | 3
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-10-18 |  |  |  | David Li | C | 3
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-10-18 |  |  |  | David Li | D | 3
001619 | GA drawing for Splitter Box | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-10-18 |  |  |  | David Li | D | 2
001621 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | 2025-10-01 | 2025-10-06 |  |  | Dhanapal | 0 | 3
001621 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | 2025-10-29 | 2026-02-24 |  |  | Dhanapal | 0 | 3
001635 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" | 2025-10-02 | 2025-10-10 |  |  | Dhanapal | 1 | 2
001684 | FAT Report for Diffuser System (Xylem) | "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" && "FAT Report for Diffuser System (Xylem)" | 2025-10-21 |  |  |  | Mohan | 1 | 3
001717 | FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight) | "Vendor Manufacturing Inspection Test Plan for Rotameter " && "FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight)" | 2025-10-01 | 2026-02-16 |  |  | Dhanapal | 0 | 2
001718 | SAT Procedure for MDB Panels (Sunlight) | "SAT Procedure for MDB Panels (Sunlight)" | 2025-10-01 | 2025-11-25 |  |  | Dhanapal | 0 | 1
001719 | Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd. | "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." | 2025-10-01 | 2025-10-08 |  |  | Yuen Fatt | 0 | 1
001720 | Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd. | "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." | 2025-10-01 | 2025-10-08 |  |  | Yuen Fatt | 0 | 1
001721 | G2D Line Surge Load Calculation Report | "G2D Line Surge Load Calculation Report " | 2025-10-03 | 2026-01-30 |  |  | NA | 0 | 1
001722 | FAT Report for & Operating Instructions for Air Flow Control Valve (Effektiv/Emile Egger & Cie SA) | "FAT Report for & Operating Instructions for Air Flow Control Valve (Effektiv/Emile Egger & Cie SA)" | 2025-10-06 | 2025-10-22 |  |  | Mohan | 0 | 1
001723 | SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team) | "SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team)" | 2025-10-06 | 2025-10-13 |  |  | Kumar | 0 | 1
001724 | FAT Report for MCC Panels WSD11-MCC-0001 A & B (Sunlight) | "FAT Report for MCC Panels WSD11-MCC-0001 A & B (Sunlight)" | 2025-10-06 | 2026-02-09 |  |  | Dhanapal | 0 | 1
001725 | Factory Acceptance Test Report for Electromagnetic Flow Transmitter (THP) | "Factory Acceptance Test Report for Electromagnetic Flow Transmitter (THP)" | 2025-10-06 | 2025-12-10 |  |  | Dhanapal | 0 | 1
001726 | Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP) | "Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP)" | 2025-10-06 | 2025-12-10 |  |  | Dhanapal | 0 | 1
001727 | SAT Report for WSD11-MCC-0101A & WSD11-MCC-0101B | "SAT Report for WSD11-MCC-0101A & WSD11-MCC-0101B" | 2025-10-06 | 2026-02-09 |  |  | Dhanapal | 0 | 1
001728 | ST617 THP-PF-02 Fabrication Drawing (PE Endorsed) | "ST617 THP-PF-02 Fabrication Drawing (PE Endorsed)" | 2025-10-08 | 2025-11-24 |  |  | Aaron | NA | 1
001729 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | 2026-01-02 |  |  | Aaron | A | 2
001729 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | 2026-01-02 |  |  | Aaron | A | 2
001729 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | 2026-01-02 |  |  | Aaron | A | 1
001729 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | 2026-01-02 |  |  | Aaron | A | 2
001729 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | 2026-01-02 |  |  | Aaron | A | 2
001729 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | 2026-01-02 |  |  | Aaron | A | 1
001730 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-10-08 | 2026-01-02 |  |  | Aaron | H | 4
001730 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-10-08 | 2026-01-02 |  |  | Aaron | H | 2
001730 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-10-08 | 2026-01-02 |  |  | Aaron | F | 4
001731 | VCM Submission for 2025-09 | "VCM Submission for 2025-09" | 2025-10-08 | 2025-10-29 |  |  | Heng Peng | 0 | 1
001732 | SSN and THP Local Control Station (LCS) Components Datasheet | "SSN and THP Local Control Station (LCS) Components Datasheet" | 2025-10-08 | 2026-02-24 |  |  | Freedomer | 0 | 1
001733 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | "Shop Drawing for SWPR-03 Platform A&B Cat ladder" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-10-09 | 2025-10-14 |  |  | Aaron | A.3 | 3
001734 | THP-PF01 Grating Fabrication Drawing | "THP-PF01 Grating Fabrication Drawing" | 2025-10-09 | 2025-11-13 |  |  | Aaron | NA | 1
001735 | Preliminary Design and Vendor Approval – Hose Point | "Preliminary Design and Vendor Approval – Hose Point" | 2025-10-10 | 2025-11-24 |  |  | David | 0 | 1
001736 | Line List for Hydrotest (CA system) | "Line List for Hydrotest (CA system)" | 2025-10-10 | 2025-11-24 |  |  | K Balaji | 0 | 1
001737 | C4B Monthly Progress Report Number No. 29 (09 25) | "C4B Monthly Progress Report Number No. 29 (09 25)" | 2025-10-11 | 2025-11-27 |  |  | Htet Nu | 0_VOID | 2
001738 | FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) | "FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) " | 2025-10-13 |  |  |  | Mohan | 0 | 1
001739 | FAT report for Steam Jet Heater (Steam Sparger) | "FAT report for Steam Jet Heater (Steam Sparger) " | 2025-10-13 |  |  |  | Mohan | 0 | 1
001740 | Datasheet for ACMV Equipment | "Datasheet for ACMV Equipment" | 2025-10-13 | 2025-10-22 |  |  | Yuen Fatt | 0 | 1
001741 | FAT Report for Lamella Clarifier Biomass Separator (ARS-1) | "FAT Report for Lamella Clarifier Biomass Separator (ARS-1)" | 2025-10-13 | 2025-10-30 |  |  | Mohan | 0 | 1
001742 | FAT Report for Lamella Clarifier Biomass Separator (ARS-2) | "FAT Report for Lamella Clarifier Biomass Separator (ARS-2)" | 2025-10-13 | 2025-10-30 |  |  | Mohan | 0 | 1
001743 | FAT Report for Lamella Clarifier Biomass Separator (ARS-3) | "FAT Report for Lamella Clarifier Biomass Separator (ARS-3)" | 2025-10-13 | 2025-10-30 |  |  | Mohan | 0 | 1
001744 | FAT Report for Lamella Clarifier Biomass Separator (ARS-4) | "FAT Report for Lamella Clarifier Biomass Separator (ARS-4) " | 2025-10-13 | 2025-10-30 |  |  | Mohan | 0 | 1
001745 | Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal) | "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" | 2025-10-13 | 2025-10-23 |  |  | Kumar | 0 | 1
001746 | C4B Monthly Progress Report Number No. 29 (09 25) | "C4B Monthly Progress Report Number No. 29 (09 25)" | 2025-10-13 | 2025-10-17 |  |  | Jeline | 0_VOID | 2
001747 | FAT Report for LCS panels WST02-401-LCS-P-0101,W SD11-111-LCS-P-0101,W ST02-201-LCS-P-0101, WSR02-204-LC-P-0102-(Sunlight) | "FAT Report for LCS panels WST02-401-LCS-P-0101,W SD11-111-LCS-P-0101,W ST02-201-LCS-P-0101, WSR02-204-LC-P-0102-(Sunlight)" | 2025-10-14 | 2025-11-27 |  |  | Dhanapal | 0 | 1
001748 | Payment Claim No. 27 | "Payment Claim No. 27" | 2025-10-16 | 2025-11-13 |  |  | Yi Hao | 0 | 1
001749 | Line List for Hydrotest (Sitewide PipeRack) | "Sidewide Piperack Line List" && "Line List for Hydrotest (Sitewide PipeRack)" | 2025-10-16 | 2025-11-24 |  |  | K Balaji | 0 | 2
001750 | Line List for Hydrotest (Biosolid Building) | "Line List for Hydrotest (Biosolid Building)" | 2025-10-16 | 2025-11-24 |  |  | K Balaji | 0 | 1
001751 | Line List for Hydrotest (THP Courtyard - Interconnecting Pipe Rack) | "Line List for Hydrotest (THP Courtyard - Interconnecting Pipe Rack)" | 2025-10-16 | 2025-11-24 |  |  | K Balaji | 0 | 1
001752 | Line List for Hydrotest (THP Courtyard - Cooler Platforms) | "Line List for Hydrotest (THP Courtyard - Cooler Platforms)" | 2025-10-16 | 2025-11-24 |  |  | K Balaji | 0 | 1
001753 | Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | "Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG" | 2025-10-16 |  |  |  | Vincent | 0 | 1
001754 | Blower Aeration Air Piping Stress Calculation Report | "Blower Aeration Air Piping Stress Calculation Report" | 2025-10-18 |  |  |  | David | 0 | 1
001755 | O&M Manual for Hyperbolic Mixer | "O&M Manual for Hyperbolic Mixer" | 2025-10-18 |  |  |  | Yibo | 0 | 1
001756 | Preliminary Design And Vendor Approval For Chute | "Preliminary Design And Vendor Approval For Chute" | 2025-10-18 | 2025-11-24 |  |  | Yibo | 0 | 1
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001 SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001 SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001 SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001 SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001 SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-10 |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-20 |  |  | Freedomer | B | 2
001766 | THP UPSDB-0101A SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-10-24 |  |  | Freedomer | B | 3
001766 | THP UPSDB-0101A SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-10-24 |  |  | Freedomer | B | 3
001766 | THP UPSDB-0101A SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-10-24 |  |  | Freedomer | B | 3
001766 | THP UPSDB-0101A SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-10-24 |  |  | Freedomer | B | 3
001766 | THP UPSDB-0101A SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-10-24 |  |  | Freedomer | B | 3
001766 | THP UPSDB-0101A SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-10-24 |  |  | Freedomer | B | 3
001767 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001768 | THP UPSDB-0106 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001768 | THP UPSDB-0106 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001768 | THP UPSDB-0106 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001768 | THP UPSDB-0106 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001768 | THP UPSDB-0106 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-12-11 |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-27 |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-27 |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-27 |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-27 |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | 2025-11-27 |  |  | Freedomer | B | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001770 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | A | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-27 |  |  | Freedomer | B | 2
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-12-09 |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-12-09 |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-12-09 |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-12-09 |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-12-09 |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-12-09 |  |  | Freedomer | B | 3
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-20 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-20 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-20 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-20 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-20 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-20 |  |  | Freedomer | B | 4
001775 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-10-24 |  |  | Freedomer | B | 4
001775 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-10-24 |  |  | Freedomer | B | 4
001775 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-10-24 |  |  | Freedomer | B | 4
001775 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-10-24 |  |  | Freedomer | B | 4
001775 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-10-24 |  |  | Freedomer | B | 4
001775 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-10-24 |  |  | Freedomer | B | 4
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2025-10-23 | 2025-11-10 |  |  | Freedomer | A | 3
001778 | SSN Functional Design Specification Workshop | "SSN Functional Design Specification Workshop" | 2025-10-23 | 2026-01-12 |  |  | Joo Kwan | 0 | 1
001779 | GA for Steam Strainer | "GA for Steam Strainer" | 2025-10-23 |  |  |  | Joo Kwan | 0 | 1
001780 | GA for Steam Relief Valve | "GA for Steam Relief Valve" | 2025-10-23 |  |  |  | Joo Kwan | 0 | 1
001781 | ST617 THP-PF-01 TOS 15.875 Grating Fabrication Drawing (PE endorsement) | "ST617 THP-PF-01 TOS 15.875 Grating Fabrication Drawing (PE endorsement)" | 2025-10-23 | 2025-12-17 |  |  | Aaron | NA | 1
001782 | Hookup Drawing - Pressure Gauge | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001782 | Hookup Drawing - Pressure Gauge | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001782 | Hookup Drawing - Pressure Gauge | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001782 | Hookup Drawing - Pressure Gauge | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001782 | Hookup Drawing - Pressure Gauge | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001783 | Hookup Drawing - Rotameter | "Hookup Drawing - Rotameter" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001783 | Hookup Drawing - Rotameter | "Hookup Drawing - Rotameter" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001784 | Hookup Drawing - Capacitive Level Switch | "Hookup Drawing - Capacitive Level Switch" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001784 | Hookup Drawing - Capacitive Level Switch | "Hookup Drawing - Capacitive Level Switch" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001784 | Hookup Drawing - Capacitive Level Switch | "Hookup Drawing - Capacitive Level Switch" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001785 | Hookup Drawing - Conductivity Analyser | "Hookup Drawing - Conductivity Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001785 | Hookup Drawing - Conductivity Analyser | "Hookup Drawing - Conductivity Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001786 | Hookup Drawing - DO Analyser | "Hookup Drawing - DO Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001786 | Hookup Drawing - DO Analyser | "Hookup Drawing - DO Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001787 | Hookup Drawing - pH Analyser | "Hookup Drawing - pH Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001787 | Hookup Drawing - pH Analyser | "Hookup Drawing - pH Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001787 | Hookup Drawing - pH Analyser | "Hookup Drawing - pH Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001788 | Hookup Drawing -TSS Analyser | "Hookup Drawing -TSS Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001788 | Hookup Drawing -TSS Analyser | "Hookup Drawing -TSS Analyser" | 2025-10-23 | 2025-12-15 |  |  | Yean Yee | A | 1
001789 | ST617 THP-PF-01 Shop Drawing - Additional Grating Support Beams At TOS 15.875 | "ST617 THP-PF-01 Shop Drawing - Additional Grating Support Beams At TOS 15.875" | 2025-10-24 | 2025-12-19 |  |  | Aaron | A | 1
001790 | ST617 THP-PF-01 Platform & Railing Fab Drawings (PE Endrosed) | "ST617 THP-PF-01 Platform & Railing Fab Drawings (PE Endrosed)" | 2025-10-24 | 2025-12-09 |  |  | Aaron | A | 1
001791 | Rectangular Bellow Drawing | "Rectangular Bellow Drawing" | 2025-10-27 | 2025-11-24 |  |  | Yibo | A | 1
001792 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager) | "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" | 2025-10-27 | 2025-12-11 |  |  | Yuen Fatt | 0 | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2025-10-27 | 2025-12-11 |  |  | Karthik | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2025-10-27 | 2025-12-11 |  |  | Karthik | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2025-10-27 | 2025-12-11 |  |  | Karthik | A | 1
001794 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Distribution Board (GSM) | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Distribution Board (GSM)" | 2025-10-27 | 2026-02-02 |  |  | Dhanapal | 0 | 1
001795 | SSN Master Blower HMI Graphic List and Graphic Screen | "SSN Master Blower HMI Graphic List and Graphic Screen" | 2025-10-28 | 2025-12-09 |  |  | Balaji | 0 | 1
001796 | MSRA, SWP for ACMV System works | "MSRA, SWP for ACMV System works" | 2025-10-28 |  |  |  | Bryan | 0 | 1
001797 | MSRA for MCCB Replacement Works | "MSRA for MCCB Replacement Works" | 2025-10-28 | 2026-02-02 |  |  | Bryan | 0 | 1
001798 | MSRA, SWP for FRP Tanks Defect Repair Lamination Works | "MSRA, SWP for FRP Tanks Defect Repair Lamination Works " | 2025-10-28 | 2025-12-29 |  |  | Bryan | 0 | 1
001799 | Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM) | "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | 2025-10-29 | 2026-02-20 |  |  | Dhanapal | 0 | 1
001800 | Unpriced PO for Valve for Condensate System (Spirax Sarco) | "Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng)" && "Unpriced PO for Valve for Condensate System (Spirax Sarco)" | 2025-10-31 | 2025-11-24 |  |  | Caedan | 0 | 2
001801 | Unpriced PO for Manual Lifting Equipment (Growa) | "Unpriced PO for Manual Lifting Equipment (Growa)" | 2025-10-31 |  |  |  | Caedan | 0 | 1
001802 | Shop Drawing for THP-PF-01 & 02 Cat ladders | "Shop Drawing for THP-PF-01 & 02 Cat ladders " | 2025-10-31 | 2026-01-12 |  |  | Aaron | A | 1
001803 | Shop Drawing for SSN Area and Electrical Building Cat ladders | "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-10-31 | 2026-01-12 |  |  | Aaron | A | 1
001804 | THP Functional Design Specification Workshop | "THP Functional Design Specification Workshop" | 2025-10-31 | 2026-02-09 |  |  | Joo Kwan | 0 | 1
001805 | CV of Team Member (ECO) | "CV of Team Member (ECO)" | 2025-10-31 | 2025-12-10 |  |  | Htet Nu | 0 | 1
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-11-27 |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-11-27 |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-11-27 |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-11-27 |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-11-27 |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 3
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 3
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 3
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-09 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 3
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001811 | MSRA & Safe Work Procedure For NDT Activities | "MSRA & Safe Work Procedure For NDT Activities" | 2025-10-31 | 2025-12-29 |  |  | Bryan | 0 | 1
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | A | 1
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-17 |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-17 |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-17 |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-17 |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-17 |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | 2025-12-11 |  |  | Freedomer | B | 2

## 2025-11
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | 0 | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A1 | 4
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 4
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 4
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 4
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | C | 8
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | B | 5
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 3
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A | 2
000292 | Milestone 3 THP Overall & Equipment Layout | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2025-11-28 |  |  |  | Heng Peng/ Muthu | A.1 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2025-11-17 | 2025-12-17 |  |  | Aaron/HP | A.4 | 7
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 7
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.2 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2025-11-18 | 2025-12-17 |  |  | Zora/HP | A.4 | 3
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.2 | 3
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-11-07 | 2025-12-02 |  |  | Aaron | A.2 | 6
000645 | SSN Lux Simulation Report | "SSN Lux Simulation Report" | 2025-11-20 | 2025-12-17 |  |  | Freedomer | 3 | 4
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2025-11-21 | 2025-12-04 |  |  | Yuen Fatt | A.2 | 4
000833 | SSN Door Window Schedule | "SSN Door Window Schedule" | 2025-11-21 | 2025-12-04 |  |  | Yuen Fatt | A.2 | 2
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001176 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-11-17 | 2025-12-16 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 4
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001177 | SSN Panel RIO-204 - GA & Schematic Drawings | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.4 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A | 3
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.1 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-11-18 | 2025-12-17 |  |  | Aaron | A.2 | 4
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001191 | SSN Panel RIO-205 - GA & Schematic Drawings | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" | 2025-11-17 | 2026-01-27 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001192 | SSN RIO-206 - GA & Schematic Drawings | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001193 | SSN Panel (RIO-207) - GA & Schematic Drawings | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001194 | SSN Panel RIO-208 - GA & Schematic Drawings | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" | 2025-11-17 | 2025-12-15 |  |  | Balaji | B | 3
001195 | Manual Butterfly Valve | "Manual Butterfly Valve " | 2025-11-26 |  |  |  | Joo Kwan | 2 | 3
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 2
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 1
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 1
001230 | THP WAP FFOTP_GA & Wiring Diagram | "THP WAP FFOTP_GA & Wiring Diagram" | 2025-11-11 | 2025-12-16 |  |  | Balaji | B | 1
001319 | Data Sheet and Drawing for Davit Crane | "Data Sheet and Drawing for Davit Crane" | 2025-11-26 |  |  |  | Yibo | B | 2
001319 | Data Sheet and Drawing for Davit Crane | "Data Sheet and Drawing for Davit Crane" | 2025-11-26 |  |  |  | Yibo | B | 2
001353 | Vendor Approval of SSN Package - Magnetic Level Gauge | "Vendor Approval of SSN Package - Magnetic Level Gauge" | 2025-11-05 | 2025-11-26 |  |  | Yean Yee | 1 | 2
001359 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " | 2025-11-13 | 2025-12-29 |  |  | Dhanapal | 2 | 3
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2025-11-21 | 2025-12-11 |  |  | Yuen Fatt | 1 | 2
001403 | FAT Report for Chemical Dosing Pumps (PROMINENT) | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-11-10 | 2025-12-23 |  |  | Radha | 3 | 4
001459 | Valve Chamber Design for SSN- Portable Water Line | "Valve Chamber Design for SSN- Portable Water Line" | 2025-11-28 | 2026-01-15 |  |  | Aaron | NA | 2
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 4
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 4
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 2
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 2
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-11-07 | 2025-11-24 |  |  | Aaron | A.6 | 3
001564 | Factory Acceptance Test Report for Fire Alarm System | "Factory Acceptance Test Report for Fire Alarm System " | 2025-11-27 |  |  |  | Dhanapal | 1 | 2
001586 | SWPR _Platform A and B- Cat ladders | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | 2026-01-08 |  |  | Aaron | A.3 | 1
001586 | SWPR _Platform A and B- Cat ladders | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | 2026-01-08 |  |  | Aaron | A.3 | 1
001586 | SWPR _Platform A and B- Cat ladders | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | 2026-01-08 |  |  | Aaron | A.3 | 1
001586 | SWPR _Platform A and B- Cat ladders | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | 2026-01-08 |  |  | Aaron | A.3 | 1
001586 | SWPR _Platform A and B- Cat ladders | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | 2026-01-08 |  |  | Aaron | B | 1
001604 | Shop Drawing for Louvre Door and Window | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | A.2 | 5
001604 | Shop Drawing for Louvre Door and Window | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | A.2 | 4
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 1 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 1 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 0 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 0 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 1 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 0 | 1
001604 | Shop Drawing for Louvre Door and Window | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | 2025-12-04 |  |  | Yuen Fatt | 0 | 1
001640 | HDG Grating Clamp Details | "HDG Grating Clamp Details" | 2025-11-05 | 2025-11-13 |  |  | Aaron | NA | 1
001640 | HDG Grating Clamp Details | "HDG Grating Clamp Details" | 2025-11-24 | 2025-12-29 |  |  | Aaron | NA | 1
001733 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | "Shop Drawing for SWPR-03 Platform A&B Cat ladder" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-11-06 | 2026-01-12 |  |  | Aaron | A.3 | 3
001733 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-11-06 | 2026-01-12 |  |  | Aaron | A.6 | 4
001733 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-11-06 | 2026-01-12 |  |  | Aaron | A.3 | 1
001733 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2025-11-06 | 2026-01-12 |  |  | Aaron | A.3 | 1
001819 | FAT Report for Lamella Clarifier Biomass Separator (ARS-5) | "FAT Report for Lamella Clarifier Biomass Separator (ARS-5)" | 2025-11-04 |  |  |  | Mohan | 0 | 1
001820 | Data Sheet for SSN IA Pressure Reducing Valve | "Data Sheet for SSN IA Pressure Reducing Valve " | 2025-11-05 |  |  |  | Joo Kwan | 0 | 1
001821 | FAT Report for SS 316L Pipes - 32 Nos | "FAT Report for SS 316L Pipes - 32 Nos" | 2025-11-05 | 2026-01-30 |  |  | Mohan | 0 | 1
001822 | Hookup Drawing - Autosampler | "Hookup Drawing - Autosampler" | 2025-11-05 |  |  |  | Yean Yee | 0 | 1
001823 | FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" | 2025-11-05 | 2026-02-09 |  |  | Mohan | 0 | 1
001824 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | "FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite)" | 2025-11-05 | 2026-01-30 |  |  | Mohan | 1 | 2
001825 | FAT Report for SS 316L Pipes - 21 Nos | "FAT Report for SS 316L Pipes - 21 Nos" | 2025-11-06 | 2026-01-30 |  |  | Mohan | 0 | 1
001826 | FAT Report for SS 316L Pipes - 40 Nos | "FAT Report for SS 316L Pipes - 40 Nos" | 2025-11-06 | 2026-01-30 |  |  | Mohan | 0 | 1
001827 | Shop Drawing for SWPR-Platform A & B_Railing (PE Endorsed) | "Shop Drawing for SWPR-Platform A & B_Railing (PE Endorsed)" | 2025-11-06 | 2026-01-02 |  |  | Aaron | A | 1
001828 | Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+) | "Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+)" | 2025-11-06 |  |  |  | Mohan | 0 | 1
001829 | FAT Report for (CWP 204 ) SS 316L Pipes - 88 Pcs | "FAT Report for (CWP 204 ) SS 316L Pipes - 88 Pcs" | 2025-11-06 | 2026-01-30 |  |  | Mohan | 0 | 1
001830 | Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" | 2025-11-07 | 2025-12-24 |  |  | Kumar | 0 | 1
001831 | VCM Submission for 2025-10 | "VCM Submission for 2025-10" | 2025-11-10 | 2025-12-02 |  |  | Hang Peng | 0 | 1
001832 | FAT Report & Mill Test Certificates for Hyperbolic Mixer | "FAT Report & Mill Test Certificates for Hyperbolic Mixer" && "Material & Test Certificates for Blower's Encapsulation " | 2025-11-10 | 2026-01-30 |  |  | Mohan | 0 | 2
001833 | Material & Test Certificates for Blower's Encapsulation | "FAT Report & Mill Test Certificates for Hyperbolic Mixer" && "Material & Test Certificates for Blower's Encapsulation " | 2025-11-10 |  |  |  | Mohan | 0 | 2
001834 | FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets | "FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets" | 2025-11-11 |  |  |  | Mohan | 0 | 1
001835 | Payment Claim No.28 | "Payment Claim No.28" | 2025-11-11 | 2025-12-10 |  |  | Yi Hao | 0 | 1
001836 | FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area | "FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area" | 2025-11-11 |  |  |  | Mohan | 0 | 1
001837 | FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area | "FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area" | 2025-11-11 |  |  |  | Mohan | 0 | 1
001838 | FAT Report for SS 316L Pipes for streamline-55 pcs | "FAT Report for SS 316L Pipes for streamline-55 pcs" | 2025-11-12 |  |  |  | Mohan | 0 | 1
001839 | FAT Report for ARI-Armaturen Safety Valve - (OVS) | "FAT Report for ARI-Armaturen Safety Valve - (OVS) " | 2025-11-12 |  |  |  | Mohan | 0 | 1
001840 | FAT document for SSN Blower PLC/RIO Panels | "FAT document for SSN Blower PLC/RIO Panels" | 2025-11-12 | 2025-12-11 |  |  | Dhanapal | 0 | 1
001841 | FAT Report for Carbon Steel Pipe Support | "FAT Report for Carbon Steel Pipe Support" | 2025-11-13 |  |  |  | Mohan | 0 | 1
001842 | FAT Report for Motorized Steam Ball Valves (OVS/Rotork) | "FAT Report for Motorized Steam Ball Valves (OVS/Rotork)" | 2025-11-14 |  |  |  | Mohan | 0 | 1
001843 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | 2026-02-27 |  |  | Yi Bo | A | 1
001843 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | 2026-02-27 |  |  | Yi Bo | A | 1
001843 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | 2026-02-27 |  |  | Yi Bo | A | 1
001843 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | 2026-02-27 |  |  | Yi Bo | A | 1
001843 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | 2026-02-27 |  |  | Yi Bo | A | 1
001843 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | 2026-02-27 |  |  | Yi Bo | A | 1
001844 | Hookup Drawing -Thermal Mass Flowmeter | "Hookup Drawing -Thermal Mass Flowmeter" | 2025-11-18 | 2025-12-15 |  |  | Yean Yee | A | 1
001844 | Hookup Drawing -Thermal Mass Flowmeter | "Hookup Drawing -Thermal Mass Flowmeter" | 2025-11-18 | 2025-12-15 |  |  | Yean Yee | A | 1
001844 | Hookup Drawing -Thermal Mass Flowmeter | "Hookup Drawing -Thermal Mass Flowmeter" | 2025-11-18 | 2025-12-15 |  |  | Yean Yee | A | 1
001845 | Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks | "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2025-11-18 | 2026-01-02 |  |  | Kumar | 0 | 1
001846 | FAT Procedure for Portable A Frame & T-Davit (Growa) | "FAT Procedure for Portable A Frame & T-Davit (Growa)" | 2025-11-18 |  |  |  | Mohan | 0 | 1
001847 | Method Statement for the Installation of Fine Bubble Diffuser | "Method Statement for the Installation of Fine Bubble Diffuser" | 2025-11-18 | 2025-12-23 |  |  | K Balaji | 0 | 1
001848 | Notice For Extension Of Time And Cost For Delays For Power Turn On | "Notice For Extension Of Time And Cost For Delays For Power Turn On" | 2025-11-19 |  |  |  | Vincent | 0 | 1
001849 | C4B Monthly Progress Report Number No. 30 (10 25) | "C4B Monthly Progress Report Number No. 30 (10 25)" | 2025-11-19 | 2026-02-23 |  |  | Htet Nu | 0 | 1
001850 | Detailed Design PVC Strainer Data Sheet | "Detailed Design PVC Strainer Data Sheet" | 2025-11-19 |  |  |  | Joo Kwan | 0 | 1
001851 | Detailed Design SS316 Strainer Data Sheet | "Detailed Design SS316 Strainer Data Sheet" | 2025-11-19 |  |  |  | Joo Kwan | 0 | 1
001852 | Datat Sheet & Drawing for Portable A-Frame | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 |  |  |  | Yibo | 0 | 1
001852 | Datat Sheet & Drawing for Portable A-Frame | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 |  |  |  | Yibo | 0 | 1
001852 | Datat Sheet & Drawing for Portable A-Frame | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 |  |  |  | Yibo | 0 | 1
001852 | Datat Sheet & Drawing for Portable A-Frame | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 |  |  |  | Yibo | 0 | 1
001852 | Datat Sheet & Drawing for Portable A-Frame | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 |  |  |  | Yibo | 0 | 1
001853 | Material & Test Certificates for Flange Adaptors (Synchong Hoe) | "Material & Test Certificates for Flange Adaptors (Synchong Hoe)" | 2025-11-20 |  |  |  | Mohan | 0 | 1
001854 | Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng) | "Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng)" | 2025-11-20 |  |  |  | Balaji | 0 | 1
001855 | Quarterly Risk Management Workshop 9th Quarterly RM Workshop – 31 Oct 2025 | "Quarterly Risk Management Workshop 9th Quarterly RM Workshop – 31 Oct 2025" | 2025-11-20 | 2025-12-23 |  |  | Max | 0 | 1
001856 | Safety Review Report for SSN Steel Structures and MEICA Equipment Installation | "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" | 2025-11-20 |  |  |  | Max | 0 | 1
001857 | FAT Report for NON Return Check Valve (Breen) | "FAT Report for NON Return Check Valve (Breen)" | 2025-11-20 |  |  |  | Soe Myat | 0 | 1
001858 | FAT Report for Sampling Sinks (4 units) | "FAT Report for Sampling Sinks (4 units)" | 2025-11-20 |  |  |  | Soe Myat | 0 | 1
001859 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | 2026-01-20 |  |  | Htet Nu | 0 | 1
001859 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | 2026-01-20 |  |  | Htet Nu | 0 | 1
001859 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | 2026-01-20 |  |  | Htet Nu | 0 | 1
001859 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | 2026-01-20 |  |  | Htet Nu | 0 | 1
001860 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" | 2025-11-24 | 2025-12-16 |  |  | Dhanapal | 1 | 2
001861 | Factory Acceptance Test Report for Pressure Switch | "Factory Acceptance Test Report for Pressure Switch" | 2025-11-24 | 2025-12-16 |  |  | Dhanapal | 1 | 2
001862 | FAT Report for THP Courtyard Area Pipe Supports (Less than 2m) | "FAT Report for THP Courtyard Area Pipe Supports (Less than 2m)" | 2025-11-24 |  |  |  | Mohan | 0 | 1
001863 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units | "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units" | 2025-11-25 |  |  |  | Mohan | 0 | 1
001864 | CSA Meeting Minutes 0052, 0053_07082025 & 21082025 | "CSA Meeting Minutes 0052, 0053_07082025 & 21082025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001864 | CSA Meeting Minutes 0052, 0053_07082025 & 21082025 | "CSA Meeting Minutes 0052, 0053_07082025 & 21082025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001865 | CSA Meeting Minutes 0054, 0055_04092025 & 18092025 | "CSA Meeting Minutes 0054, 0055_04092025 & 18092025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001865 | CSA Meeting Minutes 0054, 0055_04092025 & 18092025 | "CSA Meeting Minutes 0054, 0055_04092025 & 18092025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001866 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001866 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001866 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | 2025-11-26 | 2025-12-04 |  |  | Htet Nu | 0 | 1
001867 | SSN BMS Network Architecture Drawing | "SSN BMS Network Architecture Drawing" | 2025-11-26 |  |  |  | Balaji | A | 1
001868 | FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15) | "FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15)" | 2025-11-27 |  |  |  | Mohan | 0 | 1
001869 | Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd) | "Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd)" | 2025-11-27 | 2025-12-24 |  |  | Kumar | 0 | 1
001870 | Shop Drawing for SSN Biomass GI Railing - Rev A | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | 2026-02-12 |  |  | Aaron | A | 1
001870 | Shop Drawing for SSN Biomass GI Railing - Rev A | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | 2026-02-12 |  |  | Aaron | A | 1
001870 | Shop Drawing for SSN Biomass GI Railing - Rev A | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | 2026-02-12 |  |  | Aaron | A | 1
001870 | Shop Drawing for SSN Biomass GI Railing - Rev A | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | 2026-02-12 |  |  | Aaron | A | 1
001870 | Shop Drawing for SSN Biomass GI Railing - Rev A | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | 2026-02-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A | 1
001871 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | 2026-01-12 |  |  | Aaron | A.5 | 7
001872 | SSN- I/O List-BIO-0001 | "SSN- I/O List-BIO-0001 " | 2025-11-27 | 2025-12-29 |  |  | Balaji | 0 | 2
001873 | SSN- I/O List-BIO-0002 | "SSN- I/O List-BIO-0002 " | 2025-11-27 | 2025-12-29 |  |  | Balaji | 0 | 2
001874 | Incentive/ Disincentive Audit Scheme for Jul 2025 | "Incentive/ Disincentive Audit Scheme for Jul 2025" | 2025-11-28 | 2025-12-23 |  |  | Malon | 0 | 1
001875 | Incentive/ Disincentive Audit Scheme for Sept 2025 | "Incentive/ Disincentive Audit Scheme for Sept 2025" | 2025-11-28 | 2025-12-23 |  |  | Malon | 0 | 1
001876 | Commissioning Plan for Reactor and Blowers | " Commissioning Plan for Reactor and Blowers" | 2025-11-28 | 2026-01-02 |  |  | Joo Kwan | 0 | 1

## 2025-12
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-12-15 | 2026-02-02 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" | 2025-12-15 | 2026-02-02 |  |  | Freedomer | D | 5
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2025-12-15 | 2026-02-02 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" | 2025-12-15 | 2026-02-02 |  |  | Freedomer | D | 4
000160 | SSN Lighting Layout Plan | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" | 2025-12-15 | 2026-02-02 |  |  | Freedomer | D | 5
000163 | Milestone 3 SSN Water Tank | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | 2025-12-16 | 2026-01-27 |  |  | Heng Peng/ Muthu | 0 | 2
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-12-14 | 2026-02-02 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-12-14 | 2026-02-02 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-12-14 | 2026-02-02 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-12-14 | 2026-02-02 |  |  | Freedomer | C | 8
000218 | THP Lighting Layout Plan | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-12-14 | 2026-02-02 |  |  | Freedomer | C | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.2 | 3
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2025-12-03 | 2026-01-05 |  |  | Aaron | A.2 | 6
000644 | THP Lux Simulation Report | "THP Lux Simulation Report" | 2025-12-15 | 2026-02-02 |  |  | Freedomer | 2 | 4
000962 | FAT report for THP Train 1 (Part-1) | "FAT report for THP Train 1 (Part-1)" | 2025-12-08 | 2025-12-08 |  |  | Soe Myat | 3 | 4
000962 | FAT report for THP Train 1 (Part-1) | "FAT report for THP Train 1 (Part-1)" | 2025-12-08 | 2025-12-23 |  |  | Soe Myat | 3 | 4
000976 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-12-09 | 2025-12-23 |  |  | Soe Myat | 2 | 3
000983 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | 2025-12-02 | 2025-12-23 |  |  | Radha | 1 | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001166 | SSN Panel (FIOP) - GA & Wiring Drawings | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-12-15 | 2026-01-27 |  |  | Balaji | D | 2
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.4 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A | 3
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.1 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2025-12-23 | 2026-01-12 |  |  | Aaron | A.2 | 4
001227 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" | 2025-12-08 | 2026-02-20 |  |  | Bryan | 1 | 2
001229 | Datasheet for Tuning Fork Level Switch | "Datasheet for Tuning Fork Level Switch " | 2025-12-08 | 2026-02-09 |  |  | Yean Yee | 1 | 2
001250 | FAT report for THP Sludge cooler B Stage 1 | "FAT report for THP Sludge cooler B Stage 1" | 2025-12-02 | 2025-12-23 |  |  | Soe Myat | 1 | 2
001256 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" | 2025-12-04 | 2025-12-23 |  |  | Radha | 1 | 2
001261 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" | 2025-12-03 | 2025-12-23 |  |  | Radha | 1 | 2
001281 | FAT report for THP Sludge cooler D Stage 2 | "FAT report for THP Sludge cooler D Stage 2" | 2025-12-02 | 2025-12-23 |  |  | Radha | 1 | 2
001315 | FAT Report for THP Sludge Cooler C Stage 2 | "FAT Report for THP Sludge Cooler C Stage 2" | 2025-12-02 | 2025-12-23 |  |  | Radha | 1 | 2
001337 | Method Statement & Risk Assessment for Piping Installation at SWPR | "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2025-12-05 | 2025-12-29 |  |  | K Balaji | 1 | 2
001398 | MSRA, SWP for fire protection services | "MSRA, SWP for fire protection services " | 2025-12-04 | 2025-12-17 |  |  | Bryan | 2 | 3
001549 | Vendor Approval of Building Management System (BMS) (Willowglen) | "Vendor Approval of Building Management System (BMS) (Willowglen)" | 2025-12-04 | 2026-02-09 |  |  | Balaji | 2 | 3
001572 | THP Courtyard Sump Design (Updates) | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" | 2025-12-14 | 2026-01-08 |  |  | Aaron | A | 5
001572 | THP Courtyard Sump Design (Updates) | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" | 2025-12-14 | 2026-01-08 |  |  | Aaron | A | 4
001606 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | "Test Procedure for Pull & Push Load Test - Aluminium Handrail" | 2025-12-10 | 2025-12-17 |  |  | Radha | 2 | 3
001860 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" | 2025-12-18 |  |  |  | Dhanapal | 1 | 2
001877 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN" | 2025-12-02 |  |  |  | Dhanapal | 0 | 1
001878 | FAT Report for SS316L Pipes - G2D Line | " FAT Report for SS316L Pipes - G2D Line" | 2025-12-03 |  |  |  | Mohan | 0 | 1
001879 | Steam Piping Stress Calculation Report | "Steam Piping Stress Calculation Report" | 2025-12-04 |  |  |  | Franklin | 0 | 1
001880 | Payment Claim No.29 | "Payment Claim No.29" | 2025-12-04 |  |  |  | Yi Hao | 0 | 1
001881 | Standardize Support Design for Shelter 1 | "Standardize Support Design for Shelter 1" | 2025-12-05 | 2026-01-14 |  |  | Aaron | A | 1
001881 | Standardize Support Design for Shelter 1 | "Standardize Support Design for Shelter 1" | 2025-12-05 | 2026-01-14 |  |  | Aaron | A | 1
001881 | Standardize Support Design for Shelter 1 | "Standardize Support Design for Shelter 1" | 2025-12-05 | 2026-01-14 |  |  | Aaron | A | 1
001881 | Standardize Support Design for Shelter 1 | "Standardize Support Design for Shelter 1" | 2025-12-05 | 2026-01-14 |  |  | Aaron | A | 1
001881 | Standardize Support Design for Shelter 1 | "Standardize Support Design for Shelter 1" | 2025-12-05 | 2026-01-14 |  |  | Aaron | A | 1
001881 | Standardize Support Design for Shelter 1 | "Standardize Support Design for Shelter 1" | 2025-12-05 | 2026-01-14 |  |  | Aaron | A | 1
001882 | SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000 | "SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000" | 2025-12-08 |  |  |  | Balaji | 0 | 1
001883 | Datasheet for NO2 & NO3 (SSN) | "Datasheet for NO2 & NO3 (SSN)" | 2025-12-08 | 2026-02-12 |  |  | Yean Yee | 0 | 1
001884 | Datasheet for Ammonia Analyser (SSN) | "Datasheet for Ammonia Analyser (SSN)" | 2025-12-08 | 2026-02-12 |  |  | Yean Yee | 0 | 1
001885 | SAT Report for MDB Panels WST02-MDB-0001A & WST02-MDB-0001B | " SAT Report for MDB Panels WST02-MDB-0001A & WST02-MDB-0001B" | 2025-12-08 | 2026-02-24 |  |  | Dhanapal | 0 | 1
001886 | SAT Report for MCC Panels WST02-MCC-0101A & WST02-MCC-0101B | "SAT Report for MCC Panels WST02-MCC-0101A & WST02-MCC-0101B" | 2025-12-08 | 2026-02-24 |  |  | Dhanapal | 0 | 1
001887 | SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B | " SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B" | 2025-12-08 | 2026-02-24 |  |  | Dhanapal | 0 | 1
001888 | VCM Submission for 2025-11 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2025-12-08 | 2025-12-31 |  |  | Heng Peng | 0 | 4
001889 | FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX) | "FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX)" | 2025-12-09 | 2025-12-19 |  |  | Dhanapal | 0 | 1
001890 | FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX) | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-12-09 | 2025-12-19 |  |  | NA | VOID | 9
001891 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | 2025-12-09 |  |  |  | NA | 0 | 2
001892 | Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A” | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-12-12 |  |  |  | NA | VOID | 9
001893 | THP URA Amendment submissions | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 2
001893 | THP URA Amendment submissions | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 2
001893 | THP URA Amendment submissions | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 2
001893 | THP URA Amendment submissions | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 3
001893 | THP URA Amendment submissions | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 3
001893 | THP URA Amendment submissions | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 2
001893 | THP URA Amendment submissions | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 3
001893 | THP URA Amendment submissions | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2025-12-14 |  |  |  | NA | A | 3
001894 | Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" | 2025-12-15 | 2025-12-29 |  |  | Kumar | 0 | 1
001895 | G1 Booster Pump LCP Drawings | "G1 Booster Pump LCP Drawings" | 2025-12-15 | 2026-02-24 |  |  | Freedomer | A | 1
001895 | G1 Booster Pump LCP Drawings | "G1 Booster Pump LCP Drawings" | 2025-12-15 | 2026-02-24 |  |  | Freedomer | A | 1
001895 | G1 Booster Pump LCP Drawings | "G1 Booster Pump LCP Drawings" | 2025-12-15 | 2026-02-24 |  |  | Freedomer | A | 1
001895 | G1 Booster Pump LCP Drawings | "G1 Booster Pump LCP Drawings" | 2025-12-15 | 2026-02-24 |  |  | Freedomer | A | 1
001895 | G1 Booster Pump LCP Drawings | "G1 Booster Pump LCP Drawings" | 2025-12-15 | 2026-02-24 |  |  | Freedomer | A | 1
001895 | G1 Booster Pump LCP Drawings | "G1 Booster Pump LCP Drawings" | 2025-12-15 | 2026-02-24 |  |  | Freedomer | A | 1
001896 | ITP for Portable A Frame & T-Davit (Growa) | "ITP for Portable A Frame & T-Davit (Growa)" | 2025-12-15 |  |  |  | NA | 0 | 1
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 2
001897 | THP FOIP-0001 GA & Wiring Drawings | "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | 2026-02-09 |  |  | Balaji | A | 1
001898 | SSNR Master Control | "SSNR Master Control" | 2025-12-15 | 2026-02-16 |  |  | Joo Kwan | 0 | 1
001899 | C4B Monthly Progress Report Number No.31 (11 25) | "C4B Monthly Progress Report Number No.31 (11 25)" | 2025-12-16 |  |  |  | NA | 0 | 1
001900 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | 2025-12-16 | 2026-01-07 |  |  | Yuen Fatt | 0 | 1
001901 | Typical Fire Alarm Installation Detail (THP) | "Typical Fire Alarm Installation Detail (THP)" | 2025-12-16 | 2026-01-07 |  |  | NA | A | 1
001902 | Dry Riser Installation Details | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" | 2025-12-16 |  |  |  | NA | A1 | 4
001902 | Dry Riser Installation Details | "Dry Riser Installation Details" | 2025-12-16 |  |  |  | NA | A | 1
001902 | Dry Riser Installation Details | "THP-Dry Riser System" && "Dry Riser Installation Details" | 2025-12-16 |  |  |  | NA | A1 | 2
001903 | Datasheet for Magnetic Level Gauge (SSN) | "Datasheet for Magnetic Level Gauge (SSN)" | 2025-12-16 | 2026-02-12 |  |  | Yean Yee | 0 | 1
001904 | Hook-up drawing for PDSH for CAS (THP) | "Hook up Drawing for PDSH - CAS" && "Hook-up drawing for PDSH for CAS (THP)" | 2025-12-16 | 2026-02-12 |  |  | Yean Yee | B | 2
001905 | As Built Drawing for ST619 (THP Cooler Platform) | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-12-17 |  |  |  | NA | VOID | 9
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 1
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 3
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001906 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 |  |  |  | NA | X | 2
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001907 | As built drawing for ST621 (SWPR PR 01 & 02) | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 |  |  |  | NA | X | 1
001908 | SSN-Transformer Bay Gravel Sieve Analysis Report | "SSN-Transformer Bay Gravel Sieve Analysis Report" | 2025-12-18 | 2026-02-24 |  |  | Jun | 0 | 1
001909 | SAT Procedure for Public Address System | "SAT Procedure for Public Address System" | 2025-12-18 | 2026-01-07 |  |  | NA | 0 | 1
001910 | THP PF02 Grating Support Beam Fab Drawing_TOS 15.785m SHD (PE Endorsed) | "THP PF02 Grating Support Beam Fab Drawing_TOS 15.785m SHD (PE Endorsed)" | 2025-12-18 | 2026-01-12 |  |  | NA | NA | 1
001911 | Site Acceptance Test Procedure for Clean Gas System Panel | "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-12-18 | 2026-01-07 |  |  | NA | 0 | 1
001912 | ST Updates for SSN Staircase (ST607) | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | 2025-12-18 | 2026-02-04 |  |  | NA | A.6 | 4
001913 | THP RIO 0201 I/O List | "THP RIO 0201 I/O List" | 2025-12-18 | 2026-02-04 |  |  | Balaji | 0 | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | C | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | C | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | B.1 | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | A | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | H | 4
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | H | 2
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | C | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | C | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | F | 1
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | F | 4
001914 | SSN - Tank pipe support Anchor bolts embedment design drill depths | "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-12-18 | 2026-02-20 |  |  | Charles | E | 1
001915 | Data Sheet for Davit Arm and Mount Socket | "Data Sheet for Davit Arm and Mount Socket" | 2025-12-18 |  |  |  | Franklin | 0 | 1
001915 | Data Sheet for Davit Arm and Mount Socket | "Data Sheet for Davit Arm and Mount Socket" | 2025-12-18 |  |  |  | Franklin | 0 | 1
001916 | O&M Manual for A-Frame and T-Davit | "O&M Manual for A-Frame and T-Davit" | 2025-12-18 |  |  |  | NA | 0 | 1
001917 | Long term storage & Preservation procedure for A-Frame and T-Davit | "Long term storage & Preservation procedure for A-Frame and T-Davit" | 2025-12-18 |  |  |  | NA | 0 | 1
001918 | SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B) | "SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B)" | 2025-12-18 | 2026-02-24 |  |  | NA | 0 | 1
001919 | SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B | "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-12-18 | 2026-02-24 |  |  | NA | 0 | 1
001920 | SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B | "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-12-18 | 2026-02-23 |  |  | NA | 0 | 1
001921 | SAT Report for MDB Panels WST02-MDB-1001A & WST02-MDB-1001B | "SAT Report for MDB Panels WST02-MDB-1001A & WST02-MDB-1001B" | 2025-12-18 | 2026-02-24 |  |  | NA | 0 | 1
001922 | FAT Report for SS 316L (CWP 205) Pipes -149 Nos | "FAT Report for SS 316L (CWP 205) Pipes -149 Nos" | 2025-12-19 |  |  |  | NA | 0 | 1
001923 | Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN | "Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN" | 2025-12-19 |  |  |  | NA | 0 | 1
001924 | SSN URA Submission | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 5
001924 | SSN URA Submission | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 7
001924 | SSN URA Submission | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A | 2
001924 | SSN URA Submission | "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 2
001924 | SSN URA Submission | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 4
001924 | SSN URA Submission | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 2
001924 | SSN URA Submission | "SSN URA Submission" | 2025-12-22 | 2026-01-12 |  |  | NA | A.2 | 2
001925 | SSN Blower Plant Control Narrative | "SSN Blower Plant Control Narrative" | 2025-12-22 | 2026-02-09 |  |  | NA | 0 | 1
001926 | FAT Report for Solenoid Valves (Norgren) | "FAT Report for Solenoid Valves (Norgren)" | 2025-12-23 |  |  |  | NA | 0 | 1
001927 | FAT Report for SS 316L Pipes - 77 Nos | "FAT Report for SS 316L Pipes - 77 Nos" | 2025-12-23 |  |  |  | NA | 0 | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | X | 1
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001928 | As built drawing for ST614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | 2026-02-23 |  |  | Aaron | E | 2
001929 | Earthing System Test Report (SSN Electrical Building) | "Earthing System Test Report (SSN Electrical Building)" | 2025-12-30 | 2026-02-24 |  |  | NA | 0 | 1
001930 | Notice For Extension Of Time and Cost For Delays For Change In Country Regulations, Laws, Requirements By Authorities | "Notice For Extension Of Time and Cost For Delays For Change In Country Regulations, Laws, Requirements By Authorities" | 2025-12-31 | 2026-02-24 |  |  | NA | 0 | 1

## 2026-01
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000191 | Milestone 3 SSN Electrical Building | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | 2026-01-16 |  |  |  | Heng Peng/ Muthu | 0 | 2
000192 | Milestone 3 SSN Chemical Dosing Area | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 |  |  |  | Heng Peng/ Muthu | 0 | 2
000192 | Milestone 3 SSN Chemical Dosing Area | "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 |  |  |  | Heng Peng/ Muthu | C | 1
000192 | Milestone 3 SSN Chemical Dosing Area | "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 |  |  |  | Heng Peng/ Muthu | A | 1
000192 | Milestone 3 SSN Chemical Dosing Area | "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 |  |  |  | Heng Peng/ Muthu | A | 1
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2026-01-19 |  |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" | 2026-01-19 |  |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" | 2026-01-19 |  |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "SSN Power Layout Plan" | 2026-01-19 |  |  |  | Freedomer | D | 4
000227 | SSN Power Layout Plan | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" | 2026-01-19 |  |  |  | Freedomer | D | 5
000227 | SSN Power Layout Plan | "SSN Power Layout Plan" | 2026-01-19 |  |  |  | Freedomer | D | 1
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.2 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 9
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A | 1
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A | 2
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 7
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.4 | 3
000338 | PUB DC Drainage Submission | "PUB DC Drainage Submission " | 2026-01-12 |  |  |  | Aaron/HP | A.2 | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.2 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A | 1
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A | 2
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 8
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 7
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.4 | 4
000396 | LTA & Nparks submission Set | "LTA & Nparks submission Set" | 2026-01-09 |  |  |  | Aaron | A.2 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.2 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A | 1
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 5
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 3
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.4 | 2
000397 | NEA DC submission Set | "NEA DC submission Set " | 2026-01-06 |  |  |  | Zora/HP | A.2 | 2
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.3 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.2 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.2 | 3
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.2 | 6
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.3 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 7
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.5 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 8
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.4 | 9
000402 | SSN_FSSD (BP) Submission | "SSN_FSSD (BP) Submission " | 2026-01-07 |  |  |  | Aaron | A.2 | 6
000907 | SSN Harmonics Study Report | "SSN Harmonics Study Report" | 2026-01-20 |  |  |  | Freedomer | 1 | 2
000962 | FAT report for THP Train 1 (Part-1) | "FAT report for THP Train 1 (Part-1)" | 2026-01-06 |  |  |  | Soe Myat | 3 | 4
000976 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2026-01-06 |  |  |  | Soe Myat | 2 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 3
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 1 | 4
000993 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 3
001173 | Datasheet for Temperature Transmitter | "Datasheet for Temperature Transmitter " | 2026-01-21 |  |  |  | Yean Yee | 1 | 3
001181 | Datasheet for Pressure Switch | "Datasheet for Pressure Switch" | 2026-01-30 |  |  |  | Yean Yee | 2 | 3
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.4 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A | 3
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.1 | 4
001186 | SSN BCA BP Submission | "SSN BCA BP Submission" | 2026-01-20 |  |  |  | Aaron | A.2 | 4
001403 | FAT Report for Chemical Dosing Pumps (PROMINENT) | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2026-01-08 | 2030-01-01 |  |  | Radha | 3 | 4
001545 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" | 2026-01-15 |  |  |  | Dhanapal | 1 | 2
001565 | SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | "SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi)" | 2026-01-02 | 2026-02-02 |  |  | Dhanapal | 1 | 2
001606 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | "Test Procedure for Pull & Push Load Test - Aluminium Handrail" | 2026-01-07 | 2026-01-12 |  |  | Radha | 2 | 3
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001636 | Testing Check List (Process) | "Testing Check List (Process)" && "T&C Check List " | 2026-01-28 |  |  |  | Joo Kwan | 0 | 2
001685 | Datasheet for Thermal Flow Switch | "Datasheet for Thermal Flow Switch" | 2026-01-15 |  |  |  | Yean Yee | 1 | 2
001695 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | 2026-01-27 |  |  |  | Mohan | 1 | 3
001697 | FAT Report for Actuated Ball Valves (OVS/Rotork) | "FAT Report for Actuated Ball Valves (OVS/Rotork)" | 2026-01-27 |  |  |  | Soe Myat | 1 | 2
001758 | THP UPSDB-0001A SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001A SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001A SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001A SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001A SLD, Schematic and GA Drawing | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001758 | THP UPSDB-0001A SLD, Schematic and GA Drawing | "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 1
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001759 | THP UPSDB-0001B SLD, Schematic and GA Drawing | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 1
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001760 | THP UPSDB-0105A SLD, Schematic and GA Drawing | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 1
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001763 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 1
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001764 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 1
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | Freedomer | B | 2
001765 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | Freedomer | B | 1
001767 | THP UPSDB-0106A SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0106A SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0106A SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0106A SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0106A SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 2
001767 | THP UPSDB-0106A SLD, Schematic and GA Drawing | "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | B | 1
001768 | THP UPSDB-0107 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001768 | THP UPSDB-0107 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001768 | THP UPSDB-0107 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001768 | THP UPSDB-0107 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001768 | THP UPSDB-0107 SLD, Schematic and GA Drawing | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 2
001768 | THP UPSDB-0107 SLD, Schematic and GA Drawing | "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 |  |  |  | Freedomer | B | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001793 | BMS Panel GA & Wiring Drawing | "BMS Panel GA & Wiring Drawing " | 2026-01-28 |  |  |  | M Balaji | A | 1
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001814 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 1
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 2
001815 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | B | 1
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001816 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 1
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001817 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 1
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 2
001818 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | Freedomer | B | 1
001861 | Factory Acceptance Test Report for Pressure Switch | "Factory Acceptance Test Report for Pressure Switch" | 2026-01-13 |  |  |  | Dhanapal | 1 | 2
001872 | SSN- I/O List-BIO-0001 | "SSN- I/O List-BIO-0001 " | 2026-01-28 |  |  |  | Balaji | 0 | 2
001873 | SSN- I/O List-BIO-0002 | "SSN- I/O List-BIO-0002 " | 2026-01-28 |  |  |  | Balaji | 0 | 2
001900 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | 2026-01-27 | 2026-02-09 |  |  | Yuen Fatt | 2 | 2
001931 | THP BCA BP Submission | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 2
001931 | THP BCA BP Submission | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 2
001931 | THP BCA BP Submission | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 2
001931 | THP BCA BP Submission | "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 1
001931 | THP BCA BP Submission | "THP Layout, Elevations and Section Details" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 2
001931 | THP BCA BP Submission | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 3
001931 | THP BCA BP Submission | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 3
001931 | THP BCA BP Submission | "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 2
001931 | THP BCA BP Submission | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 3
001931 | THP BCA BP Submission | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" | 2026-01-05 |  |  |  | NA | A | 3
001932 | MSRA, SWP for Testing and Commissioning for ACMV System works | "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2026-01-05 | 2026-01-07 |  |  | Bryan | 0 | 1
001933 | Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP) | "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP)" | 2026-01-05 | 2026-01-22 |  |  | Dhanapal | 0 | 1
001934 | Memo-Appointment of LEW Representatives_01 Nov 2025 | "Memo-Appointment of LEW Representatives_01 Nov 2025" | 2026-01-05 | 2026-02-09 |  |  | Freedomer | 0 | 1
001935 | Factory Acceptance Test Report for Thermal Flow Switch (THP) | "Factory Acceptance Test Report for Thermal Flow Switch (THP)" | 2026-01-07 | 2026-01-22 |  |  | Dhanapal | 0 | 1
001936 | THP and SSN Cable Ladder/ Tray Data Sheet and Specifications | "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2026-01-07 |  |  |  | Freedomer | 0 | 1
001937 | SSN ACB Lifting Truck Data Sheet | "SSN ACB Lifting Truck Data Sheet" | 2026-01-07 | 2026-02-09 |  |  | Freedomer | 0 | 1
001938 | Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen) | "Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen)" | 2026-01-07 |  |  |  | Mohan | 0 | 1
001939 | FAT Report for SS 316L (CWP 205) Pipes - 201 Nos | "FAT Report for SS 316L (CWP 205) Pipes - 201 Nos" | 2026-01-07 |  |  |  | Mohan | 0 | 1
001940 | SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team) | "SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team)" | 2026-01-08 | 2026-02-12 |  |  | Kumar | 0 | 1
001941 | VCM Submission for 2025-12 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2026-01-08 |  |  |  | Heng Peng | 0 | 4
001942 | Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation | "Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation" | 2026-01-12 |  |  |  | Vincent | 0 | 1
001943 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax) | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax)" | 2026-01-12 |  |  |  | Mohan | 0 | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "WD for ST622 " | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 2
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001944 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | 2026-02-12 |  |  | Aaron | C | 1
001945 | G2D Pipe Support_Report from QPD | "G2D Pipe Support_Report from QPD" | 2026-01-12 | 2026-02-12 |  |  | Aaron | B | 1
001945 | G2D Pipe Support_Report from QPD | "G2D Pipe Support_Report from QPD" | 2026-01-12 | 2026-02-12 |  |  | Aaron | B | 1
001945 | G2D Pipe Support_Report from QPD | "Support design for compressed Air system >2m" && "G2D Pipe Support_Report from QPD" | 2026-01-12 | 2026-02-12 |  |  | Aaron | 1 | 2
001946 | FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) | "FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) " | 2026-01-12 |  |  |  | Mohan | 0 | 1
001947 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN" | 2026-01-12 |  |  |  | Dhanapal | 0 | 1
001948 | THP and SSN Earthing Material Specifications | "THP and SSN Earthing Material Specifications" | 2026-01-12 |  |  |  | Freedomer | 0 | 1
001949 | Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd) | "Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd)" | 2026-01-12 | 2026-02-02 |  |  | Kumar | 0 | 1
001950 | Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal) | "Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal)" | 2026-01-12 | 2026-02-20 |  |  | Kumar | 0 | 1
001951 | FAT Report for Non Return Check Valve - Batch 2 (Breen) | "FAT Report for Non Return Check Valve - Batch 2 (Breen)" | 2026-01-12 |  |  |  | Mohan | 0 | 1
001952 | Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax) | "Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax)" | 2026-01-13 |  |  |  | Mohan | 0 | 1
001953 | CV of Team Member (MEM) | "CV of Team Member (MEM)" && "Purchase Of Spare Parts Under SOP 10" | 2026-01-14 |  |  |  | Htet Nu | 0 | 2
001954 | Payment Claim No.30 | "Payment Claim No.30" | 2026-01-14 |  |  |  | Yi Hao | 0 | 1
001955 | C4B Monthly Progress Report Number No.32 (12 25) | "C4B Monthly Progress Report Number No.32 (12 25)" | 2026-01-15 |  |  |  | Htet Nu | 0 | 1
001956 | Datasheet for Thermal Flow Switch (THP-BOP) | "Datasheet for Thermal Flow Switch (THP-BOP)" | 2026-01-15 | 2026-01-20 |  |  | Yean Yee | 0 | 1
001957 | Hookup Drawing for NO2 / NO3 Analyser | "Hookup Drawing for NO2 / NO3 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001957 | Hookup Drawing for NO2 / NO3 Analyser | "Hookup Drawing for NO2 / NO3 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001957 | Hookup Drawing for NO2 / NO3 Analyser | "Hookup Drawing for NO2 / NO3 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001958 | Hookup Drawing for NH4 Analyser | "Hookup Drawing for NH4 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001958 | Hookup Drawing for NH4 Analyser | "Hookup Drawing for NH4 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001958 | Hookup Drawing for NH4 Analyser | "Hookup Drawing for NH4 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001958 | Hookup Drawing for NH4 Analyser | "Hookup Drawing for NH4 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001958 | Hookup Drawing for NH4 Analyser | "Hookup Drawing for NH4 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001958 | Hookup Drawing for NH4 Analyser | "Hookup Drawing for NH4 Analyser" | 2026-01-15 |  |  |  | Yean Yee | A | 1
001959 | Datasheet for Electromagnetic Flow Meter (THP-BOP) | "Datasheet for Electromagnetic Flow Meter (THP-BOP) " | 2026-01-15 |  |  |  | Yean Yee | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001960 | THP_FSSD (BP) Submission | "THP_FSSD (BP) Submission" | 2026-01-19 |  |  |  | Aaron | A | 1
001961 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron) | "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" | 2026-01-19 |  |  |  | Yuen Fatt | 0 | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | D | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | D | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | D | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | D | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 1
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001962 | QPD As Built Drawing for ST 614 (SWPR PR 03) | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | 2026-02-20 |  |  | Aaron | E | 2
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | F | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | E | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | E | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001963 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 |  |  |  | Aaron | NA | 1
001964 | Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed) | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2026-01-19 |  |  |  | Aaron | VOID | 9
001965 | Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed) | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2026-01-19 |  |  |  | Aaron | VOID | 9
001966 | THP Fire Alarm System Layout Plan | "THP Fire Alarm System Layout Plan" | 2026-01-20 |  |  |  | NA | NA | 1
001967 | Datasheet for Pressure Gauge (THP-BOP) | "Datasheet for Pressure Gauge (THP-BOP)" | 2026-01-20 | 2026-02-24 |  |  | NA | 0 | 1
001968 | Hookup Drawing -Tuning Fork Level Switch | "Hookup Drawing -Tuning Fork Level Switch" | 2026-01-20 |  |  |  | NA | NA | 1
001968 | Hookup Drawing -Tuning Fork Level Switch | "Hookup Drawing -Tuning Fork Level Switch" | 2026-01-20 |  |  |  | NA | NA | 1
001969 | Hookup Drawing for Magnetic Level Gauge | "Hookup Drawing for Magnetic Level Gauge" | 2026-01-20 |  |  |  | NA | NA | 1
001969 | Hookup Drawing for Magnetic Level Gauge | "Hookup Drawing for Magnetic Level Gauge" | 2026-01-20 |  |  |  | NA | NA | 1
001970 | Hookup Drawing for Conductive Probe Level Switch | "Hookup Drawing for Conductive Probe Level Switch" | 2026-01-20 |  |  |  | NA | NA | 1
001970 | Hookup Drawing for Conductive Probe Level Switch | "Hookup Drawing for Conductive Probe Level Switch" | 2026-01-20 |  |  |  | NA | NA | 1
001971 | Data Sheet for Lamp Pole | "Data Sheet for Lamp Pole" | 2026-01-21 | 2026-02-09 |  |  | Kyi Kyi | 0 | 1
001972 | FAT Report for G2D Booster Pumps (KSB) | "FAT Report for G2D Booster Pumps (KSB)" | 2026-01-21 |  |  |  | NA | 0 | 1
001973 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch" | 2026-01-22 |  |  |  | NA | 0 | 1
001974 | Splitter Box Structural Supports | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2026-01-22 |  |  |  | Salahudin | C | 3
001974 | Splitter Box Structural Supports | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2026-01-22 |  |  |  | Salahudin | C | 3
001974 | Splitter Box Structural Supports | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2026-01-22 |  |  |  | Salahudin | D | 3
001974 | Splitter Box Structural Supports | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2026-01-22 |  |  |  | Salahudin | D | 2
001975 | WD for ST622 | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "WD for ST622 " | 2026-01-26 | 2026-02-12 |  |  | NA | C | 2
001976 | Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP) | "Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP)" | 2026-01-26 | 2026-02-16 |  |  | NA | 0 | 2
001977 | Factory Acceptance Test Report for Pressure Gauges (THP) | "Factory Acceptance Test Report for Pressure Gauges (THP)" | 2026-01-26 | 2026-02-24 |  |  | NA | 0 | 1
001978 | Factory Acceptance Test Report for Magnetic Level Gauge | "Factory Acceptance Test Report for Magnetic Level Gauge" | 2026-01-26 |  |  |  | NA | 0 | 2
001979 | Factory Acceptance Test Report for Magnetic Level Gauge | "Factory Acceptance Test Report for Magnetic Level Gauge" | 2026-01-26 |  |  |  | NA | 0 | 2
001980 | Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP) | "Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP)" | 2026-01-26 | 2026-02-24 |  |  | NA | 0 | 2
001981 | FAT Report for Splitter Box | "FAT Report for Splitter Box" | 2026-01-26 |  |  |  | NA | 0 | 1
001982 | FAT Report for G1 Booster Pumps (KSB) | "FAT Report for G1 Booster Pumps (KSB)" | 2026-01-26 |  |  |  | NA | 0 | 1
001983 | Data Sheet of Isolator for Motorized Valves | "Data Sheet of Isolator for Motorized Valves" | 2026-01-27 | 2026-02-13 |  |  | NA | 0 | 1
001984 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001984 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001984 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001984 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001984 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001984 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001985 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001985 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001985 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001985 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001985 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001985 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001986 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001986 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001986 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001986 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001986 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001986 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 |  |  |  | Freedomer | A | 1
001987 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001987 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001987 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001987 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001987 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001987 | THP UPSDB-0105B SLD, Schematic and GA Drawing | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001988 | THP UPSDB-0106B SLD, Schematic and GA Drawing | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001988 | THP UPSDB-0106B SLD, Schematic and GA Drawing | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001988 | THP UPSDB-0106B SLD, Schematic and GA Drawing | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001988 | THP UPSDB-0106B SLD, Schematic and GA Drawing | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001988 | THP UPSDB-0106B SLD, Schematic and GA Drawing | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001988 | THP UPSDB-0106B SLD, Schematic and GA Drawing | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | 2026-02-26 |  |  | Freedomer | A | 1
001989 | Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures | "Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures" | 2026-01-27 |  |  |  | Soe Myat | 0 | 1
001990 | Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box | "Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box" | 2026-01-27 |  |  |  | Mohan | 0 | 1
001991 | Steam Trap Data Sheet | "Steam Trap Data Sheet" | 2026-01-28 |  |  |  | NA | 0 | 1
001992 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001992 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001992 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001992 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001992 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001992 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001993 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | NA | A | 1
001993 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | NA | A | 1
001993 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | NA | A | 1
001993 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | NA | A | 1
001993 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | NA | A | 1
001993 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 |  |  |  | NA | A | 1
001994 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001994 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001994 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001994 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001994 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001994 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 |  |  |  | NA | A | 1
001995 | Datasheet for Pressure Switch (THP-BOP) | "Datasheet for Pressure Switch (THP-BOP)" | 2026-01-29 |  |  |  | NA | 0 | 1
001996 | FAT Report for FFOTP Panel SSN & THP (FOX) | "FAT Report for FFOTP Panel SSN & THP (FOX)" | 2026-01-30 |  |  |  | NA | 0 | 1
001997 | FAT Report for FOIP Panel SSN & THP (FOX) | "FAT Report for FOIP Panel SSN & THP (FOX)" | 2026-01-30 |  |  |  | NA | 0 | 1
001998 | FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN | "FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN" | 2026-01-30 |  |  |  | NA | 0 | 1
001999 | Datasheet for Pressure Transmitter (THP-BOP) | "Datasheet for Pressure Transmitter (THP-BOP) " | 2026-01-30 |  |  |  | NA | 0 | 1

## 2026-02
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
000093 | Piperack P&IDs | "Piperack P&IDs" | 2026-02-24 | 2025-04-30 |  |  | Qili | E | 6
000093 | Piperack P&IDs | "Piperack P&IDs" | 2026-02-24 | 2025-04-30 |  |  | Qili | E | 6
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Process" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 6
000731 | P&ID for SSN | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 6
000731 | P&ID for SSN | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" | 2026-02-24 |  |  |  | Qili | D | 5
001113 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" | 2026-02-05 |  |  |  | K. Balaji | 2 | 3
001398 | MSRA, SWP for fire protection services | "MSRA, SWP for fire protection services " | 2026-02-13 |  |  |  | Bryan | 2 | 3
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 4
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001402 | ACMV LCP GA & Wiring Drawing | "ACMV LCP GA & Wiring Drawing" | 2026-02-04 |  |  |  | Yuen Fatt | 1 | 2
001438 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | 2026-02-24 |  |  |  | Freedomer | 2 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" | 2026-02-09 |  |  |  | Aaron | A.6 | 4
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "ST Updates for SSN Staircase (ST607)" | 2026-02-09 |  |  |  | Aaron | A.6 | 4
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 2
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 2
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 1
001528 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2026-02-09 |  |  |  | Aaron | A.6 | 3
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001757 | THP LDB-0001 SLD, Schematic and GA Drawing | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001761 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 1
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001762 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001769 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 1
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001771 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 1
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 2
001772 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 1
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 3
001773 | THP LDB-0002 SLD, Schematic and GA Drawing | "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | B | 3
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 4
001774 | SSN LDB-0001 SLD, Schematic and GA Drawing | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 4
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | A | 3
001776 | SSN LDB-0002 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | A | 3
001777 | SSN SDB-0003 SLD, Schematic and GA Drawing | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | Freedomer | A | 3
001803 | Shop Drawing for SSN Area and Electrical Building Cat ladders | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2026-02-09 |  |  |  | Aaron | A.5 | 3
001803 | Shop Drawing for SSN Area and Electrical Building Cat ladders | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2026-02-09 |  |  |  | Aaron | A.5 | 3
001803 | Shop Drawing for SSN Area and Electrical Building Cat ladders | "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2026-02-09 |  |  |  | Aaron | A.5 | 3
001803 | Shop Drawing for SSN Area and Electrical Building Cat ladders | " Railing Shop Drawing For Electrical Building" && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2026-02-09 |  |  |  | Aaron | A.5 | 7
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001806 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 1
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 2
001807 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 |  |  |  | Freedomer | B | 1
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 3
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 3
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001808 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 3
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001809 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 1
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 3
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001810 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 1
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001812 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 1
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 1
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 2
001813 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | Freedomer | B | 1
001824 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | "FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite)" | 2026-02-03 |  |  |  | Mohan | 1 | 2
001900 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | 2026-02-11 | 2026-02-25 |  |  | Yuen Fatt | 2 | 2
001924 | SSN URA Submission | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 5
001924 | SSN URA Submission | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 7
001924 | SSN URA Submission | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A | 2
001924 | SSN URA Submission | "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 2
001924 | SSN URA Submission | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 4
001924 | SSN URA Submission | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 3
001924 | SSN URA Submission | "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 2
001924 | SSN URA Submission | "SSN URA Submission" | 2026-02-03 |  |  |  | NA | A.2 | 2
002000 | THP LDB-0001B SLD, Schematic and GA Drawing | "THP LDB-0001B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002000 | THP LDB-0001B SLD, Schematic and GA Drawing | "THP LDB-0001B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002000 | THP LDB-0001B SLD, Schematic and GA Drawing | "THP LDB-0001B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002000 | THP LDB-0001B SLD, Schematic and GA Drawing | "THP LDB-0001B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002000 | THP LDB-0001B SLD, Schematic and GA Drawing | "THP LDB-0001B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002000 | THP LDB-0001B SLD, Schematic and GA Drawing | "THP LDB-0001B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002001 | THP LDB-0002B SLD, Schematic and GA Drawing | "THP LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002001 | THP LDB-0002B SLD, Schematic and GA Drawing | "THP LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002001 | THP LDB-0002B SLD, Schematic and GA Drawing | "THP LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002001 | THP LDB-0002B SLD, Schematic and GA Drawing | "THP LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002001 | THP LDB-0002B SLD, Schematic and GA Drawing | "THP LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002001 | THP LDB-0002B SLD, Schematic and GA Drawing | "THP LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002002 | SSN LDB-0001B SLD, Schematic and GA Drawing | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002002 | SSN LDB-0001B SLD, Schematic and GA Drawing | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002002 | SSN LDB-0001B SLD, Schematic and GA Drawing | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002002 | SSN LDB-0001B SLD, Schematic and GA Drawing | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002002 | SSN LDB-0001B SLD, Schematic and GA Drawing | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002002 | SSN LDB-0001B SLD, Schematic and GA Drawing | "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002003 | SSN LDB-0002B SLD, Schematic and GA Drawing | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002003 | SSN LDB-0002B SLD, Schematic and GA Drawing | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002003 | SSN LDB-0002B SLD, Schematic and GA Drawing | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002003 | SSN LDB-0002B SLD, Schematic and GA Drawing | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002003 | SSN LDB-0002B SLD, Schematic and GA Drawing | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002003 | SSN LDB-0002B SLD, Schematic and GA Drawing | "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002004 | Unpriced PO for Magnetic Level Gauge (Pipeline Process) | "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "As Built Drawing for ST619 (THP Cooler Platform)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2026-02-03 |  |  |  | NA | VOID | 9
002005 | SSN SDB-0003B SLD, Schematic and GA Drawing | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002005 | SSN SDB-0003B SLD, Schematic and GA Drawing | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002005 | SSN SDB-0003B SLD, Schematic and GA Drawing | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002005 | SSN SDB-0003B SLD, Schematic and GA Drawing | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002005 | SSN SDB-0003B SLD, Schematic and GA Drawing | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002005 | SSN SDB-0003B SLD, Schematic and GA Drawing | "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2026-02-03 |  |  |  | NA | A | 1
002006 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002006 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002006 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002006 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002006 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002006 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | 2026-02-26 |  |  | NA | A | 1
002007 | Staircase 1 Block Wall Shop Drawing | "Staircase 1 Block Wall Shop Drawing" | 2026-02-04 |  |  |  | NA | A | 1
002007 | Staircase 1 Block Wall Shop Drawing | "Staircase 1 Block Wall Shop Drawing" | 2026-02-04 |  |  |  | NA | A | 1
002007 | Staircase 1 Block Wall Shop Drawing | "Staircase 1 Block Wall Shop Drawing" | 2026-02-04 |  |  |  | NA | A | 1
002007 | Staircase 1 Block Wall Shop Drawing | "Staircase 1 Block Wall Shop Drawing" | 2026-02-04 |  |  |  | NA | A | 1
002008 | Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve | "Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve " | 2026-02-06 |  |  |  | NA | NA | 1
002009 | VCM Submission for 2026-01 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2026-02-09 |  |  |  | NA | 0 | 4
002010 | FAT Report for SS316L Pipe (CWP 323) 117 Nos | "FAT Report for SS316L Pipe (CWP 323) 117 Nos" | 2026-02-10 |  |  |  | NA | 0 | 1
002011 | Payment Claim No.31 | "Payment Claim No.31" | 2026-02-11 | 2026-02-24 |  |  | Yihao | 0 | 1
002012 | Purchase Of Spare Parts Under SOP 10 | "CV of Team Member (MEM)" && "Purchase Of Spare Parts Under SOP 10" | 2026-02-11 |  |  |  | NA | 0 | 2
002013 | Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards | "Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards " | 2026-02-12 |  |  |  | NA | 0 | 1
002014 | C4B Monthly Progress Report Number No.33 (01 26) | "C4B Monthly Progress Report Number No.33 (01 26)" | 2026-02-20 |  |  |  | NA | 0 | 1
002015 | ITP and Test Procedure for Chemical Dosing Cabinets | "ITP and Test Procedure for Chemical Dosing Cabinets" | 2026-02-24 |  |  |  | NA | 0 | 1
002016 | RFC for Electrical Building Chequer Plate | "RFC for Electrical Building Chequer Plate" | 2026-02-24 |  |  |  | NA | 0 | 1
002017 | FAT Report for Chemical Dosing Cabinets | "FAT Report for Chemical Dosing Cabinets " | 2026-02-24 |  |  |  | NA | 0 | 1
002018 | C4B SSN Drain Hydraulic Calculation | "SSN Pavement Plan" && "C4B SSN Drain Hydraulic Calculation" | 2026-02-24 |  |  |  | NA | A | 2
002018 | C4B SSN Drain Hydraulic Calculation | "C4B SSN Drain Hydraulic Calculation" | 2026-02-24 |  |  |  | NA | 0 | 1
002019 | SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | "SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) " | 2026-02-25 |  |  |  | NA | 0 | 1

## 2026-03
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
002020 | Datasheet for Temperature Sensor (THP-BOP) | "Datasheet for Temperature Sensor (THP-BOP) " | 2026-03-02 |  |  |  | NA | 0 | 1
002021 | Datasheet for Differential Pressure Flowmeter (THP-BOP) | "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | 2026-03-02 |  |  |  | NA | 0 | 1
002025 | Notice For Extension Of Time And Cost For Delays For Power Turn On | "Notice For Extension Of Time And Cost For Delays For Power Turn On " | 2026-03-05 |  |  |  | Mabele | 0 | 1

## 2026-12
Submission_Session | Submission_Session_Subject | Consolidated_Submission_Session_Subject | Submission_Date | Review_Return_Actual_Date | Latest_Approval_Status | Latest_Approval_Code | Submitted_By | Latest_Revision | Count_of_Submissions
001649 | Solenoid Valve Data Sheet | "Solenoid Valve Data Sheet" | 2026-12-29 |  |  |  | Joo Kwan | 1 | 2