## Sheet1
Submission_Session | Submission_Session_Revision | Submitted_By | Department | Transmittal_Number | Project_Code | Facility_Code | Document_Type | Discipline | Document_Sequence_Number | Document_Revision | Document_ID | Submission_Date | Submission_Session_Subject | Review_Comments | Review_Return_Plan_Date | Review_Return_Actual_Date | Duration_of_Review | Review_Status | Resubmission_Required | Resubmission_Plan_Date | Submission_Closed | Resubmission_Overdue_Status | Delay_of_Resubmission | Resubmission_Forecast_Date | Notes | All_Submission_Sessions | First_Submittion_Date | Latest_Submittion_Date | Latest_Revision | Review_Status_Code | Latest_Approval_Status | Count_of_Submissions | Consolidated_Submission_Session_Subject | Latest_Approval_Code | Submission Month-Year
000001 | 00 | Soe Myat | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 0 | 131242-WST00-PP-PM-0001 | 2023-05-15 | Project Quality Plan | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-13 | 2023-12-05 | 146 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000001 | 2023-05-15 | 2024-05-13 | 1 | AWC | Approved with Comments | 2 | "Project Quality Plan" |  | 2023-05
000001 | 01 | Radha | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 1 | 131242-WST00-PP-PM-0001 | 2024-05-13 | Project Quality Plan | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-03 | 2024-09-10 | 86 | Approved with Comments | YES | 2024-09-30 | NO | Resubmitted | 0 |  |  | 000001 | 2023-05-15 | 2024-05-13 | 1 | AWC | Approved with Comments | 2 | "Project Quality Plan" |  | 2024-05
000002 | 00 | Shena | PMT | NA | 131242 | WST00 | PP | PC | 0001 | 0 | 131242-WST00-PP-PC-0001 | 2023-05-15 | Project Risk Management Plan | Rev 0: Approved with Comments. Refer to comment sheet and resubmit. | 2023-06-13 | 2023-06-14 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-05-15 | 2023-05-15 | 0 | AWC | Approved with Comments | 1 | "Project Risk Management Plan" |  | 2023-05
000002 | 01 | Max/Edwin | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 1 | 131242-WSW41-PP-PC-0001 | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-09-25 | 2023-09-13 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-09-05 | 2023-10-30 | 2 | AWC | Approved | 2 | "Project Risk Management Plan" |  | 2023-09
000002 | 01 | Max/Edwin | PMT | NA | #000002.0_ Reply_2023 08 31 | NA | NA | NA | NA | NA | #000002.0_ Reply_2023 08 31-NA-NA-NA-NA | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-10-03 | 2023-09-13 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-09-05 | 2023-09-05 | NA | AWC | Approved with Comments | 1 | "Project Risk Management Plan" |  | 2023-09
000002 | 02 | Max | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 2 | 131242-WSW41-PP-PC-0001 | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-20 | 2023-11-07 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-09-05 | 2023-10-30 | 2 | APP | Approved | 2 | "Project Risk Management Plan" |  | 2023-10
000002 | 02 | Max | PMT | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025 | NA | NA | NA | NA | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025-NA-NA-NA-NA | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-28 | 2023-11-07 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000002 | 2023-10-30 | 2023-10-30 | NA | APP | Approved | 1 | "Project Risk Management Plan" |  | 2023-10
000003 | 00 | Heng Peng | BIM | NA | 131242 | WST00 | PP | IM | 0001 | 0 | 131242-WST00-PP-IM-0001 | 2023-05-16 | BIM Execution Plan (BEP) | R0- Not Approved, please refer to comment sheet | 2023-06-14 | 2023-07-03 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-05-16 | 2023-05-16 | 0 | NAP | Not Approved | 1 | "BIM Execution Plan (BEP)" |  | 2023-05
000003 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 1 | 131242-WSW41-PP-IM-0001 | 2023-08-21 | BIM Execution Plan (BEP) | R1- Not Approved. Please refer to "Comment Sheet_Submittal-0003-1". | 2023-09-08 | 2023-10-20 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | NAP | Approved | 5 | "BIM Execution Plan (BEP)" |  | 2023-08
000003 | 02 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 2 | 131242-WSW41-PP-IM-0001 | 2023-12-12 | BIM Execution Plan (BEP) | R2- Not Approved, revise and resubmit. Please refer to "Comment Sheet_Submittal-0003-2". | 2024-01-03 | 2024-03-14 | 67 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | NAP | Approved | 5 | "BIM Execution Plan (BEP)" |  | 2023-12
000003 | 03 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 3 | 131242-WSW41-PP-IM-0001 | 2024-03-15 | BIM Execution Plan (BEP) | R3- Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet | 2024-04-05 | 2024-03-20 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | AWC | Approved | 5 | "BIM Execution Plan (BEP)" |  | 2024-03
000003 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 4 | 131242-WSW41-PP-IM-0001 | 2024-06-28 | BIM Execution Plan (BEP) | Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet. | 2024-07-18 | 2024-08-07 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | R3_AWC | 000003 | 2023-08-21 | 2024-09-18 | 5 | AWC | Approved | 5 | "BIM Execution Plan (BEP)" |  | 2024-06
000003 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 5 | 131242-WSW41-PP-IM-0001 | 2024-09-18 | BIM Execution Plan (BEP) | Approved | 2024-10-08 | 2024-10-02 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000003 | 2023-08-21 | 2024-09-18 | 5 | APP | Approved | 5 | "BIM Execution Plan (BEP)" |  | 2024-09
000004 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 0 | 131242-WST00-PP-HS-0001 | 2023-05-16 | Project HSE Plan | Names are not as proposed. Signatory also not as proposed for HSEM. Review and resubmit. | 2023-06-14 | 2023-07-24 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000004 | 2023-05-16 | 2023-09-27 | 1 | NAP | Approved | 2 | "Project HSE Plan" |  | 2023-05
000004 | 01 | Dharmen | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 1 | 131242-WST00-PP-HS-0001 | 2023-09-27 | Project HSE Plan | Approved from HSE standpoint. | 2023-10-17 | 2023-10-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000004 | 2023-05-16 | 2023-09-27 | 1 | APP | Approved | 2 | "Project HSE Plan" |  | 2023-09
000005 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 0 | 131242-WST00-PG-PC-0001 | 2023-05-17 | PROGRAMME OF THE WORKS | Rev. 0 - Not Approved, need to re-submit (see comments sheet) | 2023-06-15 | 2023-06-14 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-05-17 | 2023-07-13 | 1 | NAP | Not Approved | 2 | "PROGRAMME OF THE WORKS" |  | 2023-05
000005 | 01 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 1 | 131242-WST00-PG-PC-0001 | 2023-07-13 | PROGRAMME OF THE WORKS | Rev. 1 - Not Approved, need to re-submit (see attached comments sheet R1) | 2023-08-02 | 2023-07-31 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-05-17 | 2023-07-13 | 1 | NAP | Not Approved | 2 | "PROGRAMME OF THE WORKS" |  | 2023-07
000005 | 02 | Thomas | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 2 | 131242-WSW41-PG-PC-0001 | 2023-09-07 | PROGRAMME OF THE WORKS | Rev. 2 Approved with comments. Need to re-submit (see attached comment sheet) | 2023-09-27 | 2023-09-18 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" |  | 2023-09
000005 | 03 | Thomas | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 | 131242-WSW41-LT-PM-0003 | 2023-09-26 | PROGRAMME OF THE WORKS | For Information | 2023-10-16 | 2023-10-03 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  | 000040 | 000005&&000040 | 2023-07-06 | 2023-09-26 | 0 | INF | For Information | 2 | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" |  | 2023-09
000005 | 04 | Krishanthy | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 3 | 131242-WSW41-PG-PC-0001 | 2023-10-27 | PROGRAMME OF THE WORKS | Rev. 4 Approved with comments. | 2023-11-17 | 2023-11-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | To be resubmitted when there is a major change in the program of works. Thomas checked with S.O. in the meeting on 18 Jan. | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" |  | 2023-10
000005 | 05 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 4 | 131242-WSW41-PG-PC-0001 | 2024-10-19 | PROGRAMME OF THE WORKS | Rev. 5. Not-Approved need to re-submit (see attached comment sheet) - new Rebaseline of the Programme Rev.1 need to re-submit with a new Prolog Submittal Number | 2024-11-08 | 2024-11-04 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | NAP | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" |  | 2024-10
000005 | 06 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5 | 131242-WSW41-PG-PC-0001 | 2025-03-14 | PROGRAMME OF THE WORKS | Rev. 6 - Approved with comments (need to re-submit - see attached comments sheet rev.1) | 2025-04-03 | 2025-04-15 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" |  | 2025-03
000005 | 07 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5.1 | 131242-WSW41-PG-PC-0001 | 2025-04-16 | PROGRAMME OF THE WORKS | Rev. 7 - Approved with comments (No resubmission needed - See attached comments sheet rev.7) | 2025-05-06 | 2025-04-27 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000005 | 2023-09-07 | 2025-04-16 | 5.1 | AWC | Approved with Comments | 5 | "PROGRAMME OF THE WORKS" |  | 2025-04
000006 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 0 | 131242-WST00-VI-C-0001 | 2023-05-17 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-15 | 2023-06-12 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000006 | 2023-05-17 | 2023-06-23 | 1 | AWC | Approved | 2 | "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" |  | 2023-05
000006 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 1 | 131242-WST00-VI-C-0001 | 2023-06-23 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Approved | 2023-07-14 | 2023-06-30 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000006 | 2023-05-17 | 2023-06-23 | 1 | APP | Approved | 2 | "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" |  | 2023-06
000007 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0002 | 0 | 131242-WST00-PG-PC-0002 | 2023-05-18 | MOBILIZATION PROGRAMME | Rev. 0 - Not Approved need to re-submit Refer Comment sheet) | 2023-06-16 | 2023-06-13 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  | Reply to S.O. Comment Sheet Only | 000007 | 2023-05-18 | 2023-05-18 | 0 | NAP | Not Approved | 1 | "MOBILIZATION PROGRAMME " |  | 2023-05
000007 | 01 | Thomas | PCM | NA | Reply to Comment Sheet_#000007 | NA | NA | NA | NA | NA | Reply to Comment Sheet_#000007-NA-NA-NA-NA | 2023-09-13 | MOBILIZATION PROGRAMME | Approved | 2023-10-03 | 2023-09-20 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000007 | 2023-09-13 | 2023-09-13 | NA | APP | Approved | 1 | "MOBILIZATION PROGRAMME " |  | 2023-09
000008 | 00 | Frank/ Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 0 | 131242-WST00-RG-Z-0001 | 2023-05-18 | Engineering Deliverable Lists | Rev 0: Not approved - Revise and Resubmit | 2023-06-16 | 2023-11-21 | 133 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000008 | 2023-05-18 | 2024-01-15 | 1 | NAP | For Information | 2 | "Engineering Deliverable Lists" |  | 2023-05
000008 | 01 | Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 1 | 131242-WST00-RG-Z-0001 | 2024-01-15 | Engineering Deliverable Lists | For Information To revise and resubmit. Refer to attached file for comments. | 2024-02-02 | 2024-08-29 | 163 | For Information | YES | 2024-09-18 | NO | Resubmitted | 0 |  | R1_Not APP | 000008 | 2023-05-18 | 2024-01-15 | 1 | INF | For Information | 2 | "Engineering Deliverable Lists" |  | 2024-01
000009 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 0 | 131242-WST00-VI-C-0002 | 2023-05-19 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-12 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000009 | 2023-05-19 | 2023-07-03 | 1 | NAP | Approved | 2 | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" |  | 2023-05
000009 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 1 | 131242-WST00-VI-C-0002 | 2023-07-03 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Approved | 2023-07-21 | 2023-07-12 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000009 | 2023-05-19 | 2023-07-03 | 1 | APP | Approved | 2 | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" |  | 2023-07
000010 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | S | 0001 | 0 | 131242-WST00-VI-S-0001 | 2023-05-19 | Vendor Approval for CSA Consultant QP (Tenwit) | Approved | 2023-06-19 | 2023-06-12 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000010 | 2023-05-19 | 2023-05-19 | 0 | APP | Approved | 1 | "Vendor Approval for CSA Consultant QP (Tenwit)" |  | 2023-05
000011 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | G | 0001 | 0 | 131242-WST00-VI-G-0001 | 2023-05-19 | Vendor Approval for Temp ERSS QPD,QPS (Tenwit ) | Approved | 2023-06-19 | 2023-06-12 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000011 | 2023-05-19 | 2023-05-19 | 0 | APP | Approved | 1 | "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" |  | 2023-05
000012 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 0 | 131242-WST00-VI-HS-0001 | 2023-05-19 | Vendor Approval for QECP Consultant (Tenwit ) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-14 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000012 | 2023-05-19 | 2023-06-23 | 1 | NAP | Approved | 2 | "Vendor Approval for QECP Consultant (Tenwit )" |  | 2023-05
000012 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 1 | 131242-WST00-VI-HS-0001 | 2023-06-23 | Vendor Approval for QECP Consultant (Tenwit ) | Approved | 2023-07-14 | 2023-07-24 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000012 | 2023-05-19 | 2023-06-23 | 1 | APP | Approved | 2 | "Vendor Approval for QECP Consultant (Tenwit )" |  | 2023-06
000013 | 00 | Freedomer | EICA | NA | 131242 | WST00 | VI | B | 0001 | 0 | 131242-WST00-VI-B-0001 | 2023-05-21 | Vendor Approval for M&E QP (C2D Solutions Pte. LTD ) | Approved | 2023-06-19 | 2024-03-18 | 215 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000013 | 2023-05-21 | 2023-05-21 | 0 | APP | Approved | 1 | "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" |  | 2023-05
000014 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 0 | 131242-WST00-VI-C-0003 | 2023-05-22 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-20 | 2023-06-12 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000014 | 2023-05-22 | 2023-07-31 | 2 | NAP | Approved | 3 | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" |  | 2023-05
000014 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 1 | 131242-WST00-VI-C-0003 | 2023-06-23 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.1: Not Approved. Please refer to attached comment sheet for resubmission. | 2023-07-14 | 2023-07-12 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000014 | 2023-05-22 | 2023-07-31 | 2 | NAP | Approved | 3 | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" |  | 2023-06
000014 | 02 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 2 | 131242-WST00-VI-C-0003 | 2023-07-31 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Approved | 2023-08-21 | 2023-08-11 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000014 | 2023-05-22 | 2023-07-31 | 2 | APP | Approved | 3 | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" |  | 2023-07
000015 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0001 | 0 | 131242-WST00-MI-C-0001 | 2023-05-23 | CSA Meeting Minutes 0001 | For Information | 2023-06-21 | 2023-06-12 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000015 | 2023-05-23 | 2023-05-23 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0001" |  | 2023-05
000016 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 0001 | 0 | 131242-WST02-DS-M-0001 | 2023-05-26 | FRP TANK DATA SHEET | Not approved - Revise and Resubmit | 2023-06-26 | 2023-10-16 | 101 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2023-05-26 | 2023-05-26 | 0 | NAP | Not Approved | 1 | "FRP TANK DATA SHEET" |  | 2023-05
000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 0 | 131242-WST02-DS-M-5401 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-14 00:00:00 | In Progress | 000016 | 2024-09-20 | 2025-04-01 | 1 | AWC | Approved | 2 | "FRP TANK DATA SHEET" |  | 2024-09
000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5416 | 0 | 131242-WST02-DS-M-5416 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2024-09-20 | 2025-04-01 | 1 | AWC | Approved | 2 | "FRP TANK DATA SHEET" |  | 2024-09
000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 1 | 131242-WST02-DS-M-5401 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2024-09-20 | 2025-04-01 | 1 | APP | Approved | 2 | "FRP TANK DATA SHEET" |  | 2025-04
000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5416 | 1 | 131242-WST02-DS-M-5416 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000016 | 2024-09-20 | 2025-04-01 | 1 | APP | Approved | 2 | "FRP TANK DATA SHEET" |  | 2025-04
000017 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 0 | 131242-WST00-LT-PM-0001 | 2023-05-27 | CVs of Team Member | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-26 | 2023-06-27 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000017 | 2023-05-27 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" |  | 2023-05
000017 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 1 | 131242-WST00-LT-PM-0001 | 2023-07-12 | CVs of Team Member Part 1 (14 Members) | Rev.1: Approved with comments. Please refer to attached comment sheet. | 2023-08-01 | 2023-07-25 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000017 | 2023-05-27 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" |  | 2023-07
000017 | 02 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000017 | 2 | 131242-WSW41-LT-PM- Reply to Comment Sheet_#000017 | 2023-09-04 | CVs of Team Member Part 1 (14 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-22 | 2023-10-10 | 26 | Approved with Comments | YES | 2023-10-30 | NO | Resubmitted | 0 |  | To obtain S.O. evaluation & final approval based on the probation period. To check with S.O during CSA bi-weekly meeting | 000017 | 2023-09-04 | 2023-09-04 | 2 | AWC | Approved with Comments | 1 | "CVs of Team Member Part 1 (14 Members)" |  | 2023-09
000018 | 00 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-Z-0001 | 2023-05-31 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-30 | 2023-06-06 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" |  | 2023-05
000018 | 01 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 1 | 131242-WST00-DR-Z-0001 | 2023-06-06 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-26 | 2023-06-23 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" |  | 2023-06
000018 | 02 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 2 | 131242-WST00-DR-Z-0001 | 2023-06-27 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-07-18 | 2023-07-03 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" |  | 2023-06
000018 | 03 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 3 | 131242-WST00-DR-Z-0001 | 2023-07-04 | Title Block Template (CAD) | Approved | 2023-07-24 | 2023-07-03 | 0 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | APP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" |  | 2023-07
000019 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 0 | 131242-WST00-VI-C-0004 | 2023-05-31 | Vendor Approval for Cable Dectector (JLCD) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-30 | 2023-06-16 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000019 | 2023-05-31 | 2023-06-23 | 1 | AWC | Approved | 2 | "Vendor Approval for Cable Dectector (JLCD)" |  | 2023-05
000019 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 1 | 131242-WST00-VI-C-0004 | 2023-06-23 | Vendor Approval for Cable Dectector (JLCD) | Approved | 2023-07-14 | 2023-06-30 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000019 | 2023-05-31 | 2023-06-23 | 1 | APP | Approved | 2 | "Vendor Approval for Cable Dectector (JLCD)" |  | 2023-06
000020 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | FM | HS | 0001 | 0 | 131242-WST00-FM-HS-0001 | 2023-06-05 | HSE Stickers for Machineries and SIC Induction | Approved | 2023-07-04 | 2023-06-14 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000020 | 2023-06-05 | 2023-06-05 | 0 | APP | Approved | 1 | "HSE Stickers for Machineries and SIC Induction" |  | 2023-06
000021 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0001 | 0 | 131242-WST00-MI-P-0001 | 2023-06-11 | Process & MEICA Meeting Minutes 0001 | For Information | 2023-07-10 | 2023-10-18 | 92 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000021 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0001" |  | 2023-06
000022 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0002 | 0 | 131242-WST00-MI-P-0002 | 2023-06-11 | Process & MEICA Meeting Minutes 0002 | For Information | 2023-07-10 | 2024-03-18 | 200 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000022 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0002" |  | 2023-06
000023 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0003 | 0 | 131242-WST00-MI-P-0003 | 2023-06-11 | Process & MEICA Meeting Minutes 0003 | For Information | 2023-07-10 | 2024-03-18 | 200 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000023 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0003" |  | 2023-06
000024 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0004 | 0 | 131242-WST00-MI-P-0004 | 2023-06-11 | Process & MEICA Meeting Minutes 0004 | For Information | 2023-07-10 | 2024-03-18 | 200 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000024 | 2023-06-11 | 2023-06-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0004" |  | 2023-06
000025 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 0 | 131242-WST00-LT-PM-0002 | 2023-06-12 | CVs of Team Member | Approved with comments. Please refer to comment sheet for resubmission. | 2023-07-11 | 2023-06-20 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000025 | 2023-06-12 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" |  | 2023-06
000025 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 1 | 131242-WST00-LT-PM-0002 | 2023-07-12 | CVs of Team Member Part 2 (7 Members) | Rev.1: Approved with comments. Please refer to S.O. comment sheet. | 2023-08-01 | 2023-07-25 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Reply to S.O. Comment Sheet Only | 000025 | 2023-06-12 | 2023-07-12 | 1 | AWC | Approved with Comments | 2 | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" |  | 2023-07
000025 | 02 | Shena/ Htet | PMT | NA | 131242 | NA | LT | PM | Reply to Comment Sheet_#000025 | NA | 131242-NA-LT-PM-Reply to Comment Sheet_#000025 | 2023-09-11 | CVs of Team Member Part 2 (7 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-29 | 2024-09-10 | 261 | Approved with Comments | YES | 2024-09-30 | NO | Resubmitted | 0 |  |  | 000025 | 2023-09-11 | 2023-09-11 | NA | AWC | Approved with Comments | 1 | "CVs of Team Member Part 2 (7 Members)" |  | 2023-09
000026 | 00 | Bryan | HSE | NA | 131242 | WST00 | MS | C | 0001 | 0 | 131242-WST00-MS-C-0001 | 2023-06-13 | Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-29 | 12 | Not Approved | YES | 2023-07-19 | NO | Resubmitted | 0 | 2024-01-10 00:00:00 | In Progress | 000026 | 2023-06-13 | 2023-06-13 | 0 | NAP | Not Approved | 1 | "Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD)" |  | 2023-06
000027 | 00 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 0 | 131242-WST00-RT-PM-0001 | 2023-06-13 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-16 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000027 | 2023-06-13 | 2023-07-14 | 2 | NAP | Approved | 3 | "C4B Monthly Progress Report Number No.01 (05/23)" |  | 2023-06
000027 | 01 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 1 | 131242-WST00-RT-PM-0001 | 2023-07-04 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-24 | 2023-07-13 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000027 | 2023-06-13 | 2023-07-14 | 2 | NAP | Approved | 3 | "C4B Monthly Progress Report Number No.01 (05/23)" |  | 2023-07
000027 | 02 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 2 | 131242-WST00-RT-PM-0001 | 2023-07-14 | C4B Monthly Progress Report Number No.01 (05/23) | Approved | 2023-08-03 | 2023-10-18 | 68 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000027 | 2023-06-13 | 2023-07-14 | 2 | APP | Approved | 3 | "C4B Monthly Progress Report Number No.01 (05/23)" |  | 2023-07
000028 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 0 | 131242-WSD11-VI-M-0001 | 2023-06-14 | Vendor Approval for THP Package | Rev 0: Not approved - Revise and Resubmit | 2023-07-13 | 2023-07-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | NAP | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" |  | 2023-06
000028 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 1 | 131242-WSD11-VI-M-0001 | 2023-07-28 | Vendor Approval for THP Package | Rev 1: Rejected as per contractor requested email dated on 31-Jul-2023 as there has few changes and will resubmit to include the comment sheet in next revision. | 2023-08-18 | 2023-08-01 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | NAP | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" |  | 2023-07
000028 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 2 | 131242-WSD11-VI-M-0001 | 2023-08-02 | Preliminary design and Vendor Approval | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-08-23 | 2023-08-31 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | AWC | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" |  | 2023-08
000028 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 3 | 131242-WSD11-VI-M-0001 | 2023-11-10 | Preliminary design and Vendor Approval - THP Package | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-01 | 2023-12-20 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000028 | 2023-06-14 | 2024-03-01 | 4 | AWC | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" |  | 2023-11
000028 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 4 | 131242-WSD11-VI-M-0001 | 2024-03-01 | Preliminary design and Vendor Approval - THP Package | Rev 4: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-03-21 | 2024-04-26 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Rev3: AWC | 000028 | 2023-06-14 | 2024-03-01 | 4 | AWC | Approved with Comments | 5 | "Vendor Approval for THP Package" && "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" |  | 2024-03
000029 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0002 | 0 | 131242-WST00-MI-C-0002 | 2023-06-16 | CSA Meeting Minutes 0002 | For information | 2023-07-17 | 2023-06-28 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000029 | 2023-06-16 | 2023-06-16 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0002" |  | 2023-06
000030 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0003 | 0 | 131242-WST00-MI-C-0003 | 2023-06-16 | CSA Meeting Minutes 0003 | For information | 2023-07-17 | 2023-06-28 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000030 | 2023-06-16 | 2023-06-16 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0003" |  | 2023-06
000031 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | Z | 0001 | 0 | 131242-WST00-MI-Z-0001 | 2023-06-19 | Engineering Kick Off Meeting Minutes 0001 | For Information | 2023-07-18 | 2024-03-18 | 195 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000031 | 2023-06-19 | 2023-06-19 | 0 | INF | For Information | 1 | "Engineering Kick Off Meeting Minutes 0001" |  | 2023-06
000032 | 00 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 0 | 131242-WST00-MS-C-0002 | 2023-06-19 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-18 | 2023-06-29 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 | 2024-01-10 00:00:00 | In Progress | 000032 | 2023-06-19 | 2024-04-12 | 1 | NAP | Approved | 2 | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " |  | 2023-06
000032 | 01 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 1 | 131242-WST00-MS-C-0002 | 2024-04-12 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000032 | 2023-06-19 | 2024-04-12 | 1 | APP | Approved | 2 | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " |  | 2024-04
000033 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PS | HS | 0001 | 0 | 131242-WST00-PS-HS-0001 | 2023-06-20 | C4B HSE Induction Course | Noted for information | 2023-07-19 | 2023-07-24 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000033 | 2023-06-20 | 2023-06-20 | 0 | INF | For Information | 1 | "C4B HSE Induction Course" |  | 2023-06
000034 | 00 | Kristnnan | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 0 | 131242-WSW41-PP-HS-0003 | 2023-06-21 | Emergency Response Plan | Reporting timeline is not in sequence with what we have. Please use information in your KOM slides when preparing. Review and resubmit. | 2023-07-20 | 2023-08-02 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000034 | 2023-06-21 | 2023-09-07 | 1 | NAP | Approved | 2 | "Emergency Response Plan" |  | 2023-06
000034 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 1 | 131242-WSW41-PP-HS-0003 | 2023-09-07 | Emergency Response Plan | Approved | 2023-09-27 | 2023-09-25 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000034 | 2023-06-21 | 2023-09-07 | 1 | APP | Approved | 2 | "Emergency Response Plan" |  | 2023-09
000035 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0002 | 0 | 131242-WST00-PP-HS-0002 | 2023-06-22 | Project Accident Statistic Board and BCA Board | Rev.0: Not Approved. Please find attached comment sheet for resubmission. | 2023-07-21 | 2023-08-18 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000035 | 2023-06-22 | 2023-06-22 | 0 | NAP | Not Approved | 1 | "Project Accident Statistic Board and BCA Board" |  | 2023-06
000035 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0002 | 1 | 131242-WSW41-PP-HS-0002 | 2023-10-13 | Project Accident Statistic Board and BCA Board | Approved | 2023-11-02 | 2023-10-23 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000035 | 2023-10-13 | 2023-10-13 | 1 | APP | Approved | 1 | "Project Accident Statistic Board and BCA Board" |  | 2023-10
000036 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0004 | 0 | 131242-WST00-MI-C-0004 | 2023-06-28 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-07-27 | 2023-07-12 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000036 | 2023-06-28 | 2023-06-28 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0004_20230614" |  | 2023-06
000037 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0001 | 0 | 131242-WSW41-MI-IM-0001 | 2023-06-28 | BIM Bi-Weekly Meeting Minutes 0001_20230614 | For Information | 2023-07-27 | 2023-07-04 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000037 | 2023-06-28 | 2023-06-28 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0001_20230614" |  | 2023-06
000038 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | B | 0001 | 0 | 131242-WSW41-CL-B-0001 | 2023-07-05 | Temporary Utilities for Contractor’s Site Office | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-02 | 2023-07-21 | 12 | Approved with Comments | YES | 2023-08-10 | NO | Resubmitted | 0 |  |  | 000038 | 2023-07-05 | 2023-07-05 | 0 | AWC | Approved with Comments | 1 | "Temporary Utilities for Contractor’s Site Office" |  | 2023-07
000039 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0001 | 0 | 131242-WSD11-MI-P-0001 | 2023-07-05 | MI-Process & MEICA Meeting Minutes with THP (CAMBI) | For Information | 2023-08-02 | 2024-03-18 | 183 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000039 | 2023-07-05 | 2023-07-05 | 0 | INF | For Information | 1 | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" |  | 2023-07
000040 | 00 | Stanley | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 | 131242-WSW41-LT-PM-0003 | 2023-07-06 | Request for time extension_Programme of works resubmission | The Prolog Submittals number 000040 (need to void) should not be created as new submission, this submission should under Prologs number 000005 because this extension request is referring from Rev. 0 to Rev. 1 - Programme of the Works | 2023-08-03 | 2023-09-22 | 56 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000005&&000040 | 2023-07-06 | 2023-09-26 | 0 | VOID | For Information | 2 | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" |  | 2023-07
000041 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0005 | 0 | 131242-WSW41-MI-C-0005 | 2023-07-06 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-08-03 | 2023-10-18 | 74 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000041 | 2023-07-06 | 2023-07-06 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0004_20230614" |  | 2023-07
000042 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0004 | 0 | 131242-WSW41-LT-PM-0004 | 2023-07-06 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-08-03 | 2023-08-21 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000042 | 2023-07-06 | 2023-07-06 | 0 | AWC | Approved with Comments | 1 | "CVs of Team Members (Part 3)" |  | 2023-07
000042 | 01 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000042 | NA | 131242-WSW41-LT-PM-Reply to Comment Sheet_#000042 | 2023-09-04 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-09-22 | 2024-02-01 | 108 | Approved with Comments | YES | 2024-02-21 | NO | Resubmitted | 0 |  |  | 000042 | 2023-09-04 | 2023-09-04 | NA | AWC | Approved with Comments | 1 | "CVs of Team Members (Part 3)" |  | 2023-09
000043 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0001 | 0 | 131242-WSW41-PS-PM-0001 | 2023-07-07 | Presentation Slide for Monthly Progress Meeting No. 01(0523) | For information only | 2023-08-04 | 2023-07-13 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000043 | 2023-07-07 | 2023-07-07 | 0 | INF | For Information | 1 | "Presentation Slide for Monthly Progress Meeting No. 01(0523)" |  | 2023-07
000044 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0005 | 0 | 131242-WSW41-LT-PM-0005 | 2023-07-07 | CVs of Team Members (Part 4) | Approved | 2023-08-04 | 2023-07-24 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000044 | 2023-07-07 | 2023-07-07 | 0 | APP | Approved | 1 | "CVs of Team Members (Part 4)" |  | 2023-07
000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0002 | 0 | 131242-WSW41-DR-Z-0002 | 2023-07-10 | SITE UTILIZATION PLAN | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000045 | 2023-07-10 | 2023-07-10 | 0 | AWC | Approved with Comments | 1 | "SITE UTILIZATION PLAN" |  | 2023-07
000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 0 | 131242-WSW41-DR-Z-0003 | 2023-07-10 | SITE OFFICE LAYOUT (Rev1) | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000045 | 2023-07-10 | 2023-07-26 | 1 | AWC | Approved | 2 | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" |  | 2023-07
000045 | 01 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 1 | 131242-WSW41-DR-Z-0003 | 2023-07-26 | SITE OFFICE LAYOUT (Rev2) | Approved | 2023-08-16 | 2023-08-02 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000045 | 2023-07-10 | 2023-07-26 | 1 | APP | Approved | 2 | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" |  | 2023-07
000046 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 0 | 131242-WSW41-RT-PM-0002 | 2023-07-12 | C4B Monthly Progress Report Number No.02 (06/23) | Rejected as informed by contractor email dated 12-Jul-2023 there has few changes/ corrections in the attached file. | 2023-08-10 | 2023-07-14 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000046 | 2023-07-12 | 2023-07-14 | 1 | REJ | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.02 (06/23)" |  | 2023-07
000046 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 1 | 131242-WSW41-RT-PM-0002 | 2023-07-14 | C4B Monthly Progress Report Number No.02 (06/23) | Rev. 1 - Approved with comments (see the comment sheet) Resubmission required | 2023-08-03 | 2023-10-18 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000046 | 2023-07-12 | 2023-07-14 | 1 | AWC | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.02 (06/23)" |  | 2023-07
000046 | 02 | Thomas | PCM | NA | Comment Reply Sheet 08112023 | NA | NA | NA | NA | NA | Comment Reply Sheet 08112023-NA-NA-NA-NA | 2023-11-09 | C4B Monthly Progress Report Number No.02 (06/23) | Approved | 2023-11-30 | 2023-11-15 | 4 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000046 | 2023-11-09 | 2023-11-09 | NA | APP | Approved | 1 | "C4B Monthly Progress Report Number No.02 (06/23)" |  | 2023-11
000047 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0002 | 0 | 131242-WSW41-MI-IM-0002 | 2023-07-13 | BIM Bi-Weekly Meeting Minutes 0002_20230628 | For Information | 2023-08-11 | 2023-07-24 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000047 | 2023-07-13 | 2023-07-13 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0002_20230628" |  | 2023-07
000048 | 00 | Matthew | Piping/ BS | NA | 131242 | WSW41 | MI | B | 0001 | 0 | 131242-WSW41-MI-B-0001 | 2023-07-14 | BS Meeting Minutes 0001_20230706 | For Information | 2023-08-14 | 2024-02-15 | 154 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000048 | 2023-07-14 | 2023-07-14 | 0 | INF | For Information | 1 | "BS Meeting Minutes 0001_20230706" |  | 2023-07
000049 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PP | PM | 0002 | 0 | 131242-WSW41-PP-PM-0002 | 2023-07-14 | C4B Manpower Deployment Plan | Approved as noted. Please note that acceptable of the manpower deployment plan shall not relieve the Contractor's responsibility to engage key personnel whenever is required or employ additional manpower to complete and successfully deliver the project timely and safely. | 2023-08-14 | 2023-07-24 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000049 | 2023-07-14 | 2023-07-14 | 0 | APP | Approved | 1 | "C4B Manpower Deployment Plan" |  | 2023-07
000050 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0006 | 0 | 131242-WSW41-MI-C-0006 | 2023-07-14 | CSA Meeting Minutes 0004_20230705 | For Information | 2023-08-14 | 2023-07-24 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000050 | 2023-07-14 | 2023-07-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0004_20230705" |  | 2023-07
000051 | 00 | REY | PMT | NA | 131242 | WSW41 | DR | C | 1000 | 0 | 131242-WSW41-DR-C-1000 | 2023-07-18 | Drawing of Pre-Con Topographical Survey | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-08-16 | 2023-08-11 | 18 | Approved with Comments | YES | 2023-08-31 | NO | Resubmitted | 0 |  | Heng Peng: To clear BIM comments | 000051 | 2023-07-18 | 2023-07-18 | 0 | AWC | Approved with Comments | 1 | "Drawing of Pre-Con Topographical Survey" |  | 2023-07
000052 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0003 | 0 | 131242-WSW41-MI-IM-0003 | 2023-07-18 | BIM Bi-Weekly Meeting Minutes 0003_20230712 | For Information | 2023-08-16 | 2023-07-25 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000052 | 2023-07-18 | 2023-07-18 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0003_20230712" |  | 2023-07
000053 | 00 | Heng Peng | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 0 | 131242-WSW41-LT-PM-0006 | 2023-07-19 | CV of Team Member (BIM Authoring Lead) | R0- Proposed candidate doesn’t meet the requirement. Please refer to "Comment sheet - Submittal 000053.0" | 2023-08-17 | 2023-10-23 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000053 | 2023-07-19 | 2023-12-11 | 1 | NAP | Not Approved | 2 | "CV of Team Member (BIM Authoring Lead)" |  | 2023-07
000053 | 01 | Leon | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 1 | 131242-WSW41-LT-PM-0006 | 2023-12-11 | CV of Team Member (BIM Authoring Lead) | R1- Subject to 6 months' probation period. Please refer to "Comment sheet - Submittal 000053.1" | 2024-01-02 | 2023-12-22 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000053 | 2023-07-19 | 2023-12-11 | 1 | NAP | Not Approved | 2 | "CV of Team Member (BIM Authoring Lead)" |  | 2023-12
000054 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0007 | 0 | 131242-WSW41-MI-C-0007 | 2023-07-24 | CSA Meeting Minutes 0007_20230712 | For Information | 2023-08-22 | 2023-08-10 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000054 | 2023-07-24 | 2023-07-24 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0007_20230712" |  | 2023-07
000055 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0001 | 0 | 131242-WSW41-PC-W-0001 | 2023-07-24 | PROGRESS CLAIM NO.1 | Accepted. Please refer to S.O. Correspondence no. 25 dated 25 July 2023. | 2023-08-22 | 2023-08-30 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000055 | 2023-07-24 | 2023-07-24 | 0 | APP | Approved | 1 | "PROGRESS CLAIM NO.1" |  | 2023-07
000056 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0004 | 0 | 131242-WSW41-PP-HS-0004 | 2023-07-27 | Signboard Sticker for TWRP Main Gate route 3 entrance | For information | 2023-08-25 | 2023-08-02 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000056 | 2023-07-27 | 2023-07-27 | 0 | INF | For Information | 1 | "Signboard Sticker for TWRP Main Gate route 3 entrance" |  | 2023-07
000057 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0002 | 0 | 131242-WSW41-PS-PM-0002 | 2023-07-28 | Presentation Slide for Monthly Progress Meeting No. 02(0623) | For information | 2023-08-28 | 2023-08-01 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000057 | 2023-07-28 | 2023-07-28 | 0 | INF | For Information | 1 | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" |  | 2023-07
000058 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 0 | 131242-WSW41-MS-C-0003 | 2023-07-28 | MSRA, SWP for General Civil Works | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-28 | 2023-08-14 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | AWC | Approved | 4 | "MSRA, SWP for General Civil Works" |  | 2023-07
000058 | 01 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 1 | 131242-WSW41-MS-C-0003 | 2024-01-22 | MSRA, SWP for General Civil Works | Rev.1: Approved with comments. Please refer to attached comment sheet for resubmission. | 2024-02-09 | 2024-02-21 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | AWC | Approved | 4 | "MSRA, SWP for General Civil Works" |  | 2024-01
000058 | 02 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 2 | 131242-WSW41-MS-C-0003 | 2024-04-12 | MSRA, SWP for General Civil Works | Rev.2: Approved | 2024-05-03 | 2024-06-06 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | APP | Approved | 4 | "MSRA, SWP for General Civil Works" |  | 2024-04
000058 | 03 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 3 | 131242-WSW41-MS-C-0003 | 2025-03-20 | MSRA, SWP for General Civil Works | R3: Approved | 2025-04-09 | 2025-05-07 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000058 | 2023-07-28 | 2025-03-20 | 3 | APP | Approved | 4 | "MSRA, SWP for General Civil Works" |  | 2025-03
000059 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0005 | 0 | 131242-WSW41-VI-C-0005 | 2023-08-01 | Vendor Approval of Concrete Supplier-Alliance | Rev.0: Approved | 2023-08-30 | 2023-08-10 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000059 | 2023-08-01 | 2023-08-01 | 0 | APP | Approved | 1 | "Vendor Approval of Concrete Supplier-Alliance" |  | 2023-08
000060 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-W-0002 | 2023-08-01 | Adjustment of Stage Payment | Rejected as contractor would like to resubmit with the correct reference. | 2023-08-30 | 2023-08-02 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000060&&000080 | 2023-08-01 | 2023-08-25 | 0 | REJ | Approved | 2 | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" |  | 2023-08
000060 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0008 | 0 | 131242-WSW41-LT-PM-0008 | 2023-08-02 | Adjustment of Stage Payment | Rejected. Contractor to re-submit. Please refer to S.O. correspondence no. 55 dated 13 Sep 2023. | 2023-08-23 | 2023-09-15 | 32 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000060 | 2023-08-02 | 2023-08-02 | 0 | REJ | Rejected | 1 | "Adjustment of Stage Payment" |  | 2023-08
000060 | 02 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0014 | 0 | 131242-WSW41-LT-PM-0014 | 2023-10-18 | Adjustment of Stage Payment | For Information | 2023-11-07 | 2023-12-18 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000060 | 2023-10-18 | 2023-10-18 | 0 | INF | For Information | 1 | "Adjustment of Stage Payment" |  | 2023-10
000061 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0009 | 0 | 131242-WSW41-LT-PM-0009 | 2023-08-03 | CV of Team Member (CM) | Approved | 2023-09-01 | 2023-08-11 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000061 | 2023-08-03 | 2023-08-03 | 0 | APP | Approved | 1 | "CV of Team Member (CM)" |  | 2023-08
000062 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0007 | 0 | 131242-WSW41-LT-PM-0007 | 2023-08-03 | Request for Variable Site Management Team Payment | Rev(0) Accepted. Please refer to S.O. correspondence no. 84 dated 22 Nov 2023. | 2023-09-01 | 2024-01-30 | 128 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000062 | 2023-08-03 | 2023-08-03 | 0 | INF | For Information | 1 | "Request for Variable Site Management Team Payment" |  | 2023-08
000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0008 | 0 | 131242-WSW41-MI-C-0008 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000063 | 2023-08-07 | 2023-08-07 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" |  | 2023-08
000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0009 | 0 | 131242-WSW41-MI-C-0009 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000063 | 2023-08-07 | 2023-08-07 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" |  | 2023-08
000064 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 0 | 131242-WSW41-VI-C-0006 | 2023-08-08 | Vendor Approval of Concrete Supplier-Pan United | Rev.0: Approved with comment. Please refer to attached comment sheet for resubmission. | 2023-09-06 | 2023-08-30 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000064 | 2023-08-08 | 2023-09-22 | 1 | AWC | Approved | 2 | "Vendor Approval of Concrete Supplier-Pan United" |  | 2023-08
000064 | 01 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 1 | 131242-WSW41-VI-C-0006 | 2023-09-22 | Vendor Approval of Concrete Supplier-Pan United | Approved | 2023-10-12 | 2023-09-25 | 1 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000064 | 2023-08-08 | 2023-09-22 | 1 | APP | Approved | 2 | "Vendor Approval of Concrete Supplier-Pan United" |  | 2023-09
000065 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | CN | E | 0001 | 0 | 131242-WSW41-CN-E-0001 | 2023-08-08 | RFC For HV Routing (from C3B1) to SSN Transformer Room | Approved. Refer comment sheet for more details. | 2023-09-06 | 2024-02-15 | 137 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000065 | 2023-08-08 | 2023-08-08 | 0 | APP | Approved | 1 | "RFC For HV Routing (from C3B1) to SSN Transformer Room" |  | 2023-08
000066 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0001 | 0 | 131242-WSW41-CD-IM-0001 | 2023-08-08 | Submission Of BIM Coordination VCM Model (July – 2023) | Approved with Comments. Please refer to "Comments Sheet_Sub-0066-0" | 2023-09-06 | 2023-08-24 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000066 | 2023-08-08 | 2023-08-08 | 0 | AWC | Approved with Comments | 1 | "Submission Of BIM Coordination VCM Model (July – 2023)" |  | 2023-08
000067 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0007 | 0 | 131242-WSW41-VI-C-0007 | 2023-08-11 | Vendor Approval of Rebar Supplier-BRC ASIA LIMITED | Approved | 2023-09-08 | 2023-08-30 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000067 | 2023-08-11 | 2023-08-11 | 0 | APP | Approved | 1 | "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" |  | 2023-08
000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0005 | 0 | 131242-WSW41-MI-P-0005 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000068 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" |  | 2023-08
000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0006 | 0 | 131242-WSW41-MI-P-0006 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000068 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" |  | 2023-08
000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0001 | 0 | 131242-WST02-MI-P-0001 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000069 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" |  | 2023-08
000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0002 | 0 | 131242-WST02-MI-P-0002 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | 155 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000069 | 2023-08-14 | 2023-08-14 | 0 | INF | For Information | 1 | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" |  | 2023-08
000070 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 0 | 131242-WSW41-RT-PM-0003 | 2023-08-14 | C4B Monthly Progress Report Number No.03 (07/23) | Rev. 0 - Approved with Comments . Refer to Comments sheet to re-submit. | 2023-09-11 | 2023-08-29 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000070 | 2023-08-14 | 2023-09-25 | 1 | AWC | Approved | 2 | "C4B Monthly Progress Report Number No.03 (07/23)" |  | 2023-08
000070 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 1 | 131242-WSW41-RT-PM-0003 | 2023-09-25 | C4B Monthly Progress Report Number No.03 (07/23) | Approved | 2023-10-13 | 2023-09-27 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000070 | 2023-08-14 | 2023-09-25 | 1 | APP | Approved | 2 | "C4B Monthly Progress Report Number No.03 (07/23)" |  | 2023-09
000071 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0009 | 0 | 131242-WSW41-VI-C-0009 | 2023-08-15 | Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000071 | 2023-08-15 | 2023-08-15 | 0 | APP | Approved | 1 | "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." |  | 2023-08
000072 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0010 | 0 | 131242-WSW41-VI-C-0010 | 2023-08-15 | Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000072 | 2023-08-15 | 2023-08-15 | 0 | APP | Approved | 1 | "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." |  | 2023-08
000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0004 | 0 | 131242-WSW41-MI-IM-0004 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000073 | 2023-08-15 | 2023-08-15 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" |  | 2023-08
000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0005 | 0 | 131242-WSW41-MI-IM-0005 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000073 | 2023-08-15 | 2023-08-15 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" |  | 2023-08
000074 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0008 | 0 | 131242-WSW41-VI-C-0008 | 2023-08-16 | Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd | Approved | 2023-09-13 | 2023-08-30 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000074 | 2023-08-16 | 2023-08-16 | 0 | APP | Approved | 1 | "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" |  | 2023-08
000075 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0011 | 0 | 131242-WSW41-LT-PM-0011 | 2023-08-22 | CV of Team Member (WSHC) | Approved | 2023-09-19 | 2023-09-25 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000075 | 2023-08-22 | 2023-08-22 | 0 | APP | Approved | 1 | "CV of Team Member (WSHC)" |  | 2023-08
000076 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0010 | 0 | 131242-WSW41-LT-PM-0010 | 2023-08-22 | Delegation of Signing Authorities | For Information | 2023-09-19 | 2023-09-25 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000076 | 2023-08-22 | 2023-08-22 | 0 | INF | For Information | 1 | "Delegation of Signing Authorities" |  | 2023-08
000077 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0003 | 0 | 131242-WSW41-PS-PM-0003 | 2023-08-28 | Presentation Slide for Monthly Progress Meeting No. 03(0723) | For Information | 2023-09-25 | 2023-08-24 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000077 | 2023-08-28 | 2023-08-28 | 0 | INF | For Information | 1 | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" |  | 2023-08
000078 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0001 | 0 | 131242-WSW41-RT-Z-0001 | 2023-08-24 | Photographic Survey Report for C4B | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-09-21 | 2023-08-30 | 4 | Not Approved | YES | 2023-09-19 | NO | Resubmitted | 0 |  |  | 000078 | 2023-08-24 | 2023-08-24 | 0 | NAP | Not Approved | 1 | "Photographic Survey Report for C4B" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 1.0 Design Brief | NA | NA | NA | NA | NA | 1.0 Design Brief-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-08-31 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | NAP | Not Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003 | NA | NA | NA | NA | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 3.0 Overall SSN area Loading Plan Marked up | NA | NA | NA | NA | NA | 3.0 Overall SSN area Loading Plan Marked up-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 4.0 SSN Overall Area Layout and Elevations | NA | NA | NA | NA | NA | 4.0 SSN Overall Area Layout and Elevations-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 5.0 Soil Report | NA | NA | NA | NA | NA | 5.0 Soil Report-NA-NA-NA-NA | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-08-24 | NA | APP | Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A | 131242-WST00-DR-C-8000_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | APP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A | 131242-WST00-DR-S-1000_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | APP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" |  | 2023-08
000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A | 131242-WST02-DR-C-1001_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | APP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-08
000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A | 131242-WST02-DR-C-5001_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | APP | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-08
000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A | 131242-WST02-DR-C-7000_ST604 | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | APP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-08
000079 | 01 | Zora | CSA | NA | 1. C4B SSN Overall Piling Design Brief | NA | NA | NA | NA | NA | 1. C4B SSN Overall Piling Design Brief-NA-NA-NA-NA | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-16 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-09-26 | 2023-09-26 | NA | NAP | Not Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-09
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | C | 0001_ST604 | 0 | 131242-WST02-CL-C-0001_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-09-26 | 2023-09-26 | 0 | NAP | Not Approved | 1 | "ST604 – Overall SSN area Piling Design" |  | 2023-09
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A1 | 131242-WST02-DR-C-1001_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-09
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A1 | 131242-WST02-DR-C-5001_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-09
000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A1 | 131242-WST02-DR-C-7000_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-09
000079 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A1 | 131242-WST00-DR-C-8000_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" |  | 2023-09
000079 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-S-1000_ST604 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" |  | 2023-09
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-S-1000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | 000079 | 2023-08-24 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" |  | 2023-11
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A1 | 131242-WST02-DR-C-1001_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-11
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A1 | 131242-WST02-DR-C-5001_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-11
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A1 | 131242-WST02-DR-C-7000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2023-11
000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A1 | 131242-WST00-DR-C-8000_ST604 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | 10 | Approved with Comments | YES | 2023-12-11 | NO | Resubmitted | 0 |  |  | 000079 | 2023-08-24 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "ST604 – Overall SSN area Piling Design" |  | 2023-11
000080 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-W-0002 | 2023-08-25 | PAYMENT CLAIM NO.2 | Accepted. Please refer to S.O. Correspondence no. 48 dated 29 August 2023. | 2023-09-22 | 2023-08-30 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000060&&000080 | 2023-08-01 | 2023-08-25 | 0 | APP | Approved | 2 | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" |  | 2023-08
000081 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 0 | 131242-WSW41-SP-C-0001 | 2023-08-28 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-09-25 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000081 | 2023-08-28 | 2023-10-05 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " |  | 2023-08
000081 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 1 | 131242-WSW41-SP-C-0001 | 2023-10-05 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.1: Approved | 2023-10-25 | 2023-10-18 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000081 | 2023-08-28 | 2023-10-05 | 1 | APP | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " |  | 2023-10
000082 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0006 | 0 | 131242-WSW41-MI-IM-0006 | 2023-08-28 | BIM Bi-Weekly Meeting Minutes 0006_20230823 | For Information | 2023-09-25 | 2023-09-06 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000082 | 2023-08-28 | 2023-08-28 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0006_20230823" |  | 2023-08
000083 | 00 | Zora | CSA | NA | 131242 | WSW41 | SK | S | 0001 | 0 | 131242-WSW41-SK-S-0001 | 2023-08-28 | Sidewide Pipe Rack GA and Reactions | Not Approved. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-10-06 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2023-08-28 | 2023-08-28 | 0 | NAP | Not Approved | 1 | "Sidewide Pipe Rack GA and Reactions" |  | 2023-08
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A | 131242-WSW41-DR-S-1000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-01 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A | 131242-WSW41-DR-S-1004_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A | 131242-WSW41-DR-S-1007_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A | 131242-WSW41-DR-S-1008_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A | 131242-WSW41-DR-S-1009_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A | 131242-WSW41-DR-S-1010_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A | 131242-WSW41-DR-S-2000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A | 131242-WSW41-DR-S-2001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A | 131242-WSW41-DR-S-2002_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A | 131242-WSW41-DR-S-3000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A | 131242-WSW41-DR-S-3001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A | 131242-WSW41-DR-S-5000_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A | 131242-WSW41-DR-S-5001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A | 131242-WSW41-DR-S-5002_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A | 131242-WSW41-DR-S-8001_ST603 | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 01 | Zora | CSA | NA | Site wide PR Reactions for information | NA | NA | NA | NA | NA | Site wide PR Reactions for information-NA-NA-NA-NA | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-01-13 | NA | NAP | Not Approved | 1 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-01
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.1 | 131242-WSW41-DR-S-1000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-01 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  | Rev 1 : Not Approved. | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A.1 | 131242-WSW41-DR-S-1004_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A.1 | 131242-WSW41-DR-S-1007_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A.1 | 131242-WSW41-DR-S-1008_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A.1 | 131242-WSW41-DR-S-1009_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A.1 | 131242-WSW41-DR-S-1010_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A.1 | 131242-WSW41-DR-S-2000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A.1 | 131242-WSW41-DR-S-2001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A.1 | 131242-WSW41-DR-S-2002_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A.1 | 131242-WSW41-DR-S-3000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A.1 | 131242-WSW41-DR-S-3001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A.1 | 131242-WSW41-DR-S-5000_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A.1 | 131242-WSW41-DR-S-5001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A.1 | 131242-WSW41-DR-S-5002_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST603 | A.1 | 131242-WSW41-DR-S-5003_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5004_ST603 | A | 131242-WSW41-DR-S-5004_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A.1 | 131242-WSW41-DR-S-8001_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST603 | A | 131242-WSW41-DR-S-0300_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST603 | A.1 | 131242-WSW41-DR-S-0301_ST603 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-03
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | CL | S | 1000_ST603 | 2 | 131242-WSW41-CL-S-1000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  | To clear technical comments first and Heng Peng to clear BIM comments. | 000083 | 2024-06-08 | 2024-06-08 | 2 | NAP | Not Approved | 1 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.2 | 131242-WSW41-DR-S-1000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A.2 | 131242-WSW41-DR-S-1004_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A.2 | 131242-WSW41-DR-S-1007_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A.2 | 131242-WSW41-DR-S-1008_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A.2 | 131242-WSW41-DR-S-1009_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A.2 | 131242-WSW41-DR-S-1010_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A.2 | 131242-WSW41-DR-S-2000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A.1 | 131242-WSW41-DR-S-2001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A.2 | 131242-WSW41-DR-S-2002_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A.1 | 131242-WSW41-DR-S-3000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A.2 | 131242-WSW41-DR-S-3001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A.1 | 131242-WSW41-DR-S-5000_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.1 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A.2 | 131242-WSW41-DR-S-5001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A.2 | 131242-WSW41-DR-S-5002_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST603 | A.2 | 131242-WSW41-DR-S-5003_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5004_ST603 | A.2 | 131242-WSW41-DR-S-5004_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A.2 | 131242-WSW41-DR-S-8001_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-01-13 | 2024-06-08 | A.2 | NAP | Not Approved | 3 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST603 | A | 131242-WSW41-DR-S-0300_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST603 | A.2 | 131242-WSW41-DR-S-0301_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-03-11 | 2024-06-08 | A.2 | NAP | Not Approved | 2 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0302_ST603 | A | 131242-WSW41-DR-S-0302_ST603 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | 15 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000083 | 2024-06-08 | 2024-06-08 | A | NAP | Not Approved | 1 | "ST603 - Site Wide Pipe Rack Details" |  | 2024-06
000084 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | S | 0002 | 0 | 131242-WSW41-VI-S-0002 | 2023-08-28 | Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd. | Approved | 2023-09-25 | 2023-09-25 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000084 | 2023-08-28 | 2023-08-28 | 0 | APP | Approved | 1 | "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." |  | 2023-08
000085 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0002 | 0 | 131242-WSW41-SP-C-0002 | 2023-08-31 | Concrete Design Mix for ULT Test Pile C50/60 (Alliance) | Approved | 2023-09-28 | 2023-09-25 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000085 | 2023-08-31 | 2023-08-31 | 0 | APP | Approved | 1 | "Concrete Design Mix for ULT Test Pile C50/60 (Alliance) " |  | 2023-08
000086 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | Z | 0001 | 0 | 131242-WSW41-CL-Z-0001 | 2023-08-31 | ECM Plan and Calculation | Approved | 2023-09-28 | 2023-10-04 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000086 | 2023-08-31 | 2023-08-31 | 0 | APP | Approved | 1 | "ECM Plan and Calculation" |  | 2023-08
000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0001 | 0 | 131242-WSW41-MI-PM-0001 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000087 | 2023-09-04 | 2023-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" |  | 2023-09
000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0002 | 0 | 131242-WSW41-MI-PM-0002 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000087 | 2023-09-04 | 2023-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" |  | 2023-09
000088 | 00 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 0 | 131242-WST02-VI-M-0001 | 2023-09-05 | Preliminary design and Vendor Approval for SSN Package | Rev 0: Not approved - Revise and Resubmit | 2023-10-03 | 2023-09-25 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000088 | 2023-09-05 | 2024-02-03 | 3 | NAP | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" |  | 2023-09
000088 | 01 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 1 | 131242-WST02-VI-M-0001 | 2023-10-05 | Preliminary design and Vendor Approval for SSN Package | Rev 1: Not approved - Revise and Resubmit Document not approved as requested by Contractor. | 2023-10-25 | 2023-10-23 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000088 | 2023-09-05 | 2024-02-03 | 3 | NAP | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" |  | 2023-10
000088 | 02 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 2 | 131242-WST02-VI-M-0001 | 2023-10-31 | Preliminary design and Vendor Approval for SSN Package | Rev 2: Approved with Comments, subject to clarification of comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-21 | 2023-11-08 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000088 | 2023-09-05 | 2024-02-03 | 3 | AWC | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" |  | 2023-10
000088 | 03 | Joo kwan | Process | NA | 131242 | WST02 | VI | M | 0001 | 3 | 131242-WST02-VI-M-0001 | 2024-02-03 | Preliminary design and Vendor Approval for SSN Package | Rev 3: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-02-23 | 2024-04-29 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Rev 2: AWC | 000088 | 2023-09-05 | 2024-02-03 | 3 | AWC | Approved with Comments | 4 | "Preliminary design and Vendor Approval for SSN Package" |  | 2024-02
000089 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0007 | 0 | 131242-WSW41-MI-P-0007 | 2023-09-05 | Process & MEICA Meeting Minutes 0007_20230718 | For Information | 2023-10-03 | 2024-03-18 | 139 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000089 | 2023-09-05 | 2023-09-05 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0007_20230718" |  | 2023-09
000090 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | D | 0001 | 0 | 131242-WSW41-VI-D-0001 | 2023-09-07 | Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq) | Approved | 2023-10-05 | 2023-09-25 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000090 | 2023-09-07 | 2023-09-07 | 0 | APP | Approved | 1 | "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" |  | 2023-09
000091 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0002 | 0 | 131242-WSW41-RT-Z-0002 | 2023-09-07 | Cable Detection Report | Approved with comments. Please refer to comment sheet for resubmission. | 2023-10-05 | 2023-09-25 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000091 | 2023-09-07 | 2023-09-07 | 0 | AWC | Approved with Comments | 1 | "Cable Detection Report" |  | 2023-09
000091 | 01 | Eng Bee | PMT | NA | Reply to Comment Sheet_#000091 | NA | NA | NA | NA | NA | Reply to Comment Sheet_#000091-NA-NA-NA-NA | 2023-10-06 | Cable Detection Report | Approved | 2023-10-26 | 2023-10-18 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000091 | 2023-10-06 | 2023-10-06 | NA | APP | Approved | 1 | "Cable Detection Report" |  | 2023-10
000092 | 00 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 0 | 131242-WSW41-SP-M-8001 | 2023-09-08 | Piping Material Specification | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-10-06 | 2023-09-25 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000092 | 2023-09-08 | 2024-12-13 | 3 | AWC | Approved | 4 | "Piping Material Specification" |  | 2023-09
000092 | 01 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 1 | 131242-WSW41-SP-M-8001 | 2024-02-22 | Piping Material Specification | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-13 | 2024-04-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Rev 0: AWC | 000092 | 2023-09-08 | 2024-12-13 | 3 | AWC | Approved | 4 | "Piping Material Specification" |  | 2024-02
000092 | 02 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 2 | 131242-WSW41-SP-M-8001 | 2024-08-07 | Piping Material Specification | Rev 2: Approved | 2024-08-28 | 2024-09-02 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000092 | 2023-09-08 | 2024-12-13 | 3 | APP | Approved | 4 | "Piping Material Specification" |  | 2024-08
000092 | 03 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 3 | 131242-WSW41-SP-M-8001 | 2024-12-13 | Piping Material Specification | Rev 3: Approved | 2025-01-03 | 2025-01-20 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000092 | 2023-09-08 | 2024-12-13 | 3 | APP | Approved | 4 | "Piping Material Specification" |  | 2024-12
000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | 0 | 131242-WSW41-DR-P-6000 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2023-09
000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | 0 | 131242-WSW41-DR-P-6001 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2023-09
000093 | 00 | Qili | Process | NA | Pipeline - All_Data Report | NA | NA | NA | NA | NA | Pipeline - All_Data Report-NA-NA-NA-NA | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2023-09-08 | NA | AWC | Approved with Comments | 1 | "Piperack P&IDs" |  | 2023-09
000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6000 | B | 131242-WSW41-DR-P-6000 | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 | Rev 0: AWC | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2024-03
000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6001 | B | 131242-WSW41-DR-P-6001 | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2024-03
000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | C | 131242-WSW41-DR-P-6000 | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2024-08
000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | C | 131242-WSW41-DR-P-6001 | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2024-08
000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | D | 131242-WSW41-DR-P-6000 | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | comments received on 14 Feb | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2024-12
000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | D | 131242-WSW41-DR-P-6001 | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2024-12
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-P-6000 | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2025-03
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | E | 131242-WSW41-DR-P-6001 | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | AWC | Approved with Comments | 6 | "Piperack P&IDs" |  | 2025-03
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-P-6000 | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 | 0 | Awaiting S.O.'s response | YES | 2025-05-20 | NO | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | PEN | Approved with Comments | 6 | "Piperack P&IDs" |  | 2026-02
000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | E | 131242-WSW41-DR-P-6001 | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 | 0 | Awaiting S.O.'s response | YES | 2025-05-20 | NO | Resubmitted | 0 |  |  | 000093 | 2023-09-08 | 2026-02-24 | E | PEN | Approved with Comments | 6 | "Piperack P&IDs" |  | 2026-02
000094 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0002 | 0 | 131242-WSW41-CD-IM-0002 | 2023-09-08 | Submission Of BIM Coordination VCM Model (Aug – 2023) | For Information | 2023-10-06 | 2023-09-21 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000094 | 2023-09-08 | 2023-09-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Aug – 2023)" |  | 2023-09
000095 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0007 | 0 | 131242-WSW41-MI-IM-0007 | 2023-09-11 | BIM Bi-Weekly Meeting Minutes 0007_20230906 | For Information | 2023-10-09 | 2023-10-03 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000095 | 2023-09-11 | 2023-09-11 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0007_20230906" |  | 2023-09
000096 | 00 | Darren | Piping/ BS | NA | 131242 | WST02 | CL | B | 0002 | 0 | 131242-WST02-CL-B-0002 | 2023-09-12 | Engineering Calculation Report For Fire Hydrant Pipe | Rev 0: Rejected as requested by contractor. | 2023-10-10 | 2023-11-10 | 43 | Rejected | NO |  | YES | Resubmitted | 0 |  | Kindly refer to Submittal 000193 | 000096&&000193 | 2023-09-12 | 2023-11-17 | 1 | REJ | Not Approved | 2 | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" |  | 2023-09
000097 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0003 | 0 | 131242-WST02-CL-B-0003 | 2023-09-12 | Engineering Calculation Report For Potable Water Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-10-10 | 2023-11-10 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000097&&000194 | 2023-09-12 | 2023-11-17 | 1 | NAP | (VOID NOT IN USE) | 2 | "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" |  | 2023-09
000097 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 1 | 131242-WST02-CL-BP-8000 | 2024-05-30 | Engineering Calculation Report For Potable Water Pipe | Rev 1: Not approved - Revise and Resubmit | 2024-06-20 | 2024-07-09 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 | 2024-08-09 00:00:00 | To check with C2D for resubmission | 000097 | 2024-05-30 | 2025-02-18 | 3 | NAP | Approved | 3 | "Engineering Calculation Report For Potable Water Pipe" |  | 2024-05
000097 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 2 | 131242-WST02-CL-BP-8000 | 2024-10-17 | Engineering Calculation Report For Potable Water Pipe | Rev 2: Not approved - Revise and Resubmit | 2024-11-07 | 2024-11-25 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000097 | 2024-05-30 | 2025-02-18 | 3 | NAP | Approved | 3 | "Engineering Calculation Report For Potable Water Pipe" |  | 2024-10
000097 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 3 | 131242-WST02-CL-BP-8000 | 2025-02-18 | Engineering Calculation Report For Potable Water Pipe | Rev3: Approved | 2025-03-10 | 2025-03-25 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000097 | 2024-05-30 | 2025-02-18 | 3 | APP | Approved | 3 | "Engineering Calculation Report For Potable Water Pipe" |  | 2025-02
000098 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 0 | 131242-WSW41-RT-PM-0004 | 2023-09-13 | C4B Monthly Progress Report Number No.04 (08/23) | Rev. 0 - Not Approved need to re-submit (see attached comment sheet) | 2023-10-11 | 2023-09-20 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000098 | 2023-09-13 | 2023-10-04 | 1 | NAP | Approved | 2 | "C4B Monthly Progress Report Number No.04 (08/23)" |  | 2023-09
000098 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 1 | 131242-WSW41-RT-PM-0004 | 2023-10-04 | C4B Monthly Progress Report Number No.04 (08/23) | Approved | 2023-10-24 | 2023-10-06 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000098 | 2023-09-13 | 2023-10-04 | 1 | APP | Approved | 2 | "C4B Monthly Progress Report Number No.04 (08/23)" |  | 2023-10
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | 0 | 131242-WSW41-DR-M-5002 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5003 | 0 | 131242-WSW41-DR-M-5003 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5004 | 0 | 131242-WSW41-DR-M-5004 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5005 | 0 | 131242-WSW41-DR-M-5005 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5006 | 0 | 131242-WSW41-DR-M-5006 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5007 | 0 | 131242-WSW41-DR-M-5007 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5008 | 0 | 131242-WSW41-DR-M-5008 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | NAP | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2023-09
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5001 | A1 | 131242-WSW41-DR-M-5001 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-01 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 | Submitted | Under M2 submission (Shall be Submitted After M3 WT) | 000099 | 2024-03-11 | 2024-03-11 | A1 | AWC | Approved with Comments | 1 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | A1 | 131242-WSW41-DR-M-5002 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5003 | A1 | 131242-WSW41-DR-M-5003 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5004 | A1 | 131242-WSW41-DR-M-5004 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5005 | A1 | 131242-WSW41-DR-M-5005 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5006 | A1 | 131242-WSW41-DR-M-5006 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5007 | A1 | 131242-WSW41-DR-M-5007 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5008 | A1 | 131242-WSW41-DR-M-5008 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | 38 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000099 | 2023-09-13 | 2024-03-11 | A1 | AWC | Approved with Comments | 2 | "C4B Sitewide Piping GA Drawing" |  | 2024-03
000100 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0001 | 0 | 131242-WSD11-PO-M-0001 | 2023-09-14 | Unpriced PO for THP Package (Cambi) | For Information | 2023-10-12 | 2023-11-27 | 52 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000100 | 2023-09-14 | 2023-09-14 | 0 | INF | For Information | 1 | "Unpriced PO for THP Package (Cambi)" |  | 2023-09
000101 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0005 | 0 | 131242-WSW41-PP-HS-0005 | 2023-09-14 | Heat Stress Prevention Program | Approved | 2023-10-12 | 2023-09-25 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000101 | 2023-09-14 | 2023-09-14 | 0 | APP | Approved | 1 | "Heat Stress Prevention Program" |  | 2023-09
000102 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 0 | 131242-WSW41-VI-M-0011 | 2023-09-18 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000102 | 2023-09-18 | 2024-06-07 | 2 | AWC | Approved | 3 | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" |  | 2023-09
000102 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 1 | 131242-WSW41-VI-M-0011 | 2024-01-04 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-24 | 2024-02-15 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Drawings are ready to re-submit. Pending update data sheet from INGERSOLL-RAND. | 000102 | 2023-09-18 | 2024-06-07 | 2 | AWC | Approved | 3 | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" |  | 2024-01
000102 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 2 | 131242-WSW41-VI-M-0011 | 2024-06-07 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 2: Approved | 2024-06-28 | 2024-07-12 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  | R1_AWC | 000102 | 2023-09-18 | 2024-06-07 | 2 | APP | Approved | 3 | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" |  | 2024-06
000103 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 0 | 131242-WSW41-VI-M-0004 | 2023-09-18 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 00:00:00 |  | 000103 | 2023-09-18 | 2025-05-30 | 1 | AWC | Approved | 2 | "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" |  | 2023-09
000103 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 1 | 131242-WSW41-VI-M-0004 | 2025-05-30 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev1: Approved | 2025-06-19 | 2025-08-01 | 45 | Approved | NO |  | YES | Resubmitted | 0 | 2025-02-20 00:00:00 |  | 000103 | 2023-09-18 | 2025-05-30 | 1 | APP | Approved | 2 | "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" |  | 2025-05
000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0008 | 0 | 131242-WSW41-MI-P-0008 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | 129 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000104 | 2023-09-19 | 2023-09-19 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" |  | 2023-09
000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0009 | 0 | 131242-WSW41-MI-P-0009 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | 129 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000104 | 2023-09-19 | 2023-09-19 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" |  | 2023-09
000105 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0012 | 0 | 131242-WSW41-LT-PM-0012 | 2023-09-19 | CV of Team Member (WSHO) | Approved | 2023-10-17 | 2023-10-18 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000105 | 2023-09-19 | 2023-09-19 | 0 | APP | Approved | 1 | "CV of Team Member (WSHO)" |  | 2023-09
000106 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0004 | 0 | 131242-WSW41-PS-PM-0004 | 2023-09-21 | Monthly Progress Presentation No. 04 (0823) | For Information | 2023-10-19 | 2023-09-25 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000106 | 2023-09-21 | 2023-09-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 04 (0823)" |  | 2023-09
000107 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 0 | 131242-WSW41-VI-M-0006 | 2023-09-25 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Approved with Comments. To revise and resubmit. Refer to comments file. | 2023-10-23 | 2023-10-16 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 | In Progress | 000107 | 2023-09-25 | 2024-07-31 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" |  | 2023-09
000107 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 1 | 131242-WSW41-VI-M-0006 | 2024-07-31 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Rev 1: Approved | 2024-08-21 | 2024-09-02 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000107 | 2023-09-25 | 2024-07-31 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" |  | 2024-07
000108 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | Superceded | 131242-WSW41-CT-W-0001 | 2023-09-27 | On-Demand Bond for THP System | Rev(0): Rejected as requested by Contractor. Note Contractor need to attach a transmittal signed by PUB to the said submittal. | 2023-10-25 | 2023-10-02 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000108 | 2023-09-27 | 2023-10-03 | 0 | REJ | Approved | 2 | "On-Demand Bond for THP System" |  | 2023-09
000108 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | 0 | 131242-WSW41-CT-W-0001 | 2023-10-03 | On-Demand Bond for THP System | Approved. | 2023-10-23 | 2023-10-09 | 4 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000108 | 2023-09-27 | 2023-10-03 | 0 | APP | Approved | 2 | "On-Demand Bond for THP System" |  | 2023-10
000109 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0010 | 0 | 131242-WSW41-MI-C-0010 | 2023-09-27 | CSA Meeting Minutes 0010_20230802 | For Information | 2023-10-25 | 2023-10-18 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000109 | 2023-09-27 | 2023-09-27 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0010_20230802" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | 0 | 131242-WST00-DR-S-0001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 | 2024-07-18 00:00:00 | MEICA layout released on 29/02/2024. Updating as per latest Layout changes of SSN-SH-002 area with Pump pit. Tenwit updating In-Progress. | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0002_ST606 | 0 | 131242-WST00-DR-S-0002_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0003_ST606 | 0 | 131242-WST00-DR-S-0003_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606 | 0 | 131242-WST02-DR-S-1006_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606 | 0 | 131242-WST02-DR-S-1007_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606 | 0 | 131242-WST02-DR-S-1008_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST606 | 0 | 131242-WST02-DR-S-1013_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606 | 0 | 131242-WST02-DR-S-3000_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3001_ST606 | 0 | 131242-WST02-DR-S-3001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5000_ST606 | 0 | 131242-WST02-DR-S-5000_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606 | 0 | 131242-WST02-DR-S-5001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606 | 0 | 131242-WST02-DR-S-5002_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST606 | 0 | 131242-WST02-DR-S-5005_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606 | 0 | 131242-WST02-DR-S-7000_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606 | 0 | 131242-WST02-DR-S-7001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606 | 0 | 131242-WST02-DR-S-7002_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | NAP | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2023-09
000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST606 | 0 | 131242-WST02-DR-S-8001_ST606 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | 13 | Not Approved | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000110 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "ST606 : SSN Overall Sub-Structure Drawings " |  | 2023-09
000111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0003 | 0 | 131242-WSW41-PC-W-0003 | 2023-09-29 | PAYMENT CLAIM NO.3 | Approved | 2023-10-27 | 2023-10-23 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000111 | 2023-09-29 | 2023-09-29 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.3" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-1_URA | 0 | 131242-WST02-DR-A-3D-1_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-2_URA | 0 | 131242-WST02-DR-A-3D-2_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | 0 | NAP | Not Approved | 1 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A | 131242-WST02-DR-A-1000_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A | 131242-WST02-DR-A-1001_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A | 131242-WST02-DR-A-1002_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A | 131242-WST02-DR-A-1003_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A | 131242-WST02-DR-A-1004_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A | 131242-WST02-DR-A-1006_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A | 131242-WST02-DR-A-1009_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A | 131242-WST02-DR-A-2000_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A | 131242-WST02-DR-A-2001_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A | 131242-WST02-DR-A-2002_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A | 131242-WST02-DR-A-2003_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | NAP | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf | NA | NA | NA | NA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf-NA-NA-NA-NA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | NA | NAP | Not Approved | 1 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx | NA | NA | NA | NA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx-NA-NA-NA-NA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | NA | NAP | Not Approved | 1 | "SSN URA Submission" |  | 2023-09
000112 | 00 | Zora | CSA | NA | GFA DWG Supporting Docs | NA | NA | NA | NA | NA | GFA DWG Supporting Docs-NA-NA-NA-NA | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-09-29 | NA | NAP | Not Approved | 1 | "SSN URA Submission" |  | 2023-09
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-A-1000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-06 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A1 | 131242-WST02-DR-A-1001_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A1 | 131242-WST02-DR-A-1002_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A1 | 131242-WST02-DR-A-1003_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A1 | 131242-WST02-DR-A-1004_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A1 | 131242-WST02-DR-A-1006_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A1 | 131242-WST02-DR-A-1009_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A1 | 131242-WST02-DR-A-2000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A1 | 131242-WST02-DR-A-2001_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A1 | 131242-WST02-DR-A-2002_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A1 | 131242-WST02-DR-A-2003_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 9000_URA | A1 | 131242-WST02-DR-A-9000_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 9001_URA | A1 | 131242-WST02-DR-A-9001_URA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | S000112.0_Reply_2023 10 17 | NA | NA | NA | NA | A1 | S000112.0_Reply_2023 10 17-NA-NA-NA-NA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-10-17 | A1 | AWC | Approved with Comments | 1 | "SSN URA Submission" |  | 2023-10
000112 | 01 | Zora | CSA | NA | Supporting Docs | NA | NA | NA | NA | NA | Supporting Docs-NA-NA-NA-NA | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-10-17 | NA | AWC | Approved with Comments | 1 | "SSN URA Submission" |  | 2023-10
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-A-1000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A1 | 131242-WST02-DR-A-1001_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A1 | 131242-WST02-DR-A-1002_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A1 | 131242-WST02-DR-A-1003_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A1 | 131242-WST02-DR-A-1004_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A1 | 131242-WST02-DR-A-1006_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A1 | 131242-WST02-DR-A-1009_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A1 | 131242-WST02-DR-A-2000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A1 | 131242-WST02-DR-A-2001_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A1 | 131242-WST02-DR-A-2002_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A1 | 131242-WST02-DR-A-2003_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A1 | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-09-29 | 2023-11-07 | A | AWC | Approved with Comments | 3 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 9000_URA | A1 | 131242-WST02-DR-A-9000_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 9001_URA | A1 | 131242-WST02-DR-A-9001_URA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-10-17 | 2023-11-07 | A1 | AWC | Approved with Comments | 2 | "SSN URA Submission" |  | 2023-11
000112 | 02 | Zora/ HP | CSA | NA | S000112.1_Reply_2023 10 17 | NA | NA | NA | NA | NA | S000112.1_Reply_2023 10 17-NA-NA-NA-NA | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | 12 | Approved with Comments | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000112 | 2023-11-07 | 2023-11-07 | NA | AWC | Approved with Comments | 1 | "SSN URA Submission" |  | 2023-11
000113 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | E | 0001 | 0 | 131242-WSW41-MS-E-0001 | 2023-10-04 | MSRA, SWP for Soil Resistivity Test | Approved with Comments | 2023-11-01 | 2023-10-13 | 7 | Approved with Comments | YES | 2023-11-02 | NO | Resubmitted | 0 |  |  | 000113 | 2023-10-04 | 2023-10-04 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Soil Resistivity Test" |  | 2023-10
000114 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0008 | 0 | 131242-WSW41-MI-IM-0008 | 2023-10-05 | BIM Bi-Weekly Meeting Minutes 0008_20230920 | For Information | 2023-11-02 | 2023-10-16 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000114 | 2023-10-05 | 2023-10-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0008_20230920" |  | 2023-10
000115 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 0 | 131242-WSW41-PP-PC-0002 | 2023-10-05 | Project Control Plan | Rev. 0 - Approved with comments, need to re-submit (refer comment sheet) | 2023-11-02 | 2023-10-27 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000115 | 2023-10-05 | 2023-11-10 | 1 | AWC | Approved | 2 | "Project Control Plan" |  | 2023-10
000115 | 01 | Stanley | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 1 | 131242-WSW41-PP-PC-0002 | 2023-11-10 | Project Control Plan | Rev. 1 - Approved. | 2023-12-01 | 2023-11-15 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000115 | 2023-10-05 | 2023-11-10 | 1 | APP | Approved | 2 | "Project Control Plan" |  | 2023-11
000116 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0002 | 0 | 131242-WSW41-CN-M-0002 | 2023-10-06 | Proposed change of Manufacturer for SSN Aeration blowers | Rejected as CES requested as No RFC is needed according to the discussion with S.O. | 2023-11-03 | 2023-10-25 | 13 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000116 | 2023-10-06 | 2023-10-06 | 0 | REJ | Rejected | 1 | "Proposed change of Manufacturer for SSN Aeration blowers" |  | 2023-10
000117 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 0 | 131242-WSW41-CN-M-0001 | 2023-10-06 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Rev 0: Not approved - Revise and Resubmit | 2023-11-03 | 2023-11-28 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000117 | 2023-10-06 | 2023-12-12 | 1 | NAP | Approved with Comments | 2 | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" |  | 2023-10
000117 | 01 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 1 | 131242-WSW41-CN-M-0001 | 2023-12-12 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-03 | 2024-01-29 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000117 | 2023-10-06 | 2023-12-12 | 1 | AWC | Approved with Comments | 2 | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" |  | 2023-12
000118 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 0 | 131242-WSW41-MS-C-0004 | 2023-10-06 | MSRA, SWP for Bored Piling Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000118 | 2023-10-06 | 2023-11-01 | 1 | AWC | Approved with Comments | 2 | "MSRA, SWP for Bored Piling Work" |  | 2023-10
000118 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 1 | 131242-WSW41-MS-C-0004 | 2023-11-01 | MSRA, SWP for Bored Piling Work | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-22 | 2023-12-01 | 22 | Approved with Comments | YES | 2023-12-21 | NO | Resubmitted | 0 |  |  | 000118 | 2023-10-06 | 2023-11-01 | 1 | AWC | Approved with Comments | 2 | "MSRA, SWP for Bored Piling Work" |  | 2023-11
000119 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0005 | 0 | 131242-WSW41-MS-C-0005 | 2023-10-06 | MSRA, SWP for Site Set-Up & Associated Works (Seong) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-19 | 9 | Approved with Comments | YES | 2023-11-08 | NO | Resubmitted | 0 |  |  | 000119 | 2023-10-06 | 2023-10-06 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Site Set-Up & Associated Works (Seong)" |  | 2023-10
000120 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-IM-0003 | 2023-10-06 | Milestone 1.1 (Sidewide piperack) | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-11-03 | 2024-03-28 | 124 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000121 | 2023-10-06 | 2023-10-10 | 0 | AWC | For Information | 2 | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" |  | 2023-10
000120 | 01 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 0 | 131242-WSW41-CD-IM-0028 | 2024-05-27 | Milestone 1.2 Sitewide Pipe Rack | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-05-27 | 2024-06-05 | 1 | NAP | Approved with Comments | 2 | "Milestone 1.2 Sitewide Pipe Rack" |  | 2024-05
000120 | 02 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 1 | 131242-WSW41-CD-IM-0028 | 2024-06-05 | Milestone 1.2 Sitewide Pipe Rack | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-05-27 | 2024-06-05 | 1 | AWC | Approved with Comments | 2 | "Milestone 1.2 Sitewide Pipe Rack" |  | 2024-06
000120 | 03 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042 | 2024-08-24 | Milestone 2 Sitewide Pipe Rack | Rev3: Not Approved, as requested by contractor. | 2024-09-12 | 2024-10-01 | 26 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | REJ | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" |  | 2024-08
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | NAP | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-EK-1000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 3000 | B | 131242-WSW41-DR-EK-3000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 1000 | A.2 | 131242-WSW41-DR-M-1000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3000 | A.2 | 131242-WSW41-DR-M-3000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3001 | A.2 | 131242-WSW41-DR-M-3001 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3002 | A.2 | 131242-WSW41-DR-M-3002 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3003 | A.2 | 131242-WSW41-DR-M-3003 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3004 | A.2 | 131242-WSW41-DR-M-3004 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3005 | A.2 | 131242-WSW41-DR-M-3005 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4000 | A.2 | 131242-WSW41-DR-M-4000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4001 | A.2 | 131242-WSW41-DR-M-4001 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4002 | A.2 | 131242-WSW41-DR-M-4002 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4003 | A.2 | 131242-WSW41-DR-M-4003 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4004 | A.2 | 131242-WSW41-DR-M-4004 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4005 | A.2 | 131242-WSW41-DR-M-4005 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 8000 | A.2 | 131242-WSW41-DR-M-8000 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | 43 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | NAP | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2024-10
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | AWC | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 1000 | A.2 | 131242-WSW41-DR-EK-1000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 3000 | A.2 | 131242-WSW41-DR-EK-3000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 1000 | A.3 | 131242-WSW41-DR-M-1000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3000 | A.3 | 131242-WSW41-DR-M-3000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3001 | A.3 | 131242-WSW41-DR-M-3001 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3002 | A.3 | 131242-WSW41-DR-M-3002 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3003 | A.3 | 131242-WSW41-DR-M-3003 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3004 | A.3 | 131242-WSW41-DR-M-3004 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3005 | A.3 | 131242-WSW41-DR-M-3005 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4000 | A.3 | 131242-WSW41-DR-M-4000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4001 | A.3 | 131242-WSW41-DR-M-4001 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4002 | A.3 | 131242-WSW41-DR-M-4002 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4003 | A.3 | 131242-WSW41-DR-M-4003 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4004 | A.3 | 131242-WSW41-DR-M-4004 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4005 | A.3 | 131242-WSW41-DR-M-4005 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 8000 | A.3 | 131242-WSW41-DR-M-8000 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120 | 2024-10-05 | 2025-02-26 | A.3 | AWC | Approved with Comments | 2 | "Milestone 2 Sitewide Pipe Rack" |  | 2025-02
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 1 | 131242-WSW41-CD-IM-0042 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 82 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 000120 | 2024-08-24 | 2025-10-08 | 1 | AWC | Approved with Comments | 4 | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" |  | 2025-10
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | E | 1130 | A | 131242-WSW41-DR-E-1130 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 82 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 000120 | 2025-10-08 | 2025-10-08 | A | AWC | Approved with Comments | 1 | "Milestone 3 Sitewide Pipe Rack" |  | 2025-10
000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | E | 3000 | A | 131242-WSW41-DR-E-3000 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | 82 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 000120 | 2025-10-08 | 2025-10-08 | A | AWC | Approved with Comments | 1 | "Milestone 3 Sitewide Pipe Rack" |  | 2025-10
000121 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-IM-0003 | 2023-10-10 | Submission Of BIM Coordination VCM Model (Sept – 2023) | For Information | 2023-11-07 | 2023-10-23 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000121 | 2023-10-06 | 2023-10-10 | 0 | INF | For Information | 2 | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" |  | 2023-10
000122 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0006 | 0 | 131242-WSW41-MS-C-0006 | 2023-10-10 | MSRA, SWP for Erection of Site Office (Cape) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-07 | 2023-10-18 | 6 | Approved with Comments | YES | 2023-11-07 | NO | Resubmitted | 0 |  |  | 000122 | 2023-10-10 | 2023-10-10 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Erection of Site Office (Cape)" |  | 2023-10
000123 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0006 | 0 | 131242-WSW41-PP-HS-0006 | 2023-10-10 | Traffic Management Plan | Approved | 2023-11-07 | 2023-10-18 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000123 | 2023-10-10 | 2023-10-10 | 0 | APP | Approved | 1 | "Traffic Management Plan " |  | 2023-10
000124 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | PP | PM | 0003 | 0 | 131242-WSW41-PP-PM-0003 | 2023-10-10 | Project Execution Plan | Rev. 0 - Not Approved - need to re-submit (refer comment sheet) | 2023-11-07 | 2023-10-27 | 13 | Not Approved | YES | 2023-11-16 | NO | Resubmitted | 0 |  |  | 000124 | 2023-10-10 | 2023-10-10 | 0 | NAP | Not Approved | 1 | "Project Execution Plan" |  | 2023-10
000125 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0011 | 0 | 131242-WSW41-VI-C-0011 | 2023-10-11 | Vendor Approval of UXO Survey – EXPLOMO | Approved | 2023-11-08 | 2023-10-18 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000125 | 2023-10-11 | 2023-10-11 | 0 | APP | Approved | 1 | "Vendor Approval of UXO Survey – EXPLOMO" |  | 2023-10
000126 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0010 | 0 | 131242-WSW41-MI-P-0010 | 2023-10-12 | Process & MEICA Meeting Minutes 0010_20230928 | For Information | 2023-11-09 | 2024-03-18 | 112 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000126 | 2023-10-12 | 2023-10-12 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0010_20230928" |  | 2023-10
000127 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0005 | 0 | 131242-WSW41-RT-PM-0005 | 2023-10-14 | C4B Monthly Progress Report Number No.05 (09/23) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-10 | 2023-10-27 | 9 | Not Approved | YES | 2023-11-16 | NO | Resubmitted | 0 |  |  | 000127 | 2023-10-14 | 2023-10-14 | 0 | NAP | Not Approved | 1 | "C4B Monthly Progress Report Number No.05 (09/23)" |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A | 131242-WST00-DR-C-8001_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A | 131242-WST02-DR-C-1023_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A | 131242-WST02-DR-C-1024_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A | 131242-WST02-DR-C-3000_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A | 131242-WST02-DR-C-5004_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A | 131242-WST02-DR-C-5005_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A | 131242-WST02-DR-C-5006_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A | 131242-WST02-DR-C-5007_ST610 | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-10
000128 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | 1 | 131242-WST00-DR-C-8001_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-19 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A | 131242-WST02-DR-C-5004_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A | 131242-WST02-DR-C-5005_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A | 131242-WST02-DR-C-5006_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A | 131242-WST02-DR-C-5007_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A | 131242-WST02-DR-C-1023_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A | 131242-WST02-DR-C-1024_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A | 131242-WST02-DR-C-3000_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | A | 131242-WST02-DR-C-3001_ST610 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2023-12
000128 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A.1 | 131242-WST00-DR-C-8001_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A.1 | 131242-WST02-DR-C-5004_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A.1 | 131242-WST02-DR-C-5005_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A.1 | 131242-WST02-DR-C-5006_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A.1 | 131242-WST02-DR-C-5007_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A.1 | 131242-WST02-DR-C-1023_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A.1 | 131242-WST02-DR-C-1024_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A.1 | 131242-WST02-DR-C-3000_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | A.1 | 131242-WST02-DR-C-3001_ST610 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-03
000128 | 03 | Zora | CSA | NA | 131242 | NA | NA | NA | S# 128 Cmt Sheet Reply 2024 06 12 | NA | 131242-NA-NA-NA-S# 128 Cmt Sheet Reply 2024 06 12 | 2024-06-12 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  | To close after addressing the comments of S#475 . Zora to follow up with Grace for JMH calculation | 000128 | 2024-06-12 | 2024-06-12 | NA | NAP | Not Approved | 1 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " |  | 2024-06
000128 | 04 | Aaron | CSA | NA | 131242 | WST02 | NA | C | S# 128 Cmt Sheet Reply 2024 10 08 | NA | 131242-WST02-NA-C-S# 128 Cmt Sheet Reply 2024 10 08 | 2024-10-08 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-28 | 2024-10-29 | 15 | Not Approved | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000128 | 2024-10-08 | 2024-10-08 | NA | NAP | Not Approved | 1 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " |  | 2024-10
000129 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0007 | 0 | 131242-WSW41-MS-C-0007 | 2023-10-17 | MSRA, SWP for Erection of Site Office (UXO) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | 11 | Approved with Comments | YES | 2023-11-21 | NO | Resubmitted | 0 |  |  | 000129 | 2023-10-17 | 2023-10-17 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Erection of Site Office (UXO)" |  | 2023-10
000130 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0004 | 0 | 131242-WSW41-PC-W-0004 | 2023-10-18 | PAYMENT CLAIM NO.4 | Rev(0): Approved. Please refer to S.O. correspondence no. 73 dated 20 Oct 2023. | 2023-11-16 | 2023-10-23 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000130 | 2023-10-18 | 2023-10-18 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.4" |  | 2023-10
000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0011 | 0 | 131242-WSW41-MI-C-0011 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000131 | 2023-10-18 | 2023-10-18 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" |  | 2023-10
000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0012 | 0 | 131242-WSW41-MI-C-0012 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000131 | 2023-10-18 | 2023-10-18 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" |  | 2023-10
000132 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 0 | 131242-WSW41-SP-C-0003 | 2023-10-19 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-17 | 2023-11-17 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000132 | 2023-10-19 | 2023-12-21 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " |  | 2023-10
000132 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 1 | 131242-WSW41-SP-C-0003 | 2023-12-21 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Approved | 2024-01-12 | 2024-01-15 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000132 | 2023-10-19 | 2023-12-21 | 1 | APP | Approved | 2 | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " |  | 2023-12
000133 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 0 | 131242-WSD11-BQ-P-0001 | 2023-10-20 | THP Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-20 | 2023-11-27 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000133 | 2023-10-20 | 2024-04-26 | 1 | AWC | Approved with Comments | 2 | "THP Equipment List" |  | 2023-10
000133 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 1 | 131242-WSD11-BQ-P-0001 | 2024-04-26 | THP Equipment List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-17 | 2024-05-27 | 21 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2024-07-31 00:00:00 |  | 000133 | 2023-10-20 | 2024-04-26 | 1 | AWC | Approved with Comments | 2 | "THP Equipment List" |  | 2024-04
000134 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0012 | 0 | 131242-WSW41-VI-C-0012 | 2023-10-23 | Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-11-17 | 19 | Approved with Comments | YES | 2023-12-07 | NO | Resubmitted | 0 |  |  | 000134 | 2023-10-23 | 2023-10-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD." |  | 2023-10
000135 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 0 | 131242-WSW41-VI-M-0002 | 2023-10-23 | Preliminary Design and Vendor Approval of Blower (Robuschi) | Rev 0: Not approved - Revise and Resubmit | 2023-11-21 | 2023-11-27 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000135 | 2023-10-23 | 2024-06-25 | 2 | NAP | Approved with Comments | 3 | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" |  | 2023-10
000135 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 1 | 131242-WSW41-VI-M-0002 | 2023-12-26 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-16 | 2024-01-29 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | To re-submit after vendor provide update data sheet and drawing. Kick-off meeting done on 26 March | 000135 | 2023-10-23 | 2024-06-25 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" |  | 2023-12
000135 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 2 | 131242-WSW41-VI-M-0002 | 2024-06-25 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-07-15 | 2024-07-31 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | R1_AWC | 000135 | 2023-10-23 | 2024-06-25 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Preliminary Design and Vendor Approval of Blower (Aerzen)" |  | 2024-06
000136 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SK | Z | 0001 | 0 | 131242-WSW41-SK-Z-0001 | 2023-10-23 | Time Lapse Camera Location | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-12-18 | 40 | Approved with Comments | YES | 2024-01-05 | NO | Resubmitted | 0 |  |  | 000136 | 2023-10-23 | 2023-10-23 | 0 | AWC | Approved with Comments | 1 | "Time Lapse Camera Location" |  | 2023-10
000137 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0005 | 0 | 131242-WSW41-PS-PM-0005 | 2023-10-25 | Monthly Progress Presentation No. 05 (0923) | For Information | 2023-11-23 | 2023-10-26 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000137 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 05 (0923)" |  | 2023-10
000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0003 | 0 | 131242-WSW41-MI-PM-0003 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000138 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" |  | 2023-10
000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0004 | 0 | 131242-WSW41-MI-PM-0004 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000138 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" |  | 2023-10
000139 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 0 | 131242-WSW41-VI-M-0003 | 2023-10-25 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-11-23 | 2023-12-22 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 00:00:00 | Yibo to check with JK for process data. Vendor need to provide revised design data and layout drawings once Process confirmed. | 000139 | 2023-10-25 | 2024-11-06 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval of Diffuser (Xylem)" |  | 2023-10
000139 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 1 | 131242-WSW41-VI-M-0003 | 2024-11-06 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 1: Approved | 2024-11-26 | 2025-03-04 | 84 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000139 | 2023-10-25 | 2024-11-06 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval of Diffuser (Xylem)" |  | 2024-11
000140 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PS | P | 0001 | 0 | 131242-WSD11-PS-P-0001 | 2023-10-25 | Thermal Hydrolysis Process Presentation | For Information | 2023-11-23 | 2023-11-27 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000140 | 2023-10-25 | 2023-10-25 | 0 | INF | For Information | 1 | "Thermal Hydrolysis Process Presentation" |  | 2023-10
000141 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 0 | 131242-WSD11-CH-P-0001 | 2023-10-25 | Process Functional Description | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-23 | 64 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2023-10
000141 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 1 | 131242-WSD11-CH-P-0001 | 2024-04-02 | Process Functional Description | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-04-26 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-08-30 00:00:00 | R0: AWC | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2024-04
000141 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 2 | 131242-WSD11-CH-P-0001 | 2024-07-28 | Process Functional Description | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2024-07
000141 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 3 | 131242-WSD11-CH-P-0001 | 2024-09-30 | Process Functional Description | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-12-05 | 48 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000141 | 2023-10-25 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2024-09
000142 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 0 | 131242-WSD11-CH-P-0002 | 2023-10-25 | Process Design Basis | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-15 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" |  | 2023-10
000142 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 1 | 131242-WSD11-CH-P-0002 | 2024-03-20 | THP Process Design Basis | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-26 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-08-30 00:00:00 | R0: AWC | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" |  | 2024-03
000142 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 2 | 131242-WSD11-CH-P-0002 | 2024-07-28 | THP Process Design Basis | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" |  | 2024-07
000142 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 3 | 131242-WSD11-CH-P-0002 | 2024-11-04 | THP Process Design Basis | Rev 3: Approved with Comments. No active comments on the document. Resubmittal is required if there are any changes during detail engineering. No resubmittal at the moment. | 2024-11-22 | 2025-01-02 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000142 | 2023-10-25 | 2024-11-04 | 3 | AWC | Approved with Comments | 4 | "Process Design Basis" && "THP Process Design Basis" |  | 2024-11
000143 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-P-7001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000143 | 2023-10-26 | 2024-08-26 | B | NAP | Approved with Comments | 3 | "THP Process Flow Diagram" |  | 2023-10
000143 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-Z-0001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000018&&000143 | 2023-05-31 | 2023-10-26 | 0 | NAP | Not Approved | 5 | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "THP Process Flow Diagram" |  | 2023-10
000143 | 00 | Joo Kwan | Process | NA | DGN FILES | WSD11 | DR | P | 7001 | A | DGN FILES-WSD11-DR-P-7001 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000143 | 2023-10-26 | 2023-10-26 | A | NAP | Not Approved | 1 | "THP Process Flow Diagram" |  | 2023-10
000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-P-7001 | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-08 | 2024-03-28 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 |  | 000143 | 2023-10-26 | 2024-08-26 | B | AWC | Approved with Comments | 3 | "THP Process Flow Diagram" |  | 2024-03
000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7002 | A | 131242-WSD11-DR-P-7002 | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-17 | 2024-03-28 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000143 | 2024-03-18 | 2024-08-26 | B | AWC | Approved with Comments | 2 | "THP Process Flow Diagram" |  | 2024-03
000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | B | 131242-WSD11-DR-P-7001 | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | 33 | Approved with Comments | YES | 2024-10-30 | NO | Resubmitted | 0 |  |  | 000143 | 2023-10-26 | 2024-08-26 | B | AWC | Approved with Comments | 3 | "THP Process Flow Diagram" |  | 2024-08
000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7002 | B | 131242-WSD11-DR-P-7002 | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | 33 | Approved with Comments | YES | 2024-10-30 | NO | Resubmitted | 0 |  |  | 000143 | 2024-03-18 | 2024-08-26 | B | AWC | Approved with Comments | 2 | "THP Process Flow Diagram" |  | 2024-08
000144 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 0 | 131242-WSW41-QA-C-0001 | 2023-10-27 | Inspection Test Plan for Earthwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000144 | 2023-10-27 | 2023-12-21 | 1 | NAP | Approved | 2 | "Inspection Test Plan for Earthwork" |  | 2023-10
000144 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 1 | 131242-WSW41-QA-C-0001 | 2023-12-21 | Inspection Test Plan for Earthwork | Approved | 2024-01-12 | 2024-01-15 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000144 | 2023-10-27 | 2023-12-21 | 1 | APP | Approved | 2 | "Inspection Test Plan for Earthwork" |  | 2023-12
000145 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 0 | 131242-WSW41-QA-C-0002 | 2023-10-27 | Inspection Test Plan for Bored piling work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000145 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Bored piling work" |  | 2023-10
000145 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-C-0002 | 2023-12-21 | Inspection Test Plan for Bored piling work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000145 | 2023-10-27 | 2024-01-29 | 1 | AWC | Approved | 3 | "Inspection Test Plan for Bored piling work" |  | 2023-12
000145 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-C-0002 | 2024-01-29 | Inspection Test Plan for Bored piling work | Approved | 2024-02-19 | 2024-02-21 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000145 | 2023-10-27 | 2024-01-29 | 1 | APP | Approved | 3 | "Inspection Test Plan for Bored piling work" |  | 2024-01
000146 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 0 | 131242-WSW41-QA-C-0003 | 2023-10-27 | Inspection Test Plan for Reinforcement work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000146 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Reinforcement work" |  | 2023-10
000146 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-C-0003 | 2023-12-21 | Inspection Test Plan for Reinforcement work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000146 | 2023-10-27 | 2024-01-29 | 1 | AWC | Approved | 3 | "Inspection Test Plan for Reinforcement work" |  | 2023-12
000146 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-C-0003 | 2024-01-29 | Inspection Test Plan for Reinforcement work | Approved | 2024-02-19 | 2024-02-21 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000146 | 2023-10-27 | 2024-01-29 | 1 | APP | Approved | 3 | "Inspection Test Plan for Reinforcement work" |  | 2024-01
000147 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 0 | 131242-WSW41-QA-C-0004 | 2023-10-27 | Inspection Test Plan for Concreting Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000147 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Concreting Work" |  | 2023-10
000147 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-C-0004 | 2023-12-21 | Inspection Test Plan for Concreting Work | Not Approved. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-12 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000147 | 2023-10-27 | 2024-01-29 | 1 | NAP | Approved | 3 | "Inspection Test Plan for Concreting Work" |  | 2023-12
000147 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-C-0004 | 2024-01-29 | Inspection Test Plan for Concreting Work | Approved | 2024-02-19 | 2024-02-21 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000147 | 2023-10-27 | 2024-01-29 | 1 | APP | Approved | 3 | "Inspection Test Plan for Concreting Work" |  | 2024-01
000148 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 0 | 131242-WSW41-QA-C-0005 | 2023-10-27 | Inspection Test Plan for Formwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000148 | 2023-10-27 | 2023-12-21 | 1 | NAP | Approved with Comments | 2 | "Inspection Test Plan for Formwork" |  | 2023-10
000148 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 1 | 131242-WSW41-QA-C-0005 | 2023-12-21 | Inspection Test Plan for Formwork | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | 17 | Approved with Comments | YES | 2024-02-02 | NO | Resubmitted | 0 | 2024-03-13 00:00:00 |  | 000148 | 2023-10-27 | 2023-12-21 | 1 | AWC | Approved with Comments | 2 | "Inspection Test Plan for Formwork" |  | 2023-12
000149 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0006 | 0 | 131242-WSW41-QA-C-0006 | 2023-10-27 | Inspection Test Plan for Waterproofing Concrete and Application Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | YES | 2023-12-07 | NO | Resubmitted | 0 | 2024-01-11 00:00:00 | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000149 | 2023-10-27 | 2023-10-27 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Waterproofing Concrete and Application Work" |  | 2023-10
000150 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0007 | 0 | 131242-WSW41-QA-C-0007 | 2023-10-27 | Inspection Test Plan for Roadwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | 15 | Not Approved | YES | 2023-12-07 | NO | Resubmitted | 0 | 2024-01-12 00:00:00 | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000150 | 2023-10-27 | 2023-10-27 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Roadwork" |  | 2023-10
000151 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | E | 0000 | 0 | 131242-WSD11-BQ-E-0000 | 2023-10-27 | THP-Electrical Load List | Approved with comments. To Revise and resubmit. Please refer to the comment sheet. | 2023-11-27 | 2024-02-02 | 70 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000151 | 2023-10-27 | 2025-02-10 | 2 | AWC | Approved with Comments | 3 | "THP-Electrical Load List" |  | 2023-10
000151 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 1 | 131242-WSD11-BQ-E-0000 | 2024-03-28 | THP-Electrical Load List | Rev 0: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2024-04-19 | 2024-08-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000151 | 2023-10-27 | 2025-02-10 | 2 | AWC | Approved with Comments | 3 | "THP-Electrical Load List" |  | 2024-03
000151 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 2 | 131242-WSD11-BQ-E-0000 | 2025-02-10 | THP-Electrical Load List | Rev 2: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | 60 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000151 | 2023-10-27 | 2025-02-10 | 2 | AWC | Approved with Comments | 3 | "THP-Electrical Load List" |  | 2025-02
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0009 | 0 | 131242-WSW41-MI-IM-0009 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" |  | 2023-10
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0009 | 0 | 131242-WSW41-PS-IM-0009 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" |  | 2023-10
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0010 | 0 | 131242-WSW41-MI-IM-0010 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" |  | 2023-10
000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0010 | 0 | 131242-WSW41-PS-IM-0010 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000152 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" |  | 2023-10
000153 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0011 | 0 | 131242-WSW41-MI-P-0011 | 2023-10-30 | Process & MEICA Meeting Minutes 0011_20231012 | For Information | 2023-11-28 | 2024-03-18 | 100 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000153 | 2023-10-30 | 2023-10-30 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0011_20231012" |  | 2023-10
000154 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0015 | 0 | 131242-WSW41-LT-PM-0015 | 2023-10-31 | CV of Team Member (WSHC) | Approved | 2023-11-29 | 2023-12-04 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000154 | 2023-10-31 | 2023-10-31 | 0 | APP | Approved | 1 | "CV of Team Member (WSHC)" |  | 2023-10
000155 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0002 | 0 | 131242-WSW41-CT-W-0002 | 2023-10-31 | Professional Indemnity Insurance Letter | Acceptable for information. | 2023-11-29 | 2023-11-07 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000155 | 2023-10-31 | 2023-10-31 | 0 | INF | For Information | 1 | "Professional Indemnity Insurance Letter" |  | 2023-10
000156 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LT | AGC | 0001 | 0 | 131242-WSW41-LT-AGC-0001 | 2023-11-02 | Approval Letter to Commence Works Requiring Earth Control Measure | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-01 | 2023-11-09 | 5 | Approved with Comments | YES | 2023-11-29 | NO | Resubmitted | 0 |  |  | 000156 | 2023-11-02 | 2023-11-02 | 0 | AWC | Approved with Comments | 1 | "Approval Letter to Commence Works Requiring Earth Control Measure" |  | 2023-11
000157 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0002 | 0 | 131242-WSW41-PS-HS-0002 | 2023-11-02 | Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023 | For Information | 2023-12-01 | 2023-12-01 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000157 | 2023-11-02 | 2023-11-02 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" |  | 2023-11
000158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 0 | 131242-WST02-BQ-E-0000 | 2023-11-03 | SSN Electrical Load List | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2023-12-04 | 2024-04-29 | 126 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000158 | 2023-11-03 | 2025-02-10 | 1 | AWC | Approved with Comments | 2 | "SSN Electrical Load List" |  | 2023-11
000158 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 1 | 131242-WST02-BQ-E-0000 | 2025-02-10 | SSN Electrical Load List | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | 60 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000158 | 2023-11-03 | 2025-02-10 | 1 | AWC | Approved with Comments | 2 | "SSN Electrical Load List" |  | 2025-02
000159 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0007 | 0 | 131242-WSW41-PP-HS-0007 | 2023-11-03 | Haze Management Plan | Approved | 2023-12-04 | 2023-12-01 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000159 | 2023-11-03 | 2023-11-03 | 0 | APP | Approved | 1 | "Haze Management Plan " |  | 2023-11
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | A | 131242-WST02-DR-EL-1000 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2023-11
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | A | 131242-WST02-DR-EL-1001 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2023-11
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | A | 131242-WST02-DR-EL-1002 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2023-11
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | A | 131242-WST02-DR-EL-1003 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2023-11
000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | A | 131242-WST02-DR-EL-1004 | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" |  | 2023-11
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-EL-1000 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA | PENDING C2D | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-02
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | B | 131242-WST02-DR-EL-1001 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-02
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | B | 131242-WST02-DR-EL-1002 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2025-02
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | B | 131242-WST02-DR-EL-1003 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2025-02
000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | B | 131242-WST02-DR-EL-1004 | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" |  | 2025-02
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | C | 131242-WST02-DR-EL-1000 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-08
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | C | 131242-WST02-DR-EL-1001 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-08
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | C | 131242-WST02-DR-EL-1002 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2025-08
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | C | 131242-WST02-DR-EL-1003 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2025-08
000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | C | 131242-WST02-DR-EL-1004 | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | NAP | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" |  | 2025-08
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | D | 131242-WST02-DR-EL-1000 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-12
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | D | 131242-WST02-DR-EL-1001 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-12
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | D | 131242-WST02-DR-EL-1002 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2025-12
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | D | 131242-WST02-DR-EL-1003 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 4 | "SSN Lighting Layout Plan" |  | 2025-12
000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | D | 131242-WST02-DR-EL-1004 | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Approved with Comments | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" |  | 2025-12
000161 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0004 | D | 131242-WST02-CD-IM-0004 | 2023-11-06 | Submission of Milestone 1.1 Underground Services Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2023-11-06 | 2023-11-06 | D | AWC | Approved with Comments | 1 | "Submission of Milestone 1.1 Underground Services Model" |  | 2023-11
000161 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 | 131242-WST02-CD-IM-0022 | 2024-05-27 | Milestone 1.2 Underground Services | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000363 | 2024-03-15 | 2024-06-05 | 1 | NAP | Approved with Comments | 3 | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" |  | 2024-05
000161 | 02 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 1 | 131242-WST02-CD-IM-0022 | 2024-06-05 | Milestone 1.2 Underground Services | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000363 | 2024-03-15 | 2024-06-05 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" |  | 2024-06
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-IM-0044 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | This M2 submission includes all discipline documents for the relevant area. | 000161 | 2024-10-05 | 2025-09-29 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-E-1100 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1101 | A | 131242-WST02-DR-E-1101 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1102 | A | 131242-WST02-DR-E-1102 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7750 | B | 131242-WST02-DR-E-7750 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7751 | B | 131242-WST02-DR-E-7751 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7752 | B | 131242-WST02-DR-E-7752 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1300 | A | 131242-WST02-DR-E-1300 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1301 | A | 131242-WST02-DR-E-1301 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1302 | A | 131242-WST02-DR-E-1302 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3300 | A | 131242-WST02-DR-E-3300 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3301 | A | 131242-WST02-DR-E-3301 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161 | 2024-10-05 | 2024-10-05 | A | AWC | Approved with Comments | 1 | "Milestone 2 Underground Services" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-EK-1000 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1001 | A | 131242-WST02-DR-EK-1001 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1002 | A | 131242-WST02-DR-EK-1002 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1003 | A | 131242-WST02-DR-EK-1003 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004 | A | 131242-WST02-DR-EK-1004 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1005 | A | 131242-WST02-DR-EK-1005 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2000 | A | 131242-WST02-DR-EK-2000 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2001 | A | 131242-WST02-DR-EK-2001 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2002 | A | 131242-WST02-DR-EK-2002 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2003 | A | 131242-WST02-DR-EK-2003 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5000 | A | 131242-WST02-DR-EK-5000 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5001 | A | 131242-WST02-DR-EK-5001 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5002 | A | 131242-WST02-DR-EK-5002 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1022 | A.2 | 131242-WST02-DR-M-1022 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-04-09 | 2024-10-05 | A.2 | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5011 | A.1 | 131242-WST02-DR-M-5011 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5012 | A.1 | 131242-WST02-DR-M-5012 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5013 | A.1 | 131242-WST02-DR-M-5013 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5014 | A.1 | 131242-WST02-DR-M-5014 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-10
000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5015 | A.1 | 131242-WST02-DR-M-5015 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-10
000161 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-IM-0044 | 2025-09-29 | Milestone 3 Underground Services | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-17 | 2026-01-27 | 86 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  | This M2 submission includes all discipline documents for the relevant area. | 000161 | 2024-10-05 | 2025-09-29 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" |  | 2025-09
000162 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-IM-0005 | 2023-11-06 | Submission of Milestone 1.1 Pump Stataion and Blower Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000164 | 2023-11-06 | 2023-11-06 | 0 | AWC | Approved with Comments | 2 | "Submission of Milestone 1.1 Pump Stataion and Blower Area" && "Submission of Milestone 1.1 Astrea Separator Model" |  | 2023-11
000162 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2024-05-27 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 | Requested to reject on 03 June |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | NAP | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " |  | 2024-05
000162 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 1 | 131242-WST02-CD-IM-0025 | 2024-06-05 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | AWC | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " |  | 2024-06
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | AWC | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000163 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3329 | A | 131242-WST02-DR-E-3329 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3330 | A | 131242-WST02-DR-E-3330 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3331 | A | 131242-WST02-DR-E-3331 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3332 | A | 131242-WST02-DR-E-3332 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004_MS2 | C | 131242-WST02-DR-EK-1004_MS2 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | C | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1003_MS2 | B | 131242-WST02-DR-EL-1003_MS2 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | B | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1314 | A | 131242-WST02-DR-EP-1314 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1115 | A | 131242-WST02-DR-I-1115 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1116 | A | 131242-WST02-DR-I-1116 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1117 | A | 131242-WST02-DR-I-1117 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3035 | A | 131242-WST02-DR-I-3035 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3036 | A | 131242-WST02-DR-I-3036 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3037 | A | 131242-WST02-DR-I-3037 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1011 | A | 131242-WST02-DR-M-1011 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-04
000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4002 | A | 131242-WST02-DR-M-4002 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000461 | 2024-05-06 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" |  | 2025-04
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | NAP | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162&&000163 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3329 | A | 131242-WST02-DR-E-3329 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3330 | A | 131242-WST02-DR-E-3330 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3331 | A | 131242-WST02-DR-E-3331 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3332 | A | 131242-WST02-DR-E-3332 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004_MS2 | C | 131242-WST02-DR-EK-1004_MS2 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | C | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1003_MS2 | B | 131242-WST02-DR-EL-1003_MS2 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | B | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1314 | A | 131242-WST02-DR-EP-1314 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1115 | A | 131242-WST02-DR-I-1115 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1116 | A | 131242-WST02-DR-I-1116 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1117 | A | 131242-WST02-DR-I-1117 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3035 | A | 131242-WST02-DR-I-3035 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3036 | A | 131242-WST02-DR-I-3036 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3037 | A | 131242-WST02-DR-I-3037 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1011 | A | 131242-WST02-DR-M-1011 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000162 | 2025-04-09 | 2025-10-27 | A | NAP | Not Approved | 2 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" |  | 2025-10
000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4002 | A | 131242-WST02-DR-M-4002 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | 66 | Not Approved | YES | 2026-02-16 | NO | Resubmitted | 438 |  |  | 000162&&000461 | 2024-05-06 | 2025-10-27 | A | NAP | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" |  | 2025-10
000163 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0007 | 0 | 131242-WST02-CD-IM-0007 | 2023-11-06 | Submission of Milestone 1.1 Water Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2023-11-06 | 2023-11-06 | 0 | AWC | Approved with Comments | 1 | "Submission of Milestone 1.1 Water Tank" |  | 2023-11
000163 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 | 131242-WST02-CD-IM-0023 | 2024-06-03 | Milestone 1.2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-24 | 2024-07-05 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000367 | 2024-03-18 | 2024-06-03 | 0 | AWC | Approved with Comments | 2 | "Milestone 1.2 SSN Water Tank" && "Milestone 1.2 - SSN Water Tank" |  | 2024-06
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0055 | 0 | 131242-WST02-CD-IM-0055 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | 0 | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000163 | 2025-04-09 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1315 | A | 131242-WST02-DR-E-1315 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3324 | A | 131242-WST02-DR-E-3324 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3325 | A | 131242-WST02-DR-E-3325 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3326 | A | 131242-WST02-DR-E-3326 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3327 | A | 131242-WST02-DR-E-3327 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3328 | A | 131242-WST02-DR-E-3328 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1004 | B | 131242-WST02-DR-EL-1004 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000163 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1004 | B | 131242-WST02-DR-EP-1004 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1005 | C | 131242-WST02-DR-EK-1005 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1112 | A | 131242-WST02-DR-I-1112 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1113 | A | 131242-WST02-DR-I-1113 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1114 | A | 131242-WST02-DR-I-1114 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3028 | A | 131242-WST02-DR-I-3028 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3029 | A | 131242-WST02-DR-I-3029 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3030 | A | 131242-WST02-DR-I-3030 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3031 | A | 131242-WST02-DR-I-3031 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3033 | A | 131242-WST02-DR-I-3033 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1003 | A | 131242-WST02-DR-M-1003 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1006 | A | 131242-WST02-DR-M-1006 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3001 | A | 131242-WST02-DR-M-3001 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3002 | A | 131242-WST02-DR-M-3002 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3005 | A | 131242-WST02-DR-M-3005 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4001 | A | 131242-WST02-DR-M-4001 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000461 | 2024-05-06 | 2025-04-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1008 | A | 131242-WST02-DR-M-1008 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1010 | A | 131242-WST02-DR-M-1010 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1012 | A | 131242-WST02-DR-M-1012 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1015 | A | 131242-WST02-DR-M-1015 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1016 | A | 131242-WST02-DR-M-1016 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | 106 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000163 | 2025-04-28 | 2025-04-28 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Water Tank" |  | 2025-04
000163 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-IM-0052 | 2025-12-16 | Milestone 3 SSN Water Tank | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-01-27 | 30 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000163&&001034 | 2025-02-10 | 2025-12-16 | 0 | AWC | Approved with Comments | 2 | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" |  | 2025-12
000164 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-IM-0005 | 2023-11-06 | Submission of Milestone 1.1 Astrea Separator Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-03-28 | 103 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000164 | 2023-11-06 | 2023-11-06 | 0 | AWC | Approved with Comments | 2 | "Submission of Milestone 1.1 Pump Stataion and Blower Area" && "Submission of Milestone 1.1 Astrea Separator Model" |  | 2023-11
000164 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 | 131242-WST02-CD-IM-0024 | 2024-06-04 | Milestone 1.2 SSN Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" |  | 2024-06
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-IM-0024 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1318 | A | 131242-WST02-DR-E-1318 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1319 | A | 131242-WST02-DR-E-1319 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3335 | A | 131242-WST02-DR-E-3335 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3336 | A | 131242-WST02-DR-E-3336 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1106 | A | 131242-WST02-DR-I-1106 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1107 | A | 131242-WST02-DR-I-1107 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1108 | A | 131242-WST02-DR-I-1108 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1109 | A | 131242-WST02-DR-I-1109 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3018 | A | 131242-WST02-DR-I-3018 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3019 | A | 131242-WST02-DR-I-3019 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3020 | A | 131242-WST02-DR-I-3020 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3021 | A | 131242-WST02-DR-I-3021 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3022 | A | 131242-WST02-DR-I-3022 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3023 | A | 131242-WST02-DR-I-3023 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1110 | A | 131242-WST02-DR-I-1110 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1111 | A | 131242-WST02-DR-I-1111 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3024 | A | 131242-WST02-DR-I-3024 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3026 | A | 131242-WST02-DR-I-3026 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000461 | 2024-05-06 | 2025-10-31 | 0 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1014 | A | 131242-WST02-DR-M-1014 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1009 | A | 131242-WST02-DR-M-1009 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-04
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-IM-0024 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1318 | A | 131242-WST02-DR-E-1318 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1319 | A | 131242-WST02-DR-E-1319 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3335 | A | 131242-WST02-DR-E-3335 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3336 | A | 131242-WST02-DR-E-3336 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1106 | A | 131242-WST02-DR-I-1106 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1107 | A | 131242-WST02-DR-I-1107 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1108 | A | 131242-WST02-DR-I-1108 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1109 | A | 131242-WST02-DR-I-1109 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3018 | A | 131242-WST02-DR-I-3018 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3019 | A | 131242-WST02-DR-I-3019 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3020 | A | 131242-WST02-DR-I-3020 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3021 | A | 131242-WST02-DR-I-3021 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3022 | A | 131242-WST02-DR-I-3022 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3023 | A | 131242-WST02-DR-I-3023 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1110 | A | 131242-WST02-DR-I-1110 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1111 | A | 131242-WST02-DR-I-1111 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3024 | A | 131242-WST02-DR-I-3024 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3026 | A | 131242-WST02-DR-I-3026 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 442 |  |  | 000164&&000461 | 2024-05-06 | 2025-10-31 | 0 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1014 | A | 131242-WST02-DR-M-1014 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1009 | A | 131242-WST02-DR-M-1009 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000164 | 2025-04-22 | 2025-10-31 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" |  | 2025-10
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | A | 131242-WST02-CL-EL-7000 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2023-11
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7001 | A | 131242-WST02-CL-EL-7001 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2023-11
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7002 | A | 131242-WST02-CL-EL-7002 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2023-11
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7003 | A | 131242-WST02-CL-EL-7003 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2023-11
000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7004 | A | 131242-WST02-CL-EL-7004 | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | 74 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | NAP | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2023-11
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | B | 131242-WST02-CL-EL-7000 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2024-07
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7001 | B | 131242-WST02-CL-EL-7001 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2024-07
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7002 | B | 131242-WST02-CL-EL-7002 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2024-07
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7003 | B | 131242-WST02-CL-EL-7003 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2024-07
000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7004 | B | 131242-WST02-CL-EL-7004 | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | 80 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000165 | 2023-11-06 | 2024-07-09 | B | INF | For Information | 2 | "SSN-Lux Calculation and luminaire Schedule" |  | 2024-07
000166 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 0 | 131242-WSW41-QA-A-0001 | 2023-11-06 | Inspection Test Plan for Architectural work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-07 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000166 | 2023-11-06 | 2024-12-05 | 1 | NAP | Approved | 2 | "Inspection Test Plan for Architectural work " |  | 2023-11
000166 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 1 | 131242-WSW41-QA-A-0001 | 2024-12-05 | Inspection Test Plan for Architectural work | Rev.1: Approved | 2024-12-26 | 2024-12-23 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000166 | 2023-11-06 | 2024-12-05 | 1 | APP | Approved | 2 | "Inspection Test Plan for Architectural work " |  | 2024-12
000167 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 0 | 131242-WSW41-QA-A-0002 | 2023-11-06 | Inspection Test Plan for Plastering and Painting Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000167 | 2023-11-06 | 2024-12-13 | 1 | NAP | Approved | 2 | "Inspection Test Plan for Plastering and Painting Work" |  | 2023-11
000167 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 1 | 131242-WSW41-QA-A-0002 | 2024-12-13 | Inspection Test Plan for Plastering and Painting Work | Rev 1 Approved | 2025-01-03 | 2024-12-23 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000167 | 2023-11-06 | 2024-12-13 | 1 | APP | Approved | 2 | "Inspection Test Plan for Plastering and Painting Work" |  | 2024-12
000168 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0003 | 0 | 131242-WSW41-QA-A-0003 | 2023-11-06 | Inspection Test Plan for Installation of Raised Access Floor System Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | 22 | Not Approved | YES | 2023-12-26 | NO | Resubmitted | 0 |  | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000168 | 2023-11-06 | 2023-11-06 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Installation of Raised Access Floor System Work" |  | 2023-11
000169 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0004 | 0 | 131242-WSW41-QA-A-0004 | 2023-11-06 | Inspection Test Plan for Installation of Door and Window Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-12 | 26 | Not Approved | YES | 2024-01-01 | NO | Resubmitted | 0 |  | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 000169 | 2023-11-06 | 2023-11-06 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Installation of Door and Window Work" |  | 2023-11
000170 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 0 | 131242-WSW41-VI-M-1001 | 2023-11-06 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-02-14 | 72 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 |  | 000170 | 2023-11-06 | 2025-01-21 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" |  | 2023-11
000170 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 1 | 131242-WSW41-VI-M-1001 | 2024-11-23 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-14 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000170 | 2023-11-06 | 2025-01-21 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" |  | 2024-11
000170 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 2 | 131242-WSW41-VI-M-1001 | 2025-01-21 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-10 | 2025-04-27 | 69 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000170 | 2023-11-06 | 2025-01-21 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" |  | 2025-01
000171 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | A | 131242-WSD11-DR-I-7000 | 2023-11-06 | THP Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2023-12-05 | 2023-11-21 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000171 | 2023-11-06 | 2024-07-29 | C | NAP | Approved with Comments | 3 | "THP Control System Architecture Drawing" |  | 2023-11
000171 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | B | 131242-WSD11-DR-I-7000 | 2024-03-13 | THP Control System Architecture Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-03 | 2024-06-13 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000171 | 2023-11-06 | 2024-07-29 | C | NAP | Approved with Comments | 3 | "THP Control System Architecture Drawing" |  | 2024-03
000171 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7000 | C | 131242-WSD11-DR-I-7000 | 2024-07-29 | THP Control System Architecture Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-19 | 2024-08-30 | 24 | Approved with Comments | YES | 2024-09-19 | NO | Resubmitted | 0 |  |  | 000171 | 2023-11-06 | 2024-07-29 | C | AWC | Approved with Comments | 3 | "THP Control System Architecture Drawing" |  | 2024-07
000172 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 0 | 131242-WSD11-CL-P-0001 | 2023-11-08 | THP Compressed Air Calculation | Approved with Comments. To revise and resubmit. Refer to comments files | 2023-12-07 | 2024-01-17 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000172 | 2023-11-08 | 2024-08-15 | 2 | AWC | Approved with Comments | 3 | "THP Compressed Air Calculation" |  | 2023-11
000172 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 1 | 131242-WSD11-CL-P-0001 | 2024-04-19 | THP Compressed Air Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-07-26 | 70 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000172 | 2023-11-08 | 2024-08-15 | 2 | AWC | Approved with Comments | 3 | "THP Compressed Air Calculation" |  | 2024-04
000172 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 2 | 131242-WSD11-CL-P-0001 | 2024-08-15 | THP Compressed Air Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-11-07 | 60 | Approved with Comments | YES | 2024-11-27 | NO | Resubmitted | 0 |  |  | 000172 | 2023-11-08 | 2024-08-15 | 2 | AWC | Approved with Comments | 3 | "THP Compressed Air Calculation" |  | 2024-08
000173 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 0 | 131242-WST02-CL-P-0001 | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | 2 | AWC | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " |  | 2023-11
000173 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | A | 131242-WST02-DR-P-7011 | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | C | AWC | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " |  | 2023-11
000173 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 1 | 131242-WST02-CL-P-0001 | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | 2 | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " |  | 2024-05
000173 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | B | 131242-WST02-DR-P-7011 | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | C | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " |  | 2024-05
000173 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 2 | 131242-WST02-CL-P-0001 | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  | Resubmitted as per SO comments | 000173 | 2023-11-08 | 2024-08-07 | 2 | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " |  | 2024-08
000173 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | C | 131242-WST02-DR-P-7011 | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000173 | 2023-11-08 | 2024-08-07 | C | APP | Approved | 3 | "SSN: Plant Drain Hydraulic Profile and calculation " |  | 2024-08
000174 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0006 | 0 | 131242-WSW41-RT-PM-0006 | 2023-11-08 | C4B Monthly Progress Report Number No.06 (10/23) | Rev. 0 - Approved | 2023-12-07 | 2023-11-21 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000174 | 2023-11-08 | 2023-11-08 | 0 | APP | Approved | 1 | "C4B Monthly Progress Report Number No.06 (10/23)" |  | 2023-11
000175 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0009 | 0 | 131242-WSW41-CD-IM-0009 | 2023-11-08 | Submission Of BIM Coordination VCM Model (Oct – 2023) | For Information | 2023-12-07 | 2023-11-21 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000175 | 2023-11-08 | 2023-11-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Oct – 2023)" |  | 2023-11
000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0011 | 0 | 131242-WSW41-MI-IM-0011 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000176 | 2023-11-09 | 2023-11-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0011_20231101" |  | 2023-11
000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0011 | 0 | 131242-WSW41-PS-IM-0011 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000176 | 2023-11-09 | 2023-11-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0011_20231101" |  | 2023-11
000177 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 0 | 131242-WSD11-DS-M-0001 | 2023-11-09 | Data Sheet of Air Compressor | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-08 | 2024-01-22 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2023-11-09 | 2024-11-06 | 3 | AWC | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" |  | 2023-11
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 1 | 131242-WSD11-DS-M-0001 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 00:00:00 | Rev 0: AWC | 000177 | 2023-11-09 | 2024-11-06 | 3 | AWC | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0161 | A | 131242-WSD11-DR-M-0161 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0101 | A | 131242-WSD11-DR-M-0101 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0102 | A | 131242-WSD11-DR-M-0102 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0103 | A | 131242-WSD11-DR-M-0103 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0104 | A | 131242-WSD11-DR-M-0104 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0131 | A | 131242-WSD11-DR-M-0131 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0132 | A | 131242-WSD11-DR-M-0132 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0133 | A | 131242-WSD11-DR-M-0133 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2024-04-04 | 2024-04-04 | A | AWC | Approved with Comments | 1 | " Data Sheet and Drawing of Air Compressor System " |  | 2024-04
000177 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 2 | 131242-WSD11-DS-M-0001 | 2024-08-12 | Data Sheet of Air Compressor System | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-25 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2023-11-09 | 2024-11-06 | 3 | AWC | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" |  | 2024-08
000177 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 3 | 131242-WSD11-DS-M-0001 | 2024-11-06 | Data Sheet of Air Compressor System | Rev 3: Approved | 2024-11-26 | 2024-12-05 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000177 | 2023-11-09 | 2024-11-06 | 3 | APP | Approved | 4 | "Data Sheet of Air Compressor" && " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor System" |  | 2024-11
000178 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 0 | 131242-WSD11-DS-M-0005 | 2023-11-10 | Data Sheet of Pressure Vessel | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-18 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" |  | 2023-11
000178 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 1 | 131242-WSD11-DS-M-0005 | 2024-03-20 | Data Sheet of Pressure Vessel | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-29 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 | Related to Detailed Design Report. | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" |  | 2024-03
000178 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 2 | 131242-WSD11-DS-M-0005 | 2024-07-28 | Data Sheet of Pressure Vessel | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" |  | 2024-07
000178 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 3 | 131242-WSD11-DS-M-0005 | 2024-11-22 | Data Sheet of Pressure Vessel | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. [Rev2 comments were not addressed by CES] | 2024-12-12 | 2024-12-05 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | AWC | Approved | 5 | "Data Sheet of Pressure Vessel" |  | 2024-11
000178 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 4 | 131242-WSD11-DS-M-0005 | 2025-03-04 | Data Sheet of Pressure Vessel | Rev 4: Approved. Please furnish PE Endorsement. | 2025-03-24 | 2025-10-06 | 154 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000178 | 2023-11-10 | 2025-03-04 | 4 | APP | Approved | 5 | "Data Sheet of Pressure Vessel" |  | 2025-03
000179 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 0 | 131242-WSD11-DS-M-0006 | 2023-11-10 | Data Sheet of PreCoolers | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-22 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000179 | 2023-11-10 | 2024-03-19 | 1 | AWC | Approved with Comments | 2 | "Data Sheet of PreCoolers" |  | 2023-11
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 1 | 131242-WSD11-DS-M-0006 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | No re-submission required | 000179 | 2023-11-10 | 2024-03-19 | 1 | AWC | Approved with Comments | 2 | "Data Sheet of PreCoolers" |  | 2024-03
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0007 | B | 131242-WSD11-DR-M-0007 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000179 | 2024-03-19 | 2024-03-19 | B | AWC | Approved with Comments | 1 | "Data Sheet of PreCoolers" |  | 2024-03
000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0008 | B | 131242-WSD11-DR-M-0008 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000179 | 2024-03-19 | 2024-03-19 | B | AWC | Approved with Comments | 1 | "Data Sheet of PreCoolers" |  | 2024-03
000180 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 0 | 131242-WSD11-DS-M-0007 | 2023-11-10 | Data Sheet of PGS | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Related to Detailed Design Report. | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" |  | 2023-11
000180 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 1 | 131242-WSD11-DS-M-0007 | 2024-03-25 | Data Sheet of PGS | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-16 | 2024-05-30 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 | Rev 0: AWC | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" |  | 2024-03
000180 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 2 | 131242-WSD11-DS-M-0007 | 2024-07-28 | Data Sheet of PGS | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-09-02 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" |  | 2024-07
000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 3 | 131242-WSD11-DS-M-0007 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | 21 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000180 | 2023-11-10 | 2024-09-30 | 3 | AWC | Approved with Comments | 4 | "Data Sheet of PGS" |  | 2024-09
000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0020 | 0 | 131242-WSD11-DS-E-0020 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | 21 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000180 | 2024-09-30 | 2024-09-30 | 0 | AWC | Approved with Comments | 1 | "Data Sheet of PGS" |  | 2024-09
000181 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 0 | 131242-WSD11-DS-M-0008 | 2023-11-10 | Data Sheet of PGC | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000181 | 2023-11-10 | 2025-03-06 | 2 | AWC | Approved | 3 | "Data Sheet of PGC" |  | 2023-11
000181 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 1 | 131242-WSD11-DS-M-0008 | 2024-03-19 | Data Sheet of PGC | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 | Related to Detailed Design Report. | 000181 | 2023-11-10 | 2025-03-06 | 2 | AWC | Approved | 3 | "Data Sheet of PGC" |  | 2024-03
000181 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 2 | 131242-WSD11-DS-M-0008 | 2025-03-06 | Data Sheet of PGC | Rev 2: Approved. | 2025-03-26 | 2025-10-06 | 152 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000181 | 2023-11-10 | 2025-03-06 | 2 | APP | Approved | 3 | "Data Sheet of PGC" |  | 2025-03
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 00 | Zora | CSA | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | NA | NA | THP-FSSD-WA 01_20231109-NA-NA-NA-NA | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000182 | 2023-11-10 | 2023-11-10 | NA | NAP | Not Approved | 2 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" |  | 2023-11
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD | 2024-01-04 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2024-01-24 | 2024-02-15 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-01
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | INF | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2023-11
000182 | 01 | Zora | CSA | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | NA | NA | THP-FSSD-WA 01_20231109-NA-NA-NA-NA | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | 69 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000182 | 2023-11-10 | 2023-11-10 | NA | INF | Not Approved | 2 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" |  | 2023-11
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0010 | 0 | 131242-WST02-CD-IM-0010 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" |  | 2023-11
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0011 | 0 | 131242-WST02-CD-IM-0011 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" |  | 2023-11
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0012 | 0 | 131242-WST02-CD-IM-0012 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" |  | 2023-11
000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | M3 | Z | 8900 | 0 | 131242-WST02-M3-Z-8900 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" |  | 2023-11
000183 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | RT | IM | 9005 | 0 | 131242-WSW41-RT-IM-9005 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | 99 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000183 | 2023-11-10 | 2023-11-10 | 0 | REJ | Rejected | 1 | "Submission of Milestone 1.1 Electrical Building" |  | 2023-11
000184 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0013 | 0 | 131242-WSW41-MI-C-0013 | 2023-11-14 | CSA Meeting Minutes 0013_20231019 | For Information | 2023-12-12 | 2023-11-23 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000184 | 2023-11-14 | 2023-11-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0013_20231019" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD | A | 131242-WST02-DR-A-1000_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  | To follow up to submit Prolog | 000185 | 2023-11-15 | 2023-11-15 | A | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD | A | 131242-WST02-DR-A-1001_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | A | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9000_FSSD | A1 | 131242-WST02-DR-A-9000_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | A1 | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9001_FSSD | A1 | 131242-WST02-DR-A-9001_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | A1 | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | P | 7001_FSSD | SSN PFD | 131242-WST02-DR-P-7001_FSSD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | SSN PFD | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | AntiprexT AD 1020 XP_English | NA | NA | NA | NA | NA | AntiprexT AD 1020 XP_English-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | Caustic Soda 50% SDS | NA | NA | NA | NA | NA | Caustic Soda 50% SDS-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | Ferric Chloride SDS | NA | NA | NA | NA | NA | Ferric Chloride SDS-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG | NA | NA | NA | NA | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022 | NA | NA | NA | NA | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | TWRP C4B SSN_chemical inventory | NA | NA | NA | NA | NA | TWRP C4B SSN_chemical inventory-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000185 | 00 | Aaron | CSA | NA | WST02_SSN-FSSD-WA 01 & 02 | NA | NA | NA | NA | NA | WST02_SSN-FSSD-WA 01 & 02-NA-NA-NA-NA | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | 6 | Not Approved | YES | 2023-12-13 | NO | Resubmitted | 0 |  |  | 000185 | 2023-11-15 | 2023-11-15 | NA | NAP | Not Approved | 1 | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" |  | 2023-11
000186 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0006 | 0 | 131242-WSW41-PS-PM-0006 | 2023-11-15 | Monthly Progress Presentation No. 06 (1023) | For Information | 2023-12-13 | 2023-11-16 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000186 | 2023-11-15 | 2023-11-15 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 06 (1023)" |  | 2023-11
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | 0 | 131242-WST02-DR-P-6300 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2023-11
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | 0 | 131242-WST02-DR-P-6301 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2023-11
000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | 0 | 131242-WST02-DR-P-6500 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2023-11
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | B | 131242-WST02-DR-P-6300 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-16 | 2024-05-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2024-04
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | B | 131242-WST02-DR-P-6301 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-27 | 2024-05-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2024-04
000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | B | 131242-WST02-DR-P-6500 | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-27 | 2024-05-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2024-04
000187 | 02 | Qili | Process | NA | 131242 | WST02 | NA | P | S#187 Cmt Reply Sheet | NA | 131242-WST02-NA-P-S#187 Cmt Reply Sheet | 2024-10-01 | Plant Drain and Safety Shower P&ID | Rev 2: The submittal is merged with SRC 731. All the open comments from this submittal are transferred to SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000187 | 2024-10-01 | 2024-10-01 | NA | APP | Approved | 1 | "Plant Drain and Safety Shower P&ID" |  | 2024-10
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | A | 131242-WST02-DR-BF-1000 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | NAP | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" |  | 2023-11
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1001 | A | 131242-WST02-DR-BF-1001 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | NAP | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" |  | 2023-11
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A | 131242-WST02-DR-BF-7000 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2024-09-28 | A.1 | NAP | Approved with Comments | 2 | "Fire Alarm-Gas Suppression" |  | 2023-11
000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | A | 131242-WST02-DR-BF-7003 | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2025-09-11 | B | NAP | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" |  | 2023-11
000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A.1 | 131242-WST02-DR-BF-7000 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2024-09-28 | A.1 | AWC | Approved with Comments | 2 | "Fire Alarm-Gas Suppression" |  | 2024-09
000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | A.1 | 131242-WST02-DR-BF-7003 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" |  | 2024-09
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | B | 131242-WST02-DR-BF-1000 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" |  | 2025-09
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1001 | B | 131242-WST02-DR-BF-1001 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" |  | 2025-09
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1006 | B | 131242-WST02-DR-BF-1006 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188 | 2025-09-11 | 2025-09-11 | B | AWC | Approved with Comments | 1 | "Fire Alarm-Gas Suppression" |  | 2025-09
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5003 | B | 131242-WST02-DR-BF-5003 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188 | 2025-09-11 | 2025-09-11 | B | AWC | Approved with Comments | 1 | "Fire Alarm-Gas Suppression" |  | 2025-09
000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | B | 131242-WST02-DR-BF-7003 | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | 77 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000188 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" |  | 2025-09
000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A | 131242-WST02-DR-BP-1000 | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-12 | 84 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | NAP | Approved with Comments | 3 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2023-11
000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A | 131242-WST02-DR-BP-7000 | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-13 | 85 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | NAP | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2023-11
000189 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.1 | 131242-WST02-DR-BP-7000 | 2024-09-26 | Plumbing and Sanitary (SSN Area) | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | NAP | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2024-09
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-BP-7000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | AWC | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2025-02
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A.1 | 131242-WST02-DR-BP-1000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | AWC | Approved with Comments | 3 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2025-02
000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 5000 | A | 131242-WST02-DR-BP-5000 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000189 | 2025-02-24 | 2025-07-15 | A.1 | AWC | Approved with Comments | 2 | "SSN Plumbing and Sanitary " |  | 2025-02
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-BP-7000 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | PEN | Approved with Comments | 4 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2025-07
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A.2 | 131242-WST02-DR-BP-1000 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 000189 | 2023-11-15 | 2025-07-15 | A.2 | PEN | Approved with Comments | 3 | "Plumbing and Sanitary (SSN Area)" && "SSN Plumbing and Sanitary " |  | 2025-07
000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 5000 | A.1 | 131242-WST02-DR-BP-5000 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 000189 | 2025-02-24 | 2025-07-15 | A.1 | PEN | Approved with Comments | 2 | "SSN Plumbing and Sanitary " |  | 2025-07
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A | 131242-WST02-DR-BF-1002 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 00:00:00 | Schemiatic to submit 27 Jul 24. Layout drawing shall be confirm with Digie | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" |  | 2023-11
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1003 | A | 131242-WST02-DR-BF-1003 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" |  | 2023-11
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1004 | A | 131242-WST02-DR-BF-1004 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190 | 2023-11-15 | 2025-02-21 | A.1 | AWC | Approved with Comments | 2 | "Hose Reel (SSN Area)" |  | 2023-11
000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7001 | A | 131242-WST02-DR-BF-7001 | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&001305 | 2023-11-15 | 2025-05-18 | A | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" |  | 2023-11
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A.1 | 131242-WST02-DR-BF-1002 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 | 2025-02-20 00:00:00 |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" |  | 2025-02
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1003 | A.1 | 131242-WST02-DR-BF-1003 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" |  | 2025-02
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1004 | A.1 | 131242-WST02-DR-BF-1004 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000190 | 2023-11-15 | 2025-02-21 | A.1 | AWC | Approved with Comments | 2 | "Hose Reel (SSN Area)" |  | 2025-02
000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7001 | A.1 | 131242-WST02-DR-BF-7001 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | 17 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000190&&001305 | 2023-11-15 | 2025-05-18 | A | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" |  | 2025-02
000191 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0010 | 0 | 131242-WSW41-CD-IM-0010 | 2023-11-17 | Electrical Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | 94 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2023-11-17 | 2023-11-17 | 0 | AWC | Approved with Comments | 1 | "Electrical Building" |  | 2023-11
000191 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-IM-0027 | 2024-06-04 | Milestone 1.2 Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2024-06-04 | 2026-01-16 | 0 | AWC | Approved with Comments | 2 | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" |  | 2024-06
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0059 | 0 | 131242-WSW41-CD-IM-0059 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1003 | B_MS2 | 131242-WST02-DR-B-1003 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1004 | B_MS2 | 131242-WST02-DR-B-1004 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1005 | B_MS2 | 131242-WST02-DR-B-1005 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1006 | B_MS2 | 131242-WST02-DR-B-1006 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1000 | A.1 | 131242-WST02-DR-BF-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1001 | A.1 | 131242-WST02-DR-BF-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000188&&000191 | 2023-11-15 | 2025-09-11 | B | AWC | Approved with Comments | 3 | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1011 | A9 | 131242-WST02-DR-BF-1011 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1012 | A9 | 131242-WST02-DR-BF-1012 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BH | 1000 | A.1 | 131242-WST02-DR-BH-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BH | 1001 | A.2 | 131242-WST02-DR-BH-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1002 | A.1_MS2 | 131242-WST02-DR-BF-1002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1003 | A.1_MS2 | 131242-WST02-DR-BF-1003 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000190&&000191 | 2023-11-15 | 2025-05-15 | A.1_MS2 | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1310 | A | 131242-WST02-DR-E-1310 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1311 | A | 131242-WST02-DR-E-1311 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1312 | A | 131242-WST02-DR-E-1312 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1313 | A | 131242-WST02-DR-E-1313 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3310 | A | 131242-WST02-DR-E-3310 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3311 | A | 131242-WST02-DR-E-3311 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3312 | A | 131242-WST02-DR-E-3312 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3313 | A | 131242-WST02-DR-E-3313 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3314 | A | 131242-WST02-DR-E-3314 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3315 | A | 131242-WST02-DR-E-3315 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3316 | A | 131242-WST02-DR-E-3316 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3317 | A | 131242-WST02-DR-E-3317 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3318 | A | 131242-WST02-DR-E-3318 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3319 | A | 131242-WST02-DR-E-3319 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3320 | A | 131242-WST02-DR-E-3320 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3321 | A | 131242-WST02-DR-E-3321 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-EP-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1001 | C | 131242-WST02-DR-EP-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-EK-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1001 | C | 131242-WST02-DR-EK-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1002 | C | 131242-WST02-DR-EK-1002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-EL-1000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1001 | B | 131242-WST02-DR-EL-1001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000160&&000191 | 2023-11-03 | 2025-12-15 | D | AWC | Approved with Comments | 5 | "SSN Lighting Layout Plan" && "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-I-5000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000554 | 2024-07-10 | 2025-05-15 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN UPS and Battery Room Layout" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-I-5001 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000555 | 2024-07-10 | 2025-05-15 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Process Non-Process room layout" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5002 | A | 131242-WST02-DR-I-5002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5003 | A | 131242-WST02-DR-I-5003 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5004 | A | 131242-WST02-DR-I-5004 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5005 | A | 131242-WST02-DR-I-5005 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4004 | 0 | 131242-WST02-DR-M-4004 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000461 | 2024-05-06 | 2025-05-15 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1002 | A | 131242-WST02-DR-M-1002 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3000 | A | 131242-WST02-DR-M-3000 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | 93 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Electrical Building" |  | 2025-05
000191 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-IM-0027 | 2026-01-16 | Milestone 3 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000191 | 2024-06-04 | 2026-01-16 | 0 | PEN | Approved with Comments | 2 | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" |  | 2026-01
000192 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0008 | 0 | 131242-WSW41-CD-IM-0008 | 2023-11-17 | Chemical Dosing Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | 94 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2023-11-17 | 2023-11-17 | 0 | AWC | Approved with Comments | 1 | "Chemical Dosing Area" |  | 2023-11
000192 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0026 | 1 | 131242-WSW41-CD-IM-0026 | 2024-06-04 | Milestone 1.2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2024-06-04 | 2024-06-04 | 1 | AWC | Approved with Comments | 1 | "Milestone 1.2 SSN Chemical Dosing Area" |  | 2024-06
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-IM-0057 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2025-05-15 | 2026-01-16 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" |  | 2025-05
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1002 | C | 131242-WST02-DR-EP-1002 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | AWC | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" |  | 2025-05
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1004 | A | 131242-WST02-DR-M-1004 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Chemical Dosing Area" |  | 2025-05
000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3003 | A | 131242-WST02-DR-M-3003 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000192 | 2025-05-15 | 2025-05-15 | A | AWC | Approved with Comments | 1 | "Milestone 2 SSN Chemical Dosing Area" |  | 2025-05
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-IM-0057 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2025-05-15 | 2026-01-16 | 0 | PEN | Approved with Comments | 2 | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" |  | 2026-01
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1317 | C | 131242-WST02-DR-E-1317 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2026-01-16 | 2026-01-16 | C | PEN | Awaiting S.O.'s response | 1 | "Milestone 3 SSN Chemical Dosing Area" |  | 2026-01
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3333 | A | 131242-WST02-DR-E-3333 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2026-01-16 | 2026-01-16 | A | PEN | Awaiting S.O.'s response | 1 | "Milestone 3 SSN Chemical Dosing Area" |  | 2026-01
000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3334 | A | 131242-WST02-DR-E-3334 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | 51 | Awaiting S.O.'s response | YES | 2026-03-05 | NO | Overdue | 0 |  |  | 000192 | 2026-01-16 | 2026-01-16 | A | PEN | Awaiting S.O.'s response | 1 | "Milestone 3 SSN Chemical Dosing Area" |  | 2026-01
000193 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0002 | 1 | 131242-WST02-CL-B-0002 | 2023-11-17 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-12-15 | 2023-12-18 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000096&&000193 | 2023-09-12 | 2023-11-17 | 1 | NAP | Not Approved | 2 | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" |  | 2023-11
000193 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8001 | 0 | 131242-WST02-CL-BF-8001 | 2024-04-04 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 1: Approved | 2024-04-25 | 2024-04-26 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000193 | 2024-04-04 | 2024-04-04 | 0 | APP | Approved | 1 | "Engineering Calculation Report for Fire Hydrant Pipe" |  | 2024-04
000194 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | CL | B | 0003 | 1 | 131242-WST02-CL-B-0003 | 2023-11-17 | Engineering Calculation Report for Potable Water Pipe | This submission is withdrown. As submitted wrongly as a new submission, which should be a Rev.1 for submittal no. 000097. | 2023-12-15 | 2023-12-06 | 13 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 | Resubmission of Submittal 000097 |  | 000097&&000194 | 2023-09-12 | 2023-11-17 | 1 | VOID | (VOID NOT IN USE) | 2 | "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" |  | 2023-11
000195 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0005 | 0 | 131242-WSW41-MI-PM-0005 | 2023-11-20 | Monthly Progress Meeting Minutes 0005_20231017 | For Information | 2023-12-18 | 2023-11-23 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000195 | 2023-11-20 | 2023-11-20 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0005_20231017" |  | 2023-11
000196 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0006 | 0 | 131242-WSW41-MI-PM-0006 | 2023-11-15 | Monthly Progress Meeting Minutes 0006_20231114 | For Information | 2023-12-13 | 2023-11-23 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000196 | 2023-11-15 | 2023-11-15 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0006_20231114" |  | 2023-11
000197 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | A | 131242-WSD11-DR-E-7000 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | 114 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-23 00:00:00 |  | 000197 | 2023-11-21 | 2025-01-21 | B | AWC | Approved with Comments | 2 | "THP Overall Single Line Diagram" |  | 2023-11
000197 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | B | 131242-WSD11-DR-E-7000 | 2025-01-21 | THP Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-02-10 | 2025-04-30 | 71 | Approved with Comments | YES | 2025-05-20 | NO | Resubmitted | 0 |  |  | 000197 | 2023-11-21 | 2025-01-21 | B | AWC | Approved with Comments | 2 | "THP Overall Single Line Diagram" |  | 2025-01
000198 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7001 | 0 | 131242-WSD11-DR-E-7001 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | 114 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-23 00:00:00 | To drop an email for combination of S198, S197. To reply the comment sheet as noted and to resubmit in order to close. | 000198 | 2023-11-21 | 2023-11-21 | 0 | AWC | Approved with Comments | 1 | "THP Overall Single Line Diagram" |  | 2023-11
000199 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 0 | 131242-WST02-CL-E-0001 | 2023-11-22 | SSN Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000199 | 2023-11-22 | 2025-05-30 | 2 | NAP | Approved with Comments | 3 | "SSN Cable Sizing Calculations" |  | 2023-11
000199 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 1 | 131242-WST02-CL-E-0001 | 2024-06-24 | SSN Cable Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000199 | 2023-11-22 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Cable Sizing Calculations" |  | 2024-06
000199 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 2 | 131242-WST02-CL-E-0001 | 2025-05-30 | SSN Cable Sizing Calculations | Rev 2: Approved with comments. To revise and resubmit. | 2025-06-19 | 2025-07-23 | 38 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 000199 | 2023-11-22 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Cable Sizing Calculations" |  | 2025-05
000200 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 0 | 131242-WST02-VI-E-0000 | 2023-11-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet. | 2023-12-20 | 2023-12-22 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000200 | 2023-11-22 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" |  | 2023-11
000200 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 1 | 131242-WST02-VI-E-0000 | 2024-05-13 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-03 | 2024-07-04 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000200 | 2023-11-22 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" |  | 2024-05
000200 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 2 | 131242-WST02-VI-E-0000 | 2024-07-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 2: Approved. | 2024-08-12 | 2024-10-29 | 71 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000200 | 2023-11-22 | 2024-07-22 | 2 | APP | Approved | 3 | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" |  | 2024-07
000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | A | 131242-WST02-DR-E-7000 | 2023-11-22 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-23 00:00:00 |  | 000201 | 2023-11-22 | 2025-02-14 | B | AWC | Approved with Comments | 2 | "SSN Overall Single Line Diagram" |  | 2023-11
000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7001 | A | 131242-WST02-DR-E-7001 | 2023-11-23 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-21 | 2024-04-29 | 112 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000201 | 2023-11-23 | 2025-02-14 | B | AWC | Approved with Comments | 2 | "SSN Overall Single Line Diagram" |  | 2023-11
000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | B | 131242-WST02-DR-E-7000 | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | 57 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000201 | 2023-11-22 | 2025-02-14 | B | AWC | Approved with Comments | 2 | "SSN Overall Single Line Diagram" |  | 2025-02
000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7001 | B | 131242-WST02-DR-E-7001 | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | 57 | Awaiting S.O.'s response | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000201 | 2023-11-23 | 2025-02-14 | B | PEN | Approved with Comments | 2 | "SSN Overall Single Line Diagram" |  | 2025-02
000202 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 0 | 131242-WSD11-BQ-E-0001 | 2023-11-22 | THP Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | NAP | Approved with Comments | 4 | "THP Cable List" |  | 2023-11
000202 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 1 | 131242-WSD11-BQ-E-0001 | 2024-06-12 | THP Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-03 | 2024-08-16 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | AWC | Approved with Comments | 4 | "THP Cable List" |  | 2024-06
000202 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 2 | 131242-WSD11-BQ-E-0001 | 2025-04-10 | THP Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-30 | 2025-05-08 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | AWC | Approved with Comments | 4 | "THP Cable List" |  | 2025-04
000202 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 3 | 131242-WSD11-BQ-E-0001 | 2025-07-21 | THP Cable List | Rev 3: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-02 | 31 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 000202 | 2023-11-22 | 2025-07-21 | 3 | AWC | Approved with Comments | 4 | "THP Cable List" |  | 2025-07
000203 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | A | 131242-WSD11-CL-E-0000 | 2023-11-22 | THP Cable sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000203 | 2023-11-22 | 2024-06-12 | B | NAP | Approved with Comments | 2 | "THP Cable sizing Calculations" |  | 2023-11
000203 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | B | 131242-WSD11-CL-E-0000 | 2024-06-12 | THP Cable sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. | 2024-07-03 | 2024-08-16 | 47 | Approved with Comments | YES | 2024-09-05 | NO | Resubmitted | 0 |  |  | 000203 | 2023-11-22 | 2024-06-12 | B | AWC | Approved with Comments | 2 | "THP Cable sizing Calculations" |  | 2024-06
000204 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 0 | 131242-WST02-BQ-E-0001 | 2023-11-22 | SSN Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | NAP | Approved with Comments | 4 | "SSN Cable List" |  | 2023-11
000204 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 1 | 131242-WST02-BQ-E-0001 | 2024-06-24 | SSN Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | AWC | Approved with Comments | 4 | "SSN Cable List" |  | 2024-06
000204 | 02 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 2 | 131242-WST02-BQ-E-0001 | 2025-04-18 | SSN Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-08 | 2025-05-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | AWC | Approved with Comments | 4 | "SSN Cable List" |  | 2025-04
000204 | 03 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 3 | 131242-WST02-BQ-E-0001 | 2025-07-11 | SSN Cable List | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-07-31 | 2025-07-23 | 8 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 000204 | 2023-11-22 | 2025-07-11 | 3 | AWC | Approved with Comments | 4 | "SSN Cable List" |  | 2025-07
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-EK-1000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | A | 131242-WST02-DR-EK-1001 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | A | 131242-WST02-DR-EK-1002 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | A | 131242-WST02-DR-EK-1003 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | A | 131242-WST02-DR-EK-1004 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | A | 131242-WST02-DR-EK-1005 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | NAP | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | A | 131242-WST02-DR-EK-2000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | A | 131242-WST02-DR-EK-2001 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | A | 131242-WST02-DR-EK-2002 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | A | 131242-WST02-DR-EK-2003 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | A | 131242-WST02-DR-EK-5000 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | A | 131242-WST02-DR-EK-5001 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | A | 131242-WST02-DR-EK-5002 | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | 113 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2023-11
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | B | 131242-WST02-DR-EK-1000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-18 00:00:00 |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | B | 131242-WST02-DR-EK-1001 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | B | 131242-WST02-DR-EK-1002 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | B | 131242-WST02-DR-EK-1003 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | B | 131242-WST02-DR-EK-1004 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | B | 131242-WST02-DR-EK-1005 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | B | 131242-WST02-DR-EK-2000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | B | 131242-WST02-DR-EK-2001 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | B | 131242-WST02-DR-EK-2002 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | B | 131242-WST02-DR-EK-2003 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | B | 131242-WST02-DR-EK-5000 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | B | 131242-WST02-DR-EK-5001 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | B | 131242-WST02-DR-EK-5002 | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2024-07
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-EK-1000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | C | 131242-WST02-DR-EK-1001 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | C | 131242-WST02-DR-EK-1002 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000191&&000205 | 2023-11-22 | 2025-05-15 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Electrical Building" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | C | 131242-WST02-DR-EK-1003 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | C | 131242-WST02-DR-EK-1004 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | C | 131242-WST02-DR-EK-1005 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000163&&000205 | 2023-11-22 | 2025-04-28 | C | AWC | Approved with Comments | 5 | "Milestone 2 Underground Services" && "Milestone 2 SSN Water Tank" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | C | 131242-WST02-DR-EK-2000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | C | 131242-WST02-DR-EK-2001 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | C | 131242-WST02-DR-EK-2002 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | C | 131242-WST02-DR-EK-2003 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | C | 131242-WST02-DR-EK-5000 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | C | 131242-WST02-DR-EK-5001 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | C | 131242-WST02-DR-EK-5002 | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | 53 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000161&&000205 | 2023-11-22 | 2025-02-20 | C | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "Lightning Protection System" && "SSN Preliminary Lightning Protection System" |  | 2025-02
000206 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 0 | 131242-WST02-CL-P-0002 | 2023-11-22 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-02-26 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | pending Puriteq confirmation | 000206 | 2023-11-22 | 2025-03-04 | 1 | AWC | For Information | 2 | "Preliminary Sizing Calculation for SSN Future OCF System" |  | 2023-11
000206 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 1 | 131242-WST02-CL-P-0002 | 2025-03-04 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 1: For Information | 2025-03-24 | 2025-10-06 | 154 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000206 | 2023-11-22 | 2025-03-04 | 1 | INF | For Information | 2 | "Preliminary Sizing Calculation for SSN Future OCF System" |  | 2025-03
000207 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-P-0002 | 2023-11-22 | THP Equipment Sizing Calculation Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-03-07 | 76 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000207&&000212 | 2023-11-22 | 2023-11-24 | 0 | AWC | (VOID NOT IN USE) | 2 | "THP Equipment Sizing Calculation Sheet" |  | 2023-11
000207 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | Comment_CES Reply 2024 03 11 | NA | 131242-WSD11-CL-P-Comment_CES Reply 2024 03 11 | 2024-03-11 | THP Equipment Sizing Calculation Sheet | Rev 1: Approved | 2024-04-01 | 2024-04-29 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  | Rev 0 : AWC | 000207 | 2024-03-11 | 2024-03-11 | NA | APP | Approved | 1 | "THP Equipment Sizing Calculation Sheet" |  | 2024-03
000208 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 0 | 131242-WSD11-RT-E-0001 | 2023-11-22 | THP Atex Hazardous Area Assessment Report | Rev 0: For Information. Response to comment sheet required. | 2023-12-20 | 2024-05-15 | 125 | For Information | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 |  | 000208 | 2023-11-22 | 2024-09-11 | 1 | INF | For Information | 2 | "THP Atex Hazardous Area Assessment Report" |  | 2023-11
000208 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 1 | 131242-WSD11-RT-E-0001 | 2024-09-11 | THP Atex Hazardous Area Assessment Report | Rev 1: For Information. | 2024-10-01 | 2024-10-25 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000208 | 2023-11-22 | 2024-09-11 | 1 | INF | For Information | 2 | "THP Atex Hazardous Area Assessment Report" |  | 2024-09
000209 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0012 | 0 | 131242-WSW41-MI-P-0012 | 2023-11-24 | C4B Minutes of Engineering Process & MEICA Meeting No.0012 | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 127 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000209 | 2023-11-24 | 2023-11-24 | 0 | INF | For Information | 1 | "C4B Minutes of Engineering Process & MEICA Meeting No.0012" |  | 2023-11
000210 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0003 | 0 | 131242-WST02-MI-P-0003 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 127 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000210 | 2023-11-24 | 2023-11-24 | 0 | INF | For Information | 1 | "C4B Minutes of SSN Ad Hoc Meeting" |  | 2023-11
000211 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0004 | 0 | 131242-WST02-MI-P-0004 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | 127 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000211 | 2023-11-24 | 2023-11-24 | 0 | INF | For Information | 1 | "C4B Minutes of SSN Ad Hoc Meeting" |  | 2023-11
000212 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-P-0002 | 2023-11-24 | THP Equipment Sizing Calculation Sheet | This submittal is withdrawn. As already submitted these drawings under in the submittal 000207 on 22 Nov 2023. | 2023-12-22 | 2023-12-08 | 10 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000207&&000212 | 2023-11-22 | 2023-11-24 | 0 | VOID | (VOID NOT IN USE) | 2 | "THP Equipment Sizing Calculation Sheet" |  | 2023-11
000213 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0014 | 0 | 131242-WSW41-MI-C-0014 | 2023-11-27 | C4B Minutes of CSA Progress Meeting No.0014 | For Information | 2023-12-26 | 2023-12-13 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000213 | 2023-11-27 | 2023-11-27 | 0 | INF | For Information | 1 | "C4B Minutes of CSA Progress Meeting No.0014" |  | 2023-11
000214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0005 | 0 | 131242-WSW41-PC-W-0005 | 2023-11-27 | PAYMENT CLAIM NO.5 | Approved. Please refer to S.O. Correspondence No. 0089 dated 1 Dec 2023. | 2023-12-26 | 2023-12-06 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000214 | 2023-11-27 | 2023-11-27 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.5" |  | 2023-11
000215 | 00 | Franklin | PMT | NA | 131242 | WSW41 | LT | PM | 0016 | 0 | 131242-WSW41-LT-PM-0016 | 2023-11-29 | Clarification on Anammox Reactor Design Capacity | Rev 0: For Information. Please find our respond as attached. | 2023-12-28 | 2024-07-26 | 172 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000215 | 2023-11-29 | 2023-11-29 | 0 | INF | For Information | 1 | "Clarification on Anammox Reactor Design Capacity" |  | 2023-11
000216 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 0 | 131242-WSW41-QA-C-0008 | 2023-11-30 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-29 | 2023-12-05 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000216 | 2023-11-30 | 2023-12-12 | 1 | AWC | Approved | 2 | "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" |  | 2023-11
000216 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 1 | 131242-WSW41-QA-C-0008 | 2023-12-12 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Approved | 2024-01-03 | 2024-01-12 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000216 | 2023-11-30 | 2023-12-12 | 1 | APP | Approved | 2 | "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" |  | 2023-12
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | 0 | 131242-WSD11-DR-EL-1000 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | 0 | 131242-WSD11-DR-EL-1001 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | 0 | 131242-WSD11-DR-EL-1002 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | 0 | 131242-WSD11-DR-EL-1003 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | 0 | 131242-WSD11-DR-EL-1004 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | REJ | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | A | 131242-WSD11-DR-EP-1000 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-26 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | A | 131242-WSD11-DR-EP-1001 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | A | 131242-WSD11-DR-EP-1002 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | A | 131242-WSD11-DR-EP-1003 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | A | 131242-WSD11-DR-EP-1004 | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | NAP | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 00:00:00 |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004 | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | C | 131242-WSD11-DR-EP-1000 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | C | 131242-WSD11-DR-EP-1001 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | C | 131242-WSD11-DR-EP-1002 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | C | 131242-WSD11-DR-EP-1003 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | C | 131242-WSD11-DR-EP-1004 | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | 16 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | A | 131242-WSD11-DR-EL-1000 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | A | 131242-WSD11-DR-EL-1001 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | A | 131242-WSD11-DR-EL-1002 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | A | 131242-WSD11-DR-EL-1003 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | A | 131242-WSD11-DR-EL-1004 | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | 55 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-11
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-09
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-09
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-09
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-09
000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004 | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | 68 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-09
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004 | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-04
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-08
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-08
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-08
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-08
000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004 | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-08
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-12
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-12
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-12
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-12
000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004 | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | NAP | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-12
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A | 131242-WST02-DR-BH-1000 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-11
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A | 131242-WST02-DR-BH-1001 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-11
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A | 131242-WST02-DR-BH-7000 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-11
000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A | 131242-WST02-DR-BH-7001 | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-11
000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.1 | 131242-WST02-DR-BH-7000 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2024-09
000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.1 | 131242-WST02-DR-BH-7001 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2024-09
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.2 | 131242-WST02-DR-BH-5000 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | NAP | Approved with Comments | 4 | "Building Services ACMV" |  | 2024-12
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.2 | 131242-WST02-DR-BH-7000 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2024-12
000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.2 | 131242-WST02-DR-BH-7001 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | NAP | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2024-12
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.3 | 131242-WST02-DR-BH-5000 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | AWC | Approved with Comments | 4 | "Building Services ACMV" |  | 2025-02
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.3 | 131242-WST02-DR-BH-7000 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-02
000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.3 | 131242-WST02-DR-BH-7001 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-02
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-BH-1000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-07
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A.4 | 131242-WST02-DR-BH-1001 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-07
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.4 | 131242-WST02-DR-BH-5000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | AWC | Approved with Comments | 4 | "Building Services ACMV" |  | 2025-07
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.4 | 131242-WST02-DR-BH-7000 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-07
000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.4 | 131242-WST02-DR-BH-7001 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | 39 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-07
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-BH-1000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-10
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A.4 | 131242-WST02-DR-BH-1001 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-10
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.4 | 131242-WST02-DR-BH-5000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000219 | 2024-12-24 | 2025-10-29 | A.4 | AWC | Approved with Comments | 4 | "Building Services ACMV" |  | 2025-10
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.4 | 131242-WST02-DR-BH-7000 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-10
000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.4 | 131242-WST02-DR-BH-7001 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | 43 | Approved with Comments | YES | 2026-01-16 | NO | Resubmitted | 33 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | AWC | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2025-10
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | A | 131242-WST02-DR-BE-7000 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7001 | A | 131242-WST02-DR-BE-7001 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7002 | A | 131242-WST02-DR-BE-7002 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7003 | A | 131242-WST02-DR-BE-7003 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7004 | A | 131242-WST02-DR-BE-7004 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7005 | A | 131242-WST02-DR-BE-7005 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7006 | A | 131242-WST02-DR-BE-7006 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7007 | A | 131242-WST02-DR-BE-7007 | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | 115 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2023-11
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | B | 131242-WST02-DR-BE-7000 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 | TBA | Pending from C2D | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7001 | B | 131242-WST02-DR-BE-7001 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7002 | B | 131242-WST02-DR-BE-7002 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7003 | B | 131242-WST02-DR-BE-7003 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7004 | B | 131242-WST02-DR-BE-7004 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7005 | B | 131242-WST02-DR-BE-7005 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7006 | B | 131242-WST02-DR-BE-7006 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7007 | B | 131242-WST02-DR-BE-7007 | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | 53 | Not Approved | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 000220 | 2023-11-30 | 2025-04-03 | B | NAP | Not Approved | 2 | "SSN Distribution Board Single Line Diagram" |  | 2025-04
000221 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0002 | 0 | 131242-WSD11-PO-M-0002 | 2023-12-01 | Unpriced PO for Air Compressor System | For Information | 2024-01-02 | 2024-01-17 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000221 | 2023-12-01 | 2023-12-01 | 0 | INF | For Information | 1 | "Unpriced PO for Air Compressor System" |  | 2023-12
000222 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0010 | 0 | 131242-WSD11-DS-M-0010 | 2023-12-01 | Progressive Cavity Pumps | Rev 0: Not approved - Revise and Resubmit | 2024-01-02 | 2024-03-07 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000222 | 2023-12-01 | 2023-12-01 | 0 | NAP | Not Approved | 1 | "Progressive Cavity Pumps" |  | 2023-12
000222 | 01 | Joo Kwan | Process | NA | 131242 | NA | DS | M | S222 Cmt Sheet Reply 2024 07 22 | NA | 131242-NA-DS-M-S222 Cmt Sheet Reply 2024 07 22 | 2024-07-22 | Progressive Cavity Pumps | Rev 1: Rejected based on contractor's request. Reply to contractor reply is attached herewith. | 2024-08-12 | 2024-08-29 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000222 | 2024-07-22 | 2024-07-22 | NA | REJ | Rejected | 1 | "Progressive Cavity Pumps" |  | 2024-07
000223 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 0 | 131242-WSD11-DS-M-0009 | 2023-12-01 | THP Plant Safety Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet | 2024-01-02 | 2024-03-07 | 69 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | JV to follow up with JK to close the submittal | 000223 | 2023-12-01 | 2024-07-28 | 1 | AWC | Approved with Comments | 2 | "THP Plant Safety Valve" |  | 2023-12
000223 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 1 | 131242-WSD11-DS-M-0009 | 2024-07-28 | THP Plant Safety Valve | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-16 | 2024-08-01 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000223 | 2023-12-01 | 2024-07-28 | 1 | AWC | Approved with Comments | 2 | "THP Plant Safety Valve" |  | 2024-07
000224 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 0 | 131242-WSD11-SP-P-0001 | 2023-12-01 | THP System Control Philosophy | The submittal is approved with comments, resubmittal is required. | 2024-01-02 | 2024-01-26 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000224 | 2023-12-01 | 2024-03-01 | 1 | AWC | Approved with Comments | 2 | "THP System Control Philosophy" |  | 2023-12
000224 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 1 | 131242-WSD11-SP-P-0001 | 2024-03-01 | THP System Control Philosophy | Rev1- The submittal is approved with comments, resubmittal is required. The comments are | 2024-03-21 | 2024-04-26 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | JV to follow up with JK to close the submittal | 000224 | 2023-12-01 | 2024-03-01 | 1 | AWC | Approved with Comments | 2 | "THP System Control Philosophy" |  | 2024-03
000224 | 02 | Joo Kwan | Process | NA | 131242 | NA | SP | P | Cmt Sheet Reply S224.0 2024 07 30 | NA | 131242-NA-SP-P-Cmt Sheet Reply S224.0 2024 07 30 | 2024-07-30 | THP System Control Philosophy | Rev2- Although there are no active comments on the document, the document is still approved as noted to accommodate for the changes if any during the detail engineering. | 2024-08-20 | 2024-09-24 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000224 | 2024-07-30 | 2024-07-30 | NA | AWC | Approved with Comments | 1 | "THP System Control Philosophy" |  | 2024-07
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1000 | 0 | 131242-WST02-DR-BH-1000 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-12
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1001 | 0 | 131242-WST02-DR-BH-1001 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-12
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 7000 | 0 | 131242-WST02-DR-BH-7000 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-12
000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 7001 | 0 | 131242-WST02-DR-BH-7001 | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | 4 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000219&&000225 | 2023-11-30 | 2025-10-29 | A.4 | VOID | Approved with Comments | 7 | "Building Services ACMV" && "SSN Electrical Building ACMV layout & Schedule" |  | 2023-12
000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0012 | 0 | 131242-WSW41-MI-IM-0012 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000226 | 2023-12-05 | 2023-12-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" |  | 2023-12
000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0013 | 0 | 131242-WSW41-MI-IM-0013 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000226 | 2023-12-05 | 2023-12-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" |  | 2023-12
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | A | 131242-WST02-DR-EP-1000 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2023-12
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | A | 131242-WST02-DR-EP-1001 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2023-12
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | A | 131242-WST02-DR-EP-1002 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" |  | 2023-12
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | A | 131242-WST02-DR-EP-1003 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | NAP | Not Approved | 4 | "SSN Power Layout Plan" |  | 2023-12
000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | A | 131242-WST02-DR-EP-1004 | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | 110 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" |  | 2023-12
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | B | 131242-WST02-DR-EP-1000 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2024-08
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | B | 131242-WST02-DR-EP-1001 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2024-08
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | B | 131242-WST02-DR-EP-1002 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" |  | 2024-08
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | B | 131242-WST02-DR-EP-1003 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | NAP | Not Approved | 4 | "SSN Power Layout Plan" |  | 2024-08
000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | B | 131242-WST02-DR-EP-1004 | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | 89 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" |  | 2024-08
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-EP-1000 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2025-04
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | C | 131242-WST02-DR-EP-1001 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2025-04
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | C | 131242-WST02-DR-EP-1002 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" |  | 2025-04
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | C | 131242-WST02-DR-EP-1003 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | NAP | Not Approved | 4 | "SSN Power Layout Plan" |  | 2025-04
000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | C | 131242-WST02-DR-EP-1004 | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | NAP | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" |  | 2025-04
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | D | 131242-WST02-DR-EP-1000 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 | TBA |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2026-01
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | D | 131242-WST02-DR-EP-1001 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000191&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Electrical Building" && "SSN Power Layout Plan" |  | 2026-01
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | D | 131242-WST02-DR-EP-1002 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000192&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Chemical Dosing Area" && "SSN Power Layout Plan" |  | 2026-01
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | D | 131242-WST02-DR-EP-1003 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000227 | 2023-12-05 | 2026-01-19 | D | PEN | Not Approved | 4 | "SSN Power Layout Plan" |  | 2026-01
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | D | 131242-WST02-DR-EP-1004 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000163&&000227 | 2023-12-05 | 2026-01-19 | D | PEN | Approved with Comments | 5 | "Milestone 2 SSN Water Tank" && "SSN Power Layout Plan" |  | 2026-01
000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1005 | D | 131242-WST02-DR-EP-1005 | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | 50 | Awaiting S.O.'s response | YES | 2026-03-06 | NO | Overdue | 0 |  |  | 000227 | 2026-01-19 | 2026-01-19 | D | PEN | Awaiting S.O.'s response | 1 | "SSN Power Layout Plan" |  | 2026-01
000228 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | RT | C | 0001 | 0 | 131242-WSW41-RT-C-0001 | 2023-12-05 | UXO Scanning Report | Approved | 2024-01-04 | 2023-12-14 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000228 | 2023-12-05 | 2023-12-05 | 0 | INF | For Information | 1 | "UXO Scanning Report" |  | 2023-12
000229 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 0 | 131242-WSW41-VI-M-0005 | 2023-12-05 | Preliminary Design and Vendor Approval of Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-04 | 2024-04-17 | 96 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 00:00:00 | To provide Vendor drawings after PO issued. | 000229 | 2023-12-05 | 2024-08-20 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval of Mixer " |  | 2023-12
000229 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 1 | 131242-WSW41-VI-M-0005 | 2024-08-20 | Preliminary Design and Vendor Approval of Mixer | Rev 1: Approved | 2024-09-09 | 2024-09-02 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000229 | 2023-12-05 | 2024-08-20 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval of Mixer " |  | 2024-08
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | 0 | 131242-WSD11-DR-P-6000 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 00:00:00 | To submit Detailed Design . Related to Detailed Design Report. | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | 0 | 131242-WSD11-DR-P-6001 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | 0 | 131242-WSD11-DR-P-6002 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | 0 | 131242-WSD11-DR-P-6003 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | 0 | 131242-WSD11-DR-P-6004 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | 0 | 131242-WSD11-DR-P-6005 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | 0 | 131242-WSD11-DR-P-6006 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | 0 | 131242-WSD11-DR-P-6007 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | 0 | 131242-WSD11-DR-P-6008 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | 0 | 131242-WSD11-DR-P-6009 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | 0 | 131242-WSD11-DR-P-6010 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | 0 | 131242-WSD11-DR-P-6011 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | 0 | 131242-WSD11-DR-P-6012 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | 0 | 131242-WSD11-DR-P-6013 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | 0 | 131242-WSD11-DR-P-6014 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | 0 | 131242-WSD11-DR-P-6015 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | 0 | 131242-WSD11-DR-P-6016 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | 0 | 131242-WSD11-DR-P-6017 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | 0 | 131242-WSD11-DR-P-6018 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | 62 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2023-12
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | B | 131242-WSD11-DR-P-6000 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 00:00:00 | Heng Peng to provide DGN dwg | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | B | 131242-WSD11-DR-P-6001 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | B | 131242-WSD11-DR-P-6002 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | B | 131242-WSD11-DR-P-6003 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | B | 131242-WSD11-DR-P-6004 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | B | 131242-WSD11-DR-P-6005 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | B | 131242-WSD11-DR-P-6006 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | B | 131242-WSD11-DR-P-6007 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | B | 131242-WSD11-DR-P-6008 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | B | 131242-WSD11-DR-P-6009 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | B | 131242-WSD11-DR-P-6010 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | B | 131242-WSD11-DR-P-6011 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | B | 131242-WSD11-DR-P-6012 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | B | 131242-WSD11-DR-P-6013 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | B | 131242-WSD11-DR-P-6014 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | B | 131242-WSD11-DR-P-6015 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | B | 131242-WSD11-DR-P-6016 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | B | 131242-WSD11-DR-P-6017 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | B | 131242-WSD11-DR-P-6018 | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-03
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | C | 131242-WSD11-DR-P-6000 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | C | 131242-WSD11-DR-P-6001 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | C | 131242-WSD11-DR-P-6002 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | C | 131242-WSD11-DR-P-6003 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | C | 131242-WSD11-DR-P-6004 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | C | 131242-WSD11-DR-P-6005 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | C | 131242-WSD11-DR-P-6006 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | C | 131242-WSD11-DR-P-6007 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | C | 131242-WSD11-DR-P-6008 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | C | 131242-WSD11-DR-P-6009 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | C | 131242-WSD11-DR-P-6010 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | C | 131242-WSD11-DR-P-6011 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | C | 131242-WSD11-DR-P-6012 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | C | 131242-WSD11-DR-P-6013 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | C | 131242-WSD11-DR-P-6014 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | C | 131242-WSD11-DR-P-6015 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | C | 131242-WSD11-DR-P-6016 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | C | 131242-WSD11-DR-P-6017 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | C | 131242-WSD11-DR-P-6018 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | C | 131242-WSD11-DR-P-6019 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | C | 131242-WSD11-DR-P-6020 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | C | 131242-WSD11-DR-P-6021 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | C | 131242-WSD11-DR-P-6022 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | C | 131242-WSD11-DR-P-6023 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | C | 131242-WSD11-DR-P-6024 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | C | 131242-WSD11-DR-P-6025 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | C | 131242-WSD11-DR-P-6026 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | C | 131242-WSD11-DR-P-6027 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | C | 131242-WSD11-DR-P-6028 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | C | 131242-WSD11-DR-P-6029 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | C | 131242-WSD11-DR-P-6030 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | C | 131242-WSD11-DR-P-6031 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | C | 131242-WSD11-DR-P-6032 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | C | 131242-WSD11-DR-P-6033 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | C | 131242-WSD11-DR-P-6034 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | C | 131242-WSD11-DR-P-6035 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | C | 131242-WSD11-DR-P-6036 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | C | 131242-WSD11-DR-P-6050 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | C | 131242-WSD11-DR-P-6063 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | B | 131242-WSD11-DR-P-6070 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | C | 131242-WSD11-DR-P-6101 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | C | 131242-WSD11-DR-P-6121 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | C | 131242-WSD11-DR-P-6200 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | C | 131242-WSD11-DR-P-6300 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | C | 131242-WSD11-DR-P-6400 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | C | 131242-WSD11-DR-P-6600 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | C | 131242-WSD11-DR-P-6601 | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-11
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | D | 131242-WSD11-DR-P-6000 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | D | 131242-WSD11-DR-P-6001 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | D | 131242-WSD11-DR-P-6002 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | D | 131242-WSD11-DR-P-6003 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | D | 131242-WSD11-DR-P-6004 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | D | 131242-WSD11-DR-P-6005 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | D | 131242-WSD11-DR-P-6006 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | D | 131242-WSD11-DR-P-6007 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | D | 131242-WSD11-DR-P-6008 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | D | 131242-WSD11-DR-P-6009 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | D | 131242-WSD11-DR-P-6010 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | D | 131242-WSD11-DR-P-6011 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | D | 131242-WSD11-DR-P-6012 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | D | 131242-WSD11-DR-P-6013 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | D | 131242-WSD11-DR-P-6014 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | D | 131242-WSD11-DR-P-6015 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | D | 131242-WSD11-DR-P-6016 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | D | 131242-WSD11-DR-P-6017 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | D | 131242-WSD11-DR-P-6018 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2023-12-06 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | D | 131242-WSD11-DR-P-6019 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | D | 131242-WSD11-DR-P-6020 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | D | 131242-WSD11-DR-P-6021 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | D | 131242-WSD11-DR-P-6022 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | D | 131242-WSD11-DR-P-6023 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | D | 131242-WSD11-DR-P-6024 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | D | 131242-WSD11-DR-P-6025 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | D | 131242-WSD11-DR-P-6026 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | D | 131242-WSD11-DR-P-6027 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | D | 131242-WSD11-DR-P-6028 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | D | 131242-WSD11-DR-P-6029 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | D | 131242-WSD11-DR-P-6030 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | D | 131242-WSD11-DR-P-6031 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | D | 131242-WSD11-DR-P-6032 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | D | 131242-WSD11-DR-P-6033 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | D | 131242-WSD11-DR-P-6034 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | D | 131242-WSD11-DR-P-6035 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | D | 131242-WSD11-DR-P-6036 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | D | 131242-WSD11-DR-P-6050 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6051 | D | 131242-WSD11-DR-P-6051 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230 | 2025-06-17 | 2025-06-17 | D | AWC | Approved with Comments | 1 | "P&ID of THP Train 1" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | D | 131242-WSD11-DR-P-6063 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | D | 131242-WSD11-DR-P-6070 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | D | 131242-WSD11-DR-P-6101 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | D | 131242-WSD11-DR-P-6121 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | D | 131242-WSD11-DR-P-6200 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | D | 131242-WSD11-DR-P-6300 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | D | 131242-WSD11-DR-P-6400 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | D | 131242-WSD11-DR-P-6600 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | D | 131242-WSD11-DR-P-6601 | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | 52 | Approved with Comments | YES | 2025-09-17 | NO | Resubmitted | 398 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2025-06
000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-S-1000_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2023-12
000231 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST604_BCA | A1 | 131242-WST02-DR-S-1001_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2023-12-07 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" |  | 2023-12
000231 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST604_BCA | A1 | 131242-WST02-DR-S-5001_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2023-12-07 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" |  | 2023-12
000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | A1 | 131242-WST00-DR-C-8000_ST604_BCA | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2023-12
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-S-1000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-05 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide latest DGN & PDF drawing | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604_BCA | A1 | 131242-WST02-DR-C-1001_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604_BCA | A1 | 131242-WST02-DR-C-1002_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604_BCA | A1 | 131242-WST02-DR-C-5001_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604_BCA | A1 | 131242-WST02-DR-C-7000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | A1 | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | A1 | 131242-WST00-DR-C-8000_ST604_BCA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2023-12-07 | 2024-01-16 | A1 | AWC | Approved with Comments | 2 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000231 | 01 | Zora/ HP | CSA | NA | A1798-00002-2018-ST604_NOA | NA | NA | NA | NA | NA | A1798-00002-2018-ST604_NOA-NA-NA-NA-NA | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | 21 | Approved with Comments | YES | 2024-03-05 | NO | Resubmitted | 0 |  |  | 000231 | 2024-01-16 | 2024-01-16 | NA | AWC | Approved with Comments | 1 | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" |  | 2024-01
000232 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 0 | 131242-WSW41-VI-M-0007 | 2023-12-08 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-09 | 2024-02-26 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 00:00:00 | Yibo WIP | 000232 | 2023-12-08 | 2025-02-28 | 2 | AWC | Approved | 3 | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" |  | 2023-12
000232 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 1 | 131242-WSW41-VI-M-0007 | 2024-07-29 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-19 | 2024-09-02 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | In progress. Only one ICA comment is open (s/n.19), will reconfirm with ICA team, Try resubmit in 1 week. | 000232 | 2023-12-08 | 2025-02-28 | 2 | AWC | Approved | 3 | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" |  | 2024-07
000232 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 2 | 131242-WSW41-VI-M-0007 | 2025-02-28 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 2: Approved | 2025-03-20 | 2025-11-24 | 191 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000232 | 2023-12-08 | 2025-02-28 | 2 | APP | Approved | 3 | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" |  | 2025-02
000233 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0012 | 0 | 131242-WSW41-CD-IM-0012 | 2023-12-08 | Submission Of BIM Coordination VCM Model (Nov – 2023) | For Information | 2024-01-09 | 2023-12-26 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000233 | 2023-12-08 | 2023-12-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Nov – 2023)" |  | 2023-12
000234 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0007 | 0 | 131242-WSW41-RT-PM-0007 | 2023-12-11 | C4B Monthly Progress Report Number No.07 (11/23) | Rev. 0 - Approved with comments (need to re-submit) | 2024-01-10 | 2023-12-18 | 5 | Approved with Comments | YES | 2024-01-05 | NO | Resubmitted | 0 |  |  | 000234 | 2023-12-11 | 2023-12-11 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.07 (11/23)" |  | 2023-12
000235 | 00 | Zora | CSA | NA | 131242 | WSW41 | RT | C | 0002 | 0 | 131242-WSW41-RT-C-0002 | 2023-12-12 | ULT Test Report of 600mm Dia. Bored Pile | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-11 | 2023-12-18 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000235 | 2023-12-12 | 2023-12-22 | 1 | AWC | Approved with Comments | 2 | "ULT Test Report of 600mm Dia. Bored Pile " |  | 2023-12
000235 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0002 | 1 | 131242-WSW41-RT-C-0002 | 2023-12-22 | ULT Test Report of 600mm Dia. Bored Pile | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-15 | 2024-01-16 | 17 | Approved with Comments | YES | 2024-02-05 | NO | Resubmitted | 0 |  |  | 000235 | 2023-12-12 | 2023-12-22 | 1 | AWC | Approved with Comments | 2 | "ULT Test Report of 600mm Dia. Bored Pile " |  | 2023-12
000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | A | 131242-WSD11-DR-E-1100 | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | 71 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-19 00:00:00 |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | A | 131242-WSD11-DR-E-1101 | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | 71 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2023-12
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-08
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1105 | B | 131242-WSD11-DR-E-1105 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" |  | 2024-08
000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1106 | B | 131242-WSD11-DR-E-1106 | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" |  | 2024-08
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | C | 131242-WSD11-DR-E-1100 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-03
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | C | 131242-WSD11-DR-E-1101 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-03
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1102 | C | 131242-WSD11-DR-E-1102 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-03
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1103 | C | 131242-WSD11-DR-E-1103 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-03
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1104 | C | 131242-WSD11-DR-E-1104 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-03
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1105 | C | 131242-WSD11-DR-E-1105 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" |  | 2025-03
000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1106 | C | 131242-WSD11-DR-E-1106 | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000236 | 2024-08-13 | 2025-03-28 | C | AWC | Approved with Comments | 2 | "THP Earthing Layout Plan" |  | 2025-03
000237 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0001 | 0 | 131242-WST02-VI-E-0001 | 2023-12-12 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | Not Approved. To revise and resubmit. Please refer to comment sheet | 2024-01-11 | 2024-01-24 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000237 | 2023-12-12 | 2023-12-12 | 0 | NAP | Not Approved | 1 | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" |  | 2023-12
000237 | 01 | Freedomer | EICA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S237.0 2024 07 22 | NA | 131242-NA-NA-NA-Cmt Sheet Reply S237.0 2024 07 22 | 2024-07-22 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | R1: Rejected as requested by C4B | 2024-08-12 | 2024-08-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000237 | 2024-07-22 | 2024-07-22 | NA | NAP | Not Approved | 1 | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" |  | 2024-07
000238 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 0 | 131242-WSW41-VI-M-1000 | 2023-12-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Not Approved. To revise and resubmit. | 2024-01-15 | 2024-02-19 | 47 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000238 | 2023-12-14 | 2024-08-07 | 2 | NAP | Approved | 3 | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" |  | 2023-12
000238 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 1 | 131242-WSW41-VI-M-1000 | 2024-03-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-04 | 2024-04-17 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-30 00:00:00 |  | 000238 | 2023-12-14 | 2024-08-07 | 2 | AWC | Approved | 3 | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" |  | 2024-03
000238 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 2 | 131242-WSW41-VI-M-1000 | 2024-08-07 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Rev 2: Approved | 2024-08-28 | 2024-09-02 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000238 | 2023-12-14 | 2024-08-07 | 2 | APP | Approved | 3 | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" |  | 2024-08
000239 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 0 | 131242-WSW41-VI-M-1002 | 2023-12-14 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-02-19 | 47 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000239 | 2023-12-14 | 2024-04-02 | 1 | NAP | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" |  | 2023-12
000239 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 1 | 131242-WSW41-VI-M-1002 | 2024-04-02 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. Please note, that the approval, corresponds to the brand/manufacturer proposed by contractor in this submittal. Approval does not include assessment for Trader/Distributor. | 2024-04-23 | 2024-04-15 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000239 | 2023-12-14 | 2024-04-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" |  | 2024-04
000240 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0015 | 0 | 131242-WSW41-MI-C-0015 | 2023-12-14 | CSA Meeting Minutes 0015_20231116 | For Information | 2024-01-15 | 2024-01-25 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000240 | 2023-12-14 | 2023-12-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0015_20231116" |  | 2023-12
000241 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0001 | 0 | 131242-WST02-VI-I-0001 | 2023-12-14 | Preliminary design and Vendor Approval – SSN Package (ICA) | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-26 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000241 | 2023-12-14 | 2024-05-02 | 1 | NAP | Approved with Comments | 2 | "Preliminary design and Vendor Approval – SSN Package (ICA)" |  | 2023-12
000241 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0001 | 1 | 131242-WST02-VI-I-0001 | 2024-05-02 | Preliminary design and Vendor Approval – SSN Package (ICA) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-23 | 2024-06-18 | 33 | Approved with Comments | YES | 2024-07-08 | NO | Resubmitted | 0 |  | Pending from MP | 000241 | 2023-12-14 | 2024-05-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – SSN Package (ICA)" |  | 2024-05
000242 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 0 | 131242-WSD11-DS-I-0003 | 2023-12-14 | THP PLC RIO Component Datasheet | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000242 | 2023-12-14 | 2024-03-11 | 1 | NAP | Not Approved | 2 | "THP PLC RIO Component Datasheet" |  | 2023-12
000242 | 01 | Low | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 1 | 131242-WSD11-DS-I-0003 | 2024-03-11 | THP PLC RIO Component Datasheet | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-01 | 2024-05-15 | 47 | Not Approved | YES | 2024-06-04 | NO | Resubmitted | 0 |  |  | 000242 | 2023-12-14 | 2024-03-11 | 1 | NAP | Not Approved | 2 | "THP PLC RIO Component Datasheet" |  | 2024-03
000243 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 0 | 131242-WSD11-CH-I-0001 | 2023-12-14 | THP IO List | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000243 | 2023-12-14 | 2024-07-16 | 1 | NAP | Not Approved | 2 | "THP IO List" |  | 2023-12
000243 | 01 | Low | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 1 | 131242-WSD11-CH-I-0001 | 2024-07-16 | THP IO List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. To revise and resubmit. | 2024-08-05 | 2024-09-17 | 45 | Not Approved | YES | 2024-10-07 | NO | Resubmitted | 0 |  |  | 000243 | 2023-12-14 | 2024-07-16 | 1 | NAP | Not Approved | 2 | "THP IO List" |  | 2024-07
000244 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0004 | 0 | 131242-WST02-CL-B-0004 | 2023-12-14 | Heat Load Calculation Report for ACMV | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-03-12 | 63 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000244 | 2023-12-14 | 2023-12-14 | 0 | NAP | Not Approved | 1 | "Heat Load Calculation Report for ACMV" |  | 2023-12
000244 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 0 | 131242-WST02-CL-BH-8001 | 2024-05-14 | Heat Load Calculation Report for ACMV | Not approved - Revise and Resubmit | 2024-06-04 | 2024-08-14 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000244 | 2024-05-14 | 2025-03-20 | 2 | NAP | Approved | 2 | "Heat Load Calculation Report for ACMV" |  | 2024-05
000244 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 2 | 131242-WST02-CL-BH-8001 | 2025-03-20 | Heat Load Calculation Report for ACMV | Rev 2: Approved | 2025-04-09 | 2025-05-25 | 47 | Approved | NO |  | YES | Resubmitted | 0 | Pending EICA input | Doc name duplicate with S#193, Fire Hydrant Calculation/ Pending by EICA info and C2D . Freedomer follow up | 000244 | 2024-05-14 | 2025-03-20 | 2 | APP | Approved | 2 | "Heat Load Calculation Report for ACMV" |  | 2025-03
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-E-1100 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2023-12
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | A | 131242-WST02-DR-E-1101 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2023-12
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | A | 131242-WST02-DR-E-1102 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | NAP | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2023-12
000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1103 | A | 131242-WST02-DR-E-1103 | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000245 | 2023-12-18 | 2023-12-18 | A | NAP | Not Approved | 1 | "SSN Earthing Layout Plan" |  | 2023-12
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B | 131242-WST02-DR-E-1100 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-19 00:00:00 |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-06
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | B | 131242-WST02-DR-E-1101 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-06
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | B | 131242-WST02-DR-E-1102 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-06
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7750 | B | 131242-WST02-DR-E-7750 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-06
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7751 | B | 131242-WST02-DR-E-7751 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-06
000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7752 | B | 131242-WST02-DR-E-7752 | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2024-06
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B_endorsed | 131242-WST02-DR-E-1100 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2025-02
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | B_endorsed | 131242-WST02-DR-E-1101 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2025-02
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | B_endorsed | 131242-WST02-DR-E-1102 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2023-12-18 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 4 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2025-02
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7750 | B_endorsed | 131242-WST02-DR-E-7750 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2025-02
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7751 | B_endorsed | 131242-WST02-DR-E-7751 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2025-02
000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7752 | B_endorsed | 131242-WST02-DR-E-7752 | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000161&&000245 | 2024-06-11 | 2025-02-25 | B_endorsed | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" |  | 2025-02
000246 | 00 | Lilian | PMT | NA | 131242 | WSW41 | LT | PM | 0017 | 0 | 131242-WSW41-LT-PM-0017 | 2023-12-18 | THP Layout and Code Compliance | As requested by contractor via email dated 5 Feb 24 to withdraw the submission. | 2024-01-17 | 2024-02-06 | 36 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  |  | 000246 | 2023-12-18 | 2023-12-18 | 0 | VOID | (VOID NOT IN USE) | 1 | "THP Layout and Code Compliance" |  | 2023-12
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1011 | 0 | 131242-WSW41-SD-S-1011 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | 17 | Not Approved | YES | 2024-02-02 | NO | Resubmitted | 0 |  | Zora checking comment sheet | 000247 | 2023-12-21 | 2023-12-21 | 0 | NAP | Not Approved | 1 | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " |  | 2023-12
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1012 | 0 | 131242-WSW41-SD-S-1012 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | 17 | Not Approved | YES | 2024-02-02 | NO | Resubmitted | 0 |  |  | 000247 | 2023-12-21 | 2023-12-21 | 0 | NAP | Not Approved | 1 | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " |  | 2023-12
000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1013 | 0 | 131242-WSW41-SD-S-1013 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | 17 | Not Approved | YES | 2024-02-02 | NO | Resubmitted | 0 |  |  | 000247 | 2023-12-21 | 2023-12-21 | 0 | NAP | Not Approved | 1 | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | CL | G | 0001_ST601 | A | 131242-WST00-CL-G-0001_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248 | 2023-12-22 | 2023-12-22 | A | NAP | Not Approved | 1 | "ST601 – ERSS Design < 4m Depth" |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2023-12
000248 | 00 | Zora | CSA | NA | 131242 | WST00 | CH | IM | 0003_ST601 | NA | 131242-WST00-CH-IM-0003_ST601 | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 1 | "ST601 – ERSS Design < 4m Depth" |  | 2023-12
000248 | 00 | Zora | CSA | NA | DGN FILES | NA | NA | NA | NA | NA | DGN FILES-NA-NA-NA-NA | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000249 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 2 | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | NAP | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601 | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | NAP | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-02
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-06 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 | 2024-07-19 00:00:00 | Heng Peng to clear BIM comments. Pending BIM updates | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601 | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | 25 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-04
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST602 | A | 131242-WST00-DR-C-8001_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2023-12-22 | A | NAP | Not Approved | 1 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | CL | G | 0002_ST602 | A | 131242-WST00-CL-G-0002_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2023-12-22 | A | NAP | Not Approved | 1 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | 131242 | WST00 | CH | IM | 0004_ST602 | NA | 131242-WST00-CH-IM-0004_ST602 | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 1 | "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 00 | Zora | CSA | NA | DGN FILES | NA | NA | NA | NA | NA | DGN FILES-NA-NA-NA-NA | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000249 | 2023-12-22 | 2023-12-22 | NA | NAP | Not Approved | 2 | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" |  | 2023-12
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-G-8001_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2024-02-24 | 2024-07-02 | A.1 | NAP | Approved | 3 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602 | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-02
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-G-8001_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-11 | 2024-07-01 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending Tenwit update. (Roobin) | 000249 | 2024-02-24 | 2024-07-02 | A.1 | AWC | Approved | 3 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602 | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | NAP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-06
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A.1 | 131242-WST00-DR-G-8001_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  | R2_APP | 000249 | 2024-02-24 | 2024-07-02 | A.1 | APP | Approved | 3 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A.1 | 131242-WST00-DR-G-0100_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A.1 | 131242-WST00-DR-G-0101_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A.1 | 131242-WST00-DR-G-1100_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A.1 | 131242-WST00-DR-G-1101_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A.1 | 131242-WST00-DR-G-1102_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A.1 | 131242-WST00-DR-G-3100_ST602 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000249 | 2023-12-22 | 2024-07-02 | A.1 | APP | Approved | 4 | "ST602 – ERSS Design < 6m Depth" |  | 2024-07
000250 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0001 | 0 | 131242-WSW41-VI-M-0001 | 2023-12-22 | Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-23 | 2024-02-26 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000250 | 2023-12-22 | 2023-12-22 | 0 | AWC | Approved with Comments | 1 | "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" |  | 2023-12
000251 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 0 | 131242-WST02-BQ-I-0001 | 2023-12-26 | C4B SSN PLC/ RIO Panel Component Catalogue | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-24 | 2024-01-29 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000251 | 2023-12-26 | 2024-04-08 | 1 | NAP | Not Approved | 2 | "C4B SSN PLC/ RIO Panel Component Catalogue" |  | 2023-12
000251 | 01 | Low | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 1 | 131242-WST02-BQ-I-0001 | 2024-04-08 | C4B SSN PLC/ RIO Panel Component Catalogue | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-29 | 2024-05-15 | 27 | Not Approved | YES | 2024-06-04 | NO | Resubmitted | 0 |  | Pending from MP | 000251 | 2023-12-26 | 2024-04-08 | 1 | NAP | Not Approved | 2 | "C4B SSN PLC/ RIO Panel Component Catalogue" |  | 2024-04
000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | A | 131242-WSW41-DR-EK-1000 | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 | ?? |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2023-12
000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | A | 131242-WSW41-DR-EK-3000 | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | NAP | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2023-12
000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-EK-1000 | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-19 00:00:00 |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2024-07
000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | B | 131242-WSW41-DR-EK-3000 | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2024-07
000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | C | 131242-WSW41-DR-EK-1000 | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | 50 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2025-02
000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | C | 131242-WSW41-DR-EK-3000 | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | 50 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000120&&000252 | 2023-12-27 | 2025-02-26 | A.2 | AWC | Approved with Comments | 5 | "Milestone 2 Sitewide Pipe Rack" && "Sitewide Piperack Lightning Protection System" |  | 2025-02
000253 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0013 | 0 | 131242-WSW41-MI-P-0013 | 2023-12-27 | Process & MEICA Meeting Minutes 0013_20231123 | Rev 0: For Information | 2024-01-25 | 2024-05-21 | 104 | For Information | NO |  | YES | Resubmitted | 0 | 2024-03-06 00:00:00 | Waiting for C2D reply | 000253 | 2023-12-27 | 2023-12-27 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0013_20231123" |  | 2023-12
000254 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0018 | 0 | 131242-WSW41-LT-PM-0018 | 2023-12-28 | CV of WSHS | Approved | 2024-01-26 | 2024-02-14 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000254 | 2023-12-28 | 2023-12-28 | 0 | APP | Approved | 1 | "CV of WSHS" |  | 2023-12
000255 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0011 | 0 | 131242-WSD11-CD-IM-0011 | 2023-12-28 | Submission of Milestone 1.1 THP MCC Room | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-01-26 | 2024-03-28 | 65 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000255 | 2023-12-28 | 2023-12-28 | 0 | AWC | Approved with Comments | 1 | "Submission of Milestone 1.1 THP MCC Room" |  | 2023-12
000255 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-IM-0034 | 2024-06-04 | Milestone 1.2 THP MCC Room | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-12-05 | 132 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000255 | 2024-06-04 | 2025-10-31 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" |  | 2024-06
000255 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-IM-0034 | 2025-02-26 | Milestone 2 THP MCC Room | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | 90 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000255 | 2024-06-04 | 2025-10-31 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" |  | 2025-02
000255 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 1 | 131242-WSD11-CD-IM-0034 | 2025-10-31 | Milestone 3 THP MCC Room | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-23 | 81 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000255 | 2024-06-04 | 2025-10-31 | 1 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" |  | 2025-10
000256 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0003 | 0 | 131242-WSW41-CT-W-0003 | 2023-12-28 | On-Demand Bond for SSN | Approved. Address as per Chin Swee Rd address as the bond was submitted (in Nov 2023) was prior to the notice (in Dec 2023) of change of address. | 2024-01-26 | 2024-01-16 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000256 | 2023-12-28 | 2023-12-28 | 0 | APP | Approved | 1 | "On-Demand Bond for SSN" |  | 2023-12
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6200 | 0 | 131242-WSD11-DR-P-6200 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 00:00:00 | Related to Detailed Design Report. | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2023-12
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6300 | 0 | 131242-WSD11-DR-P-6300 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2023-12
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6400 | 0 | 131242-WSD11-DR-P-6400 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2023-12
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6600 | 0 | 131242-WSD11-DR-P-6600 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2023-12
000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6601 | 0 | 131242-WSD11-DR-P-6601 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2023-12
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | B | 131242-WSD11-DR-P-6200 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | B | 131242-WSD11-DR-P-6300 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | B | 131242-WSD11-DR-P-6400 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | B | 131242-WSD11-DR-P-6600 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | B | 131242-WSD11-DR-P-6601 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2023-12-28 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | B | 131242-WSD11-DR-P-6101 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | B | 131242-WSD11-DR-P-6121 | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000257 | 2024-03-19 | 2025-06-17 | D | AWC | Approved with Comments | 3 | "P&ID of THP Train 1" && "P&ID of THP General System" |  | 2024-03
000258 | 00 | Yi Hao | Contracts | NA | 131242 | WST02 | PO | P | 0001 | 0 | 131242-WST02-PO-P-0001 | 2024-01-03 | Unpriced PO for SSN Package (MattenPlant) | For Information | 2024-01-31 | 2024-04-26 | 82 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000258 | 2024-01-03 | 2024-01-03 | 0 | INF | For Information | 1 | "Unpriced PO for SSN Package (MattenPlant)" |  | 2024-01
000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0014 | 0 | 131242-WSW41-MI-P-0014 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | 99 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000259 | 2024-01-03 | 2024-01-03 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" |  | 2024-01
000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0015 | 0 | 131242-WSW41-MI-P-0015 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | 99 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000259 | 2024-01-03 | 2024-01-03 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" |  | 2024-01
000260 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0013 | 0 | 131242-WST02-CD-IM-0013 | 2024-01-05 | Milestone 1.1 SSN Overall Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-02-02 | 2024-03-28 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000260 | 2024-01-05 | 2024-01-05 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 SSN Overall Area" |  | 2024-01
000260 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0038 | 0 | 131242-WST02-CD-IM-0038 | 2024-06-11 | Milestone 1.2 SSN Overall Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000260 | 2024-06-11 | 2024-06-11 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.2 SSN Overall Area" |  | 2024-06
000260 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-IM-0058 | 2025-05-15 | Milestone 2 SSN Overall Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000260 | 2025-05-15 | 2025-10-31 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" |  | 2025-05
000260 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-IM-0058 | 2025-10-31 | Milestone 3 SSN Overall Area | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | 62 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 000260 | 2025-05-15 | 2025-10-31 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" |  | 2025-10
000261 | 00 | Lilian | PMT | NA | 131242 | WSW41 | PC | W | 0006 | 0 | 131242-WSW41-PC-W-0006 | 2024-01-08 | PAYMENT CLAIM NO.6 | Approved. Please refer to S.O. correspondence no. 103 dated 8 Jan 2024. | 2024-02-05 | 2024-01-30 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000261 | 2024-01-08 | 2024-01-08 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.6" |  | 2024-01
000262 | 00 | Geno | Piping | NA | 131242 | WST02 | SH | M | 1002 | 0 | 131242-WST02-SH-M-1002 | 2024-01-08 | Tie in Schedule for SSN | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-05 | 2024-05-27 | 100 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2025-02-26 00:00:00 | Waiting for SO RFI reply . KM & Qili to check with Karthic for the response | 000262 | 2024-01-08 | 2024-01-08 | 0 | AWC | Approved with Comments | 1 | "Tie in Schedule for SSN" |  | 2024-01
000263 | 00 | Geno | Piping | NA | 131242 | WSD11 | SH | M | 1001 | 0 | 131242-WSD11-SH-M-1001 | 2024-01-09 | Tie in Schedule for THP | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | 99 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2025-02-26 00:00:00 |  | 000263 | 2024-01-09 | 2024-01-09 | 0 | AWC | Approved with Comments | 1 | "Tie in Schedule for THP" |  | 2024-01
000264 | 00 | Geno | Piping | NA | 131242 | WSW41 | SH | M | 5000 | 0 | 131242-WSW41-SH-M-5000 | 2024-01-09 | Tie in Schedule for Side wide | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | 99 | Approved with Comments | YES | 2024-06-14 | NO | Resubmitted | 0 | 2025-02-26 00:00:00 |  | 000264 | 2024-01-09 | 2024-01-09 | 0 | AWC | Approved with Comments | 1 | "Tie in Schedule for Side wide" |  | 2024-01
000265 | 00 | Lilian/ Yi Hao | PMT | NA | 131242 | WSW41 | LT | PM | 0019 | 0 | 131242-WSW41-LT-PM-0019 | 2024-01-09 | Notice of Office Relocation | For Information | 2024-02-06 | 2024-05-02 | 82 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000265 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "Notice of Office Relocation" |  | 2024-01
000266 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0013 | 0 | 131242-WSW41-CD-IM-0013 | 2024-01-09 | Submission Of BIM Coordination VCM Model (Dec – 2023) | For Information | 2024-02-06 | 2024-01-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000266 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Dec – 2023)" |  | 2024-01
000267 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0016 | 0 | 131242-WSW41-MI-C-0016 | 2024-01-09 | CSA Meeting Minutes 0016_20231130 | For Information | 2024-02-06 | 2024-01-25 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000267 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0016_20231130" |  | 2024-01
000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0014 | 0 | 131242-WSW41-MI-IM-0014 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000268 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" |  | 2024-01
000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0015 | 0 | 131242-WSW41-MI-IM-0015 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000268 | 2024-01-09 | 2024-01-09 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" |  | 2024-01
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6050 | A | 131242-WSD11-DR-P-6050 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-03-15 00:00:00 | Related to Detailed Design Report. | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-01
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6063 | A | 131242-WSD11-DR-P-6063 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-01
000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6070 | A | 131242-WSD11-DR-P-6070 | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-01
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | B | 131242-WSD11-DR-P-6050 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-03
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | B | 131242-WSD11-DR-P-6063 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | NO |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-03
000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | B | 131242-WSD11-DR-P-6070 | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | NO |  | 000230&&000269 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP General System [Part 2]" |  | 2024-03
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6019 | A | 131242-WSD11-DR-P-6019 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 | Resubmitted | Related to Detailed Design Report. | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6020 | A | 131242-WSD11-DR-P-6020 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6021 | A | 131242-WSD11-DR-P-6021 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6022 | A | 131242-WSD11-DR-P-6022 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6023 | A | 131242-WSD11-DR-P-6023 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6024 | A | 131242-WSD11-DR-P-6024 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6025 | A | 131242-WSD11-DR-P-6025 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6026 | A | 131242-WSD11-DR-P-6026 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6027 | A | 131242-WSD11-DR-P-6027 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6028 | A | 131242-WSD11-DR-P-6028 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6029 | A | 131242-WSD11-DR-P-6029 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6030 | A | 131242-WSD11-DR-P-6030 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6031 | A | 131242-WSD11-DR-P-6031 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6032 | A | 131242-WSD11-DR-P-6032 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6033 | A | 131242-WSD11-DR-P-6033 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6034 | A | 131242-WSD11-DR-P-6034 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6035 | A | 131242-WSD11-DR-P-6035 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6036 | A | 131242-WSD11-DR-P-6036 | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-01
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | B | 131242-WSD11-DR-P-6019 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | B | 131242-WSD11-DR-P-6020 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | B | 131242-WSD11-DR-P-6021 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | B | 131242-WSD11-DR-P-6022 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | B | 131242-WSD11-DR-P-6023 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | B | 131242-WSD11-DR-P-6024 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | B | 131242-WSD11-DR-P-6025 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | B | 131242-WSD11-DR-P-6026 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | B | 131242-WSD11-DR-P-6027 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | B | 131242-WSD11-DR-P-6028 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | B | 131242-WSD11-DR-P-6029 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | B | 131242-WSD11-DR-P-6030 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | B | 131242-WSD11-DR-P-6031 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | B | 131242-WSD11-DR-P-6032 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | B | 131242-WSD11-DR-P-6033 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | B | 131242-WSD11-DR-P-6034 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | B | 131242-WSD11-DR-P-6035 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | B | 131242-WSD11-DR-P-6036 | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | 27 | Approved with Comments | YES | 2024-05-15 | NO | Resubmitted | 0 |  |  | 000230&&000270 | 2024-01-10 | 2025-06-17 | D | AWC | Approved with Comments | 4 | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " |  | 2024-03
000271 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0013 | 0 | 131242-WSW41-VI-C-0013 | 2024-01-11 | Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd) | Approved | 2024-02-08 | 2024-01-22 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000271 | 2024-01-11 | 2024-01-11 | 0 | APP | Approved | 1 | "Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd)" |  | 2024-01
000272 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | E | 8001 | 0 | 131242-WSD11-DR-E-8001 | 2024-01-11 | THP ATEX Zone Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached files for comments. | 2024-02-08 | 2024-05-15 | 89 | Not Approved | YES | 2024-06-04 | NO | Resubmitted | 0 | 2024-07-26 00:00:00 |  | 000272 | 2024-01-11 | 2024-01-11 | 0 | NAP | Not Approved | 1 | "THP ATEX Zone Drawing" |  | 2024-01
000273 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | LT | IM | 0001 | 0 | 131242-WSW41-LT-IM-0001 | 2024-01-12 | Common Data Environment (CDE) Set-Up and Rollout | For Information. This document should be part of BEP under CDE workflow | 2024-02-09 | 2024-02-27 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000273 | 2024-01-12 | 2024-01-12 | 0 | INF | For Information | 1 | "Common Data Environment (CDE) Set-Up and Rollout" |  | 2024-01
000274 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 0 | 131242-WST02-CL-S-0003_ST612 | 2024-01-13 | ST612_Typical Railing Design Calculation | Rev 0: Not Approved. Please refer to comment sheet for resubmission. Drawing attached should be for information not "shop drawing". | 2024-02-09 | 2024-02-01 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | NAP | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" |  | 2024-01
000274 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 1 | 131242-WST02-CL-S-0003_ST612 | 2024-02-16 | ST612_Typical Railing Design Calculation | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-03-05 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | NAP | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" |  | 2024-02
000274 | 02 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 2 | 131242-WST02-CL-S-0003_ST612 | 2024-03-20 | ST612_Typical Railing Design Calculation | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-11 | 2024-05-13 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | NAP | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" |  | 2024-03
000274 | 03 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 3 | 131242-WST02-CL-S-0003_ST612 | 2024-06-06 | ST612_Typical Railing Design Calculation | Rev.3:Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-07-05 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-18 00:00:00 |  | 000274 | 2024-01-13 | 2024-06-06 | 3 | AWC | Approved with Comments | 4 | "ST612_Typical Railing Design Calculation" |  | 2024-06
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612 | A | 131242-WST02-DR-S-8600_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2024-07-31 | A | AWC | Approved with Comments | 1 | "ST612_Typical Railing Design Calculation" |  | 2024-07
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | E | 131242-WST02-DR-S-5600_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " |  | 2024-07
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612 | E | 131242-WST02-DR-S-5601_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | J | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " |  | 2024-07
000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612 | C | 131242-WST02-DR-S-5602_ST612 | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " |  | 2024-07
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | I | 131242-WST02-DR-S-5600_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 18 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " |  | 2025-08
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612 | J | 131242-WST02-DR-S-5601_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 18 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | J | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " |  | 2025-08
000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612 | I | 131242-WST02-DR-S-5602_ST612 | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | 18 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 000274 | 2024-07-31 | 2025-08-13 | I | AWC | Approved with Comments | 2 | "ST612_Typical Railing Design Calculation" && "ST612_Typical Railing " |  | 2025-08
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A | 131242-WST02-DR-S-1000_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | A | 131242-WST02-DR-S-1006_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | A | 131242-WST02-DR-S-1007_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | A | 131242-WST02-DR-S-1008_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | A | 131242-WST02-DR-S-1013_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | A | 131242-WST02-DR-S-1014_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | B | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | A | 131242-WST02-DR-S-1015_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | A | 131242-WST02-DR-S-1016_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | A | 131242-WST02-DR-S-1017_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | A | 131242-WST02-DR-S-1018_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | A | 131242-WST02-DR-S-1019_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | A | 131242-WST02-DR-S-1020_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | A | 131242-WST02-DR-S-1021_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | A | 131242-WST02-DR-S-1022_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | A | 131242-WST02-DR-S-3005_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | A | 131242-WST02-DR-S-3008_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | A | 131242-WST02-DR-S-3009_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | A | 131242-WST02-DR-S-5005_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | A | 131242-WST02-DR-S-5006_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | A | 131242-WST02-DR-S-7002_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | A | 131242-WST02-DR-S-7003_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | A | 131242-WST02-DR-S-7004_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | A | 131242-WST02-DR-S-7005_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | A | 131242-WST02-DR-S-8003_ST613 | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-01
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A.1 | 131242-WST02-DR-S-1000_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-04-25 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 | 2024-07-19 00:00:00 | Heng Peng: BIM to clear Aaron comments | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | A.1 | 131242-WST02-DR-S-1006_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | A.1 | 131242-WST02-DR-S-1007_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | A.1 | 131242-WST02-DR-S-1008_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | A.1 | 131242-WST02-DR-S-1013_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | A.1 | 131242-WST02-DR-S-1014_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | B | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | A.1 | 131242-WST02-DR-S-1015_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | A.1 | 131242-WST02-DR-S-1016_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | A.1 | 131242-WST02-DR-S-1017_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | A.1 | 131242-WST02-DR-S-1018_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | A.1 | 131242-WST02-DR-S-1019_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | A.1 | 131242-WST02-DR-S-1020_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | A.1 | 131242-WST02-DR-S-1021_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | A.1 | 131242-WST02-DR-S-1022_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | A.1 | 131242-WST02-DR-S-3005_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | A.1 | 131242-WST02-DR-S-3008_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | A.1 | 131242-WST02-DR-S-3009_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | A.1 | 131242-WST02-DR-S-5005_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | A.1 | 131242-WST02-DR-S-5006_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | A.1 | 131242-WST02-DR-S-7002_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | A.1 | 131242-WST02-DR-S-7003_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | A.1 | 131242-WST02-DR-S-7004_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | A.1 | 131242-WST02-DR-S-7005_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | A.1 | 131242-WST02-DR-S-8003_ST613 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | 30 | Not Approved | YES | 2024-06-05 | NO | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | NAP | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-04
000276 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0008 | 0 | 131242-WSW41-RT-PM-0008 | 2024-01-16 | C4B Monthly Progress Report Number No.08 (12/23) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-02-14 | 2024-01-31 | 11 | Approved with Comments | YES | 2024-02-20 | NO | Resubmitted | 0 |  |  | 000276 | 2024-01-16 | 2024-01-16 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.08 (12/23)" |  | 2024-01
000277 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 0 | 131242-WSW41-LC-Z-0001 | 2024-01-16 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. Please append COS. | 2024-02-14 | 2024-01-22 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000277 | 2024-01-16 | 2024-02-02 | 1 | INF | For Information | 2 | "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" |  | 2024-01
000277 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 1 | 131242-WSW41-LC-Z-0001 | 2024-02-02 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. | 2024-02-23 | 2024-02-19 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000277 | 2024-01-16 | 2024-02-02 | 1 | INF | For Information | 2 | "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" |  | 2024-02
000278 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0001 | 0 | 131242-WSD11-RT-P-0001 | 2024-01-17 | THP - Basis of Design Report | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-15 | 2024-03-01 | 32 | Approved with Comments | YES | 2024-03-21 | NO | Resubmitted | 0 | 2024-07-19 00:00:00 |  | 000278 | 2024-01-17 | 2024-01-17 | 0 | AWC | Approved with Comments | 1 | "THP - Basis of Design Report" |  | 2024-01
000279 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0016 | 0 | 131242-WSW41-MI-P-0016 | 2024-01-18 | Process & MEICA Meeting Minutes 0016_20240104 | Rev 0: For Information | 2024-02-16 | 2024-05-21 | 88 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000279 | 2024-01-18 | 2024-01-18 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0016_20240104" |  | 2024-01
000280 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0020 | 0 | 131242-WSW41-LT-PM-0020 | 2024-01-20 | CV of Team Member (ECO cum ECMO) | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-19 | 2024-02-01 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000280 | 2024-01-20 | 2024-04-12 | 1 | NAP | Approved | 2 | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" |  | 2024-01
000280 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0020 | 1 | 131242-WSW41-LT-PM-0020 | 2024-04-12 | CV of Team Member (ECO) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000280 | 2024-01-20 | 2024-04-12 | 1 | APP | Approved | 2 | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" |  | 2024-04
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 1100 | A | 131242-WSW41-DR-E-1100 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 | To withdraw | Combined with Prolog 000252 - Sitewide Piperack Lightning Protection System | 000281 | 2024-01-23 | 2024-01-23 | A | AWC | Approved with Comments | 1 | "Sitewide Piperack Earthing System" |  | 2024-01
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 2000 | A | 131242-WSW41-DR-E-2000 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 81 | Approved with Comments | YES | 2024-06-04 | NO | Resubmitted | 0 |  |  | 000281 | 2024-01-23 | 2024-01-23 | A | AWC | Approved with Comments | 1 | "Sitewide Piperack Earthing System" |  | 2024-01
000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 5000 | A | 131242-WSW41-DR-E-5000 | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | 81 | Approved with Comments | YES | 2024-06-04 | NO | Resubmitted | 0 |  |  | 000281 | 2024-01-23 | 2024-01-23 | A | AWC | Approved with Comments | 1 | "Sitewide Piperack Earthing System" |  | 2024-01
000282 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0021 | 0 | 131242-WSW41-LT-PM-0021 | 2024-01-23 | Assign of Builder License (CES_SDC Pte. Ltd.) | For Information | 2024-02-21 | 2024-05-10 | 78 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000282 | 2024-01-23 | 2024-01-23 | 0 | INF | For Information | 1 | "Assign of Builder License (CES_SDC Pte. Ltd.)" |  | 2024-01
000283 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0007 | 0 | 131242-WSW41-MI-PM-0007 | 2024-01-23 | Monthly Progress Meeting Minutes 0007_20231219 | For Information | 2024-02-21 | 2024-01-24 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000283 | 2024-01-23 | 2024-01-23 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0007_20231219" |  | 2024-01
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-S-1000_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000284 | 2024-01-23 | 2024-02-16 | B | NAP | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " |  | 2024-01
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8000_ST604 | A1 | 131242-WST02-DR-C-8000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-15 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000284 | 2024-02-16 | 2024-02-16 | A1 | NAP | Not Approved | 2 | "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | B | 131242-WST02-DR-C-1001_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2024-01
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604 | A1 | 131242-WST02-DR-C-1002_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000284 | 2024-01-23 | 2024-02-16 | A2 | NAP | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " |  | 2024-01
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | B | 131242-WST02-DR-C-7000_ST604 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2024-01
000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | B | 131242-WST02-DR-C-5001_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-15 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | NAP | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-S-1000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 0 |  | Zora to reply. (Refer to submission 340 Amendment of ST604) | 000284 | 2024-01-23 | 2024-02-16 | B | AWC | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8000_ST604 | A1 | 131242-WST02-DR-C-8000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 0 |  |  | 000284 | 2024-02-16 | 2024-02-16 | A1 | AWC | Not Approved | 2 | "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | B1 | 131242-WST02-DR-C-1001_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 67 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B1 | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604 | A2 | 131242-WST02-DR-C-1002_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 0 |  |  | 000284 | 2024-01-23 | 2024-02-16 | A2 | AWC | Approved with Comments | 2 | "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | B | 131242-WST02-DR-C-7000_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 67 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Approved with Comments | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | B | 131242-WST02-DR-C-5001_ST604 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | 9 | Approved with Comments | YES | 2024-03-20 | NO | Resubmitted | 67 |  |  | 000079&&000284 | 2023-08-24 | 2024-02-16 | B | AWC | Not Approved | 5 | "ST604 – Overall SSN area Piling Design" && "IFC of ST604 : Piling design of Minor Structures " |  | 2024-02
000285 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0007 | 0 | 131242-WSW41-PS-PM-0007 | 2024-01-24 | Monthly Progress Presentation No. 07 (1123) | For Information | 2024-02-22 | 2024-01-29 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000285 | 2024-01-24 | 2024-01-24 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 07 (1123)" |  | 2024-01
000286 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0008 | 0 | 131242-WSW41-PS-PM-0008 | 2024-01-24 | Monthly Progress Presentation No. 08 (1223) | For Information | 2024-02-22 | 2024-01-25 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000286 | 2024-01-24 | 2024-01-24 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 08 (1223)" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5000_ST604 | A | 131242-WST02-SD-C-5000_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5001_ST604 | A | 131242-WST02-SD-C-5001_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5002_ST604 | A | 131242-WST02-SD-C-5002_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5003_ST604 | A | 131242-WST02-SD-C-5003_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5004_ST604 | A | 131242-WST02-SD-C-5004_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 8000_ST604 | A | 131242-WST02-SD-C-8000_ST604 | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | A | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 00 | Zora | CSA | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing | NA | NA | NA | NA | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing -NA-NA-NA-NA | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-01-24 | 2024-01-24 | NA | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-01
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5000_ST604 | B | 131242-WST02-SD-S-5000_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-15 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-04-18 | D | NAP | Approved with Comments | 2 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5001_ST604 | B | 131242-WST02-SD-S-5001_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5002_ST604 | B | 131242-WST02-SD-S-5002_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5003_ST604 | B | 131242-WST02-SD-S-5003_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5004_ST604 | B | 131242-WST02-SD-S-5004_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8000_ST604 | B | 131242-WST02-SD-S-8000_ST604 | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-02-26 | B | NAP | Not Approved | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 02 | Zora | CSA | NA | 131242 | NA | SD | S | Relpy to comment Sheet | NA | 131242-NA-SD-S-Relpy to comment Sheet | 2024-02-28 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1&2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-03-20 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000287 | 2024-02-28 | 2024-02-28 | NA | AWC | Approved with Comments | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-02
000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5000_ST604 | D | 131242-WST02-SD-S-5000_ST604 | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-21 | 23 | Approved with Comments | YES | 2024-06-10 | NO | Resubmitted | 0 |  |  | 000287 | 2024-02-26 | 2024-04-18 | D | AWC | Approved with Comments | 2 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-04
000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5012_ST604 | D | 131242-WST02-SD-S-5012_ST604 | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-21 | 23 | Approved with Comments | YES | 2024-06-10 | NO | Resubmitted | 0 |  |  | 000287 | 2024-04-18 | 2024-04-18 | D | AWC | Approved with Comments | 1 | "Shop Drawings of ST604 : Piling Design of Minor Structures" |  | 2024-04
000288 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0007 | 0 | 131242-WSW41-PC-W-0007 | 2024-01-24 | PAYMENT CLAIM NO.7 | Approved. Please refer to S.O. correspondence no. 116 dated 25 Jan 2024. | 2024-02-22 | 2024-02-15 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000288 | 2024-01-24 | 2024-01-24 | 0 | APP | Approved | 1 | "PAYMENT CLAIM NO.7" |  | 2024-01
000289 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 0 | 131242-WSW41-CN-I-0001 | 2024-01-26 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-02-26 | 2024-04-17 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000289 | 2024-01-26 | 2024-04-19 | 1 | NAP | Rejected | 2 | "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" |  | 2024-01
000289 | 01 | Low | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 1 | 131242-WSW41-CN-I-0001 | 2024-04-19 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 1: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-05-21 | 22 | Rejected | YES | 2024-06-10 | NO | Resubmitted | 0 |  | (RFC) NO.: 1230207-RFC-0004 R1 | 000289 | 2024-01-26 | 2024-04-19 | 1 | REJ | Rejected | 2 | "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" |  | 2024-04
000290 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | I | 0002 | 0 | 131242-WSD11-DS-I-0002 | 2024-02-01 | Control Valves Data Sheet (THP) | Rev 0: Not approved - Revise and Resubmit | 2024-03-01 | 2024-04-29 | 62 | Not Approved | YES | 2024-05-17 | NO | Resubmitted | 0 | 2024-08-02 00:00:00 |  | 000290 | 2024-02-01 | 2024-02-01 | 0 | NAP | Not Approved | 1 | "Control Valves Data Sheet (THP)" |  | 2024-02
000291 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0015 | 0 | 131242-WSD11-CD-IM-0015 | 2024-02-01 | Milestone 1.1 THP EICA Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP EICA Silo Area inside Biosolid Building" |  | 2024-02
000291 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-IM-0033 | 2024-06-04 | Milestone 1.2 THP EICA Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2024-06
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0_wd | 131242-WSD11-CD-IM-0033 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | REJ | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2024-12
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A_wd | 131242-WSD11-DR-E-1030 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | REJ | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2024-12
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A_wd | 131242-WSD11-DR-E-3010 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | REJ | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-12
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A_wd | 131242-WSD11-DR-E-3011 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | REJ | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-12
000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A_wd | 131242-WSD11-DR-E-3012 | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | REJ | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2024-12
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-IM-0033 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2025-01
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A | 131242-WSD11-DR-E-1030 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2025-01
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-01
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-01
000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A | 131242-WSD11-DR-E-3012 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2025-01
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 1 | 131242-WSD11-CD-IM-0033 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291 | 2024-06-04 | 2025-10-28 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2025-10
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A | 131242-WSD11-DR-E-1030 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2025-10
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-10
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-10
000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A | 131242-WSD11-DR-E-3012 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | 85 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 000291 | 2024-12-10 | 2025-10-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" |  | 2025-10
000292 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0017 | 0 | 131242-WSD11-CD-IM-0017 | 2024-02-01 | Milestone 1.1 THP Overall & Equipment Layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP Overall & Equipment Layout" |  | 2024-02
000292 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031 | 2024-06-11 | Milestone 1.2 THP Overall & Equipment Layout | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2024-06-11 | 2025-11-28 | 0 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2024-06
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2024-06-11 | 2025-11-28 | 0 | AWC | Approved with Comments | 3 | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | AWC | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1040 | A | 131242-WSD11-DR-E-1040 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1041 | A | 131242-WSD11-DR-E-1041 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1042 | A | 131242-WSD11-DR-E-1042 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1043 | A | 131242-WSD11-DR-E-1043 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3008 | A | 131242-WSD11-DR-E-3008 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3009 | A | 131242-WSD11-DR-E-3009 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | AWC | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 1043 | A | 131242-WSD11-DR-I-1043 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | AWC | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | AWC | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | AWC | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3018 | A | 131242-WSD11-DR-I-3018 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3019 | A | 131242-WSD11-DR-I-3019 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3020 | A | 131242-WSD11-DR-I-3020 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3021 | A | 131242-WSD11-DR-I-3021 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3022 | A | 131242-WSD11-DR-I-3022 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3023 | A | 131242-WSD11-DR-I-3023 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3024 | A | 131242-WSD11-DR-I-3024 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3025 | A | 131242-WSD11-DR-I-3025 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3026 | A | 131242-WSD11-DR-I-3026 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3027 | A | 131242-WSD11-DR-I-3027 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3028 | A | 131242-WSD11-DR-I-3028 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3029 | A | 131242-WSD11-DR-I-3029 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3030 | A | 131242-WSD11-DR-I-3030 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3031 | A | 131242-WSD11-DR-I-3031 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3032 | A | 131242-WSD11-DR-I-3032 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3033 | A | 131242-WSD11-DR-I-3033 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3034 | A | 131242-WSD11-DR-I-3034 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3035 | A | 131242-WSD11-DR-I-3035 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1120 | A | 131242-WSD11-DR-M-1120 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1121 | A | 131242-WSD11-DR-M-1121 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1122 | A | 131242-WSD11-DR-M-1122 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1123 | A | 131242-WSD11-DR-M-1123 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1200 | A.1 | 131242-WSD11-DR-M-1200 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1201 | A.1 | 131242-WSD11-DR-M-1201 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1202 | A.1 | 131242-WSD11-DR-M-1202 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1203 | A.1 | 131242-WSD11-DR-M-1203 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1204 | A.1 | 131242-WSD11-DR-M-1204 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1205 | A.1 | 131242-WSD11-DR-M-1205 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 3000 | A | 131242-WSD11-DR-M-3000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-05
000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 8000 | A.1 | 131242-WSD11-DR-M-8000 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-05
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2024-06-11 | 2025-11-28 | 0 | PEN | Approved with Comments | 3 | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 228 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 228 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 228 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | PEN | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1040 | A | 131242-WSD11-DR-E-1040 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1041 | A | 131242-WSD11-DR-E-1041 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1042 | A | 131242-WSD11-DR-E-1042 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1043 | A | 131242-WSD11-DR-E-1043 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3008 | A | 131242-WSD11-DR-E-3008 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3009 | A | 131242-WSD11-DR-E-3009 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | PEN | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000291&&000292 | 2024-12-10 | 2025-11-28 | A | PEN | Approved with Comments | 5 | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 1043 | A | 131242-WSD11-DR-I-1043 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2023-12-12 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | PEN | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | PEN | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 186 |  |  | 000236&&000292 | 2024-08-13 | 2025-11-28 | B | PEN | Approved with Comments | 4 | "THP Earthing Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-07 | NO | Overdue | 0 |  |  | 000217&&000218&&000292 | 2023-11-30 | 2025-12-14 | C | PEN | Not Approved | 8 | "THP Power Layout Plan" && "THP Lighting Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 184 |  |  | 000217&&000292 | 2023-12-05 | 2025-11-28 | B | PEN | Approved with Comments | 5 | "THP Power Layout Plan" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3018 | A | 131242-WSD11-DR-I-3018 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3019 | A | 131242-WSD11-DR-I-3019 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3020 | A | 131242-WSD11-DR-I-3020 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3021 | A | 131242-WSD11-DR-I-3021 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3022 | A | 131242-WSD11-DR-I-3022 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3023 | A | 131242-WSD11-DR-I-3023 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3024 | A | 131242-WSD11-DR-I-3024 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3025 | A | 131242-WSD11-DR-I-3025 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3026 | A | 131242-WSD11-DR-I-3026 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3027 | A | 131242-WSD11-DR-I-3027 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3028 | A | 131242-WSD11-DR-I-3028 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3029 | A | 131242-WSD11-DR-I-3029 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3030 | A | 131242-WSD11-DR-I-3030 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3031 | A | 131242-WSD11-DR-I-3031 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3032 | A | 131242-WSD11-DR-I-3032 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3033 | A | 131242-WSD11-DR-I-3033 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3034 | A | 131242-WSD11-DR-I-3034 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3035 | A | 131242-WSD11-DR-I-3035 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1120 | A | 131242-WSD11-DR-M-1120 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1121 | A | 131242-WSD11-DR-M-1121 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1122 | A | 131242-WSD11-DR-M-1122 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1123 | A | 131242-WSD11-DR-M-1123 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1200 | A.1 | 131242-WSD11-DR-M-1200 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1201 | A.1 | 131242-WSD11-DR-M-1201 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1202 | A.1 | 131242-WSD11-DR-M-1202 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1203 | A.1 | 131242-WSD11-DR-M-1203 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1204 | A.1 | 131242-WSD11-DR-M-1204 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1205 | A.1 | 131242-WSD11-DR-M-1205 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A.1 | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 3000 | A | 131242-WSD11-DR-M-3000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 0 |  |  | 000292 | 2025-05-09 | 2025-11-28 | A | PEN | Approved with Comments | 2 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" |  | 2025-11
000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 8000 | A.1 | 131242-WSD11-DR-M-8000 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | 86 | Awaiting S.O.'s response | YES | 2026-01-15 | NO | Overdue | 387 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | PEN | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2025-11
000293 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0018 | 0 | 131242-WSD11-CD-IM-0018 | 2024-02-01 | Milestone 1.1 THP A100 Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP A100 Silo Area inside Biosolid Building" |  | 2024-02
000293 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-IM-0030 | 2024-06-11 | Milestone 1.2 THP A100 Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" |  | 2024-06
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-IM-0030 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 2: Not approved - Revise and Resubmit. No Electrical / ICA Cutsheets attached with submittal. | 2024-11-28 | 2024-12-05 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | NAP | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" |  | 2024-11
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1130 | A | 131242-WSD11-DR-M-1130 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-11-09 | 2024-11-09 | A | NAP | Not Approved | 1 | "Milestone 2 THP A100 Silo Area inside Biosolid Building" |  | 2024-11
000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1131 | A | 131242-WSD11-DR-M-1131 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-11-09 | 2024-11-09 | A | NAP | Not Approved | 1 | "Milestone 2 THP A100 Silo Area inside Biosolid Building" |  | 2024-11
000293 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-IM-0030 | 2025-04-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" |  | 2025-04
000293 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-IM-0030 | 2025-10-31 | Milestone 3 THP A100 Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-20 | 80 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 000293 | 2024-06-11 | 2025-10-31 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" |  | 2025-10
000294 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0019 | 0 | 131242-WSD11-CD-IM-0019 | 2024-02-01 | Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-02-01 | 2024-02-01 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-02
000294 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-IM-0032 | 2024-06-11 | Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-06
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-IM-0032 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | REJ | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_WD | A | 131242-WSD11-DR-B-1003_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_WD | A | 131242-WSD11-DR-BH-1000_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_WD | A | 131242-WSD11-DR-BH-1001_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_WD | A | 131242-WSD11-DR-BH-1002_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_WD | A | 131242-WSD11-DR-BH-3000_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175 | A_WD | 131242-WSD11-DR-M-1175 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176 | A_WD | 131242-WSD11-DR-M-1176 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177 | A_WD | 131242-WSD11-DR-M-1177 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178 | A_WD | 131242-WSD11-DR-M-1178 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179 | A_WD | 131242-WSD11-DR-M-1179 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180 | A_WD | 131242-WSD11-DR-M-1180 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | 33 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-12-03 | 2024-12-03 | A_WD | REJ | Rejected | 1 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2024-12
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-IM-0032 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_MS2 | A | 131242-WSD11-DR-B-1003_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | A | 131242-WSD11-DR-BH-1000_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | A | 131242-WSD11-DR-BH-1001_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | A | 131242-WSD11-DR-BH-1002_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | A | 131242-WSD11-DR-BH-3000_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175_MS2 | A | 131242-WSD11-DR-M-1175_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176_MS2 | A | 131242-WSD11-DR-M-1176_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177_MS2 | A | 131242-WSD11-DR-M-1177_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178_MS2 | A | 131242-WSD11-DR-M-1178_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179_MS2 | A | 131242-WSD11-DR-M-1179_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180_MS2 | A | 131242-WSD11-DR-M-1180_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1140_MS2 | A | 131242-WSD11-DR-M-1140_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1141_MS2 | A | 131242-WSD11-DR-M-1141_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1142_MS2 | A | 131242-WSD11-DR-M-1142_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1143_MS2 | A | 131242-WSD11-DR-M-1143_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1144_MS2 | A | 131242-WSD11-DR-M-1144_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1145_MS2 | A | 131242-WSD11-DR-M-1145_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1146_MS2 | A | 131242-WSD11-DR-M-1146_MS2 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | 116 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-01
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-IM-0032 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2024-06-11 | 2025-10-27 | 1 | AWC | Approved with Comments | 4 | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_MS2 | A | 131242-WSD11-DR-B-1003_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | A | 131242-WSD11-DR-BH-1000_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | A | 131242-WSD11-DR-BH-1001_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | A | 131242-WSD11-DR-BH-1002_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | A | 131242-WSD11-DR-BH-3000_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175_MS2 | A | 131242-WSD11-DR-M-1175_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176_MS2 | A | 131242-WSD11-DR-M-1176_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177_MS2 | A | 131242-WSD11-DR-M-1177_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178_MS2 | A | 131242-WSD11-DR-M-1178_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179_MS2 | A | 131242-WSD11-DR-M-1179_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180_MS2 | A | 131242-WSD11-DR-M-1180_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1140_MS2 | A | 131242-WSD11-DR-M-1140_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1141_MS2 | A | 131242-WSD11-DR-M-1141_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1142_MS2 | A | 131242-WSD11-DR-M-1142_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1143_MS2 | A | 131242-WSD11-DR-M-1143_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1144_MS2 | A | 131242-WSD11-DR-M-1144_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1145_MS2 | A | 131242-WSD11-DR-M-1145_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1146_MS2 | A | 131242-WSD11-DR-M-1146_MS2 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000294 | 2025-01-21 | 2025-10-27 | A | AWC | Approved with Comments | 2 | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" |  | 2025-10
000295 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 0 | 131242-WSW41-VI-M-0017 | 2024-02-01 | Preliminary Design and Vendor Approval of Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-04-16 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-31 00:00:00 | Related to Tank accessories. In Progress. To check the lead time after PO issue to meet the ROS date (1st Wk of Oct 24) | 000295 | 2024-02-01 | 2024-07-31 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" |  | 2024-02
000295 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 1 | 131242-WSW41-VI-M-0017 | 2024-07-31 | Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-21 | 2024-08-29 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000295 | 2024-02-01 | 2024-07-31 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" |  | 2024-07
000296 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 0 | 131242-WSW41-SP-C-0004 | 2024-02-01 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-01 | 2024-02-16 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000296 | 2024-02-01 | 2024-07-15 | 2 | NAP | Approved | 3 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" |  | 2024-02
000296 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 1 | 131242-WSW41-SP-C-0004 | 2024-06-13 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-28 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000296 | 2024-02-01 | 2024-07-15 | 2 | NAP | Approved | 3 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" |  | 2024-06
000296 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 2 | 131242-WSW41-SP-C-0004 | 2024-07-15 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.2: Approved | 2024-08-02 | 2024-08-12 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000296 | 2024-02-01 | 2024-07-15 | 2 | APP | Approved | 3 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" |  | 2024-07
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A | 131242-WSW41-DR-M-5100 | 2024-02-01 | Pipe Support Standard - General Notes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 00:00:00 |  | 000297&&000909 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 3 | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A | 131242-WSW41-DR-M-5101 | 2024-02-01 | Pipe Support Standard - S01 U-Bolt | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5102 | A | 131242-WSW41-DR-M-5102 | 2024-02-01 | Pipe Support Standard - S02 SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5103 | A | 131242-WSW41-DR-M-5103 | 2024-02-01 | Pipe Support Standard - S03 PAD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S03 PAD" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A | 131242-WSW41-DR-M-5104 | 2024-02-01 | Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5105 | A | 131242-WSW41-DR-M-5105 | 2024-02-01 | Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5106 | A | 131242-WSW41-DR-M-5106 | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S06 DUMMY PIPE SHEET 1" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5107 | A | 131242-WSW41-DR-M-5107 | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S06 DUMMY PIPE SHEET 2" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5108 | A | 131242-WSW41-DR-M-5108 | 2024-02-01 | Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5109 | A | 131242-WSW41-DR-M-5109 | 2024-02-01 | Pipe Support Standard - S08 SLIDE STOOL | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5110 | A | 131242-WSW41-DR-M-5110 | 2024-02-01 | Pipe Support Standard - S09 TIGHT STOOL | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A | 131242-WSW41-DR-M-5111 | 2024-02-01 | Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5112 | A | 131242-WSW41-DR-M-5112 | 2024-02-01 | Pipe Support Standard - S11 GUIDE FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5113 | A | 131242-WSW41-DR-M-5113 | 2024-02-01 | Pipe Support Standard - S12 STOPPER FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5114 | A | 131242-WSW41-DR-M-5114 | 2024-02-01 | Pipe Support Standard - S13 BRACKET SUPPORT | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S13 BRACKET SUPPORT" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5115 | A | 131242-WSW41-DR-M-5115 | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5116 | A | 131242-WSW41-DR-M-5116 | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5117 | A | 131242-WSW41-DR-M-5117 | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5118 | A | 131242-WSW41-DR-M-5118 | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5119 | A | 131242-WSW41-DR-M-5119 | 2024-02-01 | Pipe Support Standard - S16 STANCHION | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S16 STANCHION" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5120 | A | 131242-WSW41-DR-M-5120 | 2024-02-01 | Pipe Support Standard - S17 STANCHION (REINFORCED) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S17 STANCHION (REINFORCED)" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5121 | A | 131242-WSW41-DR-M-5121 | 2024-02-01 | Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5122 | A | 131242-WSW41-DR-M-5122 | 2024-02-01 | Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5123 | A | 131242-WSW41-DR-M-5123 | 2024-02-01 | Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5124 | A | 131242-WSW41-DR-M-5124 | 2024-02-01 | Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5125 | A | 131242-WSW41-DR-M-5125 | 2024-02-01 | Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450)" |  | 2024-02
000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5126 | A | 131242-WSW41-DR-M-5126 | 2024-02-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2024-02-01 | A | AWC | Approved with Comments | 1 | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" |  | 2024-02
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-M-5100 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 00:00:00 |  | 000297&&000909 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 3 | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.1 | 131242-WSW41-DR-M-5101 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5102 | A.1 | 131242-WSW41-DR-M-5102 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5103 | A.1 | 131242-WSW41-DR-M-5103 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S03 PAD" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A.1 | 131242-WSW41-DR-M-5104 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5105 | A.1 | 131242-WSW41-DR-M-5105 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5108 | A.1 | 131242-WSW41-DR-M-5108 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5109 | A.1 | 131242-WSW41-DR-M-5109 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5110 | A.1 | 131242-WSW41-DR-M-5110 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A.1 | 131242-WSW41-DR-M-5111 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5112 | A.1 | 131242-WSW41-DR-M-5112 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5113 | A.1 | 131242-WSW41-DR-M-5113 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5121 | A.1 | 131242-WSW41-DR-M-5121 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5123 | A.1 | 131242-WSW41-DR-M-5123 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5124 | A.1 | 131242-WSW41-DR-M-5124 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5140 | A | 131242-WSW41-DR-M-5140 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2025-03-13 | 2025-06-25 | A.1 | AWC | Approved with Comments | 2 | "Standard Pipe Support - For All Area " |  | 2025-03
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.2 | 131242-WSW41-DR-M-5101 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S01 U-Bolt" && "Standard Pipe Support - For All Area " |  | 2025-06
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A.2 | 131242-WSW41-DR-M-5104 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " |  | 2025-06
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A.2 | 131242-WSW41-DR-M-5111 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2024-02-01 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " |  | 2025-06
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5139 | A | 131242-WSW41-DR-M-5139 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2025-06-25 | 2025-06-25 | A | AWC | Approved with Comments | 1 | "Standard Pipe Support - For All Area " |  | 2025-06
000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5140 | A.1 | 131242-WSW41-DR-M-5140 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297 | 2025-03-13 | 2025-06-25 | A.1 | AWC | Approved with Comments | 2 | "Standard Pipe Support - For All Area " |  | 2025-06
000298 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0017 | 0 | 131242-WSW41-MI-P-0017 | 2024-02-02 | Process & MEICA Meeting Minutes 0017_20240118 | Rev 0: For Information | 2024-03-04 | 2024-05-21 | 77 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000298 | 2024-02-02 | 2024-02-02 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0017_20240118" |  | 2024-02
000299 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 0 | 131242-WST02-VI-E-0002 | 2024-02-03 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-03-04 | 2024-03-01 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | AWC | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" |  | 2024-02
000299 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 1 | 131242-WST02-VI-E-0002 | 2024-03-25 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-04-16 | 2024-05-23 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | AWC | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" |  | 2024-03
000299 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 2 | 131242-WST02-VI-E-0002 | 2024-06-07 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-06-28 | 2024-08-15 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | AWC | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" |  | 2024-06
000299 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 3 | 131242-WST02-VI-E-0002 | 2024-10-16 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 3: Approved. | 2024-11-06 | 2024-11-04 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000299 | 2024-02-03 | 2024-10-16 | 3 | APP | Approved | 4 | "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" |  | 2024-10
000300 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0003 | 0 | 131242-WSW41-PS-HS-0003 | 2024-02-03 | Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024 | Rev 0: Noted for information | 2024-03-04 | 2024-03-18 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000300 | 2024-02-03 | 2024-02-03 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" |  | 2024-02
000301 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0008 | 0 | 131242-WSW41-MI-PM-0008 | 2024-02-05 | Monthly Progress Meeting Minutes 0008_20240123 | For Information | 2024-03-05 | 2024-02-07 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000301 | 2024-02-05 | 2024-02-05 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0008_20240123" |  | 2024-02
000302 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0014 | 0 | 131242-WSD11-CD-IM-0014 | 2024-02-06 | Milestone 1.1 THP Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-06 | 2024-03-28 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-02-06 | 2024-02-06 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.1 THP Compressed Air System" |  | 2024-02
000302 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0029 | 0 | 131242-WSD11-CD-IM-0029 | 2024-06-11 | Milestone 1.2 THP Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-06-11 | 2024-06-11 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.2 THP Compressed Air System" |  | 2024-06
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 0 | 131242-WSD11-CD-IM-0047 | 2024-10-17 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-17 | 2025-10-27 | 2 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1165 | A.1 | 131242-WSD11-DR-M-1165 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | NAP | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1166 | A.1 | 131242-WSD11-DR-M-1166 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | NAP | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1020 | A | 131242-WSD11-DR-E-1020 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1021 | A | 131242-WSD11-DR-E-1021 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3000 | A | 131242-WSD11-DR-E-3000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3001 | A | 131242-WSD11-DR-E-3001 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-18 | 2024-10-18 | A | NAP | Not Approved | 1 | "Milestone 2 THP Compressed Air System" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 1000 | A.1_MS2 | 131242-WSB01-DR-BH-1000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 3000 | A.1_MS2 | 131242-WSB01-DR-BH-3000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2024-10
000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 5000 | A.1_MS2 | 131242-WSB01-DR-BH-5000 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2024-10
000302 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 1 | 131242-WSD11-CD-IM-0047 | 2025-04-10 | Milestone 2 THP Compressed Air System | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-30 | 2025-07-02 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302 | 2024-10-17 | 2025-10-27 | 2 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" |  | 2025-04
000302 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 2 | 131242-WSD11-CD-IM-0047 | 2025-10-27 | Milestone 3 THP Compressed Air System | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | 85 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000302 | 2024-10-17 | 2025-10-27 | 2 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" |  | 2025-10
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1003_ST605_BCA | A1 | 131242-WST02-DR-C-1003_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide DGN drawing | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" |  | 2024-02
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1004_ST605_BCA | A1 | 131242-WST02-DR-C-1004_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" |  | 2024-02
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5002_ST605_BCA | A1 | 131242-WST02-DR-C-5002_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" |  | 2024-02
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7001_ST605_BCA | A1 | 131242-WST02-DR-C-7001_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" |  | 2024-02
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8001_ST605_BCA | A1 | 131242-WST00-DR-C-8001_ST605_BCA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" |  | 2024-02
000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | ST605-NOA | A1 | 131242-WST02-DR-C-ST605-NOA | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | 11 | Approved with Comments | YES | 2024-03-12 | NO | Resubmitted | 0 |  |  | 000303 | 2024-02-06 | 2024-02-06 | A1 | AWC | Approved with Comments | 1 | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" |  | 2024-02
000304 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0020 | 0 | 131242-WSW41-CD-IM-0020 | 2024-02-06 | Submission Of BIM Coordination VCM Model (Jan–2024) | For Information | 2024-03-06 | 2024-02-22 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000304 | 2024-02-06 | 2024-02-06 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Jan–2024)" |  | 2024-02
000305 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0009 | 0 | 131242-WSW41-RT-PM-0009 | 2024-02-08 | C4B Monthly Progress Report Number No.09 (01 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-03-08 | 2024-03-08 | 21 | Approved with Comments | YES | 2024-03-28 | NO | Resubmitted | 0 |  |  | 000305 | 2024-02-08 | 2024-02-08 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.09 (01 24)" |  | 2024-02
000306 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0008 | 0 | 131242-WSW41-PC-W-0008 | 2024-02-08 | Payment Claim No. 8 | Rev(0): Approved. Refer to S.O. correspondence no. 121 dated 9 Feb 2024. | 2024-03-08 | 2024-05-10 | 66 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000306 | 2024-02-08 | 2024-02-08 | 0 | APP | Approved | 1 | "Payment Claim No. 8" |  | 2024-02
000307 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | A | 131242-WST02-DR-EP-5000 | 2024-02-13 | Typical Installation Details for Power | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | 64 | Rejected | NO |  | YES | Resubmitted | 0 | 2025-02-27 00:00:00 |  | 000307 | 2024-02-13 | 2025-03-25 | B | REJ | Not Approved | 2 | "Typical Installation Details for Power" |  | 2024-02
000307 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | B | 131242-WST02-DR-EP-5000 | 2025-03-25 | Typical Installation Details for Power | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Not Approved | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000307 | 2024-02-13 | 2025-03-25 | B | NAP | Not Approved | 2 | "Typical Installation Details for Power" |  | 2025-03
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7002 | A | 131242-WST02-DR-E-7002 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 61 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2024-02-13 | A | NAP | Not Approved | 1 | "SSN Single Line Diagram for MOV DB" |  | 2024-02
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | A | 131242-WST02-DR-E-7003 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 61 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | NAP | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" |  | 2024-02
000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | A | 131242-WST02-DR-E-7004 | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | 61 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | NAP | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" |  | 2024-02
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | B | 131242-WST02-DR-E-7003 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 00:00:00 |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" |  | 2024-07
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | B | 131242-WST02-DR-E-7004 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" |  | 2024-07
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7005 | B | 131242-WST02-DR-E-7005 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2024-07
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7006 | B | 131242-WST02-DR-E-7006 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2024-07
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7007 | B | 131242-WST02-DR-E-7007 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2024-07
000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7008 | B | 131242-WST02-DR-E-7008 | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | 81 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2024-07
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | C | 131242-WST02-DR-E-7003 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" |  | 2025-03
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | C | 131242-WST02-DR-E-7004 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-02-13 | 2025-03-27 | C | AWC | Approved with Comments | 3 | "SSN Single Line Diagram for MOV DB" |  | 2025-03
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7005 | C | 131242-WST02-DR-E-7005 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2025-03
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7006 | C | 131242-WST02-DR-E-7006 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2025-03
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7007 | C | 131242-WST02-DR-E-7007 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2025-03
000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7008 | C | 131242-WST02-DR-E-7008 | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | 30 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  |  | 000308 | 2024-07-06 | 2025-03-27 | C | AWC | Approved with Comments | 2 | "SSN Single Line Diagram for MOV DB" |  | 2025-03
000309 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | A | 131242-WST02-BQ-E-0003 | 2024-02-13 | SSN Listing of Interface Points | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 66 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000309 | 2024-02-13 | 2024-07-22 | B | AWC | Approved with Comments | 2 | "SSN Listing of Interface Points" |  | 2024-02
000309 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | B | 131242-WST02-BQ-E-0003 | 2024-07-22 | SSN Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-10-29 | 71 | Approved with Comments | NO |  | YES | Resubmitted | 0 | NO NEED TO RESUBMIT | No need to resubmit as there is no major updates made - "Please resubmit if there are major updates or changes to the information stated". | 000309 | 2024-02-13 | 2024-07-22 | B | AWC | Approved with Comments | 2 | "SSN Listing of Interface Points" |  | 2024-07
000310 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | A | 131242-WST02-DR-EL-5000 | 2024-02-13 | Typical Installation Details for Lighting | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | 64 | Not Approved | NO |  | YES | Resubmitted | 0 | 2025-02-27 00:00:00 |  | 000310 | 2024-02-13 | 2025-03-25 | B | NAP | Not Approved | 2 | "Typical Installation Details for Lighting" |  | 2024-02
000310 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | B | 131242-WST02-DR-EL-5000 | 2025-03-25 | Typical Installation Details for Lighting | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Not Approved | YES | 2025-05-26 | NO | Resubmitted | 0 |  | To check with C2D | 000310 | 2024-02-13 | 2025-03-25 | B | NAP | Not Approved | 2 | "Typical Installation Details for Lighting" |  | 2025-03
000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | A | 131242-WSD11-DR-EK-1000 | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 | 2025-02-19 00:00:00 |  | 000311 | 2024-02-13 | 2025-02-25 | B | NAP | Approved with Comments | 2 | "THP Lightning Protection System" |  | 2024-02
000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 3000 | A | 131242-WSD11-DR-EK-3000 | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | 66 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000311 | 2024-02-13 | 2025-02-25 | B | NAP | Approved with Comments | 2 | "THP Lightning Protection System" |  | 2024-02
000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | B | 131242-WSD11-DR-EK-1000 | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000311 | 2024-02-13 | 2025-02-25 | B | AWC | Approved with Comments | 2 | "THP Lightning Protection System" |  | 2025-02
000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 3000 | B | 131242-WSD11-DR-EK-3000 | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | 49 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 000311 | 2024-02-13 | 2025-02-25 | B | AWC | Approved with Comments | 2 | "THP Lightning Protection System" |  | 2025-02
000312 | 00 | Soe Myat | PMT | NA | 131242 | WSW41 | LT | PM | 0022 | 0 | 131242-WSW41-LT-PM-0022 | 2024-02-14 | CV of Team Member (QA/QC Manager) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-03-13 | 2024-02-19 | 3 | Approved with Comments | YES | 2024-03-08 | NO | Resubmitted | 0 |  |  | 000312 | 2024-02-14 | 2024-02-14 | 0 | AWC | Approved with Comments | 1 | "CV of Team Member (QA/QC Manager)" |  | 2024-02
000313 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0018 | 0 | 131242-WSW41-MI-P-0018 | 2024-02-15 | Process & MEICA Meeting Minutes 0018_20240201 | Rev 0: For Information | 2024-03-14 | 2024-05-21 | 68 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000313 | 2024-02-15 | 2024-02-15 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0018_20240201" |  | 2024-02
000314 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0001 | 0 | 131242-WSW41-RT-HS-0001 | 2024-02-15 | 1st CONSAAS Audit report_2023 | Rev 0: Noted for information | 2024-03-14 | 2024-03-18 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000314 | 2024-02-15 | 2024-02-15 | 0 | INF | For Information | 1 | "1st CONSAAS Audit report_2023" |  | 2024-02
000315 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 0 | 131242-WSW41-VI-I-0001 | 2024-02-19 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-03-18 | 2024-04-08 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000315 | 2024-02-19 | 2024-04-15 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" |  | 2024-02
000315 | 01 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 1 | 131242-WSW41-VI-I-0001 | 2024-04-15 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-05-15 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000315 | 2024-02-19 | 2024-04-15 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" |  | 2024-04
000315 | 02 | Balaji/ Karthik | EICA | NA | Comment Reply Sheet 20240716 | NA | NA | NA | NA | A.C | Comment Reply Sheet 20240716-NA-NA-NA-NA | 2024-07-17 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | 44 | Approved with Comments | YES | 2024-10-07 | NO | Resubmitted | 0 |  |  | 000315 | 2024-07-17 | 2024-07-17 | A.C | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" |  | 2024-07
000316 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0001 | 0 | 131242-WSW41-QA-M-0001 | 2024-02-20 | Inspection Test Plan for Structural Steel Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-08-14 | 126 | Not Approved | YES | 2024-09-03 | NO | Resubmitted | 0 |  |  | 000316 | 2024-02-20 | 2024-02-20 | 0 | NAP | Not Approved | 1 | "Inspection Test Plan for Structural Steel Work" |  | 2024-02
000317 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | VI | HS | 0002 | 0 | 131242-WSW41-VI-HS-0002 | 2024-02-20 | Vendor Approval of CONSAAS Audit (ACE EHS) | Rev 0: Noted for information | 2024-03-19 | 2024-03-18 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000317 | 2024-02-20 | 2024-02-20 | 0 | INF | For Information | 1 | "Vendor Approval of CONSAAS Audit (ACE EHS)" |  | 2024-02
000318 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 0 | 131242-WST02-VI-E-0003 | 2024-02-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to the comment sheet | 2024-03-20 | 2024-03-20 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000318 | 2024-02-21 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" |  | 2024-02
000318 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 1 | 131242-WST02-VI-E-0003 | 2024-05-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-11 | 2024-07-04 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000318 | 2024-02-21 | 2024-07-22 | 2 | AWC | Approved | 3 | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" |  | 2024-05
000318 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 2 | 131242-WST02-VI-E-0003 | 2024-07-22 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 2: Approved. | 2024-08-12 | 2024-09-24 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000318 | 2024-02-21 | 2024-07-22 | 2 | APP | Approved | 3 | "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" |  | 2024-07
000319 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0009 | 0 | 131242-WSW41-PS-PM-0009 | 2024-02-21 | Monthly Progress Presentation No. 09 (0124) | For Information | 2024-03-20 | 2024-02-22 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000319 | 2024-02-21 | 2024-02-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 09 (0124)" |  | 2024-02
000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0017 | 0 | 131242-WSW41-MI-C-0017 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000320 | 2024-02-22 | 2024-02-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" |  | 2024-02
000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0018 | 0 | 131242-WSW41-MI-C-0018 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000320 | 2024-02-22 | 2024-02-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0017 & 0018_20231228 20240111" |  | 2024-02
000321 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 0 | 131242-WSD11-BQ-E-0003 | 2024-02-23 | THP Listing of Interface Points | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-03-22 | 2024-05-15 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000321 | 2024-02-23 | 2025-07-21 | 1 | NAP | Approved with Comments | 2 | "THP Listing of Interface Points" |  | 2024-02
000321 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 1 | 131242-WSD11-BQ-E-0003 | 2025-07-21 | THP Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-10-01 | 52 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000321 | 2024-02-23 | 2025-07-21 | 1 | AWC | Approved with Comments | 2 | "THP Listing of Interface Points" |  | 2025-07
000322 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 0 | 131242-WST02-CH-P-0002 | 2024-02-23 | Process Functional Description | Rev 0 : There are no active comments on the submittal. However, if there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 2024-03-22 | 2024-03-13 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-19 00:00:00 | If there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 000322 | 2024-02-23 | 2025-03-04 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2024-02
000322 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 1 | 131242-WST02-CH-P-0002 | 2024-07-23 | Process Functional Description | Rev 1: Approved | 2024-08-13 | 2024-08-29 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000322 | 2024-02-23 | 2025-03-04 | 3 | APP | Approved with Comments | 4 | "Process Functional Description" |  | 2024-07
000322 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 2 | 131242-WST02-CH-P-0002 | 2024-10-15 | Process Functional Description | Rev 2: Approved with comments. Please address the comments and resubmit. | 2024-11-05 | 2024-12-18 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000322 | 2024-02-23 | 2025-03-04 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2024-10
000322 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 3 | 131242-WST02-CH-P-0002 | 2025-03-04 | Process Functional Description | Rev 3: Approved with comments. Resubmittal is required if there are any changes during the detail engineering. | 2025-03-24 | 2025-04-28 | 39 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000322 | 2024-02-23 | 2025-03-04 | 3 | AWC | Approved with Comments | 4 | "Process Functional Description" |  | 2025-03
000323 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0019 | 0 | 131242-WSW41-MI-P-0019 | 2024-02-23 | Process & MEICA Meeting Minutes 0019_20240215 | Rev 0: For Information | 2024-03-22 | 2024-05-21 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000323 | 2024-02-23 | 2024-02-23 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0019_20240215" |  | 2024-02
000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0001 | 0 | 131242-WSD11-LT-P-0001 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | 93 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000324 | 2024-02-24 | 2024-02-24 | 0 | REJ | Rejected | 1 | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" |  | 2024-02
000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0002 | 0 | 131242-WSD11-LT-P-0002 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | 93 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000324 | 2024-02-24 | 2024-02-24 | 0 | REJ | Rejected | 1 | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" |  | 2024-02
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-S-8001_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | REJ | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | B | 131242-WST02-DR-S-1003_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST605 | B | 131242-WST02-DR-S-1004_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST605 | B | 131242-WST02-DR-S-5002_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | B | 131242-WST02-DR-S-7001_ST605 | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | 1 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-S-8001_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-20 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A1 | 131242-WST02-DR-S-1003_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST605 | B | 131242-WST02-DR-S-1004_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST605 | B | 131242-WST02-DR-S-5002_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-02-29 | B | NAP | Not Approved | 2 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | B | 131242-WST02-DR-S-7001_ST605 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-02
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-S-8001_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-17 | 2024-05-14 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-04
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A2 | 131242-WST02-DR-S-1003_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-28 | 2024-05-14 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-04
000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | A2 | 131242-WST02-DR-S-7001_ST605 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-28 | 2024-05-14 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | NAP | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-04
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-S-8001_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-06 | 2024-06-03 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | INF | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-04
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A2 | 131242-WST02-DR-S-1003_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-14 | 2024-06-03 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | INF | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-04
000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | A2 | 131242-WST02-DR-S-7001_ST605 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-14 | 2024-06-03 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000325 | 2024-02-26 | 2024-04-26 | A2 | INF | Not Approved | 4 | "IFC of ST605_SSN Piling Layout of Main Water Tanks " |  | 2024-04
000326 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 0 | 131242-WSD11-PO-E-0001 | 2024-02-26 | Unpriced PO for Transformer (Hitachi) | Rev 0: Rejected. Please refer to attached file to comments. | 2024-03-25 | 2024-03-20 | 17 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000326 | 2024-02-26 | 2024-03-20 | 1 | REJ | For Information | 2 | "Unpriced PO for Transformer (Hitachi)" |  | 2024-02
000326 | 01 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 1 | 131242-WSD11-PO-E-0001 | 2024-03-20 | Unpriced PO for Transformer (Hitachi) | For Information | 2024-04-11 | 2024-04-29 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000326 | 2024-02-26 | 2024-03-20 | 1 | INF | For Information | 2 | "Unpriced PO for Transformer (Hitachi)" |  | 2024-03
000327 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0004 | 0 | 131242-WSD11-PO-M-0004 | 2024-02-26 | Unpriced PO for Blower (Aerzen) | For Information | 2024-03-25 | 2024-05-21 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000327 | 2024-02-26 | 2024-02-26 | 0 | INF | For Information | 1 | "Unpriced PO for Blower (Aerzen)" |  | 2024-02
000328 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0003 | 0 | 131242-WSD11-PO-M-0003 | 2024-02-26 | Unpriced PO for Diffuser (Xylem) | For Information | 2024-03-25 | 2024-05-21 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000328 | 2024-02-26 | 2024-02-26 | 0 | INF | For Information | 1 | "Unpriced PO for Diffuser (Xylem)" |  | 2024-02
000329 | 00 | Low | EICA | NA | 131242 | WST02 | VI | I | 0002 | 0 | 131242-WST02-VI-I-0002 | 2024-02-28 | Vendor Approval of SSN Package (ORP Analyser) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-04-08 | 28 | (VOID / NOT IN USE) | NO |  | YES | Resubmitted | 0 |  | To check with Qili whether ORP required or not. | 000329 | 2024-02-28 | 2024-02-28 | 0 | VOID | (VOID NOT IN USE) | 1 | "Vendor Approval of SSN Package (ORP Analyser)" |  | 2024-02
000330 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | MI | I | 0001 | 0 | 131242-WSD11-MI-I-0001 | 2024-02-28 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 0: Accepted for information. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-05-09 | 51 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000330 | 2024-02-28 | 2024-02-28 | 0 | AWC | Approved with Comments | 1 | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" |  | 2024-02
000330 | 01 | Freedomer | EICA | NA | 131242 | NA | MI | E | Comment Reply Sheet 20240716 S330.0 | NA | 131242-NA-MI-E-Comment Reply Sheet 20240716 S330.0 | 2024-07-17 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 1: Accepted for information. No resubmission required. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | 44 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000330 | 2024-07-17 | 2024-07-17 | NA | INF | For Information | 1 | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" |  | 2024-07
000331 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0003 | 0 | 131242-WSD11-LT-P-0003 | 2024-02-28 | THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-27 | 2024-03-20 | 15 | Not Approved | YES | 2024-04-09 | NO | Resubmitted | 0 | 2024-07-19 00:00:00 |  | 000331 | 2024-02-28 | 2024-02-28 | 0 | NAP | Not Approved | 1 | "THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor" |  | 2024-02
000332 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | A.1 | 131242-WSW41-VI-M-0018 | 2024-02-29 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rejected as requested by Contractor as there still need to attach the document | 2024-03-28 | 2024-03-01 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000332&&000559 | 2024-02-29 | 2024-07-12 | 0 | REJ | Approved | 3 | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" |  | 2024-02
000332 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-M-0018 | 2024-03-04 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-22 | 2024-04-15 | 30 | Approved with Comments | YES | 2024-05-03 | NO | Resubmitted | 0 |  |  | 000332&&000559 | 2024-02-29 | 2024-07-12 | 0 | AWC | Approved | 3 | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" |  | 2024-03
000333 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0019 | 0 | 131242-WSW41-VI-M-0019 | 2024-02-29 | Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-28 | 2024-04-16 | 33 | Approved with Comments | YES | 2024-05-06 | NO | Resubmitted | 0 |  |  | 000333 | 2024-02-29 | 2024-02-29 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." |  | 2024-02
000334 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 0 | 131242-WST02-VI-E-0004 | 2024-02-29 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-28 | 2024-03-20 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" |  | 2024-02
000334 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 1 | 131242-WST02-VI-E-0004 | 2024-03-26 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-17 | 2024-04-29 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" |  | 2024-03
000334 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 2 | 131242-WST02-VI-E-0004 | 2024-05-16 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-06 | 2024-07-04 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" |  | 2024-05
000334 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 3 | 131242-WST02-VI-E-0004 | 2024-07-28 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-16 | 2024-08-16 | 14 | Approved with Comments | YES | 2024-09-05 | NO | Resubmitted | 0 |  |  | 000334 | 2024-02-29 | 2024-07-28 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" |  | 2024-07
000335 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0009 | 0 | 131242-WSW41-MI-PM-0009 | 2024-03-01 | Monthly Progress Meeting Minutes 0009_20240220 | For Information | 2024-04-01 | 2024-03-04 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000335 | 2024-03-01 | 2024-03-01 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0009_20240220" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | A | 131242-WST02-SD-S-8001_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | C | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5005_ST605 | A | 131242-WST02-SD-S-5005_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5006_ST605 | A | 131242-WST02-SD-S-5006_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5007_ST605 | A | 131242-WST02-SD-S-5007_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5008_ST605 | A | 131242-WST02-SD-S-5008_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5009_ST605 | A | 131242-WST02-SD-S-5009_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5010_ST605 | A | 131242-WST02-SD-S-5010_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5011_ST605 | A | 131242-WST02-SD-S-5011_ST605 | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | A.1 | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-03
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | C | 131242-WST02-SD-S-8001_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to clear BIM comments. | 000336 | 2024-03-01 | 2024-05-17 | C | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5005_ST605 | D | 131242-WST02-SD-S-5005_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5006_ST605 | B | 131242-WST02-SD-S-5006_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5007_ST605 | D | 131242-WST02-SD-S-5007_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5008_ST605 | D | 131242-WST02-SD-S-5008_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | D | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5009_ST605 | B | 131242-WST02-SD-S-5009_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5010_ST605 | B | 131242-WST02-SD-S-5010_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | B | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5011_ST605 | A.1 | 131242-WST02-SD-S-5011_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-03-01 | 2024-05-17 | A.1 | NAP | Not Approved | 2 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5013_ST605 | B | 131242-WST02-SD-S-5013_ST605 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 11 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000336 | 2024-05-17 | 2024-05-17 | B | NAP | Not Approved | 1 | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" |  | 2024-05
000337 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1003 | 0 | 131242-WSW41-VI-M-1003 | 2024-03-01 | Vendor Approval of cPVC Pipes & Fittings (GF) | Approved | 2024-04-01 | 2024-04-17 | 33 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000337 | 2024-03-01 | 2024-03-01 | 0 | APP | Approved | 1 | "Vendor Approval of cPVC Pipes & Fittings (GF)" |  | 2024-03
000338 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB | 2024-03-01 | PUB DC Drainage Submission | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " |  | 2024-03
000338 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB | 2024-03-28 | PUB DC Drainage Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-13 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " |  | 2024-03
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A | 131242-WST02-DR-A-1000_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A | 131242-WST02-DR-A-1002_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A | 131242-WST02-DR-A-1003_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A | 131242-WST02-DR-A-1004_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A | 131242-WST02-DR-A-1009_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A | 131242-WST02-DR-A-2000_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | A | 131242-WST02-DR-A-2001_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | A | 131242-WST02-DR-A-2002_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | A | 131242-WST02-DR-A-2003_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | A | 131242-WST02-DR-A-2007_PUB | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-05
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_PUB | B | 131242-WST02-DR-A-0001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0002_PUB | B | 131242-WST02-DR-A-0002_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | B | 131242-WST02-DR-A-1000_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | B | 131242-WST02-DR-A-1001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | B | 131242-WST02-DR-A-1002_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | B | 131242-WST02-DR-A-1003_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | B | 131242-WST02-DR-A-1004_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_PUB | B | 131242-WST02-DR-A-1006_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A | NAP | Not Approved | 2 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | B | 131242-WST02-DR-A-1009_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | B | 131242-WST02-DR-A-2000_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | B | 131242-WST02-DR-A-2001_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | B | 131242-WST02-DR-A-2002_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | B | 131242-WST02-DR-A-2003_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | B | 131242-WST02-DR-A-2007_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_PUB | B | 131242-WST02-DR-A-3000_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A.2 | NAP | Not Approved | 2 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 5004_PUB | B | 131242-WST02-DR-A-5004_PUB | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "PUB DC Drainage Submission " |  | 2024-10
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | REJ | Rejected | 9 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.2 | 131242-WST02-DR-A-1002_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.2 | 131242-WST02-DR-A-1003_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.1 | 131242-WST02-DR-A-1004_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.2 | 131242-WST02-DR-A-1009_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.2 | 131242-WST02-DR-A-1002_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.2 | 131242-WST02-DR-A-1003_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.1 | 131242-WST02-DR-A-1004_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.2 | 131242-WST02-DR-A-1009_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-03
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | NAP | Rejected | 9 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.3 | 131242-WST02-DR-A-1002_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.3 | 131242-WST02-DR-A-1003_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.3 | 131242-WST02-DR-A-1004_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.3 | 131242-WST02-DR-A-1009_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | NAP | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-08
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | REJ | Rejected | 9 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.3 | 131242-WST02-DR-A-1002_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.3 | 131242-WST02-DR-A-1003_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.3 | 131242-WST02-DR-A-1004_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.3 | 131242-WST02-DR-A-1009_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | REJ | Rejected | 7 | "PUB DC Drainage Submission " |  | 2025-11
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.2 | 131242-WST02-DR-A-1000_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.2 | PEN | Rejected | 7 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.4 | 131242-WST02-DR-A-1001_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-03-01 | 2026-01-12 | A.4 | PEN | Rejected | 9 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.4 | 131242-WST02-DR-A-1002_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.4 | 131242-WST02-DR-A-1003_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.4 | 131242-WST02-DR-A-1004_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1005_PUB | A | 131242-WST02-DR-A-1005_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2026-01-12 | 2026-01-12 | A | PEN | Awaiting S.O.'s response | 1 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_PUB | A | 131242-WST02-DR-A-1006_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A | PEN | Not Approved | 2 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.4 | 131242-WST02-DR-A-1009_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.4 | 131242-WST02-DR-A-2000_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Rejected | 7 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | A.4 | 131242-WST02-DR-A-2001_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | A.4 | 131242-WST02-DR-A-2002_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | A.4 | 131242-WST02-DR-A-2003_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | A.4 | 131242-WST02-DR-A-2007_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-05-20 | 2026-01-12 | A.4 | PEN | Not Approved | 3 | "PUB DC Drainage Submission " |  | 2026-01
000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_PUB | A.2 | 131242-WST02-DR-A-3000_PUB | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | 55 | Awaiting S.O.'s response | YES | 2026-02-27 | NO | Overdue | 0 |  |  | 000338 | 2024-10-30 | 2026-01-12 | A.2 | PEN | Not Approved | 2 | "PUB DC Drainage Submission " |  | 2026-01
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0016 | 0 | 131242-WSW41-MI-IM-0016 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000339 | 2024-03-05 | 2024-03-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" |  | 2024-03
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0017 | 0 | 131242-WSW41-MI-IM-0017 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000339 | 2024-03-05 | 2024-03-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" |  | 2024-03
000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0018 | 0 | 131242-WSW41-MI-IM-0018 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000339 | 2024-03-05 | 2024-03-05 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | INF | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-03
000340 | 00 | Zora | CSA | NA | 131242 | NA | DR | S | Submission Acknowledgement | A.1 | 131242-NA-DR-S-Submission Acknowledgement | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000340 | 2024-03-05 | 2024-03-05 | A.1 | INF | For Information | 1 | "ST615 – Amendment of ST604 (BCA Submission for Information) " |  | 2024-03
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to clear BIM comments and to provide Native files | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | 13 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000341 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 0 | 131242-WSD11-CD-I-0004 | 2024-03-05 | THP UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" |  | 2024-03
000341 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 1 | 131242-WSD11-CD-I-0004 | 2024-04-19 | THP UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" |  | 2024-04
000341 | 02 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 2 | 131242-WSD11-CD-I-0004 | 2024-10-22 | THP UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2024-12-18 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" |  | 2024-10
000341 | 03 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 3 | 131242-WSD11-CD-I-0004 | 2025-01-21 | THP UPS Loading List | Not Approved - Revise and resubmit | 2025-02-10 | 2025-05-15 | 82 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | NAP | Approved with Comments | 5 | "THP UPS Loading List" |  | 2025-01
000341 | 04 | Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 4 | 131242-WSD11-CD-I-0004 | 2025-05-27 | THP UPS Loading List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-16 | 2025-09-11 | 77 | Approved with Comments | YES | 2025-10-01 | NO | Resubmitted | 0 |  |  | 000341 | 2024-03-05 | 2025-05-27 | 4 | AWC | Approved with Comments | 5 | "THP UPS Loading List" |  | 2025-05
000342 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | CD | I | 0007 | 0 | 131242-WST02-CD-I-0007 | 2024-03-05 | SSN UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" |  | 2024-03
000342 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0007 | 1 | 131242-WST02-CD-I-0007 | 2024-04-19 | SSN UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" |  | 2024-04
000342 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 2 | 131242-WST02-CD-I-0007 | 2024-11-20 | SSN UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-10 | 2024-12-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" |  | 2024-11
000342 | 03 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 3 | 131242-WST02-CD-I-0007 | 2025-01-21 | SSN UPS Loading List | Rev 3: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-10 | 2025-03-04 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" |  | 2025-01
000342 | 04 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 4 | 131242-WST02-CD-I-0007 | 2025-03-06 | SSN UPS Loading List | Not Approved - Revise and resubmit | 2025-03-26 | 2025-05-15 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | NAP | Approved with Comments | 6 | "SSN UPS Loading List" |  | 2025-03
000342 | 05 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 5 | 131242-WST02-CD-I-0007 | 2025-06-16 | SSN UPS Loading List | Rev 5: Approved with comments. No need resubmission. Refer attached file for comments. | 2025-07-04 | 2025-09-11 | 63 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000342 | 2024-03-05 | 2025-06-16 | 5 | AWC | Approved with Comments | 6 | "SSN UPS Loading List" |  | 2025-06
000343 | 00 | Yuen Fatt | PMT | NA | 131242 | WSW41 | LT | PM | 0023 | 0 | 131242-WSW41-LT-PM-0023 | 2024-03-06 | CV of Team Member (LEW) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-04 | 2024-05-20 | 53 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000343 | 2024-03-06 | 2024-03-06 | 0 | AWC | Approved with Comments | 1 | "CV of Team Member (LEW)" |  | 2024-03
000344 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 0 | 131242-WST02-VI-I-0004 | 2024-03-06 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-09 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000344 | 2024-03-06 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductivity Analyser)" |  | 2024-03
000344 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 1 | 131242-WST02-VI-I-0004 | 2024-12-05 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 108 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000344 | 2024-03-06 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductivity Analyser)" |  | 2024-12
000345 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-I-0003 | 2024-03-06 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-15 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" |  | 2024-03
000345 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-I-0003 | 2024-10-04 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rejected as requested | 2024-10-24 | 2024-10-18 | 10 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | REJ | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" |  | 2024-10
000345 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 1 | 131242-WST02-VI-I-0003 | 2024-10-18 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" |  | 2024-10
000345 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 2 | 131242-WST02-VI-I-0003 | 2025-02-27 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 3: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000345 | 2024-03-06 | 2025-02-27 | 2 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" |  | 2025-02
000346 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 0 | 131242-WST02-VI-I-0005 | 2024-03-07 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-05 | 2024-05-16 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000346 | 2024-03-07 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" |  | 2024-03
000346 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 1 | 131242-WST02-VI-I-0005 | 2024-12-05 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 108 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000346 | 2024-03-07 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" |  | 2024-12
000347 | 00 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0008 | 0 | 131242-WSW41-MS-C-0008 | 2024-03-08 | MSRA, SWP for Time Lapse Camera Steel Pole Erection | Approved | 2024-04-08 | 2024-03-20 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000347 | 2024-03-08 | 2024-03-08 | 0 | APP | Approved | 1 | "MSRA, SWP for Time Lapse Camera Steel Pole Erection" |  | 2024-03
000348 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0014 | 0 | 131242-WSW41-CD-IM-0014 | 2024-03-08 | Submission Of BIM Coordination VCM Model (Feb-2024) | For Information | 2024-04-08 | 2024-03-20 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000348 | 2024-03-08 | 2024-03-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Feb-2024)" |  | 2024-03
000349 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | 0 | 131242-WSD11-CL-EL-7000 | 2024-03-08 | THP Lux Calculation and Luminaire Schedule | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-08 | 2024-05-07 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000349 | 2024-03-08 | 2024-07-16 | B | NAP | For Information | 2 | "THP Lux Calculation and Luminaire Schedule" |  | 2024-03
000349 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | B | 131242-WSD11-CL-EL-7000 | 2024-07-16 | THP Lux Calculation and Luminaire Schedule | Rev 1: For Information. | 2024-08-05 | 2024-10-29 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000349 | 2024-03-08 | 2024-07-16 | B | INF | For Information | 2 | "THP Lux Calculation and Luminaire Schedule" |  | 2024-07
000350 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 0 | 131242-WST02-VI-I-0006 | 2024-03-11 | Vendor Approval of SSN Package (pH Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-09 | 2024-05-14 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000350 | 2024-03-11 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (pH Analyzer)" |  | 2024-03
000350 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 1 | 131242-WST02-VI-I-0006 | 2024-12-05 | Vendor Approval of SSN Package (pH Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | 108 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000350 | 2024-03-11 | 2024-12-05 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (pH Analyzer)" |  | 2024-12
000351 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 0 | 131242-WSW41-SP-C-0005 | 2024-03-11 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-04-09 | 2024-03-26 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000351 | 2024-03-11 | 2024-06-20 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" |  | 2024-03
000351 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 1 | 131242-WSW41-SP-C-0005 | 2024-06-20 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Rev.1: Approved | 2024-07-10 | 2024-06-28 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000351 | 2024-03-11 | 2024-06-20 | 1 | APP | Approved | 2 | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" |  | 2024-06
000352 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 0 | 131242-WSW41-VI-M-1009 | 2024-03-12 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rejected. The proposed vendor is dealer/sales representative and not the manufacturer/brand of pipes and fittings. | 2024-04-11 | 2024-04-17 | 26 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000352 | 2024-03-12 | 2024-05-10 | 1 | REJ | Approved | 2 | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" |  | 2024-03
000352 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 1 | 131242-WSW41-VI-M-1009 | 2024-05-10 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rev 0: Approved Please note, that the approval, corresponds to the brand (FROCH and JNDIA) proposed by CES_SDC in this submittal. Approval does not include assessment for TRADER. | 2024-05-31 | 2024-08-06 | 62 | Approved | NO |  | YES | Resubmitted | 0 |  | R0_Rej | 000352 | 2024-03-12 | 2024-05-10 | 1 | APP | Approved | 2 | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" |  | 2024-05
000353 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0020 | 0 | 131242-WSW41-MI-P-0020 | 2024-03-12 | Process & MEICA Meeting Minutes 0020_20240229 | Rev 0: For Information | 2024-04-11 | 2024-05-21 | 50 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000353 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0020_20240229" |  | 2024-03
000354 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0004 | 0 | 131242-WSW41-PS-HS-0004 | 2024-03-12 | Incentive / Disincentive Audit Scheme for November 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000354 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for November 2023" |  | 2024-03
000355 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0005 | 0 | 131242-WSW41-PS-HS-0005 | 2024-03-12 | Incentive / Disincentive Audit Scheme for December 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000355 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for December 2023" |  | 2024-03
000356 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 0 | 131242-WST02-CL-E-0000 | 2024-03-12 | SSN Transformer Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-11 | 2024-05-20 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000356 | 2024-03-12 | 2025-05-30 | 2 | NAP | Approved with Comments | 3 | "SSN Transformer Sizing Calculations" |  | 2024-03
000356 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 1 | 131242-WST02-CL-E-0000 | 2024-12-14 | SSN Transformer Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-03 | 2025-02-13 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-04 00:00:00 |  | 000356 | 2024-03-12 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Sizing Calculations" |  | 2024-12
000356 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 2 | 131242-WST02-CL-E-0000 | 2025-05-30 | SSN Transformer Sizing Calculations | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments | 2025-06-19 | 2025-07-23 | 38 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  | Pending Reply from Sunlight. Pending UPS details from Jacobs | 000356 | 2024-03-12 | 2025-05-30 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Sizing Calculations" |  | 2025-05
000357 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0024 | 0 | 131242-WSW41-LT-PM-0024 | 2024-03-12 | Notice of Unforeseeable Underground Obstruction Near Chemical Dosing | Refer to S.O. Correspondence No.150. | 2024-04-11 | 2024-05-10 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  | Refer to S.O. Correspondence No.150. | 000357 | 2024-03-12 | 2024-03-12 | 0 | INF | For Information | 1 | "Notice of Unforeseeable Underground Obstruction Near Chemical Dosing" |  | 2024-03
000358 | 00 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 0 | 131242-WST02-BQ-P-0001 | 2024-03-12 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-05-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 00:00:00 |  | 000358 | 2024-03-12 | 2024-11-15 | 2 | AWC | For Information | 3 | "C4B Sidestream Nitrogen Removal Process Equipment List" |  | 2024-03
000358 | 01 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 1 | 131242-WST02-BQ-P-0001 | 2024-07-24 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-14 | 2024-08-29 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000358 | 2024-03-12 | 2024-11-15 | 2 | AWC | For Information | 3 | "C4B Sidestream Nitrogen Removal Process Equipment List" |  | 2024-07
000358 | 02 | Qili | Process | NA | 131242 | WST02 | BQ | P | 0001 | 2 | 131242-WST02-BQ-P-0001 | 2024-11-15 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 2: For Information | 2024-12-05 | 2025-03-04 | 77 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000358 | 2024-03-12 | 2024-11-15 | 2 | INF | For Information | 3 | "C4B Sidestream Nitrogen Removal Process Equipment List" |  | 2024-11
000359 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 0 | 131242-WSD11-VI-I-0001 | 2024-03-13 | Vendor Approval of THP Train Instrument | Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-12 | 2024-05-16 | 46 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" |  | 2024-03
000359 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 1 | 131242-WSD11-VI-I-0001 | 2024-06-07 | Vendor Approval of THP Train Instrument (Siemens) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-05 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" |  | 2024-06
000359 | 02 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 2 | 131242-WSD11-VI-I-0001 | 2024-08-20 | Vendor Approval of THP Train Instrument (Siemens) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-09-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" |  | 2024-08
000359 | 03 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 3 | 131242-WSD11-VI-I-0001 | 2025-03-21 | Vendor Approval of THP Train Instrument (Siemens) | Rev 3: Approved with comments (except Electromagnetic flowmeter). To revise and resubmit. Refer attached file for comments. | 2025-04-10 | 2025-05-06 | 32 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000359 | 2024-03-13 | 2025-03-21 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" |  | 2025-03
000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | A | 131242-WST02-DR-P-7001 | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-03
000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | A | 131242-WST02-DR-P-7002 | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-03
000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7001 | B | 131242-WST02-DR-P-7001 | 2024-06-19 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | R1_AWC | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-06
000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7002 | B | 131242-WST02-DR-P-7002 | 2024-03-14 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | 105 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-03
000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001 | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-08
000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002 | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-08
000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001 | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | 57 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | comments received on 14 Feb | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-10
000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002 | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | 57 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2024-10
000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001 | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2025-02
000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002 | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2025-02
000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | D | 131242-WST02-DR-P-7001 | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2025-07
000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | D | 131242-WST02-DR-P-7002 | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000360 | 2024-03-14 | 2025-07-14 | D | AWC | Approved with Comments | 6 | "SSN PFD" |  | 2025-07
000361 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0006 | 0 | 131242-WSW41-PS-HS-0006 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Jan 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000361 | 2024-03-14 | 2024-03-14 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for Jan 2024" |  | 2024-03
000362 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0007 | 0 | 131242-WSW41-PS-HS-0007 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Feb 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000362 | 2024-03-14 | 2024-03-14 | 0 | INF | For Information | 1 | "Incentive / Disincentive Audit Scheme for Feb 2024" |  | 2024-03
000363 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 | 131242-WST02-CD-IM-0022 | 2024-03-15 | Milestone 1.2 - Underground Services | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000363 | 2024-03-15 | 2024-06-05 | 1 | REJ | Approved with Comments | 3 | "Milestone 1.2 Underground Services" && "Milestone 1.2 - Underground Services" |  | 2024-03
000364 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 | 131242-WST02-CD-IM-0024 | 2024-03-15 | Milestone 1.2 - SSN Pump Station and Lamella Clarifier | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000164&&000364 | 2024-03-15 | 2025-10-31 | 1 | REJ | Approved with Comments | 4 | "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" |  | 2024-03
000365 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0028 | 0 | 131242-WST02-CD-IM-0028 | 2024-03-15 | Milestone 1.2 - Sitewide Pipe Rack | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000365 | 2024-03-15 | 2024-03-15 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - Sitewide Pipe Rack" |  | 2024-03
000366 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0035 | 0 | 131242-WST02-CD-IM-0035 | 2024-03-15 | Milestone 1.2 - SSN Minor Drain | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000366 | 2024-03-15 | 2024-03-15 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - SSN Minor Drain" |  | 2024-03
000367 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 | 131242-WST02-CD-IM-0023 | 2024-03-18 | Milestone 1.2 - SSN Water Tank | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000163&&000367 | 2024-03-18 | 2024-06-03 | 0 | REJ | Approved with Comments | 2 | "Milestone 1.2 SSN Water Tank" && "Milestone 1.2 - SSN Water Tank" |  | 2024-03
000368 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025 | 2024-03-18 | Milestone 1.2 - SSN Pump Station and Blower | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000162&&000368 | 2024-03-18 | 2025-10-27 | 0 | REJ | Not Approved | 5 | "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "Milestone 1.2 - SSN Pump Station and Blower " |  | 2024-03
000369 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0026 | 0 | 131242-WST02-CD-IM-0026 | 2024-03-18 | Milestone 1.2 - SSN Chemical Dosing Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000369 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - SSN Chemical Dosing Area " |  | 2024-03
000370 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0027 | 0 | 131242-WST02-CD-IM-0027 | 2024-03-18 | Milestone 1.2 - SSN Electrical Building | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000370 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - SSN Electrical Building " |  | 2024-03
000371 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0029 | 0 | 131242-WST02-CD-IM-0029 | 2024-03-18 | Milestone 1.2 - THP Air Compress System | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000371 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Air Compress System " |  | 2024-03
000372 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0030 | 0 | 131242-WST02-CD-IM-0030 | 2024-03-18 | Milestone 1.2 - THP Silo Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000372 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Silo Area " |  | 2024-03
000373 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0031 | 0 | 131242-WST02-CD-IM-0031 | 2024-03-18 | Milestone 1.2 - THP Trains | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000373 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Trains " |  | 2024-03
000374 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0032 | 0 | 131242-WST02-CD-IM-0032 | 2024-03-18 | Milestone 1.2 - THP Drainage | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000374 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Drainage " |  | 2024-03
000375 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0033 | 0 | 131242-WST02-CD-IM-0033 | 2024-03-18 | Milestone 1.2 - THP Building Service | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000375 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP Building Service" |  | 2024-03
000376 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0034 | 0 | 131242-WST02-CD-IM-0034 | 2024-03-18 | Milestone 1.2 - THP MCC Room | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | 46 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000376 | 2024-03-18 | 2024-03-18 | 0 | REJ | Rejected | 1 | "Milestone 1.2 - THP MCC Room " |  | 2024-03
000377 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0010 | 0 | 131242-WSW41-RT-PM-0010 | 2024-03-18 | C4B Monthly Progress Report Number No.10 (02 24) | Rev. 0 - Approved with comments - need to re-submit (see attached comment sheet) | 2024-04-17 | 2024-04-01 | 10 | Approved with Comments | YES | 2024-04-19 | NO | Resubmitted | 0 |  |  | 000377 | 2024-03-18 | 2024-03-18 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.10 (02 24)" |  | 2024-03
000378 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 0 | 131242-WSD11-SP-I-0002 | 2024-03-19 | Plant Control Narrative | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-30 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending MP info | 000378 | 2024-03-19 | 2024-10-21 | 1 | AWC | Approved with Comments | 3 | "Plant Control Narrative" |  | 2024-03
000378 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 1 | 131242-WSD11-SP-I-0002 | 2024-10-21 | Plant Control Narrative | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000378 | 2024-03-19 | 2024-10-21 | 1 | AWC | Approved with Comments | 3 | "Plant Control Narrative" |  | 2024-10
000378 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 2 | 131242-WSD11-SP-I-0002 | 2024-10-21 | Plant Control Narrative | Rev 2: Approved. Please note: if there are any changes in controls, C4B will have to re-issue the document.” | 2024-11-11 | 2025-10-10 | 254 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000378 | 2024-03-19 | 2024-10-21 | 1 | APP | Approved with Comments | 3 | "Plant Control Narrative" |  | 2024-10
000379 | 00 | Boopathi | PMT | NA | 131242 | WSW41 | VI | C | 0014 | 0 | 131242-WSW41-VI-C-0014 | 2024-03-19 | Vendor Approval for Waterproof Additive Specialist (CementAID) | Approved. | 2024-04-18 | 2024-03-26 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000379 | 2024-03-19 | 2024-03-19 | 0 | APP | Approved | 1 | "Vendor Approval for Waterproof Additive Specialist (CementAID)" |  | 2024-03
000380 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-C-0007 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000380&&000433 | 2024-03-20 | 2024-06-20 | 1 | AWC | Approved with Comments | 3 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" |  | 2024-03
000380 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 1 | 131242-WSW41-SP-C-0007 | 2024-06-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-06-28 | 6 | Approved with Comments | YES | 2024-07-18 | NO | Resubmitted | 29 |  |  | 000380&&000433 | 2024-03-20 | 2024-06-20 | 1 | AWC | Approved with Comments | 3 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" |  | 2024-06
000381 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0006 | 0 | 131242-WSW41-SP-C-0006 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 | 4 | Approved with Comments | YES | 2024-04-15 | NO | Resubmitted | 0 |  |  | 000381 | 2024-03-20 | 2024-03-20 | 0 | AWC | Approved with Comments | 1 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance)" |  | 2024-03
000382 | 00 | Zora | CSA | NA | 131242 | WSW41 | CN | C | 0001 | 0 | 131242-WSW41-CN-C-0001 | 2024-03-20 | RFC For SSN Surface Drainage Layout | Approved | 2024-04-19 | 2024-08-29 | 116 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000382 | 2024-03-20 | 2024-03-20 | 0 | APP | Approved | 1 | "RFC For SSN Surface Drainage Layout" |  | 2024-03
000383 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0025 | 0 | 131242-WSW41-LT-PM-0025 | 2024-03-20 | Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rejected | 2024-04-19 | 2024-06-21 | 67 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000383 | 2024-03-20 | 2024-03-20 | 0 | REJ | Rejected | 1 | "Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" |  | 2024-03
000383 | 01 | Theint Theint | Contracts | NA | 131242 | WSW41 | LT | PM | 0033 | 0 | 131242-WSW41-LT-PM-0033 | 2024-06-22 | Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rev 1: Approved | 2024-07-11 | 2024-08-28 | 47 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000383 | 2024-06-22 | 2024-06-22 | 0 | APP | Approved | 1 | "Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" |  | 2024-06
000384 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 0 | 131242-WST02-CL-P-0003 | 2024-03-20 | SSN Process Design Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-19 | 2024-04-25 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending MP info | 000384 | 2024-03-20 | 2024-08-01 | 1 | AWC | Approved with Comments | 2 | "SSN Process Design Calculation" |  | 2024-03
000384 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 1 | 131242-WST02-CL-P-0003 | 2024-08-01 | SSN Process Design Calculation | Rev 1: Approved with Comments. Although there are no active comments the submittal is approved with comments to accommodate changes and resubmittal during the detail engineering. | 2024-08-22 | 2024-09-04 | 24 | Approved with Comments | YES | 2024-09-24 | NO | Resubmitted | 0 |  |  | 000384 | 2024-03-20 | 2024-08-01 | 1 | AWC | Approved with Comments | 2 | "SSN Process Design Calculation" |  | 2024-08
000385 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 0 | 131242-WST02-CH-P-0001 | 2024-03-20 | SSN Process Design Basis | R0: Not Approved. Please resubmit | 2024-04-19 | 2024-04-30 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000385 | 2024-03-20 | 2025-02-24 | 3 | NAP | Approved with Comments | 4 | "SSN Process Design Basis" |  | 2024-03
000385 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 1 | 131242-WST02-CH-P-0001 | 2024-08-02 | SSN Process Design Basis | R1: Approved with comments. Address the comments and resubmit. | 2024-08-23 | 2024-09-04 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000385 | 2024-03-20 | 2025-02-24 | 3 | AWC | Approved with Comments | 4 | "SSN Process Design Basis" |  | 2024-08
000385 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 2 | 131242-WST02-CH-P-0001 | 2024-11-04 | SSN Process Design Basis | R2: Approved with comments. Address the comments and resubmit. | 2024-11-22 | 2025-01-09 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-19 00:00:00 | comments received on 14 Feb | 000385 | 2024-03-20 | 2025-02-24 | 3 | AWC | Approved with Comments | 4 | "SSN Process Design Basis" |  | 2024-11
000385 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 3 | 131242-WST02-CH-P-0001 | 2025-02-24 | SSN Process Design Basis | R3: Approved with comments. | 2025-03-14 | 2025-03-13 | 13 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 | 2025-02-19 00:00:00 |  | 000385 | 2024-03-20 | 2025-02-24 | 3 | AWC | Approved with Comments | 4 | "SSN Process Design Basis" |  | 2025-02
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0001_ST617 | 0 | 131242-WSD11-CL-S-0001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | 0 | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST617 | A | 131242-WSW41-DR-S-1000_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1001_ST617 | A | 131242-WSW41-DR-S-1001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1002_ST617 | A | 131242-WSW41-DR-S-1002_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1003_ST617 | A | 131242-WSW41-DR-S-1003_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST617 | A | 131242-WSW41-DR-S-2001_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST617 | A | 131242-WSW41-DR-S-2002_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2003_ST617 | A | 131242-WSW41-DR-S-2003_ST617 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | A | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | NA | THP_PF01 reaction table | 0 | 131242-WSD11-CL-NA-THP_PF01 reaction table | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | 0 | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | NA | THP_PF02_PR01 reaction table | 0 | 131242-WSD11-CL-NA-THP_PF02_PR01 reaction table | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-03-20 | 2024-03-20 | 0 | NAP | Not Approved | 1 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" |  | 2024-03
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-S-0300_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | A | 131242-WSD11-DR-S-0301_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | A | 131242-WSD11-DR-S-1000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | A | 131242-WSD11-DR-S-1001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | A | 131242-WSD11-DR-S-1002_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | A | 131242-WSD11-DR-S-1003_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1004_ST617 | A | 131242-WSD11-DR-S-1004_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386 | 2024-07-04 | 2024-10-11 | B | NAP | Approved with Comments | 2 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | A | 131242-WSD11-DR-S-2000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | A | 131242-WSD11-DR-S-2001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | A | 131242-WSD11-DR-S-3000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | A | 131242-WSD11-DR-S-3001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | A | 131242-WSD11-DR-S-3002_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | A | 131242-WSD11-DR-S-5000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | A | 131242-WSD11-DR-S-5001_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | A | 131242-WSD11-DR-S-5002_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | A | 131242-WSD11-DR-S-5003_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | A | 131242-WSD11-DR-S-5004_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | A | 131242-WSD11-DR-S-5005_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | A | 131242-WSD11-DR-S-5006_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | A | 131242-WSD11-DR-S-8000_ST617 | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | NAP | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-07
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | B | 131242-WSD11-DR-S-0300_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | B | 131242-WSD11-DR-S-0301_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | B | 131242-WSD11-DR-S-1000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | B | 131242-WSD11-DR-S-1001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | B | 131242-WSD11-DR-S-1002_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | B | 131242-WSD11-DR-S-1003_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1004_ST617 | B | 131242-WSD11-DR-S-1004_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386 | 2024-07-04 | 2024-10-11 | B | AWC | Approved with Comments | 2 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | B | 131242-WSD11-DR-S-2000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | B | 131242-WSD11-DR-S-2001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | B | 131242-WSD11-DR-S-3000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | B | 131242-WSD11-DR-S-3001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | B | 131242-WSD11-DR-S-3002_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | B | 131242-WSD11-DR-S-5000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | B | 131242-WSD11-DR-S-5001_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | B | 131242-WSD11-DR-S-5002_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | B | 131242-WSD11-DR-S-5003_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | B | 131242-WSD11-DR-S-5004_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | B | 131242-WSD11-DR-S-5005_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | B | 131242-WSD11-DR-S-5006_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | B | 131242-WSD11-DR-S-8000_ST617 | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | 12 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-10
000387 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0010 | 0 | 131242-WSW41-PS-PM-0010 | 2024-03-22 | Monthly Progress Presentation No. 10 (0224) | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000387 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 10 (0224)" |  | 2024-03
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0019 | 0 | 131242-WSW41-MI-C-0019 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000388 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" |  | 2024-03
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0020 | 0 | 131242-WSW41-MI-C-0020 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000388 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" |  | 2024-03
000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0021 | 0 | 131242-WSW41-MI-C-0021 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000388 | 2024-03-22 | 2024-03-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" |  | 2024-03
000389 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0009 | 0 | 131242-WSW41-PC-W-0009 | 2024-03-23 | Payment Claim No.9 | Rev(0): Approved. Refer to S.O. correspondence no. 137 dated 27 Mar 2024. | 2024-04-23 | 2024-05-10 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000389 | 2024-03-23 | 2024-03-23 | 0 | APP | Approved | 1 | "Payment Claim No.9" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A | 131242-WSD11-DR-I-1000 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 | 2024-07-16 00:00:00 |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1001 | A | 131242-WSD11-DR-I-1001 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1002 | A | 131242-WSD11-DR-I-1002 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1003 | A | 131242-WSD11-DR-I-1003 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3000 | A | 131242-WSD11-DR-I-3000 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3001 | A | 131242-WSD11-DR-I-3001 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3002 | A | 131242-WSD11-DR-I-3002 | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-03
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A.1 | 131242-WSD11-DR-I-1000 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-16 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1001 | A.1 | 131242-WSD11-DR-I-1001 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1002 | A.1 | 131242-WSD11-DR-I-1002 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1003 | A.1 | 131242-WSD11-DR-I-1003 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3000 | A.1 | 131242-WSD11-DR-I-3000 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3001 | A.1 | 131242-WSD11-DR-I-3001 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3002 | A.1 | 131242-WSD11-DR-I-3002 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000390 | 2024-03-23 | 2024-08-27 | A.1 | INF | For Information | 2 | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" |  | 2024-08
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | 0 | 131242-WSD11-DR-M-1170 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | YES | 2024-08-30 | NO | Resubmitted | 0 |  | Submitted as S000681.1 | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-03
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | 0 | 131242-WSD11-DR-M-1171 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-03
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | 0 | 131242-WSD11-DR-M-1172 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-03
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | 0 | 131242-WSD11-DR-M-3170 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-03
000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | 0 | 131242-WSD11-DR-M-3171 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | 100 | For Information | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | INF | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7308 | A | 131242-WSD11-DR-I-7308 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7309 | A | 131242-WSD11-DR-I-7309 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7310 | A | 131242-WSD11-DR-I-7310 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7311 | A | 131242-WSD11-DR-I-7311 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7312 | A | 131242-WSD11-DR-I-7312 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7313 | A | 131242-WSD11-DR-I-7313 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7314 | A | 131242-WSD11-DR-I-7314 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7315 | A | 131242-WSD11-DR-I-7315 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7316 | A | 131242-WSD11-DR-I-7316 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7317 | A | 131242-WSD11-DR-I-7317 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7318 | A | 131242-WSD11-DR-I-7318 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7319 | A | 131242-WSD11-DR-I-7319 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7320 | A | 131242-WSD11-DR-I-7320 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7321 | A | 131242-WSD11-DR-I-7321 | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-03
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | B | 131242-WSD11-DR-I-7307 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-06-26 | 2025-06-16 | E | NAP | Approved with Comments | 3 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7308 | B | 131242-WSD11-DR-I-7308 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7309 | B | 131242-WSD11-DR-I-7309 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7310 | B | 131242-WSD11-DR-I-7310 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7311 | B | 131242-WSD11-DR-I-7311 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7312 | B | 131242-WSD11-DR-I-7312 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7313 | B | 131242-WSD11-DR-I-7313 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7314 | B | 131242-WSD11-DR-I-7314 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7315 | B | 131242-WSD11-DR-I-7315 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7316 | B | 131242-WSD11-DR-I-7316 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7317 | B | 131242-WSD11-DR-I-7317 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7318 | B | 131242-WSD11-DR-I-7318 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7319 | B | 131242-WSD11-DR-I-7319 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7320 | B | 131242-WSD11-DR-I-7320 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7321 | B | 131242-WSD11-DR-I-7321 | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | NAP | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2024-06
000392 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | C | 131242-WSD11-DR-I-7306 | 2024-11-19 | Compressor Sequencer Panel | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-09 | 2024-12-18 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-11-19 | 2025-06-16 | E | NAP | Approved with Comments | 3 | "Compressor Sequencer Panel" |  | 2024-11
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | D | 131242-WSD11-DR-I-7306 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000392 | 2024-11-19 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7307 | D | 131242-WSD11-DR-I-7307 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-06-26 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7308 | D | 131242-WSD11-DR-I-7308 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7309 | D | 131242-WSD11-DR-I-7309 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7310 | D | 131242-WSD11-DR-I-7310 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7311 | D | 131242-WSD11-DR-I-7311 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7312 | D | 131242-WSD11-DR-I-7312 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7313 | D | 131242-WSD11-DR-I-7313 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7314 | D | 131242-WSD11-DR-I-7314 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7315 | D | 131242-WSD11-DR-I-7315 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7316 | D | 131242-WSD11-DR-I-7316 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7317 | D | 131242-WSD11-DR-I-7317 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7318 | D | 131242-WSD11-DR-I-7318 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7319 | D | 131242-WSD11-DR-I-7319 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7320 | D | 131242-WSD11-DR-I-7320 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7321 | D | 131242-WSD11-DR-I-7321 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7322 | D | 131242-WSD11-DR-I-7322 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7323 | D | 131242-WSD11-DR-I-7323 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7324 | D | 131242-WSD11-DR-I-7324 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7325 | D | 131242-WSD11-DR-I-7325 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7326 | D | 131242-WSD11-DR-I-7326 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7327 | D | 131242-WSD11-DR-I-7327 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7328 | D | 131242-WSD11-DR-I-7328 | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | 49 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-01
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7306 | E | 131242-WSD11-DR-I-7306 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 000392 | 2024-11-19 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | E | 131242-WSD11-DR-I-7307 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-06-26 | 2025-06-16 | E | AWC | Approved with Comments | 3 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7308 | E | 131242-WSD11-DR-I-7308 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7309 | E | 131242-WSD11-DR-I-7309 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7310 | E | 131242-WSD11-DR-I-7310 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7311 | E | 131242-WSD11-DR-I-7311 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7312 | E | 131242-WSD11-DR-I-7312 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7313 | E | 131242-WSD11-DR-I-7313 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7314 | E | 131242-WSD11-DR-I-7314 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7315 | E | 131242-WSD11-DR-I-7315 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7316 | E | 131242-WSD11-DR-I-7316 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7317 | E | 131242-WSD11-DR-I-7317 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7318 | E | 131242-WSD11-DR-I-7318 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7319 | E | 131242-WSD11-DR-I-7319 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7320 | E | 131242-WSD11-DR-I-7320 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7321 | E | 131242-WSD11-DR-I-7321 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2024-03-25 | 2025-06-16 | E | AWC | Approved with Comments | 4 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7322 | E | 131242-WSD11-DR-I-7322 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7323 | E | 131242-WSD11-DR-I-7323 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7324 | E | 131242-WSD11-DR-I-7324 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7325 | E | 131242-WSD11-DR-I-7325 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7326 | E | 131242-WSD11-DR-I-7326 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7327 | E | 131242-WSD11-DR-I-7327 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7328 | E | 131242-WSD11-DR-I-7328 | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | 126 | Approved with Comments | YES | 2025-12-29 | NO | Resubmitted | 63 |  |  | 000392 | 2025-01-15 | 2025-06-16 | E | AWC | Approved with Comments | 2 | "Compressor Sequencer Panel" |  | 2025-06
000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-E-7700 | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 00:00:00 |  | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" |  | 2024-03
000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7701 | A | 131242-WSD11-DR-E-7701 | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" |  | 2024-03
000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-E-7700 | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 | TBA | To check with Yibo and will advise later the submission date. | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" |  | 2024-08
000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7701 | A | 131242-WSD11-DR-E-7701 | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000393 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air System" |  | 2024-08
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-E-7720 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 00:00:00 |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-03
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7721 | A | 131242-WSD11-DR-E-7721 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-03
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7722 | A | 131242-WSD11-DR-E-7722 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-03
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7723 | A | 131242-WSD11-DR-E-7723 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-03
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7724 | A | 131242-WSD11-DR-E-7724 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-03
000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7725 | A | 131242-WSD11-DR-E-7725 | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-03
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-E-7720 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-02 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 | TBA | To check with Yibo and will advise later the submission date. | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-08
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7721 | A | 131242-WSD11-DR-E-7721 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-08
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7722 | A | 131242-WSD11-DR-E-7722 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-08
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7723 | A | 131242-WSD11-DR-E-7723 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-08
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7724 | A | 131242-WSD11-DR-E-7724 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-08
000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7725 | A | 131242-WSD11-DR-E-7725 | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | 63 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000394 | 2024-03-25 | 2024-08-13 | A | AWC | Approved with Comments | 2 | "THP Schematic Diagram for Compressed Air Dryer" |  | 2024-08
000395 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | A | 131242-WSD11-DR-E-3160 | 2024-03-25 | Air Compressor Motor Outline Drawing | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached files for comments. | 2024-04-24 | 2024-05-16 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-24 00:00:00 |  | 000395 | 2024-03-25 | 2024-08-16 | B | AWC | Approved | 2 | "Air Compressor Motor Outline Drawing " |  | 2024-03
000395 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | B | 131242-WSD11-DR-E-3160 | 2024-08-16 | Air Compressor Motor Outline Drawing | Rev 1: Approved. | 2024-09-05 | 2024-11-04 | 56 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000395 | 2024-03-25 | 2024-08-16 | B | APP | Approved | 2 | "Air Compressor Motor Outline Drawing " |  | 2024-08
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-A-1000_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A | 131242-WST02-DR-A-1001_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A | 131242-WST02-DR-A-1002_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A | 131242-WST02-DR-A-1003_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A | 131242-WST02-DR-A-1004_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A | 131242-WST02-DR-A-1009_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A | 131242-WST02-DR-A-2001_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A | 131242-WST02-DR-A-2002_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A | 131242-WST02-DR-A-2003_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-03
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-A-0001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2024-10-30 | A | NAP | Not Approved | 2 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-A-1000_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A | 131242-WST02-DR-A-1001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A | 131242-WST02-DR-A-1002_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A | 131242-WST02-DR-A-1003_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A | 131242-WST02-DR-A-1004_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A | 131242-WST02-DR-A-1009_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A | 131242-WST02-DR-A-2000_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A | 131242-WST02-DR-A-2001_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A | 131242-WST02-DR-A-2002_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A | 131242-WST02-DR-A-2003_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-05
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.1 | 131242-WST02-DR-A-1001_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.1 | 131242-WST02-DR-A-1002_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.1 | 131242-WST02-DR-A-1003_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | A.1 | 131242-WST02-DR-A-1006_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A | NAP | Not Approved | 2 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.1 | 131242-WST02-DR-A-1009_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.1 | 131242-WST02-DR-A-2000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A.1 | 131242-WST02-DR-A-2001_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A.1 | 131242-WST02-DR-A-2002_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A.1 | 131242-WST02-DR-A-2003_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | A | 131242-WST02-DR-A-3000_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A.2 | NAP | Not Approved | 2 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5004_LTA_NPKS | A | 131242-WST02-DR-A-5004_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2024-10-30 | A | NAP | Not Approved | 1 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-A-0001_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2024-10-30 | A | NAP | Not Approved | 2 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 0002_LTA_NPKS | B | 131242-WST02-DR-A-0002_LTA_NPKS | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "LTA & Nparks submission Set" |  | 2024-10
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  | Rejected as CES requested as drawings need to be included PE endorsement | 000396 | 2024-03-25 | 2026-01-09 | A.2 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.2 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.2 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.2 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | REJ | Rejected | 7 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.2 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.2 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.2 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" |  | 2025-03
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.3 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.3 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.3 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.3 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | NAP | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | NAP | Rejected | 7 | "LTA & Nparks submission Set" |  | 2025-08
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.3 | 131242-WST02-DR-A-1002_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.3 | 131242-WST02-DR-A-1003_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.3 | 131242-WST02-DR-A-1004_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.3 | 131242-WST02-DR-A-1009_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | REJ | Rejected | 8 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | REJ | Rejected | 7 | "LTA & Nparks submission Set" |  | 2025-11
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.2 | 131242-WST02-DR-A-1000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.2 | PEN | Rejected | 8 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.4 | 131242-WST02-DR-A-1001_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.4 | 131242-WST02-DR-A-1002_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.4 | 131242-WST02-DR-A-1003_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.4 | 131242-WST02-DR-A-1004_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_LTA_NPKS | A | 131242-WST02-DR-A-1005_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2026-01-09 | 2026-01-09 | A | PEN | Awaiting S.O.'s response | 1 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | A | 131242-WST02-DR-A-1006_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A | PEN | Not Approved | 2 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.4 | 131242-WST02-DR-A-1009_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Rejected | 8 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.4 | 131242-WST02-DR-A-2000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-05-16 | 2026-01-09 | A.4 | PEN | Rejected | 7 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A.4 | 131242-WST02-DR-A-2001_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A.4 | 131242-WST02-DR-A-2002_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A.4 | 131242-WST02-DR-A-2003_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A.4 | 131242-WST02-DR-A-2007_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-03-25 | 2026-01-09 | A.4 | PEN | Not Approved | 4 | "LTA & Nparks submission Set" |  | 2026-01
000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | A.2 | 131242-WST02-DR-A-3000_LTA_NPKS | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | 56 | Awaiting S.O.'s response | YES | 2026-02-26 | NO | Overdue | 0 |  |  | 000396 | 2024-10-30 | 2026-01-09 | A.2 | PEN | Not Approved | 2 | "LTA & Nparks submission Set" |  | 2026-01
000397 | 00 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0000_NEA | A | 131242-WST02-DR-A-0000_NEA | 2024-03-25 | NEA DC submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-03-25 | 2024-03-25 | A | NAP | Not Approved | 1 | "NEA DC submission Set " |  | 2024-03
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.1 | 131242-WST02-DR-A-1001_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.1 | 131242-WST02-DR-A-1002_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.1 | 131242-WST02-DR-A-1003_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.1 | 131242-WST02-DR-A-1004_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_NEA | A.1 | 131242-WST02-DR-A-1006_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A | NAP | Not Approved | 2 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.1 | 131242-WST02-DR-A-1009_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.1 | 131242-WST02-DR-A-2000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 3 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_NEA | A.1 | 131242-WST02-DR-A-2001_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_NEA | A.1 | 131242-WST02-DR-A-2002_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_NEA | A.1 | 131242-WST02-DR-A-2003_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_NEA | A | 131242-WST02-DR-A-2007_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Not Approved | 2 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_NEA | A | 131242-WST02-DR-A-3000_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | NAP | Not Approved | 2 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 5004_NEA | A | 131242-WST02-DR-A-5004_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2024-10-30 | A | NAP | Not Approved | 1 | "NEA DC submission Set " |  | 2024-10
000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0002_NEA | B | 131242-WST02-DR-A-0002_NEA | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | 56 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2024-10-30 | B | NAP | Not Approved | 1 | "NEA DC submission Set " |  | 2024-10
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  | Rejected as CES requested as drawings need to be included PE endorsement | 000397 | 2024-10-30 | 2026-01-06 | A.2 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.2 | 131242-WST02-DR-A-1002_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.2 | 131242-WST02-DR-A-1003_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.2 | 131242-WST02-DR-A-1004_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.2 | 131242-WST02-DR-A-1009_NEA | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.2 | 131242-WST02-DR-A-1002_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.2 | 131242-WST02-DR-A-1003_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.2 | 131242-WST02-DR-A-1004_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.2 | 131242-WST02-DR-A-1009_NEA | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | NAP | Rejected | 5 | "NEA DC submission Set " |  | 2025-03
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-11
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-11
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.3 | 131242-WST02-DR-A-1002_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-11
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.3 | 131242-WST02-DR-A-1003_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-11
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.3 | 131242-WST02-DR-A-1004_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-11
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.3 | 131242-WST02-DR-A-1009_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 5 | "NEA DC submission Set " |  | 2025-11
000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.2 | 131242-WST02-DR-A-2000_NEA | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | REJ | Rejected | 3 | "NEA DC submission Set " |  | 2025-11
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.2 | 131242-WST02-DR-A-1000_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | PEN | Rejected | 5 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.4 | 131242-WST02-DR-A-1001_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.4 | 131242-WST02-DR-A-1002_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.4 | 131242-WST02-DR-A-1003_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.4 | 131242-WST02-DR-A-1004_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1005_NEA | A | 131242-WST02-DR-A-1005_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2026-01-06 | 2026-01-06 | A | PEN | Awaiting S.O.'s response | 1 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_NEA | A | 131242-WST02-DR-A-1006_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A | PEN | Not Approved | 2 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.4 | 131242-WST02-DR-A-1009_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 5 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.4 | 131242-WST02-DR-A-2000_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Rejected | 3 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_NEA | A.4 | 131242-WST02-DR-A-2001_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_NEA | A.4 | 131242-WST02-DR-A-2002_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_NEA | A.4 | 131242-WST02-DR-A-2003_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_NEA | A.4 | 131242-WST02-DR-A-2007_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.4 | PEN | Not Approved | 2 | "NEA DC submission Set " |  | 2026-01
000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_NEA | A.2 | 131242-WST02-DR-A-3000_NEA | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000397 | 2024-10-30 | 2026-01-06 | A.2 | PEN | Not Approved | 2 | "NEA DC submission Set " |  | 2026-01
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6000 | A | 131242-WST02-DR-P-6000 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | A | 131242-WST02-DR-P-6001 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | A | 131242-WST02-DR-P-6002 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | A | 131242-WST02-DR-P-6003 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | A | 131242-WST02-DR-P-6004 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | A | 131242-WST02-DR-P-6005 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | A | 131242-WST02-DR-P-6006 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | A | 131242-WST02-DR-P-6007 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | A | 131242-WST02-DR-P-6008 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | A | 131242-WST02-DR-P-6009 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | A | 131242-WST02-DR-P-6010 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | A | 131242-WST02-DR-P-6011 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | A | 131242-WST02-DR-P-6012 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | A | 131242-WST02-DR-P-6013 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | A | 131242-WST02-DR-P-6014 | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-03
000398 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#398 CES Reply | NA | 131242-WST02-NA-P-S#398 CES Reply | 2024-10-01 | P&ID for SSN Process | Rev 1: the submittal is closed as per the request of C4B contractor and merged to SRC 731 | 2024-10-21 | 2024-10-24 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398 | 2024-10-01 | 2024-10-01 | NA | AWC | Approved with Comments | 1 | "P&ID for SSN Process" |  | 2024-10
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | A | 131242-WST02-DR-P-6015 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-03
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | A | 131242-WST02-DR-P-6016 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-03
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | A | 131242-WST02-DR-P-6017 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-03
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | A | 131242-WST02-DR-P-6018 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-03
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | A | 131242-WST02-DR-P-6019 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-03
000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | A | 131242-WST02-DR-P-6020 | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-03
000399 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | NA | NA | S#399 CES Reply | NA | 131242-WSD11-NA-NA-S#399 CES Reply | 2024-10-01 | P&ID for SSN Process | Rev1: The submittal is merged with SRC 731. | 2024-10-21 | 2024-11-07 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399 | 2024-10-01 | 2024-10-01 | NA | AWC | Approved with Comments | 1 | "P&ID for SSN Process" |  | 2024-10
000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | A | 131242-WST02-DR-P-6200 | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Heng Peng to provide DGN dwg | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2024-03
000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | A | 131242-WST02-DR-P-6600 | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2024-03
000400 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#400 CES Reply | NA | 131242-WST02-NA-P-S#400 CES Reply | 2024-10-01 | P&ID for SSN Plant Water and Instrument Air | Rev 1: The submittal is closed and merged with SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000400 | 2024-10-01 | 2024-10-01 | NA | APP | Approved | 1 | "P&ID for SSN Plant Water and Instrument Air" |  | 2024-10
000401 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7000 | A | 131242-WST02-DR-I-7000 | 2024-03-26 | SSN Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-25 | 2024-04-30 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000401 | 2024-03-26 | 2024-08-26 | B | NAP | Approved with Comments | 2 | "SSN Control System Architecture Drawing" |  | 2024-03
000401 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7000 | B | 131242-WST02-DR-I-7000 | 2024-08-26 | SSN Control System Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-13 | 2024-10-16 | 37 | Approved with Comments | YES | 2024-11-05 | NO | Resubmitted | 0 |  |  | 000401 | 2024-03-26 | 2024-08-26 | B | AWC | Approved with Comments | 2 | "SSN Control System Architecture Drawing" |  | 2024-08
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A | 131242-WST02-DR-A-1009_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A | 131242-WST02-DR-A-2003_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-03
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-10 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A | 131242-WST02-DR-A-1009_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A | 131242-WST02-DR-A-2003_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-04
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A | 131242-WST02-DR-A-2000_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-05
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.1 | 131242-WST02-DR-A-1001_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.1 | 131242-WST02-DR-A-1002_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.1 | 131242-WST02-DR-A-1003_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.1 | 131242-WST02-DR-A-1009_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.1 | 131242-WST02-DR-A-2000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.1 | 131242-WST02-DR-A-2001_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.1 | 131242-WST02-DR-A-2002_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.1 | 131242-WST02-DR-A-2003_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A | 131242-WST02-DR-A-3000_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5004_FSSD_BP | A | 131242-WST02-DR-A-5004_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2024-10-16 | A | NAP | Not Approved | 1 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | CL | A | 0001_FSSD_BP | A | 131242-WST02-CL-A-0001_FSSD_BP | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2024-10-16 | A | NAP | Not Approved | 1 | "SSN_FSSD (BP) Submission " |  | 2024-10
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.1 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.2 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.2 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.2 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.1 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.2 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.2 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.2 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A | 131242-WST02-DR-A-3000_FSSD_BP | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-03
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.3 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.3 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.3 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.2 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.3 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.3 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.2 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.2 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.3 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | B | 131242-WST02-DR-A-3000_FSSD_BP | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-08
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.2 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.3 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2025-11-07 | 2026-01-07 | A.2 | NAP | Approved with Comments | 3 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.2 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | NAP | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.4 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | NAP | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | NAP | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-11
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-A-1000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.4 | 131242-WST02-DR-A-1004_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2025-11-07 | 2026-01-07 | A.2 | AWC | Approved with Comments | 3 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | AWC | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | AWC | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.4 | 131242-WST02-DR-A-2000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | AWC | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.5 | 131242-WST02-DR-A-2001_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | AWC | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | AWC | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2025-12
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-A-1000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.2 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.4 | 131242-WST02-DR-A-1004_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2025-11-07 | 2026-01-07 | A.2 | PEN | Approved with Comments | 3 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | PEN | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.3 | PEN | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.4 | 131242-WST02-DR-A-2000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-05-13 | 2026-01-07 | A.4 | PEN | Approved with Comments | 7 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.5 | 131242-WST02-DR-A-2001_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.5 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 8 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-03-27 | 2026-01-07 | A.4 | PEN | Approved with Comments | 9 | "SSN_FSSD (BP) Submission " |  | 2026-01
000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | 58 | Awaiting S.O.'s response | YES | 2026-02-24 | NO | Overdue | 0 |  |  | 000402 | 2024-10-16 | 2026-01-07 | A.2 | PEN | Approved with Comments | 6 | "SSN_FSSD (BP) Submission " |  | 2026-01
000403 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SP | P | 0001 | 0 | 131242-WST02-SP-P-0001 | 2024-03-27 | SSN Control Philosophy | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-26 | 2024-05-23 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | Pending MP resubmission | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" |  | 2024-03
000403 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 1 | 131242-WST02-SP-P-0001 | 2024-08-12 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-03 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" |  | 2024-08
000403 | 02 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 2 | 131242-WST02-SP-P-0001 | 2024-10-03 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-11-07 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" |  | 2024-10
000403 | 03 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 3 | 131242-WST02-SP-P-0001 | 2025-03-14 | SSN Control Philosophy | Approved with Comments | 2025-04-03 | 2025-05-15 | 44 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000403 | 2024-03-27 | 2025-03-14 | 3 | AWC | Approved with Comments | 4 | "SSN Control Philosophy" |  | 2025-03
000404 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0004 | 0 | 131242-WST02-CL-P-0004 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-23 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000404 | 2024-03-28 | 2024-10-16 | 2 | AWC | Approved | 3 | "SSN Chemical Consumption Calculation" |  | 2024-03
000404 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 1 | 131242-WST02-CL-P-0004 | 2024-07-28 | SSN Chemical Consumption Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000404 | 2024-03-28 | 2024-10-16 | 2 | AWC | Approved | 3 | "SSN Chemical Consumption Calculation" |  | 2024-07
000404 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 2 | 131242-WST02-CL-P-0004 | 2024-10-16 | SSN Chemical Consumption Calculation | Rev 2: Approved | 2024-11-06 | 2024-11-15 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000404 | 2024-03-28 | 2024-10-16 | 2 | APP | Approved | 3 | "SSN Chemical Consumption Calculation" |  | 2024-10
000405 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0002 | 0 | 131242-WSD11-RT-P-0002 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-30 | 45 | Approved with Comments | YES | 2024-06-19 | NO | Resubmitted | 0 |  | After addressing BODR | 000405 | 2024-03-28 | 2024-03-28 | 0 | AWC | Approved with Comments | 1 | "SSN Chemical Consumption Calculation" |  | 2024-03
000406 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 0 | 131242-WST02-CL-E-0005 | 2024-03-28 | SSN 22kV MV Power Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-29 | 2024-05-23 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000406 | 2024-03-28 | 2025-02-19 | 2 | NAP | Approved | 3 | "SSN 22kV MV Power Cable Sizing Calculations" |  | 2024-03
000406 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 1 | 131242-WST02-CL-E-0005 | 2024-07-06 | SSN 22kV MV Power Cable Sizing Calculations | Rev 1: Approved with comments. To revise and resubmit. | 2024-07-25 | 2024-07-22 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000406 | 2024-03-28 | 2025-02-19 | 2 | AWC | Approved | 3 | "SSN 22kV MV Power Cable Sizing Calculations" |  | 2024-07
000406 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 2 | 131242-WST02-CL-E-0005 | 2025-02-19 | SSN 22kV MV Power Cable Sizing Calculations | Rev 2: Approved. | 2025-03-11 | 2025-05-06 | 54 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000406 | 2024-03-28 | 2025-02-19 | 2 | APP | Approved | 3 | "SSN 22kV MV Power Cable Sizing Calculations" |  | 2025-02
000407 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | RT | P | 0001 | 0 | 131242-WST02-RT-P-0001 | 2024-03-28 | Basic Design Report of SSN Package | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-05-03 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000407 | 2024-03-28 | 2024-11-18 | 2 | NAP | Approved with Comments | 3 | "Basic Design Report of SSN Package" |  | 2024-03
000407 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 1 | 131242-WST02-RT-P-0001 | 2024-05-23 | Basic Design Report of SSN Package | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-12 | 2024-07-04 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | To follow up with MP for resubmission | 000407 | 2024-03-28 | 2024-11-18 | 2 | AWC | Approved with Comments | 3 | "Basic Design Report of SSN Package" |  | 2024-05
000407 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 2 | 131242-WST02-RT-P-0001 | 2024-11-18 | Basic Design Report of SSN Package | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-06 | 2025-01-08 | 37 | Approved with Comments | YES | 2025-01-28 | NO | Resubmitted | 0 | 2025-03-31 00:00:00 | comments received on 14 Feb | 000407 | 2024-03-28 | 2024-11-18 | 2 | AWC | Approved with Comments | 3 | "Basic Design Report of SSN Package" |  | 2024-11
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0015 | 1 | 131242-WST02-DS-M-0015 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | 0 | NAP | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-03
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0016 | A | 131242-WST02-DR-M-0016 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | NAP | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-03
000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0015 | A | 131242-WST02-DR-M-0015 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | NAP | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-03
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0015 | 0 | 131242-WST02-DS-M-0015 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000408 | 2024-03-28 | 2024-07-05 | 0 | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-07
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0016 | B | 131242-WST02-DR-M-0016 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-07
000408 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0015 | B | 131242-WST02-DR-M-0015 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000408 | 2024-03-28 | 2024-07-05 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-07
000408 | 01 | Qili | Process | NA | 131242 | WST02 | CL | M | 0001 | 0 | 131242-WST02-CL-M-0001 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000408 | 2024-07-05 | 2024-07-05 | 0 | AWC | Approved with Comments | 1 | "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" |  | 2024-07
000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0016 | 0 | 131242-WST02-DS-M-0016 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | 2 | NAP | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2024-03
000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0017 | 0 | 131242-WST02-DR-M-0017 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | B | NAP | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2024-03
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 1 | 131242-WST02-DS-M-0016 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000409 | 2024-03-28 | 2025-03-14 | 2 | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2024-07
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0017 | B | 131242-WST02-DR-M-0017 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | B | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2024-07
000409 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0018 | B | 131242-WST02-DR-M-0018 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000409 | 2024-07-05 | 2025-03-14 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2024-07
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 2 | 131242-WST02-DS-M-0016 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 86 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | 2 | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2025-03
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 0017 | B | 131242-WST02-DR-M-0017 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 86 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000409 | 2024-03-28 | 2025-03-14 | B | AWC | Approved with Comments | 3 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2025-03
000409 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 0018 | B | 131242-WST02-DR-M-0018 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | 86 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 000409 | 2024-07-05 | 2025-03-14 | B | AWC | Approved with Comments | 2 | "SSN Datasheet & Drawing of Biomass Separator " |  | 2025-03
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A | 131242-WST02-DR-S-1003_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide Native DGN sets | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | NAP | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-03
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A | 131242-WST02-DR-S-7001_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | NAP | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-03
000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A | 131242-WST02-DR-S-8001_ST616 | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | 25 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | NAP | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST609 | A | 131242-WST02-DR-S-1001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 | 2024-07-26 00:00:00 | Tenwit in Progress | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 2001_ST609 | A | 131242-WST02-DR-S-2001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 | Tenwit in Progress |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3001_ST609 | A | 131242-WST02-DR-S-3001_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST609 | A | 131242-WST02-DR-S-1002_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST609 | A | 131242-WST02-DR-S-1000_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 2000_ST609 | A | 131242-WST02-DR-S-2000_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3000_ST609 | A | 131242-WST02-DR-S-3000_ST609 | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | 30 | Not Approved | YES | 2024-05-29 | NO | Resubmitted | 0 |  |  | 000411 | 2024-03-28 | 2024-03-28 | A | NAP | Not Approved | 1 | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " |  | 2024-03
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide Native DGN sets and Aaron to address the comments | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000340&&000412 | 2024-03-05 | 2024-04-25 | C | NAP | Not Approved | 3 | "ST615 – Amendment of ST604 (BCA Submission for Information) " && "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_NOA | C | 131242-WST02-DR-S-A1798-00002-2018-ST615_NOA | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000412 | 2024-04-02 | 2024-04-02 | C | NAP | Not Approved | 1 | "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_Fdn Advice Letter | C | 131242-WST02-DR-S-A1798-00002-2018-ST615_Fdn Advice Letter | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | 30 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000412 | 2024-04-02 | 2024-04-02 | C | NAP | Not Approved | 1 | "ST615 BCA Approved Drawings (Amendment of ST604) " |  | 2024-04
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-S-1000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-04
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615 | C | 131242-WST02-DR-S-1001_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-04
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615 | C | 131242-WST02-DR-S-1002_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-04
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615 | C | 131242-WST02-DR-S-5001_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-04
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615 | C | 131242-WST02-DR-S-7000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-04
000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615 | C | 131242-WST02-DR-S-8000_ST615 | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-04
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-S-1000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-04 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng: BIM Pending to clear BIM comments | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-05
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615 | C | 131242-WST02-DR-S-1001_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-05
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615 | C | 131242-WST02-DR-S-1002_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-05
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615 | C | 131242-WST02-DR-S-5001_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-05
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615 | C | 131242-WST02-DR-S-7000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-05
000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615 | C | 131242-WST02-DR-S-8000_ST615 | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | 14 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000413 | 2024-04-02 | 2024-05-14 | C | NAP | Not Approved | 2 | "ST615 Issued for Construction Drawings (Amendment of ST604) " |  | 2024-05
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1000 | C01 | 131242-WSD11-DR-M-1000 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  | Pending DGN dwg drawing and CAMBI updates and to update Tagging | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" |  | 2024-04
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1001 | C01 | 131242-WSD11-DR-M-1001 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" |  | 2024-04
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1002 | C01 | 131242-WSD11-DR-M-1002 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" |  | 2024-04
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1003 | C01 | 131242-WSD11-DR-M-1003 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" |  | 2024-04
000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1004 | C01 | 131242-WSD11-DR-M-1004 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | 46 | Approved with Comments | YES | 2024-06-25 | NO | Resubmitted | 0 |  |  | 000414 | 2024-04-02 | 2024-04-02 | C01 | AWC | Approved with Comments | 1 | "THP GA Drawings" |  | 2024-04
000415 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0006 | 0 | 131242-WST02-CL-P-0006 | 2024-04-03 | SSN Equipment Sizing Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-05-23 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000415 | 2024-04-03 | 2024-08-12 | 1 | AWC | Approved with Comments | 2 | "SSN Equipment Sizing Calculation" |  | 2024-04
000415 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0006 | 1 | 131242-WST02-CL-P-0006 | 2024-08-12 | SSN Equipment Sizing Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-11 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000415 | 2024-04-03 | 2024-08-12 | 1 | AWC | Approved with Comments | 2 | "SSN Equipment Sizing Calculation" |  | 2024-08
000415 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | Comment Reply Sheet 20241118 S415.1 | NA | 131242-WST02-CL-P-Comment Reply Sheet 20241118 S415.1 | 2024-11-18 | SSN Equipment Sizing Calculation | Rev 2: Approved with Comments. The submittal is requested to be discontinued by CES. | 2024-12-06 | 2025-01-08 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000415 | 2024-11-18 | 2024-11-18 | NA | AWC | Approved with Comments | 1 | "SSN Equipment Sizing Calculation" |  | 2024-11
000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0005 | 0 | 131242-WST02-CL-P-0005 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | 2 | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" |  | 2024-04
000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7010 | 0 | 131242-WST02-DR-P-7010 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | C | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" |  | 2024-04
000416 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 1 | 131242-WST02-CL-P-0005 | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates, Need PE endosement | 000416 | 2024-04-03 | 2025-03-24 | 2 | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" |  | 2024-08
000416 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 7010 | B | 131242-WST02-DR-P-7010 | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | C | AWC | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" |  | 2024-08
000416 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 2 | 131242-WST02-CL-P-0005 | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | 140 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | 2 | APP | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" |  | 2025-03
000416 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7010 | C | 131242-WST02-DR-P-7010 | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | 140 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000416 | 2024-04-03 | 2025-03-24 | C | APP | Approved | 3 | "SSN Process Hydraulic Calculation & Drawing" |  | 2025-03
000417 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 0 | 131242-WSD11-VI-I-0002 | 2024-04-04 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-04-18 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000417 | 2024-04-04 | 2024-08-15 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" |  | 2024-04
000417 | 01 | Karthik/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 1 | 131242-WSD11-VI-I-0002 | 2024-08-15 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-04 | 2024-11-08 | 61 | Approved with Comments | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000417 | 2024-04-04 | 2024-08-15 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" |  | 2024-08
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1003 | A | 131242-WST02-DR-B-1003 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1004 | A | 131242-WST02-DR-B-1004 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1005 | A | 131242-WST02-DR-B-1005 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1006 | A | 131242-WST02-DR-B-1006 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1007 | A | 131242-WST02-DR-B-1007 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7001 | A | 131242-WST02-DR-B-7001 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7002 | A | 131242-WST02-DR-B-7002 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7003 | A | 131242-WST02-DR-B-7003 | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | 75 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | NAP | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-04
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1003 | B | 131242-WST02-DR-B-1003 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1004 | B | 131242-WST02-DR-B-1004 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1005 | B | 131242-WST02-DR-B-1005 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1006 | B | 131242-WST02-DR-B-1006 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000191&&000418 | 2024-04-04 | 2025-05-15 | B_MS2 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1007 | B | 131242-WST02-DR-B-1007 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7001 | B | 131242-WST02-DR-B-7001 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7002 | B | 131242-WST02-DR-B-7002 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7003 | B | 131242-WST02-DR-B-7003 | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | 110 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000418 | 2024-04-04 | 2024-10-22 | B | AWC | Approved with Comments | 2 | "SSN Integrated Security management system and plant CCTV" && "SSN Integrated Security management system and Plant CCTV" |  | 2024-10
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1011 | A | 131242-WST02-DR-BF-1011 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" |  | 2024-04
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1012 | A | 131242-WST02-DR-BF-1012 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | NAP | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" |  | 2024-04
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1013 | A | 131242-WST02-DR-BF-1013 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | NAP | Approved with Comments | 2 | "SSN Public Address System" |  | 2024-04
000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 7103 | A | 131242-WST02-DR-BF-7103 | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | 65 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | NAP | Approved with Comments | 2 | "SSN Public Address System" |  | 2024-04
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1011 | B | 131242-WST02-DR-BF-1011 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" |  | 2024-10
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1012 | B | 131242-WST02-DR-BF-1012 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000191&&000419 | 2024-04-04 | 2025-05-15 | A9 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Electrical Building" && "SSN Public Address System" |  | 2024-10
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1013 | B | 131242-WST02-DR-BF-1013 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | AWC | Approved with Comments | 2 | "SSN Public Address System" |  | 2024-10
000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 7103 | B | 131242-WST02-DR-BF-7103 | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | 7 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000419 | 2024-04-04 | 2024-10-18 | B | AWC | Approved with Comments | 2 | "SSN Public Address System" |  | 2024-10
000420 | 00 | Suresh | PCM | NA | 131242 | WSW41 | MI | PM | 0010 | 0 | 131242-WSW41-MI-PM-0010 | 2024-04-04 | Monthly Progress Meeting Minutes 0010_20240319 | For Information | 2024-05-06 | 2024-04-05 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000420 | 2024-04-04 | 2024-04-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0010_20240319" |  | 2024-04
000421 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 0 | 131242-WSD11-DS-M-0013 | 2024-04-05 | Data Sheet and Drawing of THP Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000421 | 2024-04-05 | 2025-01-26 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" |  | 2024-04
000421 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 1 | 131242-WSD11-DS-M-0013 | 2024-08-12 | Data Sheet of THP Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000421 | 2024-04-05 | 2025-01-26 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" |  | 2024-08
000421 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 2 | 131242-WSD11-DS-M-0013 | 2025-01-26 | Data Sheet of THP Feed Pump | Rev 2: Approved | 2025-02-13 | 2025-04-27 | 65 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000421 | 2024-04-05 | 2025-01-26 | 2 | APP | Approved | 3 | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" |  | 2025-01
000422 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 0 | 131242-WSD11-DS-M-0014 | 2024-04-06 | Data Sheet and Drawing of Reactor Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000422 | 2024-04-06 | 2025-04-10 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of Reactor Feed Pump" |  | 2024-04
000422 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 1 | 131242-WSD11-DS-M-0014 | 2024-08-12 | Data Sheet and Drawing of Reactor Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000422 | 2024-04-06 | 2025-04-10 | 2 | AWC | Approved | 3 | "Data Sheet and Drawing of Reactor Feed Pump" |  | 2024-08
000422 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 2 | 131242-WSD11-DS-M-0014 | 2025-04-10 | Data Sheet and Drawing of Reactor Feed Pump | Rev 2: Approved | 2025-04-30 | 2025-10-06 | 127 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000422 | 2024-04-06 | 2025-04-10 | 2 | APP | Approved | 3 | "Data Sheet and Drawing of Reactor Feed Pump" |  | 2025-04
000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0001 | A | 131242-WSD11-DR-S-0001 | 2024-04-06 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000423 | 2024-04-06 | 2024-04-06 | A | NAP | Not Approved | 1 | "Compressed Air System - Anchor Bolts Details & Plinth Details" |  | 2024-04
000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0004 | 0 | 131242-WSD11-CL-S-0004 | 2024-04-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000423 | 2024-04-05 | 2024-06-05 | 1 | NAP | Not Approved | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" |  | 2024-04
000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301 | A | 131242-WSD11-DR-S-5301 | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-06-26 | 2024-06-19 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000423&&000536 | 2024-06-05 | 2024-06-26 | B | APP | Approved with Comments | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" |  | 2024-06
000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0004 | 1 | 131242-WSD11-CL-S-0004 | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-07-04 | 2024-06-19 | 10 | Awaiting S.O.'s response | YES | 2024-07-09 | NO | Resubmitted | 0 |  |  | 000423 | 2024-04-05 | 2024-06-05 | 1 | PEN | Not Approved | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" |  | 2024-06
000424 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0037 | 0 | 131242-WSW41-CD-IM-0037 | 2024-04-08 | Submission Of BIM Coordination VCM Model (Mar-2024) | For Information | 2024-05-08 | 2024-04-19 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000424 | 2024-04-08 | 2024-04-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Mar-2024)" |  | 2024-04
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-S-1003_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | A2 | 131242-WST02-DR-S-7001_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | A2 | 131242-WST02-DR-S-8001_ST616_BCA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | A.1 | 131242-WST02-DR-S-A1798-00002-2018_NOA | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A.1 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-S-1003_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide Native DGN sets and Aaron to address the comments | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | A2 | 131242-WST02-DR-S-7001_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | A2 | 131242-WST02-DR-S-8001_ST616_BCA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A2 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | A.1 | 131242-WST02-DR-S-A1798-00002-2018_NOA | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | 18 | Not Approved | YES | 2024-06-03 | NO | Resubmitted | 0 |  |  | 000425 | 2024-04-08 | 2024-04-18 | A.1 | NAP | Not Approved | 2 | "ST616_Amendment of ST605 (BCA Approved Drawings) " |  | 2024-04
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A2 | 131242-WST02-DR-S-1003_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | AWC | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-04
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A2 | 131242-WST02-DR-S-7001_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | AWC | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-04
000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A2 | 131242-WST02-DR-S-8001_ST616 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | AWC | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-04
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A.2 | 131242-WST02-DR-S-1003_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-17 | 2024-05-14 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | INF | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-04
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A.2 | 131242-WST02-DR-S-7001_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-28 | 2024-05-14 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | INF | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-04
000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A.2 | 131242-WST02-DR-S-8001_ST616 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-28 | 2024-05-14 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000410&&000426 | 2024-03-28 | 2024-04-26 | A.2 | INF | For Information | 3 | "ST616_Amendment of ST605 (Main Water Tank Piling Design)" && "ST616 _Amendment of ST605 (IFC Drawings) " |  | 2024-04
000427 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 0 | 131242-WSW41-CL-S-0004 | 2024-04-08 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-22 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000427 | 2024-04-08 | 2024-04-23 | 1 | NAP | Approved | 2 | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" |  | 2024-04
000427 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 1 | 131242-WSW41-CL-S-0004 | 2024-04-23 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.1: Approved | 2024-05-14 | 2024-05-02 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000427 | 2024-04-08 | 2024-04-23 | 1 | APP | Approved | 2 | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608 | 0 | 131242-WST02-CL-S-0002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | 0 | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1005_ST608 | A | 131242-WST02-DR-S-1005_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST608 | A | 131242-WST02-DR-S-1001_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST608 | A | 131242-WST02-DR-S-1002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2000_ST608 | A | 131242-WST02-DR-S-2000_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST608 | A | 131242-WST02-DR-S-3000_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST608 | A | 131242-WST02-DR-S-1003_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2001_ST608 | A | 131242-WST02-DR-S-2001_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3001_ST608 | A | 131242-WST02-DR-S-3001_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST608 | A | 131242-WST02-DR-S-1004_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2002_ST608 | A | 131242-WST02-DR-S-2002_ST608 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-04-09 | 2024-04-09 | A | NAP | Not Approved | 1 | "ST608 - SSN-Shelters (Conceptual Design Submission) " |  | 2024-04
000428 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608 | B | 131242-WST00-DR-S-8005_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-10 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608 | B | 131242-WST02-DR-S-0302_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608 | B | 131242-WST02-DR-S-1200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608 | B | 131242-WST02-DR-S-1201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608 | B | 131242-WST02-DR-S-1202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608 | B | 131242-WST02-DR-S-1203_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608 | B | 131242-WST02-DR-S-1204_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608 | B | 131242-WST02-DR-S-1205_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608 | B | 131242-WST02-DR-S-2200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608 | B | 131242-WST02-DR-S-2201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608 | B | 131242-WST02-DR-S-2202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608 | B | 131242-WST02-DR-S-2203_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608 | B | 131242-WST02-DR-S-3200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608 | B | 131242-WST02-DR-S-3201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608 | B | 131242-WST02-DR-S-3202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608 | B | 131242-WST02-DR-S-5200_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608 | B | 131242-WST02-DR-S-5201_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608 | B | 131242-WST02-DR-S-5202_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608 | B | 131242-WST02-DR-S-5203_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608 | B | 131242-WST02-DR-S-5204_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608 | B | 131242-WST02-DR-S-5205_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608 | B | 131242-WST02-DR-S-5206_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608 | B | 131242-WST02-DR-S-5207_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608 | B | 131242-WST02-DR-S-5208_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608 | B | 131242-WST02-DR-S-5209_ST608 | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000428 | 2024-09-20 | 2024-09-20 | B | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-09
000428 | 02 | Aaron | CSA | NA | 131242 | WST02 | NA | C | NA | CES REPLY SHEET S428 | 131242-WST02-NA-C-NA | 2024-10-22 | ST608 – SSN Shelters Details | Rev.2: Not Approved. No updated drawings were submitted. | 2024-11-12 | 2024-12-18 | 41 | Not Approved | YES | 2025-01-07 | NO | Resubmitted | 0 |  |  | 000428 | 2024-10-22 | 2024-10-22 | CES REPLY SHEET S428 | NAP | Not Approved | 1 | "ST608 – SSN Shelters Details" |  | 2024-10
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A | 131242-WST02-DR-M-1022 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000161&&000429 | 2024-04-09 | 2024-10-05 | A.2 | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-04
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1023 | A | 131242-WST02-DR-M-1023 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429 | 2024-04-09 | 2024-04-09 | A | AWC | Approved with Comments | 1 | "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-04
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-M-1024 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" |  | 2024-04
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1025 | A | 131242-WST02-DR-M-1025 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" |  | 2024-04
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1026 | A | 131242-WST02-DR-M-1026 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429 | 2024-04-09 | 2024-04-09 | A | AWC | Approved with Comments | 1 | "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-04
000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1027 | A | 131242-WST02-DR-M-1027 | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000429 | 2024-04-09 | 2024-04-09 | A | AWC | Approved with Comments | 1 | "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-04
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A.1 | 131242-WST02-DR-M-1022 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 | 2025-02-26 00:00:00 | Shall update and submit under as built drawing | 000161&&000429 | 2024-04-09 | 2024-10-05 | A.2 | AWC | Approved with Comments | 3 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-07
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5011 | A.1 | 131242-WST02-DR-M-5011 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-07
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5012 | A.1 | 131242-WST02-DR-M-5012 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-07
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5013 | A.1 | 131242-WST02-DR-M-5013 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-07
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5014 | A.1 | 131242-WST02-DR-M-5014 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-07
000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5015 | A.1 | 131242-WST02-DR-M-5015 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | 36 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000161&&000429 | 2024-07-10 | 2024-10-05 | A.1 | AWC | Approved with Comments | 2 | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" |  | 2024-07
000430 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 0 | 131242-WSW41-SH-M-1002 | 2024-04-11 | Piping Special Item List | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-06-13 | 45 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000430 | 2024-04-11 | 2024-08-01 | 1 | INF | For Information | 2 | "Piping Special Item List" |  | 2024-04
000430 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 1 | 131242-WSW41-SH-M-1002 | 2024-08-01 | Piping Special Item List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-08-22 | 2024-09-02 | 22 | For Information | YES | 2024-09-20 | NO | Resubmitted | 0 | 2025-03-31 00:00:00 | Piping Special Item List is "For Information", will update after design is freezed. | 000430 | 2024-04-11 | 2024-08-01 | 1 | INF | For Information | 2 | "Piping Special Item List" |  | 2024-08
000431 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0028 | 0 | 131242-WSW41-LT-PM-0028 | 2024-04-12 | CV OF TEAM MEMBER (WSHO) | Not Approved. The proposed candidate doesn’t fully meet the requirement of 5 years’ experience as WSHO. Therefore, proposed candidate is disapproved. | 2024-05-13 | 2024-06-06 | 39 | Not Approved | YES | 2024-06-26 | NO | Resubmitted | 0 |  |  | 000431 | 2024-04-12 | 2024-04-12 | 0 | NAP | Not Approved | 1 | "CV OF TEAM MEMBER (WSHO)" |  | 2024-04
000432 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0002 | 0 | 131242-WSD11-BQ-P-0002 | 2024-04-12 | THP Valve List | Rev 0: For Information | 2024-05-13 | 2024-07-26 | 75 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000432 | 2024-04-12 | 2024-04-12 | 0 | INF | For Information | 1 | "THP Valve List" |  | 2024-04
000433 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-C-0007 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 | 14 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000380&&000433 | 2024-03-20 | 2024-06-20 | 1 | NAP | Approved with Comments | 3 | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" |  | 2024-04
000434 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0008 | 0 | 131242-WSW41-SP-C-0008 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 | 14 | Not Approved | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000434 | 2024-04-12 | 2024-04-12 | 0 | NAP | Not Approved | 1 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024" |  | 2024-04
000435 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0026 | 0 | 131242-WSW41-LT-PM-0026 | 2024-04-13 | Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project) | For Information | 2024-05-13 | 2024-05-10 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000435 | 2024-04-13 | 2024-04-13 | 0 | INF | For Information | 1 | "Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project)" |  | 2024-04
000436 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 0 | 131242-WST02-VI-I-0008 | 2024-04-15 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-14 | 2024-05-23 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000436 | 2024-04-15 | 2024-11-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (TSS Analyser - Optical)" |  | 2024-04
000436 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 1 | 131242-WST02-VI-I-0008 | 2024-11-28 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 1: Approved with comments. No need resubmission. Refer attached file for comments. | 2024-12-18 | 2025-03-25 | 83 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000436 | 2024-04-15 | 2024-11-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (TSS Analyser - Optical)" |  | 2024-11
000437 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | A.1 | 131242-WSW41-RT-PM-0011 | 2024-04-16 | C4B Monthly Progress Report Number No.11 (03 24) | Rejected as per CES request | 2024-05-15 | 2024-04-17 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000437 | 2024-04-16 | 2024-06-11 | 1 | REJ | Approved | 3 | "C4B Monthly Progress Report Number No.11 (03 24)" |  | 2024-04
000437 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | 0 | 131242-WSW41-RT-PM-0011 | 2024-04-18 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-05-09 | 2024-05-13 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000437 | 2024-04-16 | 2024-06-11 | 1 | AWC | Approved | 3 | "C4B Monthly Progress Report Number No.11 (03 24)" |  | 2024-04
000437 | 02 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | 1 | 131242-WSW41-RT-PM-0011 | 2024-06-11 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 2 - Approved | 2024-07-02 | 2024-06-18 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000437 | 2024-04-16 | 2024-06-11 | 1 | APP | Approved | 3 | "C4B Monthly Progress Report Number No.11 (03 24)" |  | 2024-06
000438 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 0 | 131242-WST02-VI-I-0007 | 2024-04-16 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-05-23 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" |  | 2024-04
000438 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 1 | 131242-WST02-VI-I-0007 | 2024-07-28 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-16 | 2024-09-18 | 37 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" |  | 2024-07
000438 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 2 | 131242-WST02-VI-I-0007 | 2024-10-18 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" |  | 2024-10
000438 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 3 | 131242-WST02-VI-I-0007 | 2025-02-27 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | 48 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000438 | 2024-04-16 | 2025-02-27 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" |  | 2025-02
000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | A | 131242-WST02-DR-E-3150 | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | NAP | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-04
000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | A | 131242-WST02-DR-E-3151 | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | NAP | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-04
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | C | 131242-WST02-DR-E-3150 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | B | 131242-WST02-DR-E-3151 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | C | 131242-WST02-DR-E-3153 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | C | 131242-WST02-DR-E-3154 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | C | 131242-WST02-DR-E-3155 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | B | 131242-WST02-DR-E-3156 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | C | 131242-WST02-DR-E-3158 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | C | 131242-WST02-DR-E-3159 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | C | 131242-WST02-DR-E-7010 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" |  | 2024-07
000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | C | 131242-WST02-DR-E-7011 | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | F | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-07
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | D | 131242-WST02-DR-E-3150 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | D | 131242-WST02-DR-E-3151 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | D | 131242-WST02-DR-E-3153 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | D | 131242-WST02-DR-E-3154 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | D | 131242-WST02-DR-E-3155 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | D | 131242-WST02-DR-E-3156 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | D | 131242-WST02-DR-E-3158 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | D | 131242-WST02-DR-E-3159 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | E | 131242-WST02-DR-E-7010 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" |  | 2024-10
000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | E | 131242-WST02-DR-E-7011 | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | F | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-10
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | E | 131242-WST02-DR-E-3150 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | E | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | D | 131242-WST02-DR-E-3151 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-04-16 | 2024-12-11 | D | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | D | 131242-WST02-DR-E-3153 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | E | 131242-WST02-DR-E-3154 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | E | 131242-WST02-DR-E-3155 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | D | 131242-WST02-DR-E-3156 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | C | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | D | 131242-WST02-DR-E-3158 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | D | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | E | 131242-WST02-DR-E-3159 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | E | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | F | 131242-WST02-DR-E-7010 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | AWC | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" |  | 2024-12
000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | F | 131242-WST02-DR-E-7011 | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | 46 | Approved with Comments | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000439 | 2024-07-12 | 2024-12-11 | F | AWC | Approved with Comments | 3 | "SSN Transformer Outline Drawing" |  | 2024-12
000440 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | 0 | 131242-WST02-DR-E-7010 | 2024-04-16 | SSN Transformer Marshalling Box Schematic Wiring Diagram | Rev 0: Rejected. Not required to resubmit. Please refer to attached comments sheet. | 2024-05-15 | 2024-05-20 | 24 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000439&&000440 | 2024-04-16 | 2024-12-11 | F | REJ | Approved with Comments | 4 | "SSN Transformer Outline Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" |  | 2024-04
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7005 | A | 131242-WST02-DR-I-7005 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441 | 2024-04-16 | 2024-04-16 | A | NAP | Not Approved | 1 | "SSN sample AC/DC/IO circuit diagram" |  | 2024-04
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7006 | A | 131242-WST02-DR-I-7006 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441 | 2024-04-16 | 2024-04-16 | A | NAP | Not Approved | 1 | "SSN sample AC/DC/IO circuit diagram" |  | 2024-04
000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7007 | A | 131242-WST02-DR-I-7007 | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000441 | 2024-04-16 | 2024-08-20 | B | NAP | Not Approved | 2 | "SSN sample AC/DC/IO circuit diagram" && "SSN IO Sample Schematic Drawing" |  | 2024-04
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7007 | B | 131242-WST02-DR-I-7007 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  | Pending from MP | 000441 | 2024-04-16 | 2024-08-20 | B | NAP | Not Approved | 2 | "SSN sample AC/DC/IO circuit diagram" && "SSN IO Sample Schematic Drawing" |  | 2024-08
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7008 | B | 131242-WST02-DR-I-7008 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" |  | 2024-08
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7009 | B | 131242-WST02-DR-I-7009 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" |  | 2024-08
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7010 | B | 131242-WST02-DR-I-7010 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441&&001333 | 2024-08-20 | 2025-05-30 | A | NAP | Not Approved | 2 | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" |  | 2024-08
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7011 | B | 131242-WST02-DR-I-7011 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441&&001333 | 2024-08-20 | 2025-05-30 | A | NAP | Not Approved | 2 | "SSN IO Sample Schematic Drawing" && "SSN Over All Network Archtecture Drawings" |  | 2024-08
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7012 | B | 131242-WST02-DR-I-7012 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" |  | 2024-08
000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7013 | B | 131242-WST02-DR-I-7013 | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | 42 | Not Approved | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000441 | 2024-08-20 | 2024-08-20 | B | NAP | Not Approved | 1 | "SSN IO Sample Schematic Drawing" |  | 2024-08
000442 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0038 | 0 | 131242-WSW41-CD-IM-0038 | 2024-04-17 | Milestone 1.2 - SSN Overall Changes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-16 | 2024-07-05 | 57 | Approved with Comments | YES | 2024-07-25 | NO | Resubmitted | 0 |  |  | 000442 | 2024-04-17 | 2024-04-17 | 0 | AWC | Approved with Comments | 1 | "Milestone 1.2 - SSN Overall Changes" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-S-0001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | A | 131242-WST02-DR-S-0002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | A | 131242-WST02-DR-S-0003_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | A | 131242-WST02-DR-S-1006_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | A | 131242-WST02-DR-S-1007_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | A | 131242-WST02-DR-S-1008_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | A | 131242-WST02-DR-S-3000_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | A | 131242-WST02-DR-S-5001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | A | 131242-WST02-DR-S-5002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | A | 131242-WST02-DR-S-7000_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | A | 131242-WST02-DR-S-7001_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | A | 131242-WST02-DR-S-7002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-S-8002_ST606_BCA | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | INF | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000444 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0009 | 0 | 131242-WSW41-SP-C-0009 | 2024-04-17 | Reinforcement Bar delivery & Testing Summary -February 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-02 | 11 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000444 | 2024-04-17 | 2024-04-17 | 0 | AWC | Approved with Comments | 1 | "Reinforcement Bar delivery & Testing Summary -February 2024" |  | 2024-04
000445 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 0001 | 0 | 131242-WSW41-SH-M-0001 | 2024-04-17 | Sidewide Piperack Line List | Rev 0: Not approved - Revise and Resubmit | 2024-05-16 | 2024-07-26 | 72 | Not Approved | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000445&&001749 | 2024-04-17 | 2025-10-16 | 0 | NAP | Approved with Comments | 2 | "Sidewide Piperack Line List" && "Line List for Hydrotest (Sitewide PipeRack)" |  | 2024-04
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000 | 0 | 131242-WSD11-DR-S-1000 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-04-19 | 2024-04-19 | 0 | NAP | Not Approved | 1 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-04
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001 | A | 131242-WSD11-DR-S-1001 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-04-19 | 2024-04-19 | A | NAP | Not Approved | 1 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-04
000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | A | 131242-WSD11-CL-S-0005 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | NAP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" |  | 2024-04
000446 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 1 | 131242-WSD11-CL-S-0005 | 2024-05-31 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-10 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | NAP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" |  | 2024-05
000446 | 02 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 5 | 131242-WSD11-CL-S-0005 | 2024-07-16 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-05 | 2024-08-16 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | NAP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" |  | 2024-07
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 7 | 131242-WSD11-CL-S-0005 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | AWC | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1400 | A | 131242-WSD11-DR-S-1400 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1401 | A | 131242-WSD11-DR-S-1401 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1402 | A | 131242-WSD11-DR-S-1402 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1403 | A | 131242-WSD11-DR-S-1403 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2400 | A | 131242-WSD11-DR-S-2400 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5400 | A | 131242-WSD11-DR-S-5400 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | AWC | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8003 | A | 131242-WSD11-DR-S-8003 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-08-28 | A | AWC | Approved with Comments | 1 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-08
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1400 | B | 131242-WSD11-DR-S-1400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1401 | B | 131242-WSD11-DR-S-1401 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1402 | B | 131242-WSD11-DR-S-1402 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1403 | B | 131242-WSD11-DR-S-1403 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 2400 | B | 131242-WSD11-DR-S-2400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5400 | B | 131242-WSD11-DR-S-5400 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-08-28 | 2024-10-07 | B | APP | Approved | 2 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000446 | 04 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8003 | B | 131242-WST00-DR-S-8003 | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446 | 2024-10-07 | 2024-10-07 | B | APP | Approved | 1 | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " |  | 2024-10
000447 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0011 | 0 | 131242-WSW41-SP-C-0011 | 2024-04-22 | Reinforcement Bar Test Reports -Rebar Size (H10 &H16) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-05-21 | 2024-05-02 | 8 | Approved with Comments | YES | 2024-05-22 | NO | Resubmitted | 0 |  |  | 000447 | 2024-04-22 | 2024-04-22 | 0 | AWC | Approved with Comments | 1 | "Reinforcement Bar Test Reports -Rebar Size (H10 &H16)" |  | 2024-04
000448 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 0 | 131242-WSW41-MS-C-0009 | 2024-04-24 | MSRA,SWP for Bored Piling WLT | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-24 | 2024-05-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000448 | 2024-04-24 | 2024-05-10 | 1 | NAP | Approved | 2 | "MSRA,SWP for Bored Piling WLT" |  | 2024-04
000448 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 1 | 131242-WSW41-MS-C-0009 | 2024-05-10 | MSRA,SWP for Bored Piling WLT | Rev.1: Approved | 2024-05-31 | 2024-05-20 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000448 | 2024-04-24 | 2024-05-10 | 1 | APP | Approved | 2 | "MSRA,SWP for Bored Piling WLT" |  | 2024-05
000449 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | VI | S | 0003 | 0 | 131242-WSW41-VI-S-0003 | 2024-04-25 | Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd) | Approved | 2024-05-27 | 2024-05-02 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000449 | 2024-04-25 | 2024-04-25 | 0 | APP | Approved | 1 | "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" |  | 2024-04
000450 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0004 | 0 | 131242-WSW41-VI-S-0004 | 2024-04-25 | Vendor Approval of ERSS Works (Singlee) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-02 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000450 | 2024-04-25 | 2024-04-25 | 0 | NAP | Not Approved | 1 | "Vendor Approval of ERSS Works (Singlee)" |  | 2024-04
000450 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | G | 0002 | 0 | 131242-WSW41-VI-G-0002 | 2024-07-09 | Vendor Approval of ERSS Works (Singlee) | Rev.1: Not Approved. Submission incomplete, proposed vendor is different in R0 and R1. Please resubmit with comment respond sheet. | 2024-07-29 | 2024-07-17 | 6 | Not Approved | YES | 2024-08-06 | NO | Resubmitted | 0 |  |  | 000450 | 2024-07-09 | 2024-07-09 | 0 | NAP | Not Approved | 1 | "Vendor Approval of ERSS Works (Singlee)" |  | 2024-07
000451 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0010 | 0 | 131242-WSW41-PC-W-0010 | 2024-04-25 | Payment Claim No.10 | Rev(0): Approved. Please refer to S.O. correspondence no. 15 dated 7 May 2024. | 2024-05-27 | 2024-05-13 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000451 | 2024-04-25 | 2024-04-25 | 0 | APP | Approved | 1 | "Payment Claim No.10" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-S-8002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide latest DGN & PDF drawing | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-S-0001_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | A | 131242-WST02-DR-S-0002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | A | 131242-WST02-DR-S-0003_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | A | 131242-WST02-DR-S-5001_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | A | 131242-WST02-DR-S-5002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | A | 131242-WST02-DR-S-1006_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | A | 131242-WST02-DR-S-1007_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | A | 131242-WST02-DR-S-1008_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | A | 131242-WST02-DR-S-7000_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | A | 131242-WST02-DR-S-7001_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | A | 131242-WST02-DR-S-7002_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | A | 131242-WST02-DR-S-3000_ST606_BCA | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | 16 | Approved with Comments | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000443&&000452 | 2024-04-17 | 2024-04-26 | A | AWC | Approved with Comments | 2 | "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" && "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" |  | 2024-04
000453 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0011 | 0 | 131242-WSW41-PS-PM-0011 | 2024-04-26 | Monthly Progress Presentation No. 11 (0324) | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000453 | 2024-04-26 | 2024-04-26 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 11 (0324)" |  | 2024-04
000454 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0011 | 0 | 131242-WSW41-MI-PM-0011 | 2024-04-26 | Monthly Progress Meeting Minutes 0011_20240423 | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000454 | 2024-04-26 | 2024-04-26 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0011_20240423" |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | B | 131242-WST02-DR-C-8001_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  | To close after addressing the comments of S#475 & S#128.3. | 000455&&000466 | 2024-04-30 | 2024-05-07 | 0 | NAP | Not Approved | 2 | "ST610 – Underground Services (BCA Submission File) " && "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610_BCA | B | 131242-WST02-DR-C-1023_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610_BCA | B | 131242-WST02-DR-C-1024_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610_BCA | B | 131242-WST02-DR-C-3000_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610_BCA | B | 131242-WST02-DR-C-3001_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610_BCA | B | 131242-WST02-DR-C-5004_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610_BCA | B | 131242-WST02-DR-C-5005_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610_BCA | B | 131242-WST02-DR-C-5006_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610_BCA | B | 131242-WST02-DR-C-5007_ST610_BCA | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | 14 | Not Approved | YES | 2024-06-07 | NO | Resubmitted | 0 |  |  | 000455 | 2024-04-30 | 2024-04-30 | B | NAP | Not Approved | 1 | "ST610 – Underground Services (BCA Submission File) " |  | 2024-04
000456 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 0 | 131242-WSW41-QA-M-0002 | 2024-04-30 | Inspection and test plan for Compressed Air System | Rev 0: Not approved - Revise and Resubmit | 2024-05-30 | 2024-07-15 | 54 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000456 | 2024-04-30 | 2024-07-22 | 1 | NAP | Approved | 2 | "Inspection and test plan for Compressed Air System" |  | 2024-04
000456 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 1 | 131242-WSW41-QA-M-0002 | 2024-07-22 | Inspection and test plan for Compressed Air System | Rev 1: Approved | 2024-08-12 | 2024-08-20 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000456 | 2024-04-30 | 2024-07-22 | 1 | APP | Approved | 2 | "Inspection and test plan for Compressed Air System" |  | 2024-07
000457 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0008 | 0 | 131242-WSW41-PS-HS-0008 | 2024-04-30 | Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024 | For Information | 2024-05-30 | 2024-06-06 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000457 | 2024-04-30 | 2024-04-30 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" |  | 2024-04
000458 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 0 | 131242-WST02-DS-E-0007 | 2024-04-30 | SSN Transformer Data Sheet | Rev 0: Approved with comments. To revise and resubmit.Please refer to attached file for comments. | 2024-05-30 | 2024-05-20 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000458 | 2024-04-30 | 2024-10-15 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Data Sheet" |  | 2024-04
000458 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 1 | 131242-WST02-DS-E-0007 | 2024-07-09 | SSN Transformer Data Sheet | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-29 | 2024-09-10 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000458 | 2024-04-30 | 2024-10-15 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Data Sheet" |  | 2024-07
000458 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 2 | 131242-WST02-DS-E-0007 | 2024-10-15 | SSN Transformer Data Sheet | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-05 | 2024-11-04 | 14 | Approved with Comments | YES | 2024-11-22 | NO | Resubmitted | 0 |  |  | 000458 | 2024-04-30 | 2024-10-15 | 2 | AWC | Approved with Comments | 3 | "SSN Transformer Data Sheet" |  | 2024-10
000459 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0009 | 0 | 131242-WST02-VI-I-0009 | 2024-05-02 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-31 | 2024-07-02 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 00:00:00 |  | 000459 | 2024-05-02 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Radar Level Transmitter)" |  | 2024-05
000459 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 1 | 131242-WST02-VI-I-0009 | 2024-07-30 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-18 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000459 | 2024-05-02 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Radar Level Transmitter)" |  | 2024-07
000459 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 2 | 131242-WST02-VI-I-0009 | 2025-02-27 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000459 | 2024-05-02 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Radar Level Transmitter)" |  | 2025-02
000460 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0021 | 0 | 131242-WSW41-MI-P-0021 | 2024-05-02 | Process & MEICA Meeting Minutes 0021_20240328 | For information | 2024-05-31 | 2024-07-26 | 61 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000460 | 2024-05-02 | 2024-05-02 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0021_20240328" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1000 | 0 | 131242-WST02-DR-M-1000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 | 2025-02-28 00:00:00 | 2nd priority | 000461 | 2024-05-06 | 2024-05-06 | 0 | AWC | Approved with Comments | 1 | "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000164&&000461 | 2024-05-06 | 2025-10-31 | 0 | AWC | Approved with Comments | 3 | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4001 | 0 | 131242-WST02-DR-M-4001 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000163&&000461 | 2024-05-06 | 2025-04-28 | A | AWC | Approved with Comments | 2 | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4002 | 0 | 131242-WST02-DR-M-4002 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000162&&000461 | 2024-05-06 | 2025-10-27 | A | AWC | Not Approved | 3 | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4003 | 0 | 131242-WST02-DR-M-4003 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000461 | 2024-05-06 | 2024-05-06 | 0 | AWC | Approved with Comments | 1 | "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4004 | 0 | 131242-WST02-DR-M-4004 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000191&&000461 | 2024-05-06 | 2025-05-15 | 0 | AWC | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7000 | 0 | 131242-WST02-DR-M-7000 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | 59 | Approved with Comments | YES | 2024-08-15 | NO | Resubmitted | 0 |  |  | 000461 | 2024-05-06 | 2024-05-06 | 0 | AWC | Approved with Comments | 1 | "SSN Overall GA & Equipment Layout Drawings" |  | 2024-05
000462 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 0 | 131242-WST02-VI-I-0010 | 2024-05-07 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2024-07-26 00:00:00 |  | 000462 | 2024-05-07 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" |  | 2024-05
000462 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 1 | 131242-WST02-VI-I-0010 | 2024-08-01 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000462 | 2024-05-07 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" |  | 2024-08
000462 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 2 | 131242-WST02-VI-I-0010 | 2025-02-27 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000462 | 2024-05-07 | 2025-02-27 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Tuning Fork Level Switches)" |  | 2025-02
000463 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 0 | 131242-WST02-VI-I-0011 | 2024-05-07 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000463 | 2024-05-07 | 2024-11-09 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" |  | 2024-05
000463 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 1 | 131242-WST02-VI-I-0011 | 2024-07-24 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-18 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000463 | 2024-05-07 | 2024-11-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" |  | 2024-07
000463 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 2 | 131242-WST02-VI-I-0011 | 2024-11-09 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000463 | 2024-05-07 | 2024-11-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" |  | 2024-11
000464 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 0 | 131242-WST02-VI-I-0012 | 2024-05-07 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000464 | 2024-05-07 | 2024-11-08 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of SSN Package (Capacitive Level Switches)" |  | 2024-05
000464 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 1 | 131242-WST02-VI-I-0012 | 2024-08-01 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000464 | 2024-05-07 | 2024-11-08 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Capacitive Level Switches)" |  | 2024-08
000464 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 2 | 131242-WST02-VI-I-0012 | 2024-11-08 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000464 | 2024-05-07 | 2024-11-08 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Capacitive Level Switches)" |  | 2024-11
000465 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 0 | 131242-WSW41-MS-C-0010 | 2024-05-07 | MSRA,SWP for Bored Piling PDA Test | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-06-12 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000465 | 2024-05-07 | 2024-06-19 | 1 | AWC | Approved | 2 | "MSRA,SWP for Bored Piling PDA Test" |  | 2024-05
000465 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 1 | 131242-WSW41-MS-C-0010 | 2024-06-19 | MSRA,SWP for Bored Piling PDA Test | Approved | 2024-07-09 | 2024-07-01 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000465 | 2024-05-07 | 2024-06-19 | 1 | APP | Approved | 2 | "MSRA,SWP for Bored Piling PDA Test" |  | 2024-06
000466 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | 0 | 131242-WST02-DR-C-8001_ST610_BCA | 2024-05-07 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-05-20 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000455&&000466 | 2024-04-30 | 2024-05-07 | 0 | NAP | Not Approved | 2 | "ST610 – Underground Services (BCA Submission File) " && "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " |  | 2024-05
000466 | 01 | Aaron | CSA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply 2024 06 12 | NA | 131242-NA-NA-NA-Cmt Sheet Reply 2024 06 12 | 2024-06-12 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 | 13 | Not Approved | YES | 2024-07-19 | NO | Resubmitted | 0 |  | To close after addressing the comments of S#475, S#128.3 | 000466 | 2024-06-12 | 2024-06-12 | NA | NAP | Not Approved | 1 | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " |  | 2024-06
000467 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0039 | 0 | 131242-WSW41-CD-IM-0039 | 2024-05-08 | Submission Of BIM Coordination VCM Model (Apr-2024) | For Information | 2024-06-06 | 2024-05-21 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000467 | 2024-05-08 | 2024-05-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Apr-2024)" |  | 2024-05
000468 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 0 | 131242-WST02-RT-C-0001 | 2024-05-09 | Design for Safety Report 2 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-06 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | NAP | Approved with Comments | 4 | "Design for Safety Report 2" |  | 2024-05
000468 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 1 | 131242-WST02-RT-C-0001 | 2024-06-07 | Design for Safety Report 2 | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-05 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | NAP | Approved with Comments | 4 | "Design for Safety Report 2" |  | 2024-06
000468 | 02 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-C-0001 | 2024-08-21 | Design for Safety Report 2 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-17 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | AWC | Approved with Comments | 4 | "Design for Safety Report 2" |  | 2024-08
000468 | 03 | Leslie | Project | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-C-0001 | 2024-11-03 | Design for Safety Report 2 | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-12-07 | 25 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000468 | 2024-05-09 | 2024-11-03 | 2 | AWC | Approved with Comments | 4 | "Design for Safety Report 2" |  | 2024-11
000469 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | C | 0005 | 0 | 131242-WSW41-CL-C-0005 | 2024-05-10 | Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47) | Rev.0: Approved | 2024-06-10 | 2024-05-20 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000469 | 2024-05-10 | 2024-05-10 | 0 | APP | Approved | 1 | "Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47)" |  | 2024-05
000470 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0022 | 0 | 131242-WSW41-MI-P-0022 | 2024-05-13 | Process & MEICA Meeting Minutes 0022_20240425 | Rev 0: For Information | 2024-06-11 | 2024-08-14 | 67 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000470 | 2024-05-13 | 2024-05-13 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0022_20240425" |  | 2024-05
000471 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000 | 0 | 131242-WST02-DR-A-1000 | 2024-05-13 | NEA Waiver Submission of SSN Plant | For Information | 2024-06-11 | 2024-05-24 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | INF | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" |  | 2024-05
000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0022 | 0 | 131242-WSW41-MI-C-0022 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000472 | 2024-05-17 | 2024-05-17 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" |  | 2024-05
000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0023 | 0 | 131242-WSW41-MI-C-0023 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000472 | 2024-05-17 | 2024-05-17 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" |  | 2024-05
000473 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 0 | 131242-WSW41-RT-PM-0012 | 2024-04-18 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-05-17 | 2024-06-03 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000473 | 2024-04-18 | 2024-06-11 | 1 | AWC | Approved | 2 | "C4B Monthly Progress Report Number No.12 (04 24)" |  | 2024-04
000473 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 1 | 131242-WSW41-RT-PM-0012 | 2024-06-11 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 1 - Approved | 2024-07-02 | 2024-06-18 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000473 | 2024-04-18 | 2024-06-11 | 1 | APP | Approved | 2 | "C4B Monthly Progress Report Number No.12 (04 24)" |  | 2024-06
000474 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 0 | 131242-WSW41-VI-M-1010 | 2024-05-18 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 0: Not approved - Revise and Resubmit | 2024-06-18 | 2024-07-04 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000474 | 2024-05-18 | 2024-10-17 | 2 | NAP | Approved with Comments | 3 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" |  | 2024-05
000474 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 1 | 131242-WSW41-VI-M-1010 | 2024-09-06 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 1: Not approved - Revise and Resubmit | 2024-09-26 | 2024-09-12 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000474 | 2024-05-18 | 2024-10-17 | 2 | NAP | Approved with Comments | 3 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" |  | 2024-09
000474 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 2 | 131242-WSW41-VI-M-1010 | 2024-10-17 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-07 | 2024-11-15 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000474 | 2024-05-18 | 2024-10-17 | 2 | AWC | Approved with Comments | 3 | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" |  | 2024-10
000475 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-C-8001_ST610 | 2024-05-18 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-05
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | C | 131242-WST02-DR-C-1023_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | C | 131242-WST02-DR-C-1024_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | C | 131242-WST02-DR-C-5004_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | C | 131242-WST02-DR-C-5005_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | C | 131242-WST02-DR-C-5006_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | C | 131242-WST02-DR-C-3000_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | C | 131242-WST02-DR-C-3001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | C | 131242-WST02-DR-C-5007_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | 0 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-C-8001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | C | 131242-WST02-DR-C-1023_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | C | 131242-WST02-DR-C-1024_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | C | 131242-WST02-DR-C-5004_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | C | 131242-WST02-DR-C-5005_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | C | 131242-WST02-DR-C-5006_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | C | 131242-WST02-DR-C-3000_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | C | 131242-WST02-DR-C-3001_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | NAP | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | C | 131242-WST02-DR-C-5007_ST610 | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | NAP | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-06
000475 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | D | 131242-WST00-DR-C-8001_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | D | 131242-WST02-DR-C-1023_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | D | 131242-WST02-DR-C-1024_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | D | 131242-WST02-DR-C-5004_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | D | 131242-WST02-DR-C-5005_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | D | 131242-WST02-DR-C-5006_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | D | 131242-WST02-DR-C-3000_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | D | 131242-WST02-DR-C-3001_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-12-29 | 2024-07-11 | D | AWC | Approved with Comments | 5 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | D | 131242-WST02-DR-C-5007_ST610 | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000128&&000475 | 2023-10-16 | 2024-07-11 | D | AWC | Approved with Comments | 6 | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " && "IFC of ST610 (Underground Services) " |  | 2024-07
000475 | 03 | Zora | CSA | NA | 131242 | WST02 | NA | C | Cmt Sheet Reply 2024 10 07 | NA | 131242-WST02-NA-C-Cmt Sheet Reply 2024 10 07 | 2024-10-09 | IFC of ST610 (Underground Services) | Rev.3: Approved with comments. | 2024-10-29 | 2024-10-24 | 11 | Approved with Comments | YES | 2024-11-13 | NO | Resubmitted | 0 |  |  | 000475 | 2024-10-09 | 2024-10-09 | NA | AWC | Approved with Comments | 1 | "IFC of ST610 (Underground Services) " |  | 2024-10
000476 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 0 | 131242-WST02-VI-I-0016 | 2024-05-21 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-20 | 2024-07-02 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-20 00:00:00 |  | 000476 | 2024-05-21 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductive Probe Level Switches)" |  | 2024-05
000476 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 1 | 131242-WST02-VI-I-0016 | 2025-03-17 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000476 | 2024-05-21 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Conductive Probe Level Switches)" |  | 2025-03
000477 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0023 | 0 | 131242-WSW41-MI-P-0023 | 2024-05-23 | Process & MEICA Meeting Minutes 0023_20240509 | Rev 0: For Information | 2024-06-21 | 2024-08-14 | 59 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000477 | 2024-05-23 | 2024-05-23 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0023_20240509" |  | 2024-05
000478 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CN | S | 0001 | 0 | 131242-WSD11-CN-S-0001 | 2024-05-23 | Handrail design loading & Testing of THP Train by CAMBI | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-03 | 7 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  | Resubmission on hold and to resubmit after BCA approval of CAMBI Steel Structure | 000478 | 2024-05-23 | 2024-05-23 | 0 | NAP | Not Approved | 1 | "Handrail design loading & Testing of THP Train by CAMBI" |  | 2024-05
000479 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0001 | 0 | 131242-WSD11-CN-E-0001 | 2024-05-23 | Proposed change of SS316 Cable Tray within THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-18 | 18 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000479 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Proposed change of SS316 Cable Tray within THP Module" |  | 2024-05
000480 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0002 | 0 | 131242-WSD11-CN-E-0002 | 2024-05-23 | Proposed change of Carbon loaded GRP Junction Box within THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | 30 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000480 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Proposed change of Carbon loaded GRP Junction Box within THP Module" |  | 2024-05
000481 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0003 | 0 | 131242-WSD11-CN-E-0003 | 2024-05-23 | Separate Terminal Box for Motor Space Heater | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 | 14 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000481 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Separate Terminal Box for Motor Space Heater" |  | 2024-05
000482 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0004 | 0 | 131242-WSD11-CN-E-0004 | 2024-05-23 | Local Control Station with THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 | 14 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000482 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Local Control Station with THP Module" |  | 2024-05
000483 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | I | 0002 | 0 | 131242-WSD11-CN-I-0002 | 2024-05-23 | Pressure Instrument Mounting in THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | 30 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000483 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Pressure Instrument Mounting in THP Module" |  | 2024-05
000484 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | M | 0001 | 0 | 131242-WSD11-CN-M-0001 | 2024-05-23 | Pump Color within THP Module | Rev 0: Rejected Refer to attached file for comments. | 2024-06-21 | 2024-08-08 | 55 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000484 | 2024-05-23 | 2024-05-23 | 0 | REJ | Rejected | 1 | "Pump Color within THP Module" |  | 2024-05
000485 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0020 | 0 | 131242-WSW41-VI-E-0020 | 2024-05-23 | Vendor Approval of Electrical Installer (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-21 | 2024-07-04 | 30 | Approved with Comments | YES | 2024-07-24 | NO | Resubmitted | 0 |  |  | 000485 | 2024-05-23 | 2024-05-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Electrical Installer (Cyclect)" |  | 2024-05
000486 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | I | 0020 | 0 | 131242-WSW41-VI-I-0020 | 2024-05-23 | Vendor Approval of ICA Installer Submission (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-21 | 2024-07-02 | 28 | Approved with Comments | YES | 2024-07-22 | NO | Resubmitted | 0 |  |  | 000486 | 2024-05-23 | 2024-05-23 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of ICA Installer Submission (Cyclect)" |  | 2024-05
000487 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | K | 0001 | 0 | 131242-WSW41-MS-K-0001 | 2024-05-27 | MSRA & SWP for Mobilization and Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 | 10 | Approved with Comments | YES | 2024-06-28 | NO | Resubmitted | 0 |  |  | 000487 | 2024-05-27 | 2024-05-27 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP for Mobilization and Demobilization of Machinery" |  | 2024-05
000488 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0001 | 0 | 131242-WSW41-MS-G-0001 | 2024-05-27 | MSRA & SWP for Sheet Piling Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 | 10 | Not Approved | YES | 2024-06-28 | NO | Resubmitted | 0 |  |  | 000488 | 2024-05-27 | 2024-05-27 | 0 | NAP | Not Approved | 1 | "MSRA & SWP for Sheet Piling Work" |  | 2024-05
000489 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0002 | 0 | 131242-WST02-RT-C-0002 | 2024-05-28 | Project Safety Review for ERSS | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-18 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000489 | 2024-05-28 | 2024-07-09 | 1 | AWC | Approved with Comments | 2 | "Project Safety Review for ERSS" |  | 2024-05
000489 | 01 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0002 | 1 | 131242-WST02-RT-C-0002 | 2024-07-09 | Project Safety Review for ERSS | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-29 | 2024-08-12 | 24 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000489 | 2024-05-28 | 2024-07-09 | 1 | AWC | Approved with Comments | 2 | "Project Safety Review for ERSS" |  | 2024-07
000490 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 0 | 131242-WST02-RT-C-0003 | 2024-05-28 | Report of DFS (Guide 3) for ERSS | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-13 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000490 | 2024-05-28 | 2024-06-19 | 1 | NAP | Approved | 2 | "Report of DFS (Guide 3) for ERSS" |  | 2024-05
000490 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 1 | 131242-WST02-RT-C-0003 | 2024-06-19 | Report of DFS (Guide 3) for ERSS | Rev.1: Approved | 2024-07-09 | 2024-07-12 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000490 | 2024-05-28 | 2024-06-19 | 1 | APP | Approved | 2 | "Report of DFS (Guide 3) for ERSS" |  | 2024-06
000491 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0030 | 0 | 131242-WSW41-LT-PM-0030 | 2024-05-28 | CV of Team member (Planner) | Rev. 0 - Approved with comments. Please refer to attached comment sheet | 2024-06-26 | 2024-06-10 | 9 | Approved with Comments | YES | 2024-06-28 | NO | Resubmitted | 0 |  |  | 000491 | 2024-05-28 | 2024-05-28 | 0 | AWC | Approved with Comments | 1 | "CV of Team member (Planner)" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | A | 131242-WST02-DR-M-5000 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | A | 131242-WST02-DR-M-5001 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | A | 131242-WST02-DR-M-5002 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | A | 131242-WST02-DR-M-5003 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | A | 131242-WST02-DR-M-5004 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | A | 131242-WST02-DR-M-5005 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | A | 131242-WST02-DR-M-5006 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | A | 131242-WST02-DR-M-5007 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | A | 131242-WST02-DR-M-5008 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7001 | A | 131242-WST02-SH-M-7001 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7002 | A | 131242-WST02-SH-M-7002 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7003 | A | 131242-WST02-SH-M-7003 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7004 | A | 131242-WST02-SH-M-7004 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7005 | A | 131242-WST02-SH-M-7005 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7006 | A | 131242-WST02-SH-M-7006 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7007 | A | 131242-WST02-SH-M-7007 | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2024-05-28 | A | AWC | Approved with Comments | 1 | "SSN Cast-in Schedule & Details" |  | 2024-05
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | B | 131242-WST02-DR-M-5000 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | B | 131242-WST02-DR-M-5001 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | B | 131242-WST02-DR-M-5002 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | B | 131242-WST02-DR-M-5003 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | B | 131242-WST02-DR-M-5004 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | B | 131242-WST02-DR-M-5005 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | B | 131242-WST02-DR-M-5006 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | B | 131242-WST02-DR-M-5007 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | B | 131242-WST02-DR-M-5008 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7001 | B | 131242-WST02-DR-M-7001 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7002 | B | 131242-WST02-DR-M-7002 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7003 | B | 131242-WST02-DR-M-7003 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7004 | B | 131242-WST02-DR-M-7004 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7005 | B | 131242-WST02-DR-M-7005 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7006 | B | 131242-WST02-DR-M-7006 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7007 | B | 131242-WST02-DR-M-7007 | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | 33 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2024-10
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | C.1 | 131242-WST02-DR-M-5000 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | C.1 | 131242-WST02-DR-M-5001 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | C.1 | 131242-WST02-DR-M-5002 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | C.1 | 131242-WST02-DR-M-5003 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | C.1 | 131242-WST02-DR-M-5004 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | C.1 | 131242-WST02-DR-M-5005 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | C.1 | 131242-WST02-DR-M-5006 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | C.1 | 131242-WST02-DR-M-5007 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | C.1 | 131242-WST02-DR-M-5008 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-05-28 | 2025-02-26 | C.1 | AWC | Approved with Comments | 3 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7001 | C.2 | 131242-WST02-DR-M-7001 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7002 | C.1 | 131242-WST02-DR-M-7002 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7003 | C.1 | 131242-WST02-DR-M-7003 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7004 | C.1 | 131242-WST02-DR-M-7004 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7005 | C.1 | 131242-WST02-DR-M-7005 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.1 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7006 | C.2 | 131242-WST02-DR-M-7006 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7007 | C.2 | 131242-WST02-DR-M-7007 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | 43 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 63 |  |  | 000492 | 2024-10-21 | 2025-02-26 | C.2 | AWC | Approved with Comments | 2 | "SSN Cast-in Schedule & Details" |  | 2025-02
000493 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0015 | 0 | 131242-WSW41-VI-C-0015 | 2024-05-29 | Vendor Approval of Testing Laboratory (TUV) | Approved | 2024-06-27 | 2024-06-03 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000493 | 2024-05-29 | 2024-05-29 | 0 | APP | Approved | 1 | "Vendor Approval of Testing Laboratory (TUV)" |  | 2024-05
000494 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 0 | 131242-WSW41-MS-C-0011 | 2024-05-29 | Method Statement for Concrete Temperature Control and Monitoring | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-10 | 8 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000494 | 2024-05-29 | 2024-07-28 | 2 | NAP | Approved with Comments | 3 | "Method Statement for Concrete Temperature Control and Monitoring" |  | 2024-05
000494 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 1 | 131242-WSW41-MS-C-0011 | 2024-06-18 | Method Statement for Concrete Temperature Control and Monitoring | Rev.1:Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-08 | 2024-07-25 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000494 | 2024-05-29 | 2024-07-28 | 2 | AWC | Approved with Comments | 3 | "Method Statement for Concrete Temperature Control and Monitoring" |  | 2024-06
000494 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 2 | 131242-WSW41-MS-C-0011 | 2024-07-28 | Method Statement for Concrete Temperature Control and Monitoring | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2024-08-16 | 2024-08-13 | 11 | Approved with Comments | YES | 2024-09-02 | NO | Resubmitted | 0 |  |  | 000494 | 2024-05-29 | 2024-07-28 | 2 | AWC | Approved with Comments | 3 | "Method Statement for Concrete Temperature Control and Monitoring" |  | 2024-07
000495 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SU | K | 0001 | 0 | 131242-WSW41-SU-K-0001 | 2024-05-29 | Time Lapse Surveys_Apr 24 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-03 | 3 | Not Approved | YES | 2024-06-21 | NO | Resubmitted | 0 |  |  | 000495 | 2024-05-29 | 2024-05-29 | 0 | NAP | Not Approved | 1 | "Time Lapse Surveys_Apr 24" |  | 2024-05
000496 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0029 | 0 | 131242-WSW41-LT-PM-0029 | 2024-05-30 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24 | Rev(0): Received for S.O.'s assessment. Please refer to S.O. correspondence no. 211 dated 22 Aug 2024. | 2024-06-28 | 2024-08-26 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000496 | 2024-05-30 | 2024-05-30 | 0 | INF | For Information | 1 | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24" |  | 2024-05
000497 | 00 | Low | EICA | NA | 131242 | WSD11 | CN | I | 0001 | 0 | 131242-WSD11-CN-I-0001 | 2024-05-30 | General Deviation from ICA G & P Spec | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-27 | 63 | Rejected | YES | 2024-09-16 | NO | Resubmitted | 0 |  | (RFC) NO.: 1230207-RFC-0013 | 000497 | 2024-05-30 | 2024-05-30 | 0 | REJ | Rejected | 1 | "General Deviation from ICA G & P Spec" |  | 2024-05
000498 | 00 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0012 | 0 | 131242-WSW41-SP-C-0012 | 2024-05-30 | Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-06-12 | 9 | Approved with Comments | YES | 2024-07-02 | NO | Resubmitted | 0 |  |  | 000498 | 2024-05-30 | 2024-05-30 | 0 | AWC | Approved with Comments | 1 | "Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115)" |  | 2024-05
000499 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 0 | 131242-WSD11-VI-M-0002 | 2024-05-30 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-28 | 2024-07-18 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000499 | 2024-05-30 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" |  | 2024-05
000499 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 1 | 131242-WSD11-VI-M-0002 | 2025-03-14 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | 82 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 000499 | 2024-05-30 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" |  | 2025-03
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601_BCA | B | 131242-WST00-DR-G-8000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | B | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601_BCA | C | 131242-WST00-DR-G-0001_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601_BCA | C | 131242-WST00-DR-G-0002_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601_BCA | C | 131242-WST00-DR-G-1000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601_BCA | C | 131242-WST00-DR-G-1001_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601_BCA | C | 131242-WST00-DR-G-1002_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601_BCA | C | 131242-WST00-DR-G-1003_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601_BCA | C | 131242-WST00-DR-G-1004_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601_BCA | C | 131242-WST00-DR-G-3000_ST601_BCA | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000500 | 2024-05-31 | 2024-05-31 | C | INF | For Information | 1 | "BCA Approval of ST601 – ERSS < 4m " |  | 2024-05
000501 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 0 | 131242-WST02-VI-I-0014 | 2024-05-31 | Vendor Approval of SSN Package (Thermal Flow Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 36 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000501 | 2024-05-31 | 2025-01-08 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow Switches)" |  | 2024-05
000501 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 1 | 131242-WST02-VI-I-0014 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow Switches) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-05-06 | 84 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000501 | 2024-05-31 | 2025-01-08 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow Switches)" |  | 2025-01
000502 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 0 | 131242-WST02-VI-I-0015 | 2024-05-31 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000502 | 2024-05-31 | 2024-08-27 | 1 | AWC | Approved | 2 | "Vendor Approval of SSN Package (Pressure Gauges)" |  | 2024-05
000502 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 1 | 131242-WST02-VI-I-0015 | 2024-08-27 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 1: Approved. | 2024-09-16 | 2024-11-08 | 53 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000502 | 2024-05-31 | 2024-08-27 | 1 | APP | Approved | 2 | "Vendor Approval of SSN Package (Pressure Gauges)" |  | 2024-08
000503 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 0 | 131242-WST02-VI-I-0013 | 2024-06-01 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000503 | 2024-06-01 | 2025-01-08 | 1 | NAP | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" |  | 2024-06
000503 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 1 | 131242-WST02-VI-I-0013 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-03-17 | 48 | Approved with Comments | YES | 2025-04-04 | NO | Resubmitted | 0 |  |  | 000503 | 2024-06-01 | 2025-01-08 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" |  | 2025-01
000504 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 0 | 131242-WSW41-VI-M-1011 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-01 | 2024-07-18 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000504 | 2024-06-01 | 2024-11-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" |  | 2024-06
000504 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 1 | 131242-WSW41-VI-M-1011 | 2024-11-02 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-21 | 2024-12-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000504 | 2024-06-01 | 2024-11-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" |  | 2024-11
000505 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1012 | 0 | 131242-WSW41-VI-M-1012 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves) | Rev 0: Not approved - Revise and Resubmit | 2024-07-01 | 2024-08-01 | 43 | Not Approved | YES | 2024-08-21 | NO | Resubmitted | 0 |  | This document is no longer valid and should be marked as "Voided." | 000505 | 2024-06-01 | 2024-06-01 | 0 | NAP | Not Approved | 1 | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves)" |  | 2024-06
000506 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0011 | 0 | 131242-WSW41-PC-W-0011 | 2024-06-03 | Payment Claim No.11 | For Information | 2024-07-02 | 2024-06-27 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000506 | 2024-06-03 | 2024-06-03 | 0 | INF | For Information | 1 | "Payment Claim No.11" |  | 2024-06
000507 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0010 | 0 | 131242-WST02-CL-P-0010 | 2024-06-03 | Blower Pressure Loss Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-07-02 | 2024-07-31 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000507 | 2024-06-03 | 2025-09-10 | 2 | NAP | Approved with Comments | 3 | "Blower Pressure Loss Calculation" |  | 2024-06
000507 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 1 | 131242-WST02-CL-P-0010 | 2024-10-22 | Blower Pressure Loss Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2024-11-19 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000507 | 2024-06-03 | 2025-09-10 | 2 | AWC | Approved with Comments | 3 | "Blower Pressure Loss Calculation" |  | 2024-10
000507 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 2 | 131242-WST02-CL-P-0010 | 2025-09-10 | Blower Pressure Loss Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. Provide PE endorsement | 2025-09-30 | 2026-02-23 | 118 | Approved with Comments | YES | 2026-03-13 | NO | Resubmitted | 0 |  |  | 000507 | 2024-06-03 | 2025-09-10 | 2 | AWC | Approved with Comments | 3 | "Blower Pressure Loss Calculation" |  | 2025-09
000508 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0031 | 0 | 131242-WSW41-LT-PM-0031 | 2024-06-04 | Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump] | Refer to S.O. Correspondence No.0194. | 2024-07-03 | 2024-08-16 | 53 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000508 | 2024-06-04 | 2024-06-04 | 0 | INF | For Information | 1 | "Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump]" |  | 2024-06
000509 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0012 | 0 | 131242-WSW41-MI-PM-0012 | 2024-06-04 | Monthly Progress Meeting Minutes 0012_20240521 | For Information | 2024-07-03 | 2024-06-04 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000509 | 2024-06-04 | 2024-06-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0012_20240521" |  | 2024-06
000510 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0012 | 0 | 131242-WSW41-PS-PM-0012 | 2024-06-04 | Monthly Progress Presentation No. 12 (0424) | For Information | 2024-07-03 | 2024-06-04 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000510 | 2024-06-04 | 2024-06-04 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 12 (0424)" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3180 | A | 131242-WST02-DR-M-3180 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3181 | A | 131242-WST02-DR-M-3181 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3182 | A | 131242-WST02-DR-M-3182 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5131 | A | 131242-WST02-DR-M-5131 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5132 | A | 131242-WST02-DR-M-5132 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5133 | A | 131242-WST02-DR-M-5133 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5101 | A | 131242-WST02-DR-M-5101 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5102 | A | 131242-WST02-DR-M-5102 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | A | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 0 | 131242-WST02-DS-M-0002 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-10-25 | 1 | NAP | Approved with Comments | 2 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | E | 0011 | 0 | 131242-WST02-DS-E-0011 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | E | 0017 | 0 | 131242-WST02-DS-E-0017 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | I | 0003 | 0 | 131242-WST02-DS-I-0003 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | OM | I | 0001 | 0 | 131242-WST02-OM-I-0001 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | OM | I | 0002 | 0 | 131242-WST02-OM-I-0002 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-06-05 | 0 | NAP | Not Approved | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-06
000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 1 | 131242-WST02-DS-M-0002 | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | 21 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000511 | 2024-06-05 | 2024-10-25 | 1 | AWC | Approved with Comments | 2 | "SSN Blower GA drawings and Data Sheets" |  | 2024-10
000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0101 | B | 131242-WST02-DR-M-0101 | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | 21 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000511 | 2024-10-25 | 2024-10-25 | B | AWC | Approved with Comments | 1 | "SSN Blower GA drawings and Data Sheets" |  | 2024-10
000512 | 00 | Radha | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 0 | 131242-WSW41-MS-C-0012 | 2024-06-05 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-27 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000512 | 2024-06-05 | 2024-07-02 | 1 | AWC | Approved | 2 | "MSRA, SWP for Bored Pile Hacking and Rectification works" |  | 2024-06
000512 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 1 | 131242-WSW41-MS-C-0012 | 2024-07-02 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.1: Approved | 2024-07-22 | 2024-07-26 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000512 | 2024-06-05 | 2024-07-02 | 1 | APP | Approved | 2 | "MSRA, SWP for Bored Pile Hacking and Rectification works" |  | 2024-07
000513 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 0 | 131242-WST02-VI-I-0017 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" |  | 2024-06
000513 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 1 | 131242-WST02-VI-I-0017 | 2024-09-16 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" |  | 2024-09
000513 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 2 | 131242-WST02-VI-I-0017 | 2025-01-10 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-30 | 2025-02-12 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | NAP | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" |  | 2025-01
000513 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 3 | 131242-WST02-VI-I-0017 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000513 | 2024-06-06 | 2025-03-17 | 3 | AWC | Approved with Comments | 4 | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" |  | 2025-03
000514 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 0 | 131242-WST02-VI-I-0018 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Switch) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000514 | 2024-06-06 | 2025-05-20 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Pressure Switch)" |  | 2024-06
000514 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 1 | 131242-WST02-VI-I-0018 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Switch) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000514 | 2024-06-06 | 2025-05-20 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Pressure Switch)" |  | 2025-03
000514 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 2 | 131242-WST02-VI-I-0018 | 2025-05-20 | Vendor Approval of SSN Package (Pressure Switch) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-09 | 2025-10-01 | 96 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000514 | 2024-06-06 | 2025-05-20 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Pressure Switch)" |  | 2025-05
000515 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 0 | 131242-WST02-VI-I-0019 | 2024-06-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000515 | 2024-06-06 | 2025-03-17 | 2 | NAP | Approved with Comments | 3 | "Vendor Approval of SSN Package (Temperature Transmitters)" |  | 2024-06
000515 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 1 | 131242-WST02-VI-I-0019 | 2024-08-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-27 | 2024-09-18 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 |  | 000515 | 2024-06-06 | 2025-03-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Temperature Transmitters)" |  | 2024-08
000515 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 2 | 131242-WST02-VI-I-0019 | 2025-03-17 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | 36 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000515 | 2024-06-06 | 2025-03-17 | 2 | AWC | Approved with Comments | 3 | "Vendor Approval of SSN Package (Temperature Transmitters)" |  | 2025-03
000516 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0040 | 0 | 131242-WSW41-CD-IM-0040 | 2024-06-07 | Submission Of BIM Coordination VCM Model (May-2024) | For Information | 2024-07-08 | 2024-06-22 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000516 | 2024-06-07 | 2024-06-07 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (May-2024)" |  | 2024-06
000517 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0024 | 0 | 131242-WSW41-MI-P-0024 | 2024-06-10 | Process & MEICA Meeting Minutes 0024_20240523 | Minutes of meeting are accepted for information. | 2024-07-09 | 2024-07-02 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000517 | 2024-06-10 | 2024-06-10 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0024_20240523" |  | 2024-06
000518 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 0 | 131242-WSW41-MS-C-0013 | 2024-06-10 | MSRA, SWP for Plate Load Test | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-06-27 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000518 | 2024-06-10 | 2024-07-04 | 1 | NAP | Approved with Comments | 2 | "MSRA, SWP for Plate Load Test" |  | 2024-06
000518 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 1 | 131242-WSW41-MS-C-0013 | 2024-07-04 | MSRA, SWP for Plate Load Test | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-05 | 22 | Approved with Comments | YES | 2024-08-23 | NO | Resubmitted | 0 |  |  | 000518 | 2024-06-10 | 2024-07-04 | 1 | AWC | Approved with Comments | 2 | "MSRA, SWP for Plate Load Test" |  | 2024-07
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 8003_ST613_BCA | A | 131242-WST00-DR-S-8003_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 | 2024-08-16 00:00:00 | Heng Peng to provide latest DGN & PDF drawing | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613_BCA | A | 131242-WST02-DR-S-1000_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613_BCA | A | 131242-WST02-DR-S-1006_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613_BCA | A | 131242-WST02-DR-S-1007_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613_BCA | A | 131242-WST02-DR-S-1008_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613_BCA | A | 131242-WST02-DR-S-1013_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613_BCA | A | 131242-WST02-DR-S-5005_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613_BCA | A | 131242-WST02-DR-S-1014_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613_BCA | A | 131242-WST02-DR-S-1015_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613_BCA | A | 131242-WST02-DR-S-1016_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613_BCA | A | 131242-WST02-DR-S-1017_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613_BCA | A | 131242-WST02-DR-S-1018_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613_BCA | A | 131242-WST02-DR-S-1019_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613_BCA | A | 131242-WST02-DR-S-1020_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613_BCA | A | 131242-WST02-DR-S-1021_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613_BCA | A | 131242-WST02-DR-S-1022_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613_BCA | A | 131242-WST02-DR-S-3005_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613_BCA | A | 131242-WST02-DR-S-3008_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613_BCA | A | 131242-WST02-DR-S-3009_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613_BCA | A | 131242-WST02-DR-S-7002_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613_BCA | A | 131242-WST02-DR-S-7003_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613_BCA | A | 131242-WST02-DR-S-7004_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613_BCA | A | 131242-WST02-DR-S-7005_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613_BCA | A | 131242-WST02-DR-S-5006_ST613_BCA | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | 15 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000519 | 2024-06-10 | 2024-06-10 | A | AWC | Approved with Comments | 1 | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-06
000520 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0013 | 0 | 131242-WSW41-RT-PM-0013 | 2024-06-12 | C4B Monthly Progress Report Number No.13 (05 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-07-11 | 2024-06-28 | 12 | Approved with Comments | YES | 2024-07-18 | NO | Resubmitted | 0 |  |  | 000520 | 2024-06-12 | 2024-06-12 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.13 (05 24)" |  | 2024-06
000521 | 00 | David | Mech | NA | 131242 | WSW41 | SP | M | 8002 | 0 | 131242-WSW41-SP-M-8002 | 2024-06-12 | Datasheet for Thermal Insulation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-11 | 2024-08-29 | 56 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 | 2025-03-28 00:00:00 | In Progress | 000521 | 2024-06-12 | 2024-06-12 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Thermal Insulation" |  | 2024-06
000522 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 0 | 131242-WSW41-VI-C-0016 | 2024-06-13 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-12 | 2024-06-28 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000522 | 2024-06-13 | 2024-07-22 | 2 | NAP | Approved | 3 | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " |  | 2024-06
000522 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 1 | 131242-WSW41-VI-C-0016 | 2024-07-04 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-17 | 9 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000522 | 2024-06-13 | 2024-07-22 | 2 | NAP | Approved | 3 | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " |  | 2024-07
000522 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 2 | 131242-WSW41-VI-C-0016 | 2024-07-22 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | R2: Approved | 2024-08-12 | 2024-08-12 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000522 | 2024-06-13 | 2024-07-22 | 2 | APP | Approved | 3 | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " |  | 2024-07
000523 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0006 | 0 | 131242-WSW41-CL-S-0006 | 2024-06-14 | Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94 | Rev.0: Approved | 2024-07-15 | 2024-06-28 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000523 | 2024-06-14 | 2024-06-14 | 0 | APP | Approved | 1 | "Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94" |  | 2024-06
000524 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0032 | 0 | 131242-WSW41-LT-PM-0032 | 2024-06-14 | NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source | Refer to S.O. Correspondence No.000213 dated 23-Aug-2024. | 2024-07-15 | 2024-08-26 | 51 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000524 | 2024-06-14 | 2024-06-14 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source " |  | 2024-06
000525 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0014 | 0 | 131242-WSW41-MS-C-0014 | 2024-06-18 | MSRA & SWP of Civil & Structure Work (Substructure) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 | 9 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000525 | 2024-06-18 | 2024-06-18 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP of Civil & Structure Work (Substructure)" |  | 2024-06
000526 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0015 | 0 | 131242-WSW41-MS-C-0015 | 2024-06-18 | MSRA & SWP of Mobilization & Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 | 9 | Approved with Comments | YES | 2024-07-19 | NO | Resubmitted | 0 |  |  | 000526 | 2024-06-18 | 2024-06-18 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP of Mobilization & Demobilization of Machinery" |  | 2024-06
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A | 131242-WSB01-DR-BH-1000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2024-06
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 3000 | A | 131242-WSB01-DR-BH-3000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2024-06
000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 5000 | A | 131242-WSB01-DR-BH-5000 | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | NAP | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2024-06
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A.1 | 131242-WSB01-DR-BH-1000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2025-01
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 3000 | A.1 | 131242-WSB01-DR-BH-3000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2025-01
000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 5000 | A.1 | 131242-WSB01-DR-BH-5000 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000302&&000527 | 2024-06-19 | 2025-01-14 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" |  | 2025-01
000528 | 00 | Balaji | EICA | NA | 131242 | WSW41 | VI | I | 0002 | 0 | 131242-WSW41-VI-I-0002 | 2024-06-19 | Vendor Approval of Communication Cable (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-17 | 2024-08-05 | 33 | Approved with Comments | YES | 2024-08-23 | NO | Resubmitted | 0 |  |  | 000528 | 2024-06-19 | 2024-06-19 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Communication Cable (Keystone)" |  | 2024-06
000529 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0025 | 0 | 131242-WSW41-MI-P-0025 | 2024-06-20 | Process & MEICA Meeting Minutes 0025_20240606 | For Information | 2024-07-18 | 2024-08-08 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000529 | 2024-06-20 | 2024-06-20 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0025_20240606" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | C | 131242-WST00-DR-S-0001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0002_ST606 | C | 131242-WST00-DR-S-0002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0003_ST606 | C | 131242-WST00-DR-S-0003_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606 | C | 131242-WST02-DR-S-1006_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606 | C | 131242-WST02-DR-S-1007_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606 | C | 131242-WST02-DR-S-1008_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606 | C | 131242-WST02-DR-S-3000_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 5001_ST606 | C | 131242-WST00-DR-S-5001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000530 | 2024-06-21 | 2024-06-21 | C | AWC | Approved with Comments | 1 | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 5002_ST606 | C | 131242-WST00-DR-S-5002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000530 | 2024-06-21 | 2024-06-21 | C | AWC | Approved with Comments | 1 | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606 | C | 131242-WST02-DR-S-7000_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606 | C | 131242-WST02-DR-S-7001_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606 | C | 131242-WST02-DR-S-7002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 227 |  |  | 000110&&000530 | 2023-09-29 | 2024-06-21 | C | AWC | Approved with Comments | 2 | "ST606 : SSN Overall Sub-Structure Drawings " && "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8002_ST606 | A | 131242-WST00-DR-S-8002_ST606 | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | 36 | Approved with Comments | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000530 | 2024-06-21 | 2024-06-21 | A | AWC | Approved with Comments | 1 | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | D | 131242-WST00-DR-G-0001_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | D | 131242-WST00-DR-G-0002_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | D | 131242-WST00-DR-G-1000_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | D | 131242-WST00-DR-G-1001_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | D | 131242-WST00-DR-G-1002_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | D | 131242-WST00-DR-G-1003_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-06-21 | D | AWC | Approved with Comments | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | D | 131242-WST00-DR-G-1004_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 5100_ST601 | D | 131242-WST00-DR-G-5100_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-06-21 | 2024-06-21 | D | AWC | Approved with Comments | 1 | "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | D.1 | 131242-WST00-DR-G-8000_ST601 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | AWC | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-06
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | E | 131242-WST00-DR-G-0001_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-12 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | E | 131242-WST00-DR-G-0002_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | E | 131242-WST00-DR-G-1000_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | E | 131242-WST00-DR-G-1004_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | E | 131242-WST00-DR-G-3000_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 4 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3001_ST601 | E | 131242-WST00-DR-G-3001_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-07-22 | 2024-07-22 | E | APP | Approved | 1 | "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3002_ST601 | E | 131242-WST00-DR-G-3002_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-07-22 | 2024-07-22 | E | APP | Approved | 1 | "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3003_ST601 | E | 131242-WST00-DR-G-3003_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000531 | 2024-07-22 | 2024-07-22 | E | APP | Approved | 1 | "IFC of ST601 – ERSS < 4m " |  | 2024-07
000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | E | 131242-WST00-DR-G-8000_ST601 | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000248&&000531 | 2023-12-22 | 2024-07-22 | E | APP | Approved | 5 | "ST601 – ERSS Design < 4m Depth" && "IFC of ST601 – ERSS < 4m " |  | 2024-07
000532 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0009 | 0 | 131242-WSW41-QA-C-0009 | 2024-06-25 | Monthly Concrete Cube Records for Structural works (02 24) | For Information | 2024-07-23 | 2024-07-05 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000532 | 2024-06-25 | 2024-06-25 | 0 | INF | For Information | 1 | "Monthly Concrete Cube Records for Structural works (02 24)" |  | 2024-06
000533 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 0 | 131242-WSW41-PC-W-0012 | 2024-06-25 | Payment Claim No.12 | Rev (0): Rejected due to some PDA test were done in June 2024. | 2024-07-23 | 2024-06-28 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000533 | 2024-06-25 | 2024-06-28 | 1 | REJ | Approved | 2 | "Payment Claim No.12" |  | 2024-06
000533 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 1 | 131242-WSW41-PC-W-0012 | 2024-06-28 | Payment Claim No.12 | Rev (1): Approved, refer to SO Correspondence No. 0181 dated 2 July 2024. | 2024-07-18 | 2024-11-07 | 94 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000533 | 2024-06-25 | 2024-06-28 | 1 | APP | Approved | 2 | "Payment Claim No.12" |  | 2024-06
000534 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6601 | 0 | 131242-WST02-DR-P-6601 | 2024-06-26 | SSN Blower P&ID | Rev 0: Not approved - Revise and Resubmit | 2024-07-24 | 2024-07-31 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000534 | 2024-06-26 | 2024-06-26 | 0 | NAP | Not Approved | 1 | "SSN Blower P&ID" |  | 2024-06
000534 | 01 | Qili | Process | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S000534 | NA | 131242-NA-NA-NA-Cmt Sheet Reply S000534 | 2024-08-15 | SSN Blower P&ID | Rev 1: Rejected | 2024-09-04 | 2024-09-06 | 16 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000534 | 2024-08-15 | 2024-08-15 | NA | REJ | Rejected | 1 | "SSN Blower P&ID" |  | 2024-08
000535 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0003 | 0 | 131242-WSD11-BQ-P-0003 | 2024-06-26 | THP Line List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-24 | 2024-08-29 | 46 | Approved with Comments | YES | 2024-09-18 | NO | Resubmitted | 0 |  |  | 000535 | 2024-06-26 | 2024-06-26 | 0 | AWC | Approved with Comments | 1 | "THP Line List" |  | 2024-06
000536 | 00 | Zora/ HP | CSA | NA | 131242 | WSD11 | DR | S | 5301 | B | 131242-WSD11-DR-S-5301 | 2024-06-26 | IFC of Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-05 | 7 | Approved with Comments | YES | 2024-07-25 | NO | Resubmitted | 0 | 2024-07-16 00:00:00 | Zora obtain QP endorsement on the drawing and Heng Peng to provide latest DGN and Tenwit (Kalaban) updating the minor comments | 000423&&000536 | 2024-06-05 | 2024-06-26 | B | AWC | Approved with Comments | 2 | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" |  | 2024-06
000537 | 00 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 0 | 131242-WSD11-CL-M-0010 | 2024-06-27 | Design Calculation for Instrument Air Receiver | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-06 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000537 | 2024-06-27 | 2024-09-03 | 1 | AWC | Approved | 2 | "Design Calculation for Instrument Air Receiver" |  | 2024-06
000537 | 01 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 1 | 131242-WSD11-CL-M-0010 | 2024-09-03 | Design Calculation for Instrument Air Receiver | Rev 1: Approved | 2024-09-23 | 2024-09-05 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000537 | 2024-06-27 | 2024-09-03 | 1 | APP | Approved | 2 | "Design Calculation for Instrument Air Receiver" |  | 2024-09
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009_ST607_BCA | A | 131242-WST02-DR-S-1009_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538 | 2024-07-01 | 2024-07-01 | A | NAP | Not Approved | 1 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-S-1010_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | A | 131242-WST02-DR-S-1011_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | A | 131242-WST02-DR-S-1012_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | A | 131242-WST02-DR-S-3002_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | A | 131242-WST02-DR-S-7003_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | A | 131242-WST02-DR-S-7004_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | A | 131242-WST02-DR-S-8003_ST607_BCA | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | 10 | Not Approved | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | NAP | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-07
000539 | 00 | Mohan | QAQC | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-C-0004 | 2024-07-02 | Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-30 | 2024-07-15 | 9 | Approved with Comments | YES | 2024-08-02 | NO | Resubmitted | 0 |  |  | 000539&&000567 | 2024-07-02 | 2024-07-15 | 0 | AWC | Approved | 2 | "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" && "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " |  | 2024-07
000540 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-C-0005 | 2024-07-02 | Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616) | For Information | 2024-07-30 | 2024-07-15 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000540&&000568 | 2024-07-02 | 2024-07-15 | 0 | INF | Approved with Comments | 2 | "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " |  | 2024-07
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | A | 131242-WST02-DR-M-5103 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | NAP | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2024-07
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | A | 131242-WST02-DR-M-5104 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | NAP | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2024-07
000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | A | 131242-WST02-DR-M-5105 | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | NAP | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2024-07
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | B | 131242-WST02-DR-M-5103 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2025-01
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | B | 131242-WST02-DR-M-5104 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2025-01
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | B | 131242-WST02-DR-M-5105 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2025-01
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5106 | A | 131242-WST02-DR-M-5106 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" |  | 2025-01
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5107 | A | 131242-WST02-DR-M-5107 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" |  | 2025-01
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5108 | A | 131242-WST02-DR-M-5108 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" |  | 2025-01
000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0031 | 0 | 131242-WST02-DS-M-0031 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-01-16 | 0 | AWC | Approved with Comments | 1 | "Blower Encapsulation GA" |  | 2025-01
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | D | 131242-WST02-DR-M-5103 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2025-06
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | D | 131242-WST02-DR-M-5104 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2025-06
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | D | 131242-WST02-DR-M-5105 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2024-07-03 | 2025-06-06 | D | AWC | Approved with Comments | 3 | "Blower Encapsulation GA" |  | 2025-06
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5106 | B | 131242-WST02-DR-M-5106 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" |  | 2025-06
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5107 | B | 131242-WST02-DR-M-5107 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" |  | 2025-06
000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5108 | B | 131242-WST02-DR-M-5108 | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | 29 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 000541 | 2025-01-16 | 2025-06-06 | B | AWC | Approved with Comments | 2 | "Blower Encapsulation GA" |  | 2025-06
000542 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0026 | A | 131242-WSW41-MI-P-0026 | 2024-07-03 | Process & MEICA Meeting Minutes 0026_20240624 | Rev 0: For Information | 2024-07-31 | 2024-08-29 | 41 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000542 | 2024-07-03 | 2024-07-03 | A | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0026_20240624" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7700 | C | 131242-WST02-DR-E-7700 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7701 | C | 131242-WST02-DR-E-7701 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7702 | C | 131242-WST02-DR-E-7702 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7703 | C | 131242-WST02-DR-E-7703 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7704 | C | 131242-WST02-DR-E-7704 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7705 | C | 131242-WST02-DR-E-7705 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7706 | C | 131242-WST02-DR-E-7706 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7707 | C | 131242-WST02-DR-E-7707 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7708 | C | 131242-WST02-DR-E-7708 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7709 | C | 131242-WST02-DR-E-7709 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7710 | C | 131242-WST02-DR-E-7710 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7711 | C | 131242-WST02-DR-E-7711 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7712 | C | 131242-WST02-DR-E-7712 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7713 | C | 131242-WST02-DR-E-7713 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7714 | C | 131242-WST02-DR-E-7714 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7715 | C | 131242-WST02-DR-E-7715 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7716 | C | 131242-WST02-DR-E-7716 | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | 83 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000543 | 2024-07-04 | 2024-07-04 | C | AWC | Approved with Comments | 1 | "Blower Circuit Diagram" |  | 2024-07
000544 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0034 | 0 | 131242-WSW41-LT-PM-0034 | 2024-07-04 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Please refer to comment sheet for resubmission. | 2024-08-01 | 2024-07-16 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000544 | 2024-07-04 | 2024-07-04 | 0 | INF | For Information | 1 | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" |  | 2024-07
000544 | 01 | Yuen Fatt | Project | NA | 131242 | NA | LT | PM | NA | NA | 131242-NA-LT-PM-NA | 2024-08-03 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Rev.1: Please refer to comment sheet for resubmission. | 2024-08-23 | 2024-08-19 | 10 | Not Approved | YES | 2024-09-06 | NO | Resubmitted | 0 |  | To change the title : Request Owner’s Approval for Use of Linabond Concrete Corrosion Protection Material | 000544 | 2024-08-03 | 2024-08-03 | NA | NAP | Not Approved | 1 | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" |  | 2024-08
000545 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0006 | 0 | 131242-WST02-RT-C-0006 | 2024-07-04 | Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615) | Approved | 2024-08-01 | 2024-07-17 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000545 | 2024-07-04 | 2024-07-04 | 0 | APP | Approved | 1 | "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" |  | 2024-07
000546 | 00 | Theint Theint | Project | NA | 131242 | WSW41 | VI | S | 0005 | 0 | 131242-WSW41-VI-S-0005 | 2024-07-05 | Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-02 | 2024-07-18 | 9 | Not Approved | YES | 2024-08-07 | NO | Resubmitted | 0 |  |  | 000546 | 2024-07-05 | 2024-07-05 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" |  | 2024-07
000547 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0002 | 0 | 131242-WSW41-PO-E-0002 | 2024-07-08 | Unpriced PO for Cables (Keystone) | For Information | 2024-08-05 | 2024-08-05 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000547 | 2024-07-08 | 2024-07-08 | 0 | INF | For Information | 1 | "Unpriced PO for Cables (Keystone)" |  | 2024-07
000548 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0005 | 0 | 131242-WSW41-PO-M-0005 | 2024-07-08 | Unpriced PO for Sludge Pump (Netzsch) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000548&&001516 | 2024-07-08 | 2025-07-22 | 0 | INF | For Information | 2 | "Unpriced PO for Sludge Pump (Netzsch) " && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" |  | 2024-07
000549 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0006 | 0 | 131242-WSW41-PO-M-0006 | 2024-07-08 | Unpriced PO for cPVC Pipes (George Fischer) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000549&&001517 | 2024-07-08 | 2025-07-22 | 0 | INF | For Information | 2 | "Unpriced PO for cPVC Pipes (George Fischer)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" |  | 2024-07
000550 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jun-2024) | For Information | 2024-08-05 | 2024-07-23 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000550&&000631 | 2024-07-08 | 2024-08-12 | 0 | INF | For Information | 3 | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" |  | 2024-07
000551 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0002 | 0 | 131242-WSW41-MS-G-0002 | 2024-07-08 | MSRA & SWP for Pre-Augering Work | Rev.0: Approved | 2024-08-05 | 2024-08-08 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000551 | 2024-07-08 | 2024-07-08 | 0 | APP | Approved | 1 | "MSRA & SWP for Pre-Augering Work" |  | 2024-07
000552 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 0 | 131242-WSW41-RT-PM-0014 | 2024-07-09 | C4B Monthly Progress Report Number No.14 (06 24) | Rejected as requested by Contractor | 2024-08-06 | 2024-07-09 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000552 | 2024-07-09 | 2024-07-13 | 1 | REJ | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.14 (06 24)" |  | 2024-07
000552 | 01 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 1 | 131242-WSW41-RT-PM-0014 | 2024-07-13 | C4B Monthly Progress Report Number No.14 (06 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-08-01 | 2024-07-30 | 11 | Approved with Comments | YES | 2024-08-19 | NO | Resubmitted | 0 |  |  | 000552 | 2024-07-09 | 2024-07-13 | 1 | AWC | Approved with Comments | 2 | "C4B Monthly Progress Report Number No.14 (06 24)" |  | 2024-07
000553 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 0 | 131242-WST02-CL-P-0007 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-07
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DS | I | 0004 | 0 | 131242-WST02-DS-I-0004 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2024-07-09 | 0 | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-07
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 0 | AWC | Approved with Comments | 3 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-07
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DR | I | 5020 | A | 131242-WST02-DR-I-5020 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2024-11-02 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-07
000553 | 00 | Qili | Process | NA | 131242 | WST02 | DR | M | 5021 | A | 131242-WST02-DR-M-5021 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-03-06 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-07
000553 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 1 | 131242-WST02-CL-P-0007 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-21 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-11
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0025 | A | 131242-WST02-DR-M-0025 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-11-02 | 2024-11-02 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-11
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0026 | A | 131242-WST02-DR-M-0026 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-11-02 | 2024-11-02 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-11
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | I | 5020 | A | 131242-WST02-DR-I-5020 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2024-11-02 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-11
000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | I | 5021 | A | 131242-WST02-DR-I-5021 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-11-02 | 2024-11-02 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2024-11
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-P-0007 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0008 | 0 | 131242-WST02-CL-P-0008 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | M | 5020 | 0 | 131242-WST02-CL-M-5020 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | M | 5021 | 0 | 131242-WST02-CL-M-5021 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 0 | AWC | Approved with Comments | 3 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0019 | 0 | 131242-WST02-DS-M-0019 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 5741 | 0 | 131242-WST02-DS-M-5741 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 5021 | A | 131242-WST02-DR-M-5021 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-03-06 | A | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 5022 | A | 131242-WST02-DR-M-5022 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1200 | A | 131242-WST02-DR-M-1200 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1201 | B | 131242-WST02-DR-M-1201 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | B | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1202 | B | 131242-WST02-DR-M-1202 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | B | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1203 | A | 131242-WST02-DR-M-1203 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1204 | A | 131242-WST02-DR-M-1204 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1205 | A | 131242-WST02-DR-M-1205 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1206 | A | 131242-WST02-DR-M-1206 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1207 | A | 131242-WST02-DR-M-1207 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1208 | A | 131242-WST02-DR-M-1208 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1209 | A | 131242-WST02-DR-M-1209 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1210 | A | 131242-WST02-DR-M-1210 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3203 | A | 131242-WST02-DR-M-3203 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3204 | A | 131242-WST02-DR-M-3204 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3205 | A | 131242-WST02-DR-M-3205 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3206 | A | 131242-WST02-DR-M-3206 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3207 | A | 131242-WST02-DR-M-3207 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3208 | A | 131242-WST02-DR-M-3208 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3209 | A | 131242-WST02-DR-M-3209 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3210 | A | 131242-WST02-DR-M-3210 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-03-06 | A | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-03
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-P-0007 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 2 | AWC | Approved with Comments | 4 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0008 | 0 | 131242-WST02-CL-P-0008 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | M | 5020 | 0 | 131242-WST02-CL-M-5020 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | M | 5021 | 0 | 131242-WST02-CL-M-5021 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2024-07-09 | 2025-08-22 | 0 | AWC | Approved with Comments | 3 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0019 | 0 | 131242-WST02-DS-M-0019 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0020 | 0 | 131242-WST02-DS-M-0020 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-08-22 | 2025-08-22 | 0 | AWC | Approved with Comments | 1 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 5741 | 0 | 131242-WST02-DS-M-5741 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | 31 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000553 | 2025-03-06 | 2025-08-22 | 0 | AWC | Approved with Comments | 2 | "Data Sheet, Drawing and Calculation of SSN Diffuser" |  | 2025-08
000554 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-I-5000 | 2024-07-10 | SSN UPS and Battery Room Layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | 38 | Not Approved | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000191&&000554 | 2024-07-10 | 2025-05-15 | A | NAP | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN UPS and Battery Room Layout" |  | 2024-07
000555 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-I-5001 | 2024-07-10 | SSN Process Non-Process room layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | 38 | Not Approved | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000191&&000555 | 2024-07-10 | 2025-05-15 | A | NAP | Approved with Comments | 2 | "Milestone 2 SSN Electrical Building" && "SSN Process Non-Process room layout" |  | 2024-07
000556 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 0 | 131242-WSD11-RT-EK-0000 | 2024-07-10 | THP LPS Risk Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000556 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "THP LPS Risk Assessment Report" |  | 2024-07
000556 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 1 | 131242-WSD11-RT-EK-0000 | 2024-10-28 | THP LPS Risk Assessment Report | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-12-08 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-24 00:00:00 |  | 000556 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "THP LPS Risk Assessment Report" |  | 2024-10
000556 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 2 | 131242-WSD11-RT-EK-0000 | 2025-07-07 | THP LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | 41 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 000556 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "THP LPS Risk Assessment Report" |  | 2025-07
000557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 0 | 131242-WST02-RT-EK-0000 | 2024-07-10 | SSN LPS Risk Assessment Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | 54 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000557 | 2024-07-10 | 2025-07-07 | 2 | NAP | Approved with Comments | 3 | "SSN LPS Risk Assessment Report" |  | 2024-07
000557 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 1 | 131242-WST02-RT-EK-0000 | 2024-10-24 | SSN LPS Risk Assessment Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-11-14 | 2024-12-08 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000557 | 2024-07-10 | 2025-07-07 | 2 | NAP | Approved with Comments | 3 | "SSN LPS Risk Assessment Report" |  | 2024-10
000557 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 2 | 131242-WST02-RT-EK-0000 | 2025-07-07 | SSN LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | 41 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 000557 | 2024-07-10 | 2025-07-07 | 2 | AWC | Approved with Comments | 3 | "SSN LPS Risk Assessment Report" |  | 2025-07
000558 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0028 | 0 | 131242-WSW41-MI-IM-0028 | 2024-07-10 | BIM Bi-Weekly Meeting Minutes 0028_20240626 | For Information | 2024-08-07 | 2024-08-30 | 37 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000558 | 2024-07-10 | 2024-07-10 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0028_20240626" |  | 2024-07
000559 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-M-0018 | 2024-07-12 | Preliminary Design and Vendor Approval for Parabolic Screen | Rev 0: Approved | 2024-08-12 | 2024-09-02 | 36 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000332&&000559 | 2024-02-29 | 2024-07-12 | 0 | APP | Approved | 3 | "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Preliminary Design and Vendor Approval for Parabolic Screen" |  | 2024-07
000560 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 0 | 131242-WSW41-VI-M-0020 | 2024-07-12 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000560 | 2024-07-12 | 2024-09-16 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" |  | 2024-07
000560 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 1 | 131242-WSW41-VI-M-0020 | 2024-09-16 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 1: Approved | 2024-10-04 | 2024-09-24 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000560 | 2024-07-12 | 2024-09-16 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" |  | 2024-09
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0024 | 0 | 131242-WSW41-MI-C-0024 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000561 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0024,0025,0026_May" |  | 2024-07
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0025 | 0 | 131242-WSW41-MI-C-0025 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000561 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0024,0025,0026_May" |  | 2024-07
000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0026 | 0 | 131242-WSW41-MI-C-0026 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | 21 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000561 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0024,0025,0026_May" |  | 2024-07
000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0027 | 0 | 131242-WSW41-MI-C-0027 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000562 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0027,0028_June" |  | 2024-07
000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0028 | 0 | 131242-WSW41-MI-C-0028 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000562 | 2024-07-12 | 2024-07-12 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0027,0028_June" |  | 2024-07
000563 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0010 | 0 | 131242-WSW41-QA-C-0010 | 2024-07-12 | Monthly Concrete Cube Records for Structural works (03 24) | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-08-12 | 2024-08-12 | 21 | Not Approved | YES | 2024-08-30 | NO | Resubmitted | 0 |  |  | 000563 | 2024-07-12 | 2024-07-12 | 0 | NAP | Not Approved | 1 | "Monthly Concrete Cube Records for Structural works (03 24)" |  | 2024-07
000564 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0002 | 0 | 131242-WSW41-MS-E-0002 | 2024-07-12 | MSRA, SWP for Electrical Work | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-12 | 2024-09-24 | 52 | Not Approved | YES | 2024-10-14 | NO | Resubmitted | 0 |  |  | 000564 | 2024-07-12 | 2024-07-12 | 0 | NAP | Not Approved | 1 | "MSRA, SWP for Electrical Work" |  | 2024-07
000565 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 0 | 131242-WSW41-MS-M-0001 | 2024-07-13 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000565 | 2024-07-13 | 2024-09-05 | 1 | AWC | Approved | 2 | "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " |  | 2024-07
000565 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 1 | 131242-WSW41-MS-M-0001 | 2024-09-05 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 1: Approved | 2024-09-25 | 2024-10-03 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000565 | 2024-07-13 | 2024-09-05 | 1 | APP | Approved | 2 | "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " |  | 2024-09
000566 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0020 | 0 | 131242-WST02-VI-I-0020 | 2024-07-13 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-12 | 2024-08-06 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000566 | 2024-07-13 | 2024-08-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" |  | 2024-07
000566 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0020 | 1 | 131242-WST02-VI-I-0020 | 2024-08-16 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-05 | 2024-10-10 | 39 | Approved with Comments | YES | 2024-10-30 | NO | Resubmitted | 0 |  | Vendor Changed to Fox | 000566 | 2024-07-13 | 2024-08-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" |  | 2024-08
000567 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-C-0004 | 2024-07-15 | Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area | Approved | 2024-08-13 | 2024-08-12 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000539&&000567 | 2024-07-02 | 2024-07-15 | 0 | APP | Approved | 2 | "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" && "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " |  | 2024-07
000568 | 00 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-C-0005 | 2024-07-15 | Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-13 | 2024-08-22 | 28 | Approved with Comments | YES | 2024-09-11 | NO | Resubmitted | 0 |  |  | 000540&&000568 | 2024-07-02 | 2024-07-15 | 0 | AWC | Approved with Comments | 2 | "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " |  | 2024-07
000569 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 0 | 131242-WSD11-CD-I-0002 | 2024-07-16 | THP Instrument Lists | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-17 | 45 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000569 | 2024-07-16 | 2024-12-13 | 1 | NAP | Not Approved | 2 | "THP Instrument Lists" |  | 2024-07
000569 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 1 | 131242-WSD11-CD-I-0002 | 2024-12-13 | THP Instrument Lists | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-03 | 2025-02-13 | 44 | Not Approved | YES | 2025-03-05 | NO | Resubmitted | 0 |  |  | 000569 | 2024-07-16 | 2024-12-13 | 1 | NAP | Not Approved | 2 | "THP Instrument Lists" |  | 2024-12
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | A | 131242-WSD11-DR-EP-7100 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | A | 131242-WSD11-DR-EP-7101 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | A | 131242-WSD11-DR-EP-7102 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | A | 131242-WSD11-DR-EP-7103 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | A | 131242-WSD11-DR-EP-7104 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | A | 131242-WSD11-DR-EP-7105 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | A | 131242-WSD11-DR-EP-7106 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | A | 131242-WSD11-DR-EP-7107 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109 | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" |  | 2024-07
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-EI-7000 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-21 | 2024-10-03 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | NAP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | B | 131242-WSD11-DR-EI-7001 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | B | 131242-WSD11-DR-EI-7002 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | B | 131242-WSD11-DR-EI-7003 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | B | 131242-WSD11-DR-EI-7004 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | B | 131242-WSD11-DR-EI-7005 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | B | 131242-WSD11-DR-EI-7006 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | B | 131242-WSD11-DR-EI-7007 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | B | 131242-WSD11-DR-EI-7008 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | B | 131242-WSD11-DR-EI-7009 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | B | 131242-WSD11-DR-EI-7010 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | B | 131242-WSD11-DR-EI-7020 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | B | 131242-WSD11-DR-EI-7021 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | B | 131242-WSD11-DR-EI-7022 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | B | 131242-WSD11-DR-EI-7023 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | B | 131242-WSD11-DR-EI-7024 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | B | 131242-WSD11-DR-EI-7025 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | B | 131242-WSD11-DR-EI-7026 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | B | 131242-WSD11-DR-EI-7027 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | B | 131242-WSD11-DR-EI-7028 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | B | 131242-WSD11-DR-EI-7029 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | B | 131242-WSD11-DR-EI-7030 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | B | 131242-WSD11-DR-EP-3000 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | B | 131242-WSD11-DR-EP-3001 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | B | 131242-WSD11-DR-EP-3002 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | B | 131242-WSD11-DR-EP-3003 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | B | 131242-WSD11-DR-EP-3004 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | B | 131242-WSD11-DR-EP-3005 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | B | 131242-WSD11-DR-EP-3006 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | B | 131242-WSD11-DR-EP-3007 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | B | 131242-WSD11-DR-EP-3008 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | B | 131242-WSD11-DR-EP-3009 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | B | 131242-WSD11-DR-EP-3010 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | B | 131242-WSD11-DR-EP-3011 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | B | 131242-WSD11-DR-EP-3012 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | B | 131242-WSD11-DR-EP-3013 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | REJ | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | B | 131242-WSD11-DR-EP-7100 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | B | 131242-WSD11-DR-EP-7101 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | B | 131242-WSD11-DR-EP-7102 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | B | 131242-WSD11-DR-EP-7103 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | B | 131242-WSD11-DR-EP-7104 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | B | 131242-WSD11-DR-EP-7105 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | B | 131242-WSD11-DR-EP-7106 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | B | 131242-WSD11-DR-EP-7107 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109 | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | 2 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-EI-7000 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | B | 131242-WSD11-DR-EI-7001 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | B | 131242-WSD11-DR-EI-7002 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | B | 131242-WSD11-DR-EI-7003 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | B | 131242-WSD11-DR-EI-7004 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | B | 131242-WSD11-DR-EI-7005 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | B | 131242-WSD11-DR-EI-7006 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | B | 131242-WSD11-DR-EI-7007 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | B | 131242-WSD11-DR-EI-7008 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | B | 131242-WSD11-DR-EI-7009 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | B | 131242-WSD11-DR-EI-7010 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | B | 131242-WSD11-DR-EI-7020 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | B | 131242-WSD11-DR-EI-7021 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | B | 131242-WSD11-DR-EI-7022 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | B | 131242-WSD11-DR-EI-7023 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | B | 131242-WSD11-DR-EI-7024 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | B | 131242-WSD11-DR-EI-7025 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | B | 131242-WSD11-DR-EI-7026 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | B | 131242-WSD11-DR-EI-7027 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | B | 131242-WSD11-DR-EI-7028 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | B | 131242-WSD11-DR-EI-7029 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | B | 131242-WSD11-DR-EI-7030 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | B | 131242-WSD11-DR-EP-3000 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | B | 131242-WSD11-DR-EP-3001 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | B | 131242-WSD11-DR-EP-3002 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | B | 131242-WSD11-DR-EP-3003 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | B | 131242-WSD11-DR-EP-3004 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | B | 131242-WSD11-DR-EP-3005 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | B | 131242-WSD11-DR-EP-3006 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | B | 131242-WSD11-DR-EP-3007 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | B | 131242-WSD11-DR-EP-3008 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | B | 131242-WSD11-DR-EP-3009 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | B | 131242-WSD11-DR-EP-3010 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | B | 131242-WSD11-DR-EP-3011 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | B | 131242-WSD11-DR-EP-3012 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | B | 131242-WSD11-DR-EP-3013 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | B | 131242-WSD11-DR-EP-7100 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | B | 131242-WSD11-DR-EP-7101 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | B | 131242-WSD11-DR-EP-7102 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | B | 131242-WSD11-DR-EP-7103 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | B | 131242-WSD11-DR-EP-7104 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | B | 131242-WSD11-DR-EP-7105 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | B | 131242-WSD11-DR-EP-7106 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | B | 131242-WSD11-DR-EP-7107 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109 | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-10
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | C | 131242-WSD11-DR-EI-7000 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | C | 131242-WSD11-DR-EI-7001 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | C | 131242-WSD11-DR-EI-7002 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | C | 131242-WSD11-DR-EI-7003 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | C | 131242-WSD11-DR-EI-7004 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | C | 131242-WSD11-DR-EI-7005 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | C | 131242-WSD11-DR-EI-7006 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | C | 131242-WSD11-DR-EI-7007 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | C | 131242-WSD11-DR-EI-7008 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | C | 131242-WSD11-DR-EI-7009 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | C | 131242-WSD11-DR-EI-7010 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | C | 131242-WSD11-DR-EI-7020 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | C | 131242-WSD11-DR-EI-7021 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | C | 131242-WSD11-DR-EI-7022 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | C | 131242-WSD11-DR-EI-7023 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | C | 131242-WSD11-DR-EI-7024 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | C | 131242-WSD11-DR-EI-7025 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | C | 131242-WSD11-DR-EI-7026 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | C | 131242-WSD11-DR-EI-7027 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | C | 131242-WSD11-DR-EI-7028 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | C | 131242-WSD11-DR-EI-7029 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | C | 131242-WSD11-DR-EI-7030 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | C | 131242-WSD11-DR-EI-7031 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-11-21 | 2025-10-23 | E | AWC | Approved | 3 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | C | 131242-WSD11-DR-EP-3000 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | C | 131242-WSD11-DR-EP-3001 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | C | 131242-WSD11-DR-EP-3002 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | C | 131242-WSD11-DR-EP-3003 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | C | 131242-WSD11-DR-EP-3004 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | C | 131242-WSD11-DR-EP-3005 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | C | 131242-WSD11-DR-EP-3006 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | C | 131242-WSD11-DR-EP-3007 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | C | 131242-WSD11-DR-EP-3008 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | C | 131242-WSD11-DR-EP-3009 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | C | 131242-WSD11-DR-EP-3010 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | C | 131242-WSD11-DR-EP-3011 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | C | 131242-WSD11-DR-EP-3012 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | C | 131242-WSD11-DR-EP-3013 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | C | 131242-WSD11-DR-EP-7100 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | C | 131242-WSD11-DR-EP-7101 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | C | 131242-WSD11-DR-EP-7102 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | C | 131242-WSD11-DR-EP-7103 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | C | 131242-WSD11-DR-EP-7104 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | C | 131242-WSD11-DR-EP-7105 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | C | 131242-WSD11-DR-EP-7106 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | C | 131242-WSD11-DR-EP-7107 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | C | 131242-WSD11-DR-EP-7108 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | C | 131242-WSD11-DR-EP-7109 | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2024-11
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | D | 131242-WSD11-DR-EI-7000 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | D | 131242-WSD11-DR-EI-7001 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | D | 131242-WSD11-DR-EI-7002 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | D | 131242-WSD11-DR-EI-7003 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | D | 131242-WSD11-DR-EI-7004 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | D | 131242-WSD11-DR-EI-7005 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | D | 131242-WSD11-DR-EI-7006 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | D | 131242-WSD11-DR-EI-7007 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | D | 131242-WSD11-DR-EI-7008 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | D | 131242-WSD11-DR-EI-7009 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | D | 131242-WSD11-DR-EI-7010 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7011 | D | 131242-WSD11-DR-EI-7011 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2025-03-07 | 2025-10-23 | E | AWC | Approved | 2 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | D | 131242-WSD11-DR-EI-7020 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | D | 131242-WSD11-DR-EI-7021 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | D | 131242-WSD11-DR-EI-7022 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | D | 131242-WSD11-DR-EI-7023 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | D | 131242-WSD11-DR-EI-7024 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | D | 131242-WSD11-DR-EI-7025 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | D | 131242-WSD11-DR-EI-7026 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | D | 131242-WSD11-DR-EI-7027 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | D | 131242-WSD11-DR-EI-7028 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | D | 131242-WSD11-DR-EI-7029 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | D | 131242-WSD11-DR-EI-7030 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | D | 131242-WSD11-DR-EI-7031 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-11-21 | 2025-10-23 | E | AWC | Approved | 3 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | D | 131242-WSD11-DR-EP-3000 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | D | 131242-WSD11-DR-EP-3001 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | D | 131242-WSD11-DR-EP-3002 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | D | 131242-WSD11-DR-EP-3003 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | D | 131242-WSD11-DR-EP-3004 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | D | 131242-WSD11-DR-EP-3005 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | D | 131242-WSD11-DR-EP-3006 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | D | 131242-WSD11-DR-EP-3007 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | D | 131242-WSD11-DR-EP-3008 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | D | 131242-WSD11-DR-EP-3009 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | D | 131242-WSD11-DR-EP-3010 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | D | 131242-WSD11-DR-EP-3011 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | D | 131242-WSD11-DR-EP-3012 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | D | 131242-WSD11-DR-EP-3013 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | AWC | Approved | 5 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | D | 131242-WSD11-DR-EP-7100 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | D | 131242-WSD11-DR-EP-7101 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | D | 131242-WSD11-DR-EP-7102 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | D | 131242-WSD11-DR-EP-7103 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | D | 131242-WSD11-DR-EP-7104 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | D | 131242-WSD11-DR-EP-7105 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | D | 131242-WSD11-DR-EP-7106 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | D | 131242-WSD11-DR-EP-7107 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | D | 131242-WSD11-DR-EP-7108 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | D | 131242-WSD11-DR-EP-7109 | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | AWC | Approved | 6 | "THP SLD" |  | 2025-03
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | E | 131242-WSD11-DR-EI-7000 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | E | 131242-WSD11-DR-EI-7001 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | E | 131242-WSD11-DR-EI-7002 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | E | 131242-WSD11-DR-EI-7003 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | E | 131242-WSD11-DR-EI-7004 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | E | 131242-WSD11-DR-EI-7005 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | E | 131242-WSD11-DR-EI-7006 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | E | 131242-WSD11-DR-EI-7007 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | E | 131242-WSD11-DR-EI-7008 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | E | 131242-WSD11-DR-EI-7009 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | E | 131242-WSD11-DR-EI-7010 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7011 | E | 131242-WSD11-DR-EI-7011 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2025-03-07 | 2025-10-23 | E | APP | Approved | 2 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | E | 131242-WSD11-DR-EI-7020 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | E | 131242-WSD11-DR-EI-7021 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | E | 131242-WSD11-DR-EI-7022 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | E | 131242-WSD11-DR-EI-7023 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | E | 131242-WSD11-DR-EI-7024 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | E | 131242-WSD11-DR-EI-7025 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | E | 131242-WSD11-DR-EI-7026 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | E | 131242-WSD11-DR-EI-7027 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | E | 131242-WSD11-DR-EI-7028 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | E | 131242-WSD11-DR-EI-7029 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | E | 131242-WSD11-DR-EI-7030 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | E | 131242-WSD11-DR-EI-7031 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-11-21 | 2025-10-23 | E | APP | Approved | 3 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | E | 131242-WSD11-DR-EP-3000 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | E | 131242-WSD11-DR-EP-3001 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | E | 131242-WSD11-DR-EP-3002 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | E | 131242-WSD11-DR-EP-3003 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | E | 131242-WSD11-DR-EP-3004 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | E | 131242-WSD11-DR-EP-3005 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | E | 131242-WSD11-DR-EP-3006 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | E | 131242-WSD11-DR-EP-3007 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | E | 131242-WSD11-DR-EP-3008 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | E | 131242-WSD11-DR-EP-3009 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | E | 131242-WSD11-DR-EP-3010 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | E | 131242-WSD11-DR-EP-3011 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | E | 131242-WSD11-DR-EP-3012 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | E | 131242-WSD11-DR-EP-3013 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-10-01 | 2025-10-23 | E | APP | Approved | 5 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | E | 131242-WSD11-DR-EP-7100 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | E | 131242-WSD11-DR-EP-7101 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | E | 131242-WSD11-DR-EP-7102 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | E | 131242-WSD11-DR-EP-7103 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | E | 131242-WSD11-DR-EP-7104 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | E | 131242-WSD11-DR-EP-7105 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | E | 131242-WSD11-DR-EP-7106 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | E | 131242-WSD11-DR-EP-7107 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | E | 131242-WSD11-DR-EP-7108 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | E | 131242-WSD11-DR-EP-7109 | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000570 | 2024-07-16 | 2025-10-23 | E | APP | Approved | 6 | "THP SLD" |  | 2025-10
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | A | 131242-WSD11-DR-EI-7000 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | A | 131242-WSD11-DR-EI-7001 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | A | 131242-WSD11-DR-EI-7002 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | A | 131242-WSD11-DR-EI-7003 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | A | 131242-WSD11-DR-EI-7004 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | A | 131242-WSD11-DR-EI-7005 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | A | 131242-WSD11-DR-EI-7006 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | A | 131242-WSD11-DR-EI-7007 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | A | 131242-WSD11-DR-EI-7008 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | A | 131242-WSD11-DR-EI-7020 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | A | 131242-WSD11-DR-EI-7021 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | A | 131242-WSD11-DR-EI-7022 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | A | 131242-WSD11-DR-EI-7023 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | A | 131242-WSD11-DR-EI-7024 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | A | 131242-WSD11-DR-EI-7025 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | A | 131242-WSD11-DR-EI-7026 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | A | 131242-WSD11-DR-EI-7027 | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | 28 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000571 | 2024-07-16 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Schematic Diagram" |  | 2024-07
000571 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#571 Cmt Reply Sht | NA | 131242-WSD11-NA-NA-S#571 Cmt Reply Sht | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000571 | 2024-10-01 | 2024-10-01 | NA | NAP | Not Approved | 1 | "THP SLD" |  | 2024-10
000572 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302 | A | 131242-WSD11-DR-S-5302 | 2024-07-17 | IFC of BSB Silo Area Pump Plinth Details | For Information | 2024-08-15 | 2024-08-28 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000572 | 2024-07-17 | 2024-07-17 | A | INF | For Information | 1 | "IFC of BSB Silo Area Pump Plinth Details " |  | 2024-07
000573 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5501 | A | 131242-WST02-DR-S-5501 | 2024-07-17 | IFC of SSN Electrical Building Transformer Plinth Details | Rev.0: Approved with comments. Revise and resubmit. | 2024-08-15 | 2024-09-14 | 43 | Approved with Comments | YES | 2024-10-03 | NO | Resubmitted | 0 |  |  | 000573 | 2024-07-17 | 2024-07-17 | A | AWC | Approved with Comments | 1 | "IFC of SSN Electrical Building Transformer Plinth Details " |  | 2024-07
000574 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0006 | 0 | 131242-WSW41-VI-S-0006 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000574 | 2024-07-17 | 2024-07-17 | 0 | APP | Approved | 1 | "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | A | 131242-WSD11-DR-EP-3000 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | A | 131242-WSD11-DR-EP-3001 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | A | 131242-WSD11-DR-EP-3002 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | A | 131242-WSD11-DR-EP-3003 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | A | 131242-WSD11-DR-EP-3004 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | A | 131242-WSD11-DR-EP-3005 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | A | 131242-WSD11-DR-EP-3006 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | A | 131242-WSD11-DR-EP-3007 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | A | 131242-WSD11-DR-EP-3008 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | A | 131242-WSD11-DR-EP-3009 | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | 21 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000570&&000575 | 2024-07-17 | 2025-10-23 | E | REJ | Approved | 6 | "THP SLD" && "THP MCC Outline Drawing" |  | 2024-07
000575 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#575 Cmt Reply Sht | NA | 131242-WSD11-NA-NA-S#575 Cmt Reply Sht | 2024-10-01 | THP MCC Outline Drawing | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 | 2 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000575 | 2024-10-01 | 2024-10-01 | NA | NAP | Not Approved | 1 | "THP MCC Outline Drawing" |  | 2024-10
000576 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0007 | 0 | 131242-WSW41-VI-S-0007 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000576 | 2024-07-17 | 2024-07-17 | 0 | APP | Approved | 1 | "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " |  | 2024-07
000577 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0017 | 0 | 131242-WSW41-VI-C-0017 | 2024-07-17 | Vendor Approval for PVC Lining System - (Linabond) | Approved | 2024-08-15 | 2024-08-12 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000577 | 2024-07-17 | 2024-07-17 | 0 | APP | Approved | 1 | "Vendor Approval for PVC Lining System - (Linabond)" |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | C | 131242-WST02-DR-S-1000_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | C | 131242-WST02-DR-S-1006_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | C | 131242-WST02-DR-S-1007_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | C | 131242-WST02-DR-S-1008_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | C | 131242-WST02-DR-S-1013_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | B | 131242-WST02-DR-S-1014_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | B | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | C | 131242-WST02-DR-S-1015_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | C | 131242-WST02-DR-S-1016_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | C | 131242-WST02-DR-S-1017_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | C | 131242-WST02-DR-S-1018_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | C | 131242-WST02-DR-S-1019_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | C | 131242-WST02-DR-S-1020_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | C | 131242-WST02-DR-S-1021_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | C | 131242-WST02-DR-S-1022_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | C | 131242-WST02-DR-S-3005_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | C | 131242-WST02-DR-S-3008_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | C | 131242-WST02-DR-S-3009_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | C | 131242-WST02-DR-S-5005_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | C | 131242-WST02-DR-S-5006_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | C | 131242-WST02-DR-S-7002_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | C | 131242-WST02-DR-S-7003_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | C | 131242-WST02-DR-S-7004_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | C | 131242-WST02-DR-S-7005_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | C | 131242-WST02-DR-S-8003_ST613 | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000275&&000578 | 2024-01-13 | 2024-07-20 | C | INF | For Information | 3 | "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " && "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " |  | 2024-07
000579 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0001 | 0 | 131242-WST02-CD-I-0001 | 2024-07-22 | SSN PLC I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-17 | 41 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | NAP | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " |  | 2024-07
000579 | 01 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 1 | 131242-WST02-CD-I-0001 | 2024-11-06 | SSN RIO 0201 I/O List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-26 | 2024-12-18 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | NAP | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " |  | 2024-11
000579 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 2 | 131242-WST02-CD-I-0001 | 2025-03-06 | SSN RIO 0201 I/O List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-26 | 2025-05-07 | 44 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | NAP | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " |  | 2025-03
000579 | 03 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 3 | 131242-WST02-CD-I-0001 | 2025-06-16 | SSN RIO 0201 I/O List | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | AWC | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " |  | 2025-06
000579 | 04 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 4 | 131242-WST02-CD-I-0001 | 2025-08-19 | SSN RIO 0201 I/O List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-15 | 19 | Approved with Comments | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 000579 | 2024-07-22 | 2025-08-19 | 4 | AWC | Approved with Comments | 5 | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " |  | 2025-08
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1191 | A | 131242-WSD11-DR-M-1191 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 | 2025-02-26 00:00:00 | To check with relevent area discipline (Target 28 Feb 2025) | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" |  | 2024-07
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3190 | A | 131242-WSD11-DR-M-3190 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 |  |  | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" |  | 2024-07
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4000 | A | 131242-WSD11-DR-M-4000 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 |  |  | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" |  | 2024-07
000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9000 | A | 131242-WSD11-DR-M-9000 | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | 53 | Approved with Comments | YES | 2024-10-24 | NO | Resubmitted | 0 |  |  | 000580 | 2024-07-23 | 2024-07-23 | A | AWC | Approved with Comments | 1 | "THP Cast in Layout Inside Bio-solid Building" |  | 2024-07
000581 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 3100 | A.1 | 131242-WSW41-SD-S-3100 | 2024-07-23 | Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details | For Information | 2024-08-21 | 2024-08-14 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000581&&001085&&001906 | 2024-07-23 | 2025-12-17 | X | INF | Not Approved | 3 | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2024-07
000582 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 1150 | A.1 | 131242-WSW41-SD-S-1150 | 2024-07-23 | Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details | For Information | 2024-08-21 | 2024-08-13 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000582 | 2024-07-23 | 2024-07-23 | A.1 | INF | For Information | 1 | "Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details" |  | 2024-07
000583 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 0 | 131242-WSW41-VI-I-0003 | 2024-07-24 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2024-08-22 | 2024-09-02 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | NAP | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" |  | 2024-07
000583 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 1 | 131242-WSW41-VI-I-0003 | 2024-11-29 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-19 | 2025-02-25 | 62 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | NAP | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" |  | 2024-11
000583 | 02 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 2 | 131242-WSW41-VI-I-0003 | 2025-03-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-08 | 2025-03-25 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" |  | 2025-03
000583 | 03 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 3 | 131242-WSW41-VI-I-0003 | 2025-06-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-09 | 2025-07-10 | 15 | Approved with Comments | YES | 2025-07-30 | NO | Resubmitted | 0 |  |  | 000583 | 2024-07-24 | 2025-06-19 | 3 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" |  | 2025-06
000584 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0027 | 0 | 131242-WSW41-MI-P-0027 | 2024-07-24 | Process & MEICA Meeting Minutes 0027_20240704 | Rev 0: For Information | 2024-08-22 | 2024-08-29 | 26 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000584 | 2024-07-24 | 2024-07-24 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0027_20240704" |  | 2024-07
000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0013 | 0 | 131242-WSW41-SP-C-0013 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000585 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " |  | 2024-07
000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0014 | 0 | 131242-WSW41-SP-C-0014 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000585 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " |  | 2024-07
000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0016 | 0 | 131242-WSW41-SP-C-0016 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000586 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" |  | 2024-07
000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0017 | 0 | 131242-WSW41-SP-C-0017 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000586 | 2024-07-25 | 2024-07-25 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" |  | 2024-07
000587 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0008 | 0 | 131242-WSW41-VI-S-0008 | 2024-07-25 | Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd. | Approved | 2024-08-23 | 2024-08-12 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000587 | 2024-07-25 | 2024-07-25 | 0 | APP | Approved | 1 | "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" |  | 2024-07
000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | 6 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" |  | 2024-07
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-12 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | NAP | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" |  | 2024-08
000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | NAP | Approved with Comments | 3 | "THP URA Submission" |  | 2024-08
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-10-29 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588&&001394 | 2024-07-25 | 2025-06-23 | A | AWC | Not Approved | 4 | "THP URA Submission" && "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | AWC | Approved with Comments | 3 | "THP URA Submission" |  | 2024-10
000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000588 | 2024-07-25 | 2024-10-09 | A | AWC | Approved with Comments | 3 | "THP URA Submission" |  | 2024-10
000589 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 0 | 131242-WST02-VI-E-0007 | 2024-07-26 | Vendor Approval of Earthing System & LPS Material | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached sheet for comments | 2024-08-26 | 2024-08-05 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000589 | 2024-07-26 | 2024-09-02 | 1 | AWC | Approved | 2 | "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" |  | 2024-07
000589 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 1 | 131242-WST02-VI-E-0007 | 2024-09-02 | Vendor Approval of Earthing System & LPS Material (Heng) | Rev 1: Approved. | 2024-09-20 | 2024-10-29 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000589 | 2024-07-26 | 2024-09-02 | 1 | APP | Approved | 2 | "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" |  | 2024-09
000590 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 0 | 131242-WST02-DS-E-0004 | 2024-07-27 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 | 13 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000590 | 2024-07-27 | 2025-04-09 | 2 | REJ | Approved with Comments | 3 | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" |  | 2024-07
000590 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 1 | 131242-WST02-DS-E-0004 | 2024-12-02 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-20 | 2025-01-16 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000590 | 2024-07-27 | 2025-04-09 | 2 | AWC | Approved with Comments | 3 | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" |  | 2024-12
000590 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 2 | 131242-WST02-DS-E-0004 | 2025-04-09 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-29 | 2025-05-08 | 21 | Approved with Comments | YES | 2025-05-28 | NO | Resubmitted | 0 |  | Pending reply from Sunlight. Will follow-up with Sunlight. | 000590 | 2024-07-27 | 2025-04-09 | 2 | AWC | Approved with Comments | 3 | "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" |  | 2025-04
000591 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 0 | 131242-WSD11-CL-P-0003 | 2024-07-28 | PLant Drain Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-08-26 | 2024-09-02 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000591 | 2024-07-28 | 2024-10-21 | 1 | NAP | Approved | 2 | "PLant Drain Hydraulic Calculation" |  | 2024-07
000591 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 1 | 131242-WSD11-CL-P-0003 | 2024-10-21 | PLant Drain Hydraulic Calculation | Rev 1: Approved | 2024-11-11 | 2024-11-15 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000591 | 2024-07-28 | 2024-10-21 | 1 | APP | Approved | 2 | "PLant Drain Hydraulic Calculation" |  | 2024-10
000592 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0006 | 0 | 131242-WST02-VI-E-0006 | 2024-07-28 | Vendor Approval of SS Cable Ladder, Trays and Accessories | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 | 13 | Approved with Comments | YES | 2024-09-04 | NO | Resubmitted | 0 |  | To follow-up with UNITED ULI. | 000592 | 2024-07-28 | 2024-07-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of SS Cable Ladder, Trays and Accessories" |  | 2024-07
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5351 | 0 | 131242-WST02-DS-M-5351 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-07
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5361 | 0 | 131242-WST02-DS-M-5361 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-07
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5371 | 0 | 131242-WST02-DS-M-5371 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-07
000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5381 | 0 | 131242-WST02-DS-M-5381 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-07
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5351 | 1 | 131242-WST02-DS-M-5351 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-12
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5361 | 1 | 131242-WST02-DS-M-5361 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | YES | 2025-04-24 | NO | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-12
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5371 | 1 | 131242-WST02-DS-M-5371 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | YES | 2025-04-24 | NO | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-12
000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5381 | 1 | 131242-WST02-DS-M-5381 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | 75 | Approved with Comments | YES | 2025-04-24 | NO | Resubmitted | 0 |  |  | 000593 | 2024-07-28 | 2024-12-23 | 1 | AWC | Approved with Comments | 2 | "Progressive Cavity Pump Data Sheet" |  | 2024-12
000594 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0003 | 0 | 131242-WSW41-PO-E-0003 | 2024-07-29 | Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight) | Rev 0: For Information. | 2024-08-27 | 2024-08-05 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000594 | 2024-07-29 | 2024-07-29 | 0 | INF | For Information | 1 | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" |  | 2024-07
000595 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0007 | 0 | 131242-WSW41-PO-M-0007 | 2024-07-30 | Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen) | For Information | 2024-08-28 | 2024-08-29 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000595 | 2024-07-30 | 2024-07-30 | 0 | INF | For Information | 1 | "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" |  | 2024-07
000596 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0035 | 0 | 131242-WSW41-LT-PM-0035 | 2024-07-30 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024 | Please refer to S.O. Correspondence No.229. | 2024-08-28 | 2024-10-07 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000596 | 2024-07-30 | 2024-07-30 | 0 | APP | Approved | 1 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024" |  | 2024-07
000597 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 0 | 131242-WSD11-CL-P-0006 | 2024-07-30 | Air Compressor Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-04 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000597 | 2024-07-30 | 2024-09-30 | 1 | AWC | Approved with Comments | 2 | "Air Compressor Pressure Loss Calculation" |  | 2024-07
000597 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 1 | 131242-WSD11-CL-P-0006 | 2024-09-30 | Air Compressor Pressure Loss Calculation | Rev 1: Approved with Comments. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 26 | Approved with Comments | YES | 2024-11-25 | NO | Resubmitted | 0 |  |  | 000597 | 2024-07-30 | 2024-09-30 | 1 | AWC | Approved with Comments | 2 | "Air Compressor Pressure Loss Calculation" |  | 2024-09
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5009 | A | 131242-WST02-DR-M-5009 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 | 2025-03-07 00:00:00 | Shall update and submit under as built drawing | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" |  | 2024-07
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5010 | A | 131242-WST02-DR-M-5010 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" |  | 2024-07
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7008 | A | 131242-WST02-SH-M-7008 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" |  | 2024-07
000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7009 | A | 131242-WST02-SH-M-7009 | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | 24 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  |  | 000598 | 2024-07-30 | 2024-07-30 | A | AWC | Approved with Comments | 1 | "Underground Cast In Schedule and Details" |  | 2024-07
000599 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 0 | 131242-WSW41-VI-I-0004 | 2024-07-30 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-28 | 2024-10-10 | 52 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000599 | 2024-07-30 | 2024-11-02 | 1 | NAP | Not Approved | 2 | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" |  | 2024-07
000599 | 01 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 1 | 131242-WSW41-VI-I-0004 | 2024-11-02 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-21 | 2024-12-18 | 32 | Not Approved | YES | 2025-01-07 | NO | Resubmitted | 0 |  |  | 000599 | 2024-07-30 | 2024-11-02 | 1 | NAP | Not Approved | 2 | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" |  | 2024-11
000600 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0004 | 0 | 131242-WSW41-QA-M-0004 | 2024-07-31 | Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings | Rev 0: Approved | 2024-08-29 | 2024-09-02 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000600 | 2024-07-31 | 2024-07-31 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" |  | 2024-07
000601 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 0 | 131242-WSD11-SP-I-0001 | 2024-07-31 | THP Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-29 | 2024-10-09 | 50 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000601 | 2024-07-31 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "THP Functional Design Specification" |  | 2024-07
000601 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 1 | 131242-WSD11-SP-I-0001 | 2025-05-19 | THP Functional Design Specification | Rev.1: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-06-06 | 2025-07-04 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000601 | 2024-07-31 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "THP Functional Design Specification" |  | 2025-05
000601 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 2 | 131242-WSD11-SP-I-0001 | 2025-08-12 | THP Functional Design Specification | Rev.2: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-09-01 | 2025-10-08 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000601 | 2024-07-31 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "THP Functional Design Specification" |  | 2025-08
000602 | 00 | Low | EICA | NA | 131242 | WSD11 | SP | I | 0003 | 0 | 131242-WSD11-SP-I-0003 | 2024-07-31 | THP Alarm List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-29 | 2024-11-08 | 72 | Not Approved | YES | 2024-11-28 | NO | Resubmitted | 0 |  |  | 000602 | 2024-07-31 | 2024-07-31 | 0 | NAP | Not Approved | 1 | "THP Alarm List" |  | 2024-07
000603 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 1000 | 0 | 131242-WST02-CL-M-1000 | 2024-07-31 | SSN Underground Piping Stress Calculation Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-08-29 | 2024-09-02 | 23 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 |  | The Only comment is to get PE endorsement (Mech Piping PE) | 000603 | 2024-07-31 | 2024-07-31 | 0 | AWC | Approved with Comments | 1 | "SSN Underground Piping Stress Calculation Report" |  | 2024-07
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | A | 131242-WST02-DR-EI-7000 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | A | 131242-WST02-DR-EI-7001 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | A | 131242-WST02-DR-EI-7002 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | A | 131242-WST02-DR-EI-7003 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | A | 131242-WST02-DR-EI-7004 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | A | 131242-WST02-DR-EI-7005 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | A | 131242-WST02-DR-EI-7006 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | A | 131242-WST02-DR-EI-7007 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | A | 131242-WST02-DR-EI-7008 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | A | 131242-WST02-DR-EI-7009 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | A | 131242-WST02-DR-EI-7010 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7011 | A | 131242-WST02-DR-EI-7011 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | REJ | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | A | 131242-WST02-DR-EI-7020 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | A | 131242-WST02-DR-EI-7021 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | A | 131242-WST02-DR-EI-7022 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | A | 131242-WST02-DR-EI-7023 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | A | 131242-WST02-DR-EI-7024 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | A | 131242-WST02-DR-EI-7025 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | A | 131242-WST02-DR-EI-7026 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | A | 131242-WST02-DR-EI-7027 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | A | 131242-WST02-DR-EI-7028 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | A | 131242-WST02-DR-EI-7029 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7030 | A | 131242-WST02-DR-EI-7030 | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | REJ | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | A | 131242-WST02-DR-EP-7100 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | A | 131242-WST02-DR-EP-7101 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | A | 131242-WST02-DR-EP-7102 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | A | 131242-WST02-DR-EP-7103 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | A | 131242-WST02-DR-EP-7104 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | A | 131242-WST02-DR-EP-7105 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | A | 131242-WST02-DR-EP-7106 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | A | 131242-WST02-DR-EP-7107 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | A | 131242-WST02-DR-EP-7108 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | A | 131242-WST02-DR-EP-7109 | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-08
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | B | 131242-WST02-DR-EI-7000 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | B | 131242-WST02-DR-EI-7001 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | B | 131242-WST02-DR-EI-7002 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | B | 131242-WST02-DR-EI-7003 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | B | 131242-WST02-DR-EI-7004 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | B | 131242-WST02-DR-EI-7005 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | B | 131242-WST02-DR-EI-7006 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | B | 131242-WST02-DR-EI-7007 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | B | 131242-WST02-DR-EI-7008 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | B | 131242-WST02-DR-EI-7009 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | B | 131242-WST02-DR-EI-7010 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7011 | B | 131242-WST02-DR-EI-7011 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | NAP | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | B | 131242-WST02-DR-EI-7020 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | B | 131242-WST02-DR-EI-7021 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | B | 131242-WST02-DR-EI-7022 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | B | 131242-WST02-DR-EI-7023 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | B | 131242-WST02-DR-EI-7024 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | B | 131242-WST02-DR-EI-7025 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | B | 131242-WST02-DR-EI-7026 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | B | 131242-WST02-DR-EI-7027 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | B | 131242-WST02-DR-EI-7028 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | B | 131242-WST02-DR-EI-7029 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7030 | B | 131242-WST02-DR-EI-7030 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2024-11-21 | B | NAP | Not Approved | 2 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | B | 131242-WST02-DR-EP-3000 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | B | 131242-WST02-DR-EP-3001 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | B | 131242-WST02-DR-EP-3002 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | B | 131242-WST02-DR-EP-3003 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | B | 131242-WST02-DR-EP-3004 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | B | 131242-WST02-DR-EP-3005 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | B | 131242-WST02-DR-EP-3006 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | B | 131242-WST02-DR-EP-3007 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | B | 131242-WST02-DR-EP-3008 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | B | 131242-WST02-DR-EP-3009 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | B | 131242-WST02-DR-EP-3010 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | B | 131242-WST02-DR-EP-3011 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | B | 131242-WST02-DR-EP-7100 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | B | 131242-WST02-DR-EP-7101 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | B | 131242-WST02-DR-EP-7102 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | B | 131242-WST02-DR-EP-7103 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | B | 131242-WST02-DR-EP-7104 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | B | 131242-WST02-DR-EP-7105 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | B | 131242-WST02-DR-EP-7106 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | B | 131242-WST02-DR-EP-7107 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | B | 131242-WST02-DR-EP-7108 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | B | 131242-WST02-DR-EP-7109 | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | NAP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2024-11
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | C | 131242-WST02-DR-EI-7000 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | C | 131242-WST02-DR-EI-7001 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | C | 131242-WST02-DR-EI-7002 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | C | 131242-WST02-DR-EI-7003 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | C | 131242-WST02-DR-EI-7004 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | C | 131242-WST02-DR-EI-7005 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | C | 131242-WST02-DR-EI-7006 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | C | 131242-WST02-DR-EI-7007 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | C | 131242-WST02-DR-EI-7008 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | C | 131242-WST02-DR-EI-7009 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | C | 131242-WST02-DR-EI-7010 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | C | 131242-WST02-DR-EI-7020 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | C | 131242-WST02-DR-EI-7021 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | C | 131242-WST02-DR-EI-7022 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | C | 131242-WST02-DR-EI-7023 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | C | 131242-WST02-DR-EI-7024 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | C | 131242-WST02-DR-EI-7025 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | C | 131242-WST02-DR-EI-7026 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | C | 131242-WST02-DR-EI-7027 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | C | 131242-WST02-DR-EI-7028 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | C | 131242-WST02-DR-EI-7029 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | C | 131242-WST02-DR-EP-3000 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | C | 131242-WST02-DR-EP-3001 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | C | 131242-WST02-DR-EP-3002 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | C | 131242-WST02-DR-EP-3003 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | C | 131242-WST02-DR-EP-3004 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | C | 131242-WST02-DR-EP-3005 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | C | 131242-WST02-DR-EP-3006 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | C | 131242-WST02-DR-EP-3007 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | C | 131242-WST02-DR-EP-3008 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | C | 131242-WST02-DR-EP-3009 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | C | 131242-WST02-DR-EP-3010 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | C | 131242-WST02-DR-EP-3011 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | C | 131242-WST02-DR-EP-7100 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | C | 131242-WST02-DR-EP-7101 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | C | 131242-WST02-DR-EP-7102 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | C | 131242-WST02-DR-EP-7103 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | C | 131242-WST02-DR-EP-7104 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | C | 131242-WST02-DR-EP-7105 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | C | 131242-WST02-DR-EP-7106 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | C | 131242-WST02-DR-EP-7107 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | C | 131242-WST02-DR-EP-7108 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | C | 131242-WST02-DR-EP-7109 | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | AWC | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-01
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | D | 131242-WST02-DR-EI-7000 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 | TBA |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | D | 131242-WST02-DR-EI-7001 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | D | 131242-WST02-DR-EI-7002 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | D | 131242-WST02-DR-EI-7003 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | D | 131242-WST02-DR-EI-7004 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | D | 131242-WST02-DR-EI-7005 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | D | 131242-WST02-DR-EI-7006 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | D | 131242-WST02-DR-EI-7007 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | D | 131242-WST02-DR-EI-7008 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | D | 131242-WST02-DR-EI-7009 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | D | 131242-WST02-DR-EI-7010 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | D | 131242-WST02-DR-EI-7020 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | D | 131242-WST02-DR-EI-7021 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | D | 131242-WST02-DR-EI-7022 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | D | 131242-WST02-DR-EI-7023 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | D | 131242-WST02-DR-EI-7024 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | D | 131242-WST02-DR-EI-7025 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | D | 131242-WST02-DR-EI-7026 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | D | 131242-WST02-DR-EI-7027 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | D | 131242-WST02-DR-EI-7028 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | D | 131242-WST02-DR-EI-7029 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000604&&000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | D | 131242-WST02-DR-EP-3000 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | D | 131242-WST02-DR-EP-3001 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | D | 131242-WST02-DR-EP-3002 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | D | 131242-WST02-DR-EP-3003 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | D | 131242-WST02-DR-EP-3004 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | D | 131242-WST02-DR-EP-3005 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | D | 131242-WST02-DR-EP-3006 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | D | 131242-WST02-DR-EP-3007 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | D | 131242-WST02-DR-EP-3008 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | D | 131242-WST02-DR-EP-3009 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | D | 131242-WST02-DR-EP-3010 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | D | 131242-WST02-DR-EP-3011 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | APP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | D | 131242-WST02-DR-EP-7100 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | D | 131242-WST02-DR-EP-7101 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | D | 131242-WST02-DR-EP-7102 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | D | 131242-WST02-DR-EP-7103 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | D | 131242-WST02-DR-EP-7104 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | D | 131242-WST02-DR-EP-7105 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | D | 131242-WST02-DR-EP-7106 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | D | 131242-WST02-DR-EP-7107 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | D | 131242-WST02-DR-EP-7108 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | D | 131242-WST02-DR-EP-7109 | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605 | 2024-08-01 | 2025-05-04 | D | APP | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" |  | 2025-05
000606 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 0 | 131242-WST02-VI-E-0008 | 2024-08-01 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-24 | 38 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000606 | 2024-08-01 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" |  | 2024-08
000606 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 1 | 131242-WST02-VI-E-0008 | 2024-10-28 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 1: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2024-11-18 | 2024-11-24 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000606 | 2024-08-01 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" |  | 2024-10
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | A | 131242-WST02-DR-EP-3000 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | A | 131242-WST02-DR-EP-3001 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | A | 131242-WST02-DR-EP-3002 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | A | 131242-WST02-DR-EP-3003 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | A | 131242-WST02-DR-EP-3004 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | A | 131242-WST02-DR-EP-3005 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | A | 131242-WST02-DR-EP-3006 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | A | 131242-WST02-DR-EP-3007 | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | 34 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000607 | 2024-08-01 | 2025-05-04 | D | REJ | Approved | 4 | "SSN LVSG 0101AB Single Line Diagram" && "SSN LVSG 0101AB Outline GA Drawing" |  | 2024-08
000608 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0008 | 0 | 131242-WSW41-PO-M-0008 | 2024-08-01 | Unpriced PO for Centrifugal Pump (KSB) | For Information | 2024-08-30 | 2024-08-29 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000608 | 2024-08-01 | 2024-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for Centrifugal Pump (KSB)" |  | 2024-08
000609 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0009 | 0 | 131242-WSW41-PO-M-0009 | 2024-08-01 | Unpriced PO for FRP Tank (Jizhou Zhongyi) | For Information | 2024-08-30 | 2024-08-29 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000609 | 2024-08-01 | 2024-08-01 | 0 | INF | For Information | 1 | "Unpriced PO for FRP Tank (Jizhou Zhongyi)" |  | 2024-08
000610 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | K | 2001 | 0 | 131242-WST02-VI-K-2001 | 2024-08-01 | LPS Sample Materials – U-Clamp Connector | Rev 0: Approved. Please refer to attached sheet for comments | 2024-08-30 | 2024-08-05 | 2 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000610 | 2024-08-01 | 2024-08-01 | 0 | APP | Approved | 1 | "LPS Sample Materials – U-Clamp Connector" |  | 2024-08
000611 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 0 | 131242-WSW41-SP-C-0019 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-02 | 2024-08-19 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000611 | 2024-08-02 | 2024-08-02 | 0 | AWC | Approved with Comments | 2 | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" |  | 2024-08
000611 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 1 | 131242-WSW41-SP-C-0019 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Approved | 2024-08-23 | 2024-09-17 | 32 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000611 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved with Comments | 2 | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" |  | 2024-08
000612 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0005 | 0 | 131242-WSW41-QA-M-0005 | 2024-08-02 | Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings | Rev 0: Approved | 2024-09-02 | 2024-09-02 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000612 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" |  | 2024-08
000613 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0013 | 0 | 131242-WSW41-PC-W-0013 | 2024-08-02 | Payment Claim No.13 | Rev(0): Approved. Please refer to S.O. correspondence no. 0196 dated 5 August 2024. | 2024-09-02 | 2024-08-16 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000613 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved | 1 | "Payment Claim No.13" |  | 2024-08
000614 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0036 | 0 | 131242-WSW41-LT-PM-0036 | 2024-08-02 | NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions | Please refer to S.O. Correspondence No.229. | 2024-09-02 | 2024-10-07 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000614 | 2024-08-02 | 2024-08-02 | 0 | APP | Approved | 1 | "NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-S-1100 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.2 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1104 | A.3 | 131242-WST02-SD-S-1104 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5100 | A.3 | 131242-WST02-SD-S-5100 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | AWC | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5101 | A.3 | 131242-WST02-SD-S-5101 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | AWC | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5102 | A.3 | 131242-WST02-SD-S-5102 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5103 | A.3 | 131242-WST02-SD-S-5103 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5104 | A.3 | 131242-WST02-SD-S-5104 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | AWC | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-S-1100 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-16 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.2 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1104 | A.3 | 131242-WST02-SD-S-1104 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5100 | A.3 | 131242-WST02-SD-S-5100 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | APP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5101 | A.3 | 131242-WST02-SD-S-5101 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | APP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5102 | A.3 | 131242-WST02-SD-S-5102 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5103 | A.3 | 131242-WST02-SD-S-5103 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5104 | A.3 | 131242-WST02-SD-S-5104 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000615 | 2024-08-05 | 2024-08-27 | A.3 | APP | Approved | 2 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" |  | 2024-08
000616 | 00 | Qili | Process | NA | 131242 | WST02 | CL | M | 0002 | 0 | 131242-WST02-CL-M-0002 | 2024-08-05 | Strength Calculation for Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-02 | 20 | Approved with Comments | YES | 2024-09-20 | NO | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending MP updates | 000616 | 2024-08-05 | 2024-08-05 | 0 | AWC | Approved with Comments | 1 | "Strength Calculation for Biomass Separator" |  | 2024-08
000617 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0009 | 0 | 131242-WSW41-PS-HS-0009 | 2024-08-05 | Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024 | For Information | 2024-09-03 | 2024-08-21 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000617 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | A | 131242-WSD11-DR-M-5051 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | A | 131242-WSD11-DR-M-5052 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | A | 131242-WSD11-DR-M-5053 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | A | 131242-WSD11-DR-M-5054 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | A | 131242-WSD11-DR-M-5071 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | A | 131242-WSD11-DR-M-5072 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | A | 131242-WSD11-DR-M-5073 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | A | 131242-WSD11-DR-M-5081 | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-08
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | B | 131242-WSD11-DR-M-5051 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-07 00:00:00 | All comments on 2D Drawing (Mech/Elec.) was closed, minor cmt on 3D, need QA/QC checklist, Drafting team will follow up..-> in 1 to 2 weeks | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | B | 131242-WSD11-DR-M-5052 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | B | 131242-WSD11-DR-M-5053 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | B | 131242-WSD11-DR-M-5054 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | B | 131242-WSD11-DR-M-5071 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | B | 131242-WSD11-DR-M-5072 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | B | 131242-WSD11-DR-M-5073 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | B | 131242-WSD11-DR-M-5081 | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | AWC | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2024-10
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | C | 131242-WSD11-DR-M-5051 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-02 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | C | 131242-WSD11-DR-M-5052 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | C | 131242-WSD11-DR-M-5053 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | C | 131242-WSD11-DR-M-5054 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | C | 131242-WSD11-DR-M-5071 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | C | 131242-WSD11-DR-M-5072 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | C | 131242-WSD11-DR-M-5073 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | C | 131242-WSD11-DR-M-5081 | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | 229 | Awaiting S.O.'s response | YES | 2025-06-30 | NO | Overdue | 0 |  |  | 000618 | 2024-08-05 | 2025-05-13 | C | PEN | Approved with Comments | 3 | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" |  | 2025-05
000619 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0006 | 0 | 131242-WSW41-RT-C-0006 | 2024-08-05 | Bored Piling Pile Eccentricity Reports (ECC 01 to 07) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | 10 | Not Approved | YES | 2024-09-06 | NO | Resubmitted | 0 |  |  | 000619 | 2024-08-05 | 2024-08-05 | 0 | NAP | Not Approved | 1 | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" |  | 2024-08
000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0015 | 0 | 131242-WSW41-SP-C-0015 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000620 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " |  | 2024-08
000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0018 | 0 | 131242-WSW41-SP-C-0018 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000620 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " |  | 2024-08
000621 | 00 | Qili | Process | NA | 131242 | WST02 | MM | P | 0001 | 0 | 131242-WST02-MM-P-0001 | 2024-08-05 | SSN Reactor Floor flat Design Memo | For Information | 2024-09-03 | 2024-08-21 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000621 | 2024-08-05 | 2024-08-05 | 0 | INF | For Information | 1 | "SSN Reactor Floor flat Design Memo" |  | 2024-08
000622 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0028 | 0 | 131242-WSW41-MI-P-0028 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000622 | 2024-08-06 | 2024-08-06 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " |  | 2024-08
000622 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0029 | 0 | 131242-WSW41-MI-P-0029 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000622 | 2024-08-06 | 2024-08-06 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " |  | 2024-08
000623 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 0 | 131242-WSW41-QA-E-0001 | 2024-08-06 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-10-29 | 60 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | AWC | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " |  | 2024-08
000623 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 1 | 131242-WSW41-QA-E-0001 | 2024-11-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-14 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | AWC | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " |  | 2024-11
000623 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 2 | 131242-WSW41-QA-E-0001 | 2025-01-16 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | APP | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " |  | 2025-01
000623 | 03 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 3 | 131242-WSW41-QA-E-0001 | 2025-02-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 3: Approved. | 2025-03-13 | 2025-04-27 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | APP | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " |  | 2025-02
000623 | 04 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 4 | 131242-WSW41-QA-E-0001 | 2025-07-03 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 4: Approved with comments. To revise and resubmit. | 2025-07-23 | 2025-09-15 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | AWC | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " |  | 2025-07
000623 | 05 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 5 | 131242-WSW41-QA-E-0001 | 2025-10-08 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 5: Approved | 2025-10-28 | 2026-02-20 | 97 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000623 | 2024-08-06 | 2025-10-08 | 5 | APP | Approved | 6 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " |  | 2025-10
000624 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 0 | 131242-WSW41-QA-M-0003 | 2024-08-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 0: Not approved - Revise and Resubmit | 2024-09-04 | 2024-09-06 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000624 | 2024-08-06 | 2024-11-21 | 2 | NAP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" |  | 2024-08
000624 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 1 | 131242-WSW41-QA-M-0003 | 2024-10-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 1: Not approved - Revise and Resubmit | 2024-10-29 | 2024-10-25 | 12 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000624 | 2024-08-06 | 2024-11-21 | 2 | NAP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" |  | 2024-10
000624 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 2 | 131242-WSW41-QA-M-0003 | 2024-11-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 2: Approved | 2024-12-11 | 2024-12-05 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000624 | 2024-08-06 | 2024-11-21 | 2 | APP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" |  | 2024-11
000625 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0007 | 0 | 131242-WSW41-QA-M-0007 | 2024-08-06 | FAT Procedure for Air Receiver and Air Dryer (Compressor air system) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-09-04 | 21 | Approved with Comments | YES | 2024-09-24 | NO | Resubmitted | 0 |  |  | 000625 | 2024-08-06 | 2024-08-06 | 0 | AWC | Approved with Comments | 1 | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" |  | 2024-08
000626 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 0 | 131242-WST02-DS-E-0000 | 2024-08-07 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-05 | 2024-10-29 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000626 | 2024-08-07 | 2024-12-19 | 1 | AWC | Approved with Comments | 2 | "SSN MV Cable and Pilot Cable Data Sheet and Specification" |  | 2024-08
000626 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 1 | 131242-WST02-DS-E-0000 | 2024-12-19 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-01-16 | 20 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000626 | 2024-08-07 | 2024-12-19 | 1 | AWC | Approved with Comments | 2 | "SSN MV Cable and Pilot Cable Data Sheet and Specification" |  | 2024-12
000627 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0011 | 0 | 131242-WSW41-QA-C-0011 | 2024-08-07 | Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 | 8 | Approved with Comments | YES | 2024-09-06 | NO | Resubmitted | 0 |  |  | 000627 | 2024-08-07 | 2024-08-07 | 0 | AWC | Approved with Comments | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" |  | 2024-08
000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0013 | 0 | 131242-WSW41-MI-PM-0013 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000628 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0013_20240618" |  | 2024-08
000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0013 | 0 | 131242-WSW41-PS-PM-0013 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000628 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0013_20240618" |  | 2024-08
000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0014 | 0 | 131242-WSW41-MI-PM-0014 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000629 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0014_20240723" |  | 2024-08
000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0014 | 0 | 131242-WSW41-PS-PM-0014 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000629 | 2024-08-07 | 2024-08-07 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0014_20240723" |  | 2024-08
000630 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 0 | 131242-WSW41-SP-C-0020 | 2024-08-07 | Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000630 | 2024-08-07 | 2024-10-02 | 1 | AWC | Approved | 2 | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" |  | 2024-08
000630 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 1 | 131242-WSW41-SP-C-0020 | 2024-10-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.1: Approved | 2024-10-22 | 2024-10-14 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000630 | 2024-08-07 | 2024-10-02 | 1 | APP | Approved | 2 | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" |  | 2024-10
000631 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jul-2024) | Resubmit: Considering the VCM submitted only contains link, Contractor to provide full list of contents (from the link) per folder/zip file with file size and timestamp (Transmittal Cover). Also, Contractor to ensure that the link provided should be Contractor's OneDrive link or link to Contractor's CDE. | 2024-08-05 | 2024-08-08 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000550&&000631 | 2024-07-08 | 2024-08-12 | 0 | INF | For Information | 3 | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" |  | 2024-07
000631 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041 | 2024-08-12 | Submission Of BIM Coordination VCM Model (Jul-2024) | For Information | 2024-08-30 | 2024-08-26 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000550&&000631 | 2024-07-08 | 2024-08-12 | 0 | INF | For Information | 3 | "Submission Of BIM Coordination VCM Model (Jun-2024)" && "Submission Of BIM Coordination VCM Model (Jul-2024)" |  | 2024-08
000632 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0016 | 0 | 131242-WSW41-MS-C-0016 | 2024-08-12 | MSRA, SWP for Erection, Dismantling and Use of Scaffold | Approved | 2024-09-09 | 2024-08-30 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000632 | 2024-08-12 | 2024-08-12 | 0 | APP | Approved | 1 | "MSRA, SWP for Erection, Dismantling and Use of Scaffold " |  | 2024-08
000633 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0017 | 0 | 131242-WSW41-MS-C-0017 | 2024-08-12 | MSRA, SWP for Jet Grouting | Approved | 2024-09-09 | 2024-09-02 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000633 | 2024-08-12 | 2024-08-12 | 0 | APP | Approved | 1 | "MSRA, SWP for Jet Grouting" |  | 2024-08
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0010 | 0 | 131242-WSD11-DS-E-0010 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" |  | 2024-08
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0012 | 0 | 131242-WSD11-DS-E-0012 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" |  | 2024-08
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0013 | 0 | 131242-WSD11-DS-E-0013 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" |  | 2024-08
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0014 | 0 | 131242-WSD11-DS-E-0014 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" |  | 2024-08
000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0015 | 0 | 131242-WSD11-DS-E-0015 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | 56 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000634 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "THP Pump Motor Data Sheet" |  | 2024-08
000635 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 0 | 131242-WSD11-DS-M-0015 | 2024-08-12 | Data Sheet of Flash Tank Discharge Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000635 | 2024-08-12 | 2024-11-13 | 1 | AWC | Approved | 2 | "Data Sheet of Flash Tank Discharge Pump " |  | 2024-08
000635 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 1 | 131242-WSD11-DS-M-0015 | 2024-11-13 | Data Sheet of Flash Tank Discharge Pump | Rev 1: Approved | 2024-12-03 | 2024-12-06 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000635 | 2024-08-12 | 2024-11-13 | 1 | APP | Approved | 2 | "Data Sheet of Flash Tank Discharge Pump " |  | 2024-11
000636 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 0 | 131242-WSD11-DS-M-0016 | 2024-08-12 | Data Sheet of Precooler S2 CIRC Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000636 | 2024-08-12 | 2024-11-13 | 1 | AWC | Approved | 2 | "Data Sheet of Precooler S2 CIRC Pump" |  | 2024-08
000636 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 1 | 131242-WSD11-DS-M-0016 | 2024-11-13 | Data Sheet of Precooler S2 CIRC Pump | Rev 1: Approved | 2024-12-03 | 2024-06-12 | 0 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000636 | 2024-08-12 | 2024-11-13 | 1 | APP | Approved | 2 | "Data Sheet of Precooler S2 CIRC Pump" |  | 2024-11
000637 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 0 | 131242-WSD11-DS-M-0017 | 2024-08-12 | Data Sheet of Digester Feed Pump | Rev 0: Not approved - Revise and Resubmit | 2024-09-09 | 2024-10-09 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000637 | 2024-08-12 | 2025-03-04 | 1 | NAP | Approved | 2 | "Data Sheet of Digester Feed Pump" |  | 2024-08
000637 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 1 | 131242-WSD11-DS-M-0017 | 2025-03-04 | Data Sheet of Digester Feed Pump | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000637 | 2024-08-12 | 2025-03-04 | 1 | APP | Approved | 2 | "Data Sheet of Digester Feed Pump" |  | 2025-03
000638 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0018 | 0 | 131242-WSW41-VI-C-0018 | 2024-08-13 | Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings) | Rev 0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-08-19 | 4 | Approved with Comments | YES | 2024-09-06 | NO | Resubmitted | 0 |  |  | 000638 | 2024-08-13 | 2024-08-13 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" |  | 2024-08
000639 | 00 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 0 | 131242-WST02-SP-I-0002 | 2024-08-13 | SSN Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-10-09 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000639 | 2024-08-13 | 2025-02-21 | 1 | AWC | Approved with Comments | 2 | "SSN Functional Design Specification" |  | 2024-08
000639 | 01 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 1 | 131242-WST02-SP-I-0002 | 2025-02-21 | SSN Functional Design Specification | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-13 | 2025-03-13 | 14 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000639 | 2024-08-13 | 2025-02-21 | 1 | AWC | Approved with Comments | 2 | "SSN Functional Design Specification" |  | 2025-02
000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1165 | A | 131242-WSD11-DR-M-1165 | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | 41 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 | 2025-02-28 00:00:00 | 2nd priority (Shall update and submit under as built drawing) | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | AWC | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" |  | 2024-08
000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1166 | A | 131242-WSD11-DR-M-1166 | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | 41 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 |  |  | 000302&&000640 | 2024-08-13 | 2024-10-18 | A.1 | AWC | Not Approved | 2 | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" |  | 2024-08
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612_BCA | F | 131242-WST02-DR-S-5600_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " |  | 2024-08
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612_BCA | F | 131242-WST02-DR-S-5601_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " |  | 2024-08
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612_BCA | F | 131242-WST02-DR-S-5602_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " |  | 2024-08
000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612_BCA | F | 131242-WST02-DR-S-8600_ST612_BCA | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000641 | 2024-08-13 | 2024-08-13 | F | INF | For Information | 1 | "BCA Approval of ST612 – Typical Railing " |  | 2024-08
000642 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 0 | 131242-WSW41-QA-M-0008 | 2024-08-13 | Inspection Test Plan for HDPE Pipe Installation | As requested to reject this submittal. | 2024-09-10 | 2024-09-24 | 30 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000642 | 2024-08-13 | 2024-10-01 | 1 | REJ | Approved | 2 | "Inspection Test Plan for HDPE Pipe Installation" |  | 2024-08
000642 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 1 | 131242-WSW41-QA-M-0008 | 2024-10-01 | Inspection Test Plan for HDPE Pipe Installation | Rev 1: Approved | 2024-10-21 | 2024-10-25 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000642 | 2024-08-13 | 2024-10-01 | 1 | APP | Approved | 2 | "Inspection Test Plan for HDPE Pipe Installation" |  | 2024-10
000643 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 0 | 131242-WSW41-QA-M-0006 | 2024-08-13 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-10 | 2024-10-16 | 46 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000643 | 2024-08-13 | 2025-09-25 | 1 | NAP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" |  | 2024-08
000643 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-M-0006 | 2024-12-12 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 1: Approved | 2025-01-02 | 2025-01-20 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000643 | 2024-08-13 | 2025-09-25 | 1 | APP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" |  | 2024-12
000643 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-M-0006 | 2025-09-25 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 2: Approved | 2025-10-15 | 2025-10-06 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000643 | 2024-08-13 | 2025-09-25 | 1 | APP | Approved | 3 | "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" |  | 2025-09
000644 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 0 | 131242-WSD11-RT-EL-0000 | 2024-08-13 | THP Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" |  | 2024-08
000644 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 1 | 131242-WSD11-RT-EL-0000 | 2025-04-22 | THP Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-05-06 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" |  | 2025-04
000644 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-EL-0000 | 2025-06-20 | THP Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-08-04 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" |  | 2025-06
000644 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-EL-0000 | 2025-12-15 | THP Lux Simulation Report | Rev 3: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | 35 | Not Approved | YES | 2026-02-20 | NO | Resubmitted | 0 |  |  | 000644 | 2024-08-13 | 2025-12-15 | 2 | NAP | Not Approved | 4 | "THP Lux Simulation Report" |  | 2025-12
000645 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 0 | 131242-WST02-RT-EL-0000 | 2024-08-13 | SSN Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | NAP | Approved with Comments | 4 | "SSN Lux Simulation Report" |  | 2024-08
000645 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 1 | 131242-WST02-RT-EL-0000 | 2025-03-12 | SSN Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-05-06 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | NAP | Approved with Comments | 4 | "SSN Lux Simulation Report" |  | 2025-03
000645 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 2 | 131242-WST02-RT-EL-0000 | 2025-06-20 | SSN Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. | 2025-07-10 | 2025-08-04 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | NAP | Approved with Comments | 4 | "SSN Lux Simulation Report" |  | 2025-06
000645 | 03 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 3 | 131242-WST02-RT-EL-0000 | 2025-11-20 | SSN Lux Simulation Report | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-10 | 2025-12-17 | 19 | Approved with Comments | YES | 2026-01-06 | NO | Resubmitted | 0 |  |  | 000645 | 2024-08-13 | 2025-11-20 | 3 | AWC | Approved with Comments | 4 | "SSN Lux Simulation Report" |  | 2025-11
000646 | 00 | Low/ Fox | EICA | NA | 131242 | WST02 | DR | I | 7002 | A | 131242-WST02-DR-I-7002 | 2024-08-13 | Aeration Blower System Architecture Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-10 | 2024-08-27 | 10 | Approved with Comments | YES | 2024-09-16 | NO | Resubmitted | 0 |  |  | 000646&&001547 | 2024-08-13 | 2025-10-28 | B | AWC | Approved with Comments | 3 | "Aeration Blower System Architecture Drawing" && " THP Overall Network Diagrams" |  | 2024-08
000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 1900 | A | 131242-WST02-DR-S-1900 | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | 21 | Approved with Comments | YES | 2024-10-01 | NO | Resubmitted | 0 |  |  | 000647 | 2024-08-13 | 2024-08-13 | A | AWC | Approved with Comments | 1 | "Waterproofing Concrete Demarcation of SSN Main Water Tank " |  | 2024-08
000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 3900 | A | 131242-WST02-DR-S-3900 | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | 21 | Approved with Comments | YES | 2024-10-01 | NO | Resubmitted | 0 |  |  | 000647 | 2024-08-13 | 2024-08-13 | A | AWC | Approved with Comments | 1 | "Waterproofing Concrete Demarcation of SSN Main Water Tank " |  | 2024-08
000648 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0012 | 0 | 131242-WSD11-DS-M-0012 | 2024-08-12 | Data Sheet of Desuperheater | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-09-03 | 16 | Approved with Comments | YES | 2024-09-23 | NO | Resubmitted | 0 |  |  | 000648 | 2024-08-12 | 2024-08-12 | 0 | AWC | Approved with Comments | 1 | "Data Sheet of Desuperheater " |  | 2024-08
000649 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0004 | 0 | 131242-WSD11-CL-P-0004 | 2024-08-15 | THP Feed Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-08 | 38 | Approved with Comments | YES | 2024-10-28 | NO | Resubmitted | 0 |  |  | 000649 | 2024-08-15 | 2024-08-15 | 0 | AWC | Approved with Comments | 1 | "THP Feed Pump Pressure Loss Calculation" |  | 2024-08
000650 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0008 | 0 | 131242-WSD11-CL-P-0008 | 2024-08-15 | Desuperheater Calculation | Rev 0: Approved with Comments. To revise and resubmit. Please include PE Endorsement. | 2024-09-12 | 2024-08-23 | 6 | Approved with Comments | YES | 2024-09-12 | NO | Resubmitted | 0 |  |  | 000650 | 2024-08-15 | 2024-08-15 | 0 | AWC | Approved with Comments | 1 | "Desuperheater Calculation" |  | 2024-08
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | A | 131242-WSD11-DR-M-5100 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2024-08
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | A | 131242-WSD11-DR-M-5110 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2024-08
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | A | 131242-WSD11-DR-M-5120 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2024-08
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | A | 131242-WSD11-DR-M-5130 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2024-08
000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | A | 131242-WSD11-DR-M-5140 | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2024-08
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | B | 131242-WSD11-DR-M-5100 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | B | 131242-WSD11-DR-M-5110 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | B | 131242-WSD11-DR-M-5120 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5121 | B | 131242-WSD11-DR-M-5121 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | B | 131242-WSD11-DR-M-5130 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5131 | B | 131242-WSD11-DR-M-5131 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5132 | B | 131242-WSD11-DR-M-5132 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | B | 131242-WSD11-DR-M-5140 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2024-08-15 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5141 | B | 131242-WSD11-DR-M-5141 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5142 | B | 131242-WSD11-DR-M-5142 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 0 |  |  | 000651 | 2025-06-12 | 2025-06-12 | B | PEN | Awaiting S.O.'s response | 1 | "THP PC Pump GA Drawings" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | B | 131242-WSD11-DR-M-5150 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 177 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" |  | 2025-06
000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | B | 131242-WSD11-DR-M-5160 | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | 207 | Awaiting S.O.'s response | YES | 2025-07-30 | NO | Overdue | 177 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | PEN | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" |  | 2025-06
000652 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0030 | 0 | 131242-WSW41-MI-P-0030 | 2024-08-06 | Process & MEICA Meeting Minutes 0030_20240801 | Rev 0: For Information | 2024-09-04 | 2024-09-03 | 20 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000652 | 2024-08-06 | 2024-08-06 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0030_20240801" |  | 2024-08
000653 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0010 | 0 | 131242-WSW41-PO-M-0010 | 2024-07-08 | Unpriced PO for Hyperbolix Mixer (Entec International) | For Information | 2024-08-05 | 2024-08-29 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000653 | 2024-07-08 | 2024-07-08 | 0 | INF | For Information | 1 | "Unpriced PO for Hyperbolix Mixer (Entec International)" |  | 2024-07
000654 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0011 | 0 | 131242-WSW41-PO-M-0011 | 2024-08-15 | Unpriced PO for Dosing Pump (ProMinent) | Rev 0: For Information | 2024-09-12 | 2024-08-29 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000654 | 2024-08-15 | 2024-08-15 | 0 | APP | Approved | 1 | "Unpriced PO for Dosing Pump (ProMinent)" |  | 2024-08
000655 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0010 | 0 | 131242-WSW41-QA-M-0010 | 2024-08-15 | Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-09-03 | 13 | Approved with Comments | YES | 2024-09-23 | NO | Resubmitted | 0 |  |  | 000655 | 2024-08-15 | 2024-08-15 | 0 | AWC | Approved with Comments | 1 | "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" |  | 2024-08
000656 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 0 | 131242-WSD11-DS-M-0011 | 2024-08-16 | Data Sheet for Steam Sparger Package | Rev 0: Not approved - Revise and Resubmit | 2024-09-13 | 2024-09-10 | 17 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000656 | 2024-08-16 | 2025-02-18 | 1 | NAP | Approved | 2 | "Data Sheet for Steam Sparger Package" |  | 2024-08
000656 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 1 | 131242-WSD11-DS-M-0011 | 2025-02-18 | Data Sheet for Steam Sparger Package | Rev 1: Approved | 2025-03-10 | 2025-03-10 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000656 | 2024-08-16 | 2025-02-18 | 1 | APP | Approved | 2 | "Data Sheet for Steam Sparger Package" |  | 2025-02
000657 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0011 | 0 | 131242-WSW41-QA-M-0011 | 2024-08-19 | Procedure for Welding of Underground HDPE Pipe | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-16 | 2024-09-10 | 16 | Approved with Comments | YES | 2024-09-30 | NO | Resubmitted | 0 |  |  | 000657 | 2024-08-19 | 2024-08-19 | 0 | AWC | Approved with Comments | 1 | "Procedure for Welding of Underground HDPE Pipe" |  | 2024-08
000658 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0015 | 0 | 131242-WSW41-RT-PM-0015 | 2024-08-19 | C4B Monthly Progress Report Number No.15 (07 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-09-16 | 2024-09-06 | 14 | Approved with Comments | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000658 | 2024-08-19 | 2024-08-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.15 (07 24)" |  | 2024-08
000659 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1382 | 0 | 131242-WST02-DS-E-1382 | 2024-08-19 | Sample Board Submission for uPVC Pipe 6” & 4” | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-09-16 | 2024-09-26 | 28 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000659 | 2024-08-19 | 2024-08-19 | 0 | APP | Approved | 1 | "Sample Board Submission for uPVC Pipe 6” & 4” " |  | 2024-08
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7020 | A | 131242-WST02-DR-I-7020 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" |  | 2024-08
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7021 | A | 131242-WST02-DR-I-7021 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" |  | 2024-08
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7022 | A | 131242-WST02-DR-I-7022 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" |  | 2024-08
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7023 | A | 131242-WST02-DR-I-7023 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" |  | 2024-08
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7024 | A | 131242-WST02-DR-I-7024 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" |  | 2024-08
000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7025 | A | 131242-WST02-DR-I-7025 | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | 14 | Not Approved | YES | 2024-09-26 | NO | Resubmitted | 0 |  |  | 000660 | 2024-08-19 | 2024-08-19 | A | NAP | Not Approved | 1 | "SSN Control Network Connection Drawing" |  | 2024-08
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-BF-7002 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000661&&001305 | 2024-08-20 | 2025-06-19 | A.1 | NAP | Approved with Comments | 3 | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" |  | 2024-08
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1005 | A | 131242-WST02-DR-BF-1005 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | NAP | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " |  | 2024-08
000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5001 | A | 131242-WST02-DR-BF-5001 | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | NAP | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " |  | 2024-08
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A.1 | 131242-WST02-DR-BF-7002 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661&&001305 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 3 | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" |  | 2025-06
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1005 | A.1 | 131242-WST02-DR-BF-1005 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " |  | 2025-06
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5001 | A.1 | 131242-WST02-DR-BF-5001 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 2 | "SSN External Fire Hydrant Layout & Details " |  | 2025-06
000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5002 | A.1 | 131242-WST02-DR-BF-5002 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | 74 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000661 | 2025-06-19 | 2025-06-19 | A.1 | AWC | Approved with Comments | 1 | "SSN External Fire Hydrant Layout & Details " |  | 2025-06
000662 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0009 | 0 | 131242-WSD11-CL-P-0009 | 2024-08-20 | Flash Tank Discharge Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-09 | 36 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 |  |  | 000662 | 2024-08-20 | 2024-08-20 | 0 | AWC | Approved with Comments | 1 | "Flash Tank Discharge Pump Pressure Loss Calculation" |  | 2024-08
000663 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0010 | 0 | 131242-WSD11-CL-P-0010 | 2024-08-20 | Precooler S2 Circ Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-08 | 35 | Approved with Comments | YES | 2024-10-28 | NO | Resubmitted | 0 |  |  | 000663 | 2024-08-20 | 2024-08-20 | 0 | AWC | Approved with Comments | 1 | "Precooler S2 Circ Pump Pressure Loss Calculation" |  | 2024-08
000664 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 0 | 131242-WSD11-CL-P-0007 | 2024-08-20 | Steam Sparger Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-09-10 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000664 | 2024-08-20 | 2025-04-10 | 1 | AWC | Approved | 2 | "Steam Sparger Calculation" |  | 2024-08
000664 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 1 | 131242-WSD11-CL-P-0007 | 2025-04-10 | Steam Sparger Calculation | Rev 1: Approved. Please furnish PE Endorsement. | 2025-04-30 | 2025-10-06 | 127 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000664 | 2024-08-20 | 2025-04-10 | 1 | APP | Approved | 2 | "Steam Sparger Calculation" |  | 2025-04
000665 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 0 | 131242-WST02-QA-E-0002 | 2024-08-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-09-24 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000665 | 2024-08-21 | 2024-10-25 | 1 | NAP | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" |  | 2024-08
000665 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 1 | 131242-WST02-QA-E-0002 | 2024-10-25 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-04 | 6 | Approved with Comments | YES | 2024-11-22 | NO | Resubmitted | 0 |  |  | 000665 | 2024-08-21 | 2024-10-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" |  | 2024-10
000666 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0010 | 0 | 131242-WSW41-PS-HS-0010 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Mar 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000666 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Mar 2024" |  | 2024-08
000667 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0011 | 0 | 131242-WSW41-PS-HS-0011 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Apr 2024 | Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000667 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Apr 2024" |  | 2024-08
000668 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0012 | 0 | 131242-WSW41-PS-HS-0012 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for May 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000668 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for May 2024" |  | 2024-08
000669 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0013 | 0 | 131242-WSW41-PS-HS-0013 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Jun 2024 | Rev 0: Scoring confirmed to be at 93/100 | 2024-09-19 | 2024-08-30 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000669 | 2024-08-22 | 2024-08-22 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jun 2024" |  | 2024-08
000670 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | - | 131242-WSW41-QA-C-0013 | 2024-08-22 | Monthly Concrete Cube Records for Structural works for Apr 2024 | Rejected as requested by Contractor | 2024-09-19 | 2024-08-30 | 6 | Rejected | NO |  | YES | Resubmitted | 0 |  | Request for Reject | 000670 | 2024-08-22 | 2024-08-27 | 0 | REJ | Rejected | 2 | "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " |  | 2024-08
000670 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | 0 | 131242-WSW41-QA-C-0013 | 2024-08-27 | Monthly Concrete Cube Records for Structural works for May 2024 | Rejected as requested by Contractor | 2024-09-16 |  | 414 | Awaiting S.O.'s response | YES | 2024-10-14 | NO | Overdue | 0 |  |  | 000670 | 2024-08-22 | 2024-08-27 | 0 | PEN | Rejected | 2 | "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " |  | 2024-08
000671 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 0 | 131242-WSW41-VI-E-0010 | 2024-08-23 | Vendor Approval of Surge Diverter | Rev 0: Approved with comments. Refer to attached file for comments. | 2024-09-20 | 2024-09-26 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000671 | 2024-08-23 | 2024-10-04 | 1 | AWC | Approved | 2 | "Vendor Approval of Surge Diverter " |  | 2024-08
000671 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 1 | 131242-WSW41-VI-E-0010 | 2024-10-04 | Vendor Approval of Surge Diverter | Rev 1: Approved. | 2024-10-24 | 2024-10-29 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000671 | 2024-08-23 | 2024-10-04 | 1 | APP | Approved | 2 | "Vendor Approval of Surge Diverter " |  | 2024-10
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1200 | A | 131242-WSD11-DR-M-1200 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 | 2025-03-05 00:00:00 | Submission unsuccessful on 11 Jul 2024. | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2024-08
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1201 | A | 131242-WSD11-DR-M-1201 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2024-08
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1202 | A | 131242-WSD11-DR-M-1202 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2024-08
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1203 | A | 131242-WSD11-DR-M-1203 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2024-08
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1204 | A | 131242-WSD11-DR-M-1204 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2024-08
000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 8000 | A | 131242-WSD11-DR-M-8000 | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | 39 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000292&&000672 | 2024-08-23 | 2025-11-28 | A.1 | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" |  | 2024-08
000673 | 00 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-Z-0001 | 2024-08-23 | SSN 30 Percent ALMOP Report | Rev 0: Not approved - Revise and Resubmit | 2024-09-20 | 2024-09-06 | 10 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000673 | 2024-08-23 | 2024-09-06 | 0 | REJ | Approved with Comments | 2 | "SSN 30 Percent ALMOP Report" |  | 2024-08
000673 | 01 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-Z-0001 | 2024-09-06 | SSN 30 Percent ALMOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-14 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000673 | 2024-08-23 | 2024-09-06 | 0 | AWC | Approved with Comments | 2 | "SSN 30 Percent ALMOP Report" |  | 2024-09
000673 | 02 | Qili | Process | NA | 131242 | WST02 | RT | Z | Comment Reply Sheet 20240716 S673.2 | 0 | 131242-WST02-RT-Z-Comment Reply Sheet 20240716 S673.2 | 2024-10-29 | SSN 30 Percent ALMOP Report | Rev 2: Approved | 2024-11-19 | 2024-11-27 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000673 | 2024-10-29 | 2024-10-29 | 0 | APP | Approved | 1 | "SSN 30 Percent ALMOP Report" |  | 2024-10
000674 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0037 | 0 | 131242-WSW41-LT-PM-0037 | 2024-08-23 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements | Received for information. Please refer to S.O. Correspondence no. 241 dated 23 Oct 2024. | 2024-09-20 | 2025-11-20 | 324 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000674 | 2024-08-23 | 2024-08-23 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements " |  | 2024-08
000675 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 0 | 131242-WSW41-VI-M-0021 | 2024-08-23 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-09-10 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-14 00:00:00 | In Progress | 000675 | 2024-08-23 | 2025-07-02 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" |  | 2024-08
000675 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 1 | 131242-WSW41-VI-M-0021 | 2025-07-02 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 1: Approved | 2025-07-22 | 2025-11-24 | 103 | Approved | NO |  | YES | Resubmitted | 0 | 2025-03-14 00:00:00 | In Progress | 000675 | 2024-08-23 | 2025-07-02 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" |  | 2025-07
000676 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 0 | 131242-WST02-QA-E-0003 | 2024-08-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-29 | 46 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000676 | 2024-08-26 | 2025-02-07 | 2 | NAP | Approved with Comments | 3 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " |  | 2024-08
000676 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 1 | 131242-WST02-QA-E-0003 | 2024-12-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-02-03 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000676 | 2024-08-26 | 2025-02-07 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " |  | 2024-12
000676 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 2 | 131242-WST02-QA-E-0003 | 2025-02-07 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-27 | 2025-02-18 | 7 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000676 | 2024-08-26 | 2025-02-07 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " |  | 2025-02
000677 | 00 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 0 | 131242-WST02-SP-I-0001 | 2024-08-26 | SSN Control Narrative | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-23 | 2024-10-09 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000677 | 2024-08-26 | 2025-03-24 | 1 | AWC | Approved with Comments | 2 | "SSN Control Narrative" |  | 2024-08
000677 | 01 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 1 | 131242-WST02-SP-I-0001 | 2025-03-24 | SSN Control Narrative | Approved with Comments | 2025-04-11 | 2025-05-15 | 38 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 000677 | 2024-08-26 | 2025-03-24 | 1 | AWC | Approved with Comments | 2 | "SSN Control Narrative" |  | 2025-03
000678 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 0 | 131242-WSD11-RT-P-0003 | 2024-08-26 | THP HAZOP Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-09 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000678 | 2024-08-26 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "THP HAZOP Report" |  | 2024-08
000678 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 1 | 131242-WSD11-RT-P-0003 | 2024-10-28 | THP HAZOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2025-04-08 | 116 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000678 | 2024-08-26 | 2024-10-28 | 1 | AWC | Approved with Comments | 2 | "THP HAZOP Report" |  | 2024-10
000679 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0021 | 0 | 131242-WSW41-VI-E-0021 | 2024-08-26 | Vendor Approval of Electrical Consultant – YHW LLP | Approved | 2024-09-23 | 2024-09-26 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000679 | 2024-08-26 | 2024-08-26 | 0 | APP | Approved | 1 | "Vendor Approval of Electrical Consultant – YHW LLP" |  | 2024-08
000680 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | QA | C | 0014 | 0 | 131242-WST02-QA-C-0014 | 2024-08-27 | Laboratory Test Report on Soil Samples | For Information | 2024-09-24 | 2024-09-17 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000680 | 2024-08-27 | 2024-08-27 | 0 | INF | For Information | 1 | "Laboratory Test Report on Soil Samples" |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.1 | 131242-WSD11-DR-M-1170 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | A.1 | 131242-WSD11-DR-M-1171 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | A.1 | 131242-WSD11-DR-M-1172 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1173 | A.1 | 131242-WSD11-DR-M-1173 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | AWC | Approved | 2 | "Biosolid Building Piping Opening " |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | A.1 | 131242-WSD11-DR-M-3170 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | A.1 | 131242-WSD11-DR-M-3171 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | AWC | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2024-08
000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4100 | A.1 | 131242-WSD11-DR-M-4100 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | AWC | Approved | 2 | "Biosolid Building Piping Opening " |  | 2024-08
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.2 | 131242-WSD11-DR-M-1170 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-10 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2025-02
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | A.2 | 131242-WSD11-DR-M-1171 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2025-02
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | A.2 | 131242-WSD11-DR-M-1172 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2025-02
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1173 | A.2 | 131242-WSD11-DR-M-1173 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | APP | Approved | 2 | "Biosolid Building Piping Opening " |  | 2025-02
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | A.2 | 131242-WSD11-DR-M-3170 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2025-02
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | A.2 | 131242-WSD11-DR-M-3171 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000391&&000681 | 2024-03-23 | 2025-02-18 | A.2 | APP | Approved | 3 | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " |  | 2025-02
000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4100 | A.2 | 131242-WSD11-DR-M-4100 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000681 | 2024-08-28 | 2025-02-18 | A.2 | APP | Approved | 2 | "Biosolid Building Piping Opening " |  | 2025-02
000682 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 0 | 131242-WSW41-QA-C-0015 | 2024-08-29 | Plate Load test report | Rev.0:Not Approved. Please refer to attached comment sheet for resubmission. | 2024-09-26 | 2024-09-18 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000682 | 2024-08-29 | 2024-10-30 | 1 | NAP | Approved | 2 | "Plate Load test report " |  | 2024-08
000682 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 1 | 131242-WSW41-QA-C-0015 | 2024-10-30 | Plate Load test report | Approved | 2024-11-20 | 2024-11-08 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000682 | 2024-08-29 | 2024-10-30 | 1 | APP | Approved | 2 | "Plate Load test report " |  | 2024-10
000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0029 | 0 | 131242-WSW41-MI-C-0029 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000683 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" |  | 2024-08
000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0030 | 0 | 131242-WSW41-MI-C-0030 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000683 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0019 | 0 | 131242-WSW41-MI-IM-0019 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0020 | 0 | 131242-WSW41-MI-IM-0020 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0021 | 0 | 131242-WSW41-MI-IM-0021 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0022 | 0 | 131242-WSW41-MI-IM-0022 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0023 | 0 | 131242-WSW41-MI-IM-0023 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0024 | 0 | 131242-WSW41-MI-IM-0024 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0025 | 0 | 131242-WSW41-MI-IM-0025 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0026 | 0 | 131242-WSW41-MI-IM-0026 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0027 | 0 | 131242-WSW41-MI-IM-0027 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0029 | 0 | 131242-WSW41-MI-IM-0029 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0030 | 0 | 131242-WSW41-MI-IM-0030 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0031 | 0 | 131242-WSW41-MI-IM-0031 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000684 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" |  | 2024-08
000685 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0031 | 0 | 131242-WSW41-MI-P-0031 | 2024-08-29 | Process & MEICA Meeting Minutes 0031_20240815 | Rev. 0 - For Information | 2024-09-26 | 2024-09-10 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000685 | 2024-08-29 | 2024-08-29 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0031_20240815" |  | 2024-08
000686 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 0 | 131242-WSD11-DS-M-0021 | 2024-08-29 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 0: Not approved - Revise and Resubmit | 2024-09-26 | 2024-10-17 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000686 | 2024-08-29 | 2025-01-20 | 2 | NAP | Approved | 3 | "Data Sheet of Pressure Relief Valve at Air Receiver" |  | 2024-08
000686 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 1 | 131242-WSD11-DS-M-0021 | 2024-11-07 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-27 | 2024-12-05 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000686 | 2024-08-29 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet of Pressure Relief Valve at Air Receiver" |  | 2024-11
000686 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 2 | 131242-WSD11-DS-M-0021 | 2025-01-20 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000686 | 2024-08-29 | 2025-01-20 | 2 | APP | Approved | 3 | "Data Sheet of Pressure Relief Valve at Air Receiver" |  | 2025-01
000687 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | Z | 0001 | 0 | 131242-WSD11-RT-Z-0001 | 2024-08-29 | THP 30 Percent ALMOP Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-17 | 35 | Approved with Comments | YES | 2024-11-06 | NO | Resubmitted | 0 |  |  | 000687 | 2024-08-29 | 2024-08-29 | 0 | AWC | Approved with Comments | 1 | "THP 30 Percent ALMOP Study Report" |  | 2024-08
000688 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 0 | 131242-WSD11-QA-M-0012 | 2024-08-30 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-11-05 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000688 | 2024-08-30 | 2025-04-21 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" |  | 2024-08
000688 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 1 | 131242-WSD11-QA-M-0012 | 2025-04-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-09 | 2025-09-08 | 100 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000688 | 2024-08-30 | 2025-04-21 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" |  | 2025-04
000689 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 0 | 131242-WSW41-QA-E-0004 | 2024-08-30 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 0: Rejected. Refer to the attached file for comments. | 2024-09-27 | 2024-11-25 | 61 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000689 | 2024-08-30 | 2025-03-14 | 2 | REJ | Approved | 3 | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" |  | 2024-08
000689 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 1 | 131242-WSW41-QA-E-0004 | 2025-02-07 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Refer to the attached file for comments. | 2025-02-27 | 2025-03-13 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000689 | 2024-08-30 | 2025-03-14 | 2 | AWC | Approved | 3 | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" |  | 2025-02
000689 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 2 | 131242-WSW41-QA-E-0004 | 2025-03-14 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 2: Approved. | 2025-04-03 | 2025-05-07 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000689 | 2024-08-30 | 2025-03-14 | 2 | APP | Approved | 3 | "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" |  | 2025-03
000690 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0011 | 0 | 131242-WSD11-CL-P-0011 | 2024-08-30 | THP Plant Process Water Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-09-27 | 2024-10-29 | 42 | Not Approved | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000690 | 2024-08-30 | 2024-08-30 | 0 | NAP | Not Approved | 1 | "THP Plant Process Water Hydraulic Calculation" |  | 2024-08
000691 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 0 | 131242-WSW41-QA-M-0013 | 2024-08-31 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-10-14 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000691 | 2024-08-31 | 2025-04-17 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " |  | 2024-08
000691 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 1 | 131242-WSW41-QA-M-0013 | 2025-04-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Approved | 2025-05-07 | 2025-05-19 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000691 | 2024-08-31 | 2025-04-17 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " |  | 2025-04
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-S-1010_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | A | 131242-WST02-DR-S-1011_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | A | 131242-WST02-DR-S-1012_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3000_ST607_BCA | A | 131242-WST02-DR-S-3000_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000692 | 2024-08-31 | 2024-08-31 | A | INF | For Information | 1 | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | A | 131242-WST02-DR-S-3002_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | A | 131242-WST02-DR-S-7003_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | A | 131242-WST02-DR-S-7004_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | A | 131242-WST02-DR-S-8003_ST607_BCA | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000538&&000692 | 2024-07-01 | 2024-08-31 | A | INF | For Information | 2 | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " && "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " |  | 2024-08
000693 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-C-0016 | 2024-08-31 | Monthly Concrete Cube Records for Structural works for July 2024 | For Information | 2024-09-27 | 2024-09-18 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000693&&000724 | 2024-08-31 | 2024-09-16 | 0 | INF | For Information | 2 | "Monthly Concrete Cube Records for Structural works for July 2024" && "Mock-up Temperature Monitoring Test Reports (Alliance)" |  | 2024-08
000694 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 0 | 131242-WSW41-QA-M-0015 | 2024-09-02 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-30 | 2024-10-13 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000694 | 2024-09-02 | 2025-03-27 | 1 | NAP | Approved | 2 | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" |  | 2024-09
000694 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 1 | 131242-WSW41-QA-M-0015 | 2025-03-27 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Approved | 2025-04-16 | 2025-05-19 | 37 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000694 | 2024-09-02 | 2025-03-27 | 1 | APP | Approved | 2 | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" |  | 2025-03
000695 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0038 | 0 | 131242-WSW41-LT-PM-0038 | 2024-09-03 | Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions | Rev(0): Rejected. Please refer to S.O. Correspondence No. 246 dated 7 Nov 2024. | 2024-10-01 | 2025-11-20 | 317 | Rejected | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 000695 | 2024-09-03 | 2024-09-03 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions" |  | 2024-09
000696 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0014 | 0 | 131242-WSW41-PC-W-0014 | 2024-09-03 | Payment Claim No.14 | Rev(0): Approved. See S.O. correspondence no. 219 dated 6 Sep 2024. | 2024-10-01 | 2024-10-09 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000696 | 2024-09-03 | 2024-09-03 | 0 | APP | Approved | 1 | "Payment Claim No.14" |  | 2024-09
000697 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 0 | 131242-WSD11-DS-M-0018 | 2024-09-03 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-14 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000697 | 2024-09-03 | 2025-05-05 | 1 | AWC | Approved with Comments | 2 | "Data Sheet for Pre Cooler Cooling Water Control Valve" |  | 2024-09
000697 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 1 | 131242-WSD11-DS-M-0018 | 2025-05-05 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | 235 | Awaiting S.O.'s response | YES | 2025-06-20 | NO | Overdue | 0 |  |  | 000697 | 2024-09-03 | 2025-05-05 | 1 | PEN | Approved with Comments | 2 | "Data Sheet for Pre Cooler Cooling Water Control Valve" |  | 2025-05
000698 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 0 | 131242-WSD11-DS-M-0019 | 2024-09-03 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-13 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000698 | 2024-09-03 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" |  | 2024-09
000698 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 1 | 131242-WSD11-DS-M-0019 | 2024-11-13 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000698 | 2024-09-03 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" |  | 2024-11
000698 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 2 | 131242-WSD11-DS-M-0019 | 2025-01-20 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000698 | 2024-09-03 | 2025-01-20 | 2 | APP | Approved | 3 | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" |  | 2025-01
000699 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0039 | 0 | 131242-WSW41-LT-PM-0039 | 2024-09-04 | Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024) | Rejected. Please refer to S.O. Correspondence no. 257 dated 2 Dec 2024. | 2024-10-02 | 2025-02-24 | 123 | Rejected | NO |  | YES | Resubmitted | 0 |  | SO Corres 000258. Sent to Vincent on 03 Dec 2025 | 000699 | 2024-09-04 | 2024-09-04 | 0 | REJ | Rejected | 1 | "Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024)" |  | 2024-09
000700 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0015 | 0 | 131242-WSW41-MI-PM-0015 | 2024-09-04 | Monthly Progress Meeting Minutes 0015_20240827 | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000700 | 2024-09-04 | 2024-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0015_20240827" |  | 2024-09
000701 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0015 | 0 | 131242-WSW41-PS-PM-0015 | 2024-09-04 | Monthly Progress Presentation No. 15 (0824) | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000701 | 2024-09-04 | 2024-09-04 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 15 (0824)" |  | 2024-09
000702 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0012 | 0 | 131242-WSW41-PO-M-0012 | 2024-09-05 | Unpriced LOA for Structural Steel Works (Sanhe) | Rev 0: For Information | 2024-10-03 | 2024-10-13 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000702 | 2024-09-05 | 2024-09-05 | 0 | INF | For Information | 1 | "Unpriced LOA for Structural Steel Works (Sanhe) " |  | 2024-09
000703 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0018 | 0 | 131242-WSW41-MS-C-0018 | 2024-09-05 | MSRA for RC Super-Structural Work | Rev.0: Approved. Please refer to comment sheet. | 2024-10-03 | 2024-09-26 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000703 | 2024-09-05 | 2024-09-05 | 0 | APP | Approved | 1 | "MSRA for RC Super-Structural Work" |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000182&&000704 | 2023-11-10 | 2024-09-06 | A | NAP | Not Approved | 3 | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_FSSD | A | 131242-WSD11-DR-A-2000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000704 | 2024-09-06 | 2024-09-06 | A | NAP | Not Approved | 1 | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_FSSD | A | 131242-WSD11-DR-A-3000_FSSD | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | 18 | Not Approved | YES | 2024-10-22 | NO | Resubmitted | 0 |  |  | 000704 | 2024-09-06 | 2024-09-06 | A | NAP | Not Approved | 1 | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " |  | 2024-09
000705 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0019 | 0 | 131242-WSW41-VI-C-0019 | 2024-09-06 | Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-04 | 2024-09-26 | 14 | Approved with Comments | YES | 2024-10-16 | NO | Resubmitted | 0 |  |  | 000705 | 2024-09-06 | 2024-09-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." |  | 2024-09
000706 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 0 | 131242-WST02-QA-E-0005 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | AWC | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" |  | 2024-09
000706 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 1 | 131242-WST02-QA-E-0005 | 2024-11-20 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-10 | 2024-12-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | AWC | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" |  | 2024-11
000706 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 2 | 131242-WST02-QA-E-0005 | 2025-01-16 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | 23 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | APP | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" |  | 2025-01
000706 | 03 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 3 | 131242-WST02-QA-E-0005 | 2025-02-26 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-03-18 | 2025-05-06 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | APP | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" |  | 2025-02
000706 | 04 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 4 | 131242-WST02-QA-E-0005 | 2025-07-03 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-07-23 | 2025-10-01 | 64 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000706 | 2024-09-06 | 2025-07-03 | 4 | APP | Approved | 5 | "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" |  | 2025-07
000707 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 0 | 131242-WST02-QA-E-0006 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000707 | 2024-09-06 | 2025-10-08 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " |  | 2024-09
000707 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 1 | 131242-WST02-QA-E-0006 | 2024-12-20 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-02-20 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000707 | 2024-09-06 | 2025-10-08 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " |  | 2024-12
000707 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 2 | 131242-WST02-QA-E-0006 | 2025-10-08 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 2: Approved | 2025-10-28 | 2026-02-20 | 97 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000707 | 2024-09-06 | 2025-10-08 | 2 | APP | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " |  | 2025-10
000708 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0001 | 0 | 131242-WSW41-QA-I-0001 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000708 | 2024-09-06 | 2024-09-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" |  | 2024-09
000709 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 0 | 131242-WSW41-QA-I-0002 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000709 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " |  | 2024-09
000709 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 1 | 131242-WSW41-QA-I-0002 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000709 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved with Comments | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " |  | 2024-12
000709 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 2 | 131242-WSW41-QA-I-0002 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-29 |  | 122 | Awaiting S.O.'s response | YES | 2025-11-26 | NO | Overdue | 0 |  |  | 000709 | 2024-09-06 | 2025-10-09 | 2 | PEN | Approved with Comments | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " |  | 2025-10
000710 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 0 | 131242-WSW41-QA-I-0003 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000710 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " |  | 2024-09
000710 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 1 | 131242-WSW41-QA-I-0003 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000710 | 2024-09-06 | 2025-10-09 | 2 | AWC | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " |  | 2024-12
000710 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 2 | 131242-WSW41-QA-I-0003 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 2: Approved | 2025-10-29 | 2026-02-20 | 96 | Approved | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 000710 | 2024-09-06 | 2025-10-09 | 2 | APP | Approved | 3 | "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " |  | 2025-10
000711 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0011 | 0 | 131242-WST02-VI-E-0011 | 2024-09-06 | Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-09 | 23 | Approved with Comments | YES | 2024-10-29 | NO | Resubmitted | 0 |  | To follow-up with VICPLAS. | 000711 | 2024-09-06 | 2024-09-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" |  | 2024-09
000712 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-E-0007 | 2024-09-06 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev.0: Rejected as per Contractor's request. | 2024-10-04 | 2024-09-09 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000712 | 2024-09-06 | 2024-09-09 | 0 | REJ | Approved | 2 | "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" |  | 2024-09
000712 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-E-0007 | 2024-09-09 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev 1: Approved. Please refer to attached file and note our comments. | 2024-09-27 | 2024-10-29 | 36 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000712 | 2024-09-06 | 2024-09-09 | 0 | APP | Approved | 2 | "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" |  | 2024-09
000713 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0007 | 0 | 131242-WSW41-RT-C-0007 | 2024-09-06 | Bored Piling Pile Eccentricity Reports (ECC 08 to 12) | Not Approved | 2024-10-04 | 2024-09-13 | 5 | Not Approved | YES | 2024-10-03 | NO | Resubmitted | 0 |  |  | 000713 | 2024-09-06 | 2024-09-06 | 0 | NAP | Not Approved | 1 | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" |  | 2024-09
000714 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | DS | C | 1384 | 0 | 131242-WST02-DS-C-1384 | 2024-09-09 | Sample Board Submission for PVC lining System (Linabond) | For Information | 2024-10-07 | 2024-09-13 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000714 | 2024-09-09 | 2024-09-09 | 0 | INF | For Information | 1 | "Sample Board Submission for PVC lining System (Linabond)" |  | 2024-09
000715 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SP | C | 0021 | 0 | 131242-WSW41-SP-C-0021 | 2024-09-09 | Datat Sheet for Steel Structure and Painting | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-07 | 2024-10-09 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000715 | 2024-09-09 | 2024-11-16 | 1 | NAP | Approved with Comments | 2 | "Datat Sheet for Steel Structure and Painting" |  | 2024-09
000715 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0021 | 1 | 131242-WSW41-SP-C-0021 | 2024-11-16 | Datat Sheet for Steel Structure and Painting | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-05 | 2024-12-08 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000715 | 2024-09-09 | 2024-11-16 | 1 | AWC | Approved with Comments | 2 | "Datat Sheet for Steel Structure and Painting" |  | 2024-11
000716 | 00 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 0 | 131242-WSD11-DS-M-0023 | 2024-09-09 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-07 | 2024-10-14 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000716 | 2024-09-09 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " |  | 2024-09
000716 | 01 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 1 | 131242-WSD11-DS-M-0023 | 2024-11-13 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000716 | 2024-09-09 | 2025-01-20 | 2 | AWC | Approved | 3 | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " |  | 2024-11
000716 | 02 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 2 | 131242-WSD11-DS-M-0023 | 2025-01-20 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000716 | 2024-09-09 | 2025-01-20 | 2 | APP | Approved | 3 | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " |  | 2025-01
000717 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0045 | 0 | 131242-WST02-CD-IM-0045 | 2024-09-09 | Submission Of BIM Coordination VCM Model (Aug-2024) | For Information. | 2024-10-07 | 2024-09-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000717 | 2024-09-09 | 2024-09-09 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Aug-2024)" |  | 2024-09
000718 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 0 | 131242-WST02-DS-E-0010 | 2024-09-10 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-10-29 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000718 | 2024-09-10 | 2025-03-07 | 2 | AWC | Approved with Comments | 3 | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" |  | 2024-09
000718 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 1 | 131242-WST02-DS-E-0010 | 2024-12-19 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-02-18 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000718 | 2024-09-10 | 2025-03-07 | 2 | AWC | Approved with Comments | 3 | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" |  | 2024-12
000718 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 2 | 131242-WST02-DS-E-0010 | 2025-03-07 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-04-27 | 36 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000718 | 2024-09-10 | 2025-03-07 | 2 | AWC | Approved with Comments | 3 | "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" |  | 2025-03
000719 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1383 | 0 | 131242-WST02-DS-E-1383 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0003) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000719 | 2024-09-10 | 2024-09-10 | 0 | APP | Approved | 1 | "Sample Board Submission for Lightning and Earthing System (MTF 0003)" |  | 2024-09
000720 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1385 | 0 | 131242-WST02-DS-E-1385 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0005) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000720 | 2024-09-10 | 2024-09-10 | 0 | APP | Approved | 1 | "Sample Board Submission for Lightning and Earthing System (MTF 0005)" |  | 2024-09
000721 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5451 | 0 | 131242-WST02-DS-M-5451 | 2024-09-10 | Data Sheet for Side Manway | Rev 0: Rejected | 2024-10-08 | 2024-10-11 | 23 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000721 | 2024-09-10 | 2024-09-10 | 0 | REJ | Rejected | 1 | "Data Sheet for Side Manway" |  | 2024-09
000722 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | Z | 0001 | 0 | 131242-WSW41-MS-Z-0001 | 2024-09-11 | MSRA SWP for Operating Forklift | Approved | 2024-10-09 | 2024-10-10 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000722 | 2024-09-11 | 2024-09-11 | 0 | APP | Approved | 1 | "MSRA SWP for Operating Forklift" |  | 2024-09
000723 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0002 | 0 | 131242-WST02-RT-P-0002 | 2024-09-12 | Detailed Design Report – SSN PACKAGE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-11-07 | 40 | Approved with Comments | YES | 2024-11-27 | NO | Resubmitted | 0 | 2025-04-30 00:00:00 | comments received on 14 Feb | 000723 | 2024-09-12 | 2024-09-12 | 0 | AWC | Approved with Comments | 1 | "Detailed Design Report – SSN PACKAGE" |  | 2024-09
000724 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-C-0016 | 2024-09-16 | Mock-up Temperature Monitoring Test Reports (Alliance) | For Information | 2024-10-14 | 2024-09-26 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000693&&000724 | 2024-08-31 | 2024-09-16 | 0 | INF | For Information | 2 | "Monthly Concrete Cube Records for Structural works for July 2024" && "Mock-up Temperature Monitoring Test Reports (Alliance)" |  | 2024-09
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5351 | 0 | 131242-WST02-CL-P-5351 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-09
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5361 | 0 | 131242-WST02-CL-P-5361 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-09
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5371 | 0 | 131242-WST02-CL-P-5371 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-09
000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5381 | 0 | 131242-WST02-CL-P-5381 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-09
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5351 | 1 | 131242-WST02-CL-P-5351 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-17 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-11
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5361 | 1 | 131242-WST02-CL-P-5361 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-11
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5371 | 1 | 131242-WST02-CL-P-5371 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-11
000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5381 | 1 | 131242-WST02-CL-P-5381 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | 8 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000725 | 2024-09-16 | 2024-11-27 | 1 | AWC | Approved with Comments | 2 | "SSN PC pump sizing calculation " |  | 2024-11
000726 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0016 | 0 | 131242-WSW41-RT-PM-0016 | 2024-09-16 | C4B Monthly Progress Report Number No.16 (08 24) | Rev. 0 - Approved with comments (need to re-submit; see attached comment sheet) | 2024-10-14 | 2024-10-01 | 11 | Approved with Comments | YES | 2024-10-21 | NO | Resubmitted | 0 |  |  | 000726 | 2024-09-16 | 2024-09-16 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.16 (08 24) " |  | 2024-09
000727 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0040 | 0 | 131242-WSW41-LT-PM-0040 | 2024-09-16 | NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA | Rejected. Please refer to S.O. Correspondence no. 258 dated 2 Dec 2024. | 2024-10-14 | 2025-02-24 | 115 | Rejected | NO |  | YES | Resubmitted | 0 |  | SO Corres 000257. Sent to Vincent on 03 Dec 2025 | 000727 | 2024-09-16 | 2024-09-16 | 0 | REJ | Rejected | 1 | "NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA" |  | 2024-09
000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 0 | 131242-WST02-DS-M-5301 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-09
000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 0 | 131242-WST02-DS-M-5311 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-09
000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 1 | 131242-WST02-DS-M-5301 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2024-12-31 | 2024-12-14 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-12
000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 1 | 131242-WST02-DS-M-5311 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2025-01-08 | 2024-12-14 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | NAP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-12
000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 2 | 131242-WST02-DS-M-5301 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-10 | 2025-01-09 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | APP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-12
000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 2 | 131242-WST02-DS-M-5311 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-20 | 2025-01-09 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000728 | 2024-09-18 | 2024-12-20 | 2 | APP | Approved | 3 | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-12
000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5301 | 0 | 131242-WST02-CL-P-5301 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-09
000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5311 | 0 | 131242-WST02-CL-P-5311 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 | 18 | Approved with Comments | YES | 2024-11-01 | NO | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-09
000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5301 | 1 | 131242-WST02-CL-P-5301 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-12-05 | 56 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-09
000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5311 | 1 | 131242-WST02-CL-P-5311 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-12-05 | 56 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000729 | 2024-09-18 | 2024-09-18 | 0 | AWC | Approved with Comments | 2 | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" |  | 2024-09
000730 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 0 | 131242-WST02-VI-E-0009 | 2024-09-18 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 0: Rejected. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-10 | 16 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000730 | 2024-09-18 | 2024-10-14 | 1 | REJ | Approved with Comments | 2 | "Vendor Approval of LPS Materials (Skypro_DEHN)" |  | 2024-09
000730 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 1 | 131242-WST02-VI-E-0009 | 2024-10-14 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 1: Approved with comments. Refer to attached file for comments. | 2024-11-04 | 2024-11-07 | 18 | Approved with Comments | YES | 2024-11-27 | NO | Resubmitted | 0 |  | To follow-up with SKYPRO. | 000730 | 2024-09-18 | 2024-10-14 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of LPS Materials (Skypro_DEHN)" |  | 2024-10
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | B | 131242-WST02-DR-P-6000 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | B | 131242-WST02-DR-P-6001 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | B | 131242-WST02-DR-P-6002 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | B | 131242-WST02-DR-P-6003 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | B | 131242-WST02-DR-P-6004 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | B | 131242-WST02-DR-P-6005 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | B | 131242-WST02-DR-P-6006 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | B | 131242-WST02-DR-P-6007 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | B | 131242-WST02-DR-P-6008 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | B | 131242-WST02-DR-P-6009 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | B | 131242-WST02-DR-P-6010 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | B | 131242-WST02-DR-P-6011 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | B | 131242-WST02-DR-P-6012 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | B | 131242-WST02-DR-P-6013 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | B | 131242-WST02-DR-P-6014 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | B | 131242-WST02-DR-P-6015 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | B | 131242-WST02-DR-P-6016 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | B | 131242-WST02-DR-P-6017 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | B | 131242-WST02-DR-P-6018 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | B | 131242-WST02-DR-P-6019 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | B | 131242-WST02-DR-P-6020 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | B | 131242-WST02-DR-P-6200 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | C | 131242-WST02-DR-P-6300 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | C | 131242-WST02-DR-P-6301 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | C | 131242-WST02-DR-P-6500 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2024-09
000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | B | 131242-WST02-DR-P-6600 | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2024-09
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | C | 131242-WST02-DR-P-6000 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | C | 131242-WST02-DR-P-6001 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | C | 131242-WST02-DR-P-6002 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | C | 131242-WST02-DR-P-6003 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | C | 131242-WST02-DR-P-6004 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | C | 131242-WST02-DR-P-6005 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | C | 131242-WST02-DR-P-6006 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | C | 131242-WST02-DR-P-6007 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | C | 131242-WST02-DR-P-6008 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | C | 131242-WST02-DR-P-6009 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | C | 131242-WST02-DR-P-6010 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | C | 131242-WST02-DR-P-6011 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | C | 131242-WST02-DR-P-6012 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | C | 131242-WST02-DR-P-6013 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | C | 131242-WST02-DR-P-6014 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | C | 131242-WST02-DR-P-6015 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | C | 131242-WST02-DR-P-6016 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | C | 131242-WST02-DR-P-6017 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | C | 131242-WST02-DR-P-6018 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | C | 131242-WST02-DR-P-6019 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | C | 131242-WST02-DR-P-6020 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | C | 131242-WST02-DR-P-6200 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2025-01
000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | C | 131242-WST02-DR-P-6600 | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | 44 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2025-01
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-P-6000 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | D | 131242-WST02-DR-P-6001 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | D | 131242-WST02-DR-P-6002 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | D | 131242-WST02-DR-P-6003 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | D | 131242-WST02-DR-P-6004 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | D | 131242-WST02-DR-P-6005 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | D | 131242-WST02-DR-P-6006 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | D | 131242-WST02-DR-P-6007 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | D | 131242-WST02-DR-P-6008 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | D | 131242-WST02-DR-P-6009 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | D | 131242-WST02-DR-P-6010 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | D | 131242-WST02-DR-P-6011 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | D | 131242-WST02-DR-P-6012 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | D | 131242-WST02-DR-P-6013 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | D | 131242-WST02-DR-P-6014 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | D | 131242-WST02-DR-P-6015 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | D | 131242-WST02-DR-P-6016 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | D | 131242-WST02-DR-P-6017 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | D | 131242-WST02-DR-P-6018 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | D | 131242-WST02-DR-P-6019 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | D | 131242-WST02-DR-P-6020 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | D | 131242-WST02-DR-P-6200 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | AWC | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2025-06
000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | D | 131242-WST02-DR-P-6600 | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | AWC | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2025-06
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-P-6000 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | D | 131242-WST02-DR-P-6001 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | D | 131242-WST02-DR-P-6002 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | D | 131242-WST02-DR-P-6003 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | D | 131242-WST02-DR-P-6004 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | D | 131242-WST02-DR-P-6005 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | D | 131242-WST02-DR-P-6006 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | D | 131242-WST02-DR-P-6007 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | D | 131242-WST02-DR-P-6008 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | D | 131242-WST02-DR-P-6009 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | D | 131242-WST02-DR-P-6010 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | D | 131242-WST02-DR-P-6011 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | D | 131242-WST02-DR-P-6012 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | D | 131242-WST02-DR-P-6013 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | D | 131242-WST02-DR-P-6014 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000398&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Process" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | D | 131242-WST02-DR-P-6015 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | D | 131242-WST02-DR-P-6016 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | D | 131242-WST02-DR-P-6017 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | D | 131242-WST02-DR-P-6018 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | D | 131242-WST02-DR-P-6019 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | D | 131242-WST02-DR-P-6020 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000399&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Chemical Dosing Systems" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | D | 131242-WST02-DR-P-6200 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | PEN | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | PEN | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000187&&000731 | 2023-11-15 | 2026-02-24 | D | PEN | Approved with Comments | 6 | "Plant Drain and Safety Shower P&ID" && "P&ID for SSN" |  | 2026-02
000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | D | 131242-WST02-DR-P-6600 | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | 24 | Awaiting S.O.'s response | YES | 2026-04-13 | NO | NO | 0 |  |  | 000400&&000731 | 2024-03-26 | 2026-02-24 | D | PEN | Approved with Comments | 5 | "P&ID for SSN Plant Water and Instrument Air" && "P&ID for SSN" |  | 2026-02
000732 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0041 | 0 | 131242-WSW41-LT-PM-0041 | 2024-09-20 | CV of Team member (Construction Manager) | Rev 0: Approved | 2024-10-18 | 2024-10-14 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000732 | 2024-09-20 | 2024-09-20 | 0 | APP | Approved | 1 | "CV of Team member (Construction Manager)" |  | 2024-09
000733 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 0 | 131242-WSW41-QA-M-0017 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000733 | 2024-09-20 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " |  | 2024-09
000733 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 1 | 131242-WSW41-QA-M-0017 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-26 | 2025-03-21 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000733 | 2024-09-20 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " |  | 2025-03
000734 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0016 | 0 | 131242-WSW41-QA-M-0016 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | 32 | Approved with Comments | YES | 2024-11-25 | NO | Resubmitted | 0 |  |  | 000734 | 2024-09-20 | 2024-09-20 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " |  | 2024-09
000735 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0042 | 0 | 131242-WSW41-LT-PM-0042 | 2024-09-20 | Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area | Rev (0): Rejected. Please refer to S.O. correspondence no. 268 16 Dec 2024. | 2024-10-18 | 2025-11-20 | 304 | Rejected | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 000735 | 2024-09-20 | 2024-09-20 | 0 | REJ | Rejected | 1 | "Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area" |  | 2024-09
000736 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0032 | 0 | 131242-WSW41-MI-P-0032 | 2024-09-27 | Process & MEICA Meeting Minutes 0032_20240829 | For Information | 2024-10-25 | 2024-10-10 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000736 | 2024-09-27 | 2024-09-27 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0032_20240829" |  | 2024-09
000737 | 00 | Krishanthy | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-C-0008 | 2024-09-27 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-25 | 2024-10-24 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000737&&000771 | 2024-09-27 | 2024-11-07 | 1 | AWC | Approved | 3 | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" |  | 2024-09
000737 | 01 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 1 | 131242-WSW41-RT-C-0008 | 2024-11-07 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.1: Approved | 2024-11-27 | 2024-11-28 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000737&&000771 | 2024-09-27 | 2024-11-07 | 1 | APP | Approved | 3 | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" |  | 2024-11
000738 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0019 | 0 | 131242-WSW41-QA-M-0019 | 2024-09-28 | Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd) | Rev 0: Approved with comments. Refer to attached comment sheet for resubmission. | 2024-10-25 | 2024-10-29 | 21 | Approved with Comments | YES | 2024-11-18 | NO | Resubmitted | 0 |  |  | 000738 | 2024-09-28 | 2024-09-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" |  | 2024-09
000739 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0016 | 0 | 131242-WSW41-MI-PM-0016 | 2024-10-01 | Monthly Progress Meeting Minutes 0016_20240924 | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000739 | 2024-10-01 | 2024-10-01 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0016_20240924" |  | 2024-10
000740 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-PM-0016 | 2024-10-01 | Monthly Progress Presentation No. 16 (0924) | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000740&&000793 | 2024-10-01 | 2024-10-31 | 0 | INF | For Information | 2 | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" |  | 2024-10
000741 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 0 | 131242-WSW41-QA-M-0014 | 2024-10-02 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-30 | 2024-11-05 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000741 | 2024-10-02 | 2025-03-18 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" |  | 2024-10
000741 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 1 | 131242-WSW41-QA-M-0014 | 2025-03-18 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 1: Approved | 2025-04-07 | 2025-04-27 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000741 | 2024-10-02 | 2025-03-18 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" |  | 2025-03
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | C | 131242-WST00-DR-S-8005_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | C | 131242-WST02-DR-S-0302_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | C | 131242-WST02-DR-S-1200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | C | 131242-WST02-DR-S-1201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | C | 131242-WST02-DR-S-1202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | C | 131242-WST02-DR-S-1203_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | C | 131242-WST02-DR-S-1204_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | C | 131242-WST02-DR-S-1205_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | C | 131242-WST02-DR-S-2200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | C | 131242-WST02-DR-S-2201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | C | 131242-WST02-DR-S-2202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | C | 131242-WST02-DR-S-2203_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | C | 131242-WST02-DR-S-3200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | C | 131242-WST02-DR-S-3201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | C | 131242-WST02-DR-S-3202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | C | 131242-WST02-DR-S-5200_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | C | 131242-WST02-DR-S-5201_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | C | 131242-WST02-DR-S-5202_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | C | 131242-WST02-DR-S-5203_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | C | 131242-WST02-DR-S-5204_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | C | 131242-WST02-DR-S-5205_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | C | 131242-WST02-DR-S-5206_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | C | 131242-WST02-DR-S-5207_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | C | 131242-WST02-DR-S-5208_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | C | 131242-WST02-DR-S-5209_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-10
000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608_BCA | 0 | 131242-WST02-CL-S-0002_ST608_BCA | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742 | 2024-10-04 | 2024-10-04 | 0 | INF | For Information | 1 | "BCA submission of ST608 – SSN Shelters (for Information) " |  | 2024-10
000743 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0015 | 0 | 131242-WSW41-PC-W-0015 | 2024-10-04 | Payment Claim No.15 | Rev(0): Approved. Please refer to S.O. correspondence no. 230 dated 4 Oct 2024 | 2024-11-04 | 2024-10-09 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000743 | 2024-10-04 | 2024-10-04 | 0 | APP | Approved | 1 | "Payment Claim No.15" |  | 2024-10
000744 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 0 | 131242-WSW41-QA-M-0018 | 2024-10-04 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-04 | 2024-10-11 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000744 | 2024-10-04 | 2024-10-30 | 1 | AWC | Approved | 2 | " Vendor Manufacturing Inspection test plan for Side Manway " |  | 2024-10
000744 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 1 | 131242-WSW41-QA-M-0018 | 2024-10-30 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 1: Approved | 2024-11-20 | 2024-12-05 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000744 | 2024-10-04 | 2024-10-30 | 1 | APP | Approved | 2 | " Vendor Manufacturing Inspection test plan for Side Manway " |  | 2024-10
000745 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0043 | 0 | 131242-WSW41-LT-PM-0043 | 2024-10-07 | Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 269 dated 17 Dec 2024. | 2024-11-05 | 2025-02-24 | 100 | Rejected | NO |  | YES | Resubmitted | 0 |  | SO Corres 000269. Sent to Vincent on 17 Dec 2025 | 000745 | 2024-10-07 | 2024-10-07 | 0 | REJ | Rejected | 1 | "Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024)" |  | 2024-10
000746 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0044 | 0 | 131242-WSW41-LT-PM-0044 | 2024-10-07 | CV of Team member (WSHO) | Approved | 2024-11-05 | 2024-11-15 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000746 | 2024-10-07 | 2024-10-07 | 0 | APP | Approved | 1 | "CV of Team member (WSHO)" |  | 2024-10
000747 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0017 | 0 | 131242-WSW41-QA-C-0017 | 2024-10-08 | Mock-up Temperature Monitoring Test Reports - G40 (Pan U) | For Information | 2024-11-06 | 2024-10-14 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000747 | 2024-10-08 | 2024-10-08 | 0 | INF | For Information | 1 | "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" |  | 2024-10
000748 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0046 | 0 | 131242-WSW41-CD-IM-0046 | 2024-10-08 | Submission Of BIM Coordination VCM Model (Sept-2024) | For Information. | 2024-11-06 | 2024-10-29 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000748 | 2024-10-08 | 2024-10-08 | 0 | INF | For Information | 1 | "Submission Of BIM Coordination VCM Model (Sept-2024)" |  | 2024-10
000749 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | C | 0007 | 0 | 131242-WST02-CL-C-0007 | 2024-10-09 | Bar chair Design for SSN Water Tanks Raft Slabs | For Information | 2024-11-07 | 2024-10-14 | 3 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000749 | 2024-10-09 | 2024-10-09 | 0 | APP | Approved | 1 | "Bar chair Design for SSN Water Tanks Raft Slabs " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602_BCA | E | 131242-WST00-DR-G-0100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602_BCA | E | 131242-WST00-DR-G-0101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602_BCA | E | 131242-WST00-DR-G-1100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602_BCA | E | 131242-WST00-DR-G-1101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602_BCA | E | 131242-WST00-DR-G-3100_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 3101_ST602_BCA | E | 131242-WST00-DR-G-3101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 5101_ST602_BCA | E | 131242-WST00-DR-G-5101_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602_BCA | E | 131242-WST00-DR-G-8001_ST602_BCA | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000750 | 2024-10-09 | 2024-10-09 | E | INF | For Information | 1 | "BCA approval of ST602 - ERSS Design < 6m " |  | 2024-10
000751 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-12-17 | 0 | AWC | Approved | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-10
000751 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A | 131242-WST02-DR-M-5451 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-10
000751 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A | 131242-WST02-DR-M-5452 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-10
000751 | 01 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-12-17 | 0 | AWC | Approved | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-11
000751 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A.1 | 131242-WST02-DR-M-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-11
000751 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A.1 | 131242-WST02-DR-M-5452 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | AWC | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-11
000751 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451 | 2024-12-17 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-12-17 | 0 | APP | Approved | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-12
000751 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A.1 | 131242-WST02-DR-M-5451 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 51 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | APP | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-11
000751 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A.1 | 131242-WST02-DR-M-5452 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | 51 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000751 | 2024-10-09 | 2024-11-08 | A.1 | APP | Approved with Comments | 3 | "Side Manway Calculation and GA Drawing" |  | 2024-11
000752 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 0 | 131242-WST02-RT-P-0003 | 2024-10-09 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-07 | 2024-11-15 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000752 | 2024-10-09 | 2025-01-20 | 2 | AWC | Approved with Comments | 3 | "SSN HAZOP Report" |  | 2024-10
000752 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 1 | 131242-WST02-RT-P-0003 | 2024-12-10 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-31 | 2024-12-14 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000752 | 2024-10-09 | 2025-01-20 | 2 | AWC | Approved with Comments | 3 | "SSN HAZOP Report" |  | 2024-12
000752 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 2 | 131242-WST02-RT-P-0003 | 2025-01-20 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-13 | 38 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000752 | 2024-10-09 | 2025-01-20 | 2 | AWC | Approved with Comments | 3 | "SSN HAZOP Report" |  | 2025-01
000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1400 | 0 | 131242-WST02-DR-S-1400 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | H | INF | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" |  | 2024-10
000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5400 | 0 | 131242-WST02-DR-S-5400 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | F | INF | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" |  | 2024-10
000754 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0045 | 0 | 131242-WSW41-LT-PM-0045 | 2024-10-10 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025 | 2024-11-08 | 2025-11-20 | 290 | Rejected | YES | 2025-12-10 | NO | Resubmitted | 0 |  |  | 000754 | 2024-10-10 | 2024-10-10 | 0 | REJ | Rejected | 1 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" |  | 2024-10
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 0 | 131242-WST02-DS-M-5501 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-07 00:00:00 | In progress. Process (Qili) will provide updated Datasheet (some change as Pump Calculation, we just received SO cmt sheet on Pump Calc last week) -> in 2 weeks | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2024-10
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5511 | 0 | 131242-WST02-DS-M-5511 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2024-10
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5521 | 0 | 131242-WST02-DS-M-5521 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2024-10
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5531 | 0 | 131242-WST02-DS-M-5531 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2024-10
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5541 | 0 | 131242-WST02-DS-M-5541 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2024-10
000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5551 | 0 | 131242-WST02-DS-M-5551 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2024-10
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 1 | 131242-WST02-DS-M-5501 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2025-03
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5511 | 1 | 131242-WST02-DS-M-5511 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2025-03
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5521 | 1 | 131242-WST02-DS-M-5521 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2025-03
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5531 | 1 | 131242-WST02-DS-M-5531 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2025-03
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5541 | 1 | 131242-WST02-DS-M-5541 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2025-03
000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5551 | 1 | 131242-WST02-DS-M-5551 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | 154 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000755 | 2024-10-11 | 2025-03-04 | 1 | AWC | Approved with Comments | 2 | "Data Sheets for Dosing Pumps" |  | 2025-03
000756 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0020 | 0 | 131242-WSW41-QA-M-0020 | 2024-10-11 | Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-11 | 2024-11-19 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000756 | 2024-10-11 | 2024-10-11 | 0 | AWC | Approved with Comments | 1 | "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" |  | 2024-10
000757 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0018 | 0 | 131242-WSW41-QA-C-0018 | 2024-10-11 | Mock-up Temperature Monitoring Test Reports – G45 (Pan U) | For information. | 2024-11-11 | 2024-10-24 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000757 | 2024-10-11 | 2024-10-11 | 0 | INF | For Information | 1 | "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" |  | 2024-10
000758 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 0 | 131242-WSW41-VI-M-1006 | 2024-10-12 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-24 | 30 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000758 | 2024-10-12 | 2025-01-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" |  | 2024-10
000758 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 1 | 131242-WSW41-VI-M-1006 | 2025-01-16 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-05 | 2025-01-20 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | As per SO response, Resubmission is not required. | 000758 | 2024-10-12 | 2025-01-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" |  | 2025-01
000759 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0_NIL | 131242-WSW41-MS-M-0002 | 2024-10-14 | Delivery and Storage of Compressor Package at Biosolids Building | Rev.0: As requested by Contractor to reject the submittal. | 2024-11-12 | 2024-10-14 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000759 | 2024-10-14 | 2024-10-30 | 1 | REJ | Approved | 3 | "Delivery and Storage of Compressor Package at Biosolids Building " |  | 2024-10
000759 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0 | 131242-WSW41-MS-M-0002 | 2024-10-15 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 0: Approved with comments - Revise and Resubmit | 2024-11-05 | 2024-10-24 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000759 | 2024-10-14 | 2024-10-30 | 1 | AWC | Approved | 3 | "Delivery and Storage of Compressor Package at Biosolids Building " |  | 2024-10
000759 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 1 | 131242-WSW41-MS-M-0002 | 2024-10-30 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 2: Approved | 2024-11-20 | 2024-12-03 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000759 | 2024-10-14 | 2024-10-30 | 1 | APP | Approved | 3 | "Delivery and Storage of Compressor Package at Biosolids Building " |  | 2024-10
000760 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0014 | 0 | 131242-WSW41-PS-HS-0014 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Jul 2024 | Rev 0: Scoring confirmed to be at 98/100 | 2024-11-12 | 2024-11-15 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000760 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jul 2024" |  | 2024-10
000761 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0015 | 0 | 131242-WSW41-PS-HS-0015 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Aug 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-11-12 | 2024-11-15 | 24 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000761 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Aug 2024" |  | 2024-10
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0031 | 0 | 131242-WSW41-MI-C-0031 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000762 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" |  | 2024-10
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0032 | 0 | 131242-WSW41-MI-C-0032 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000762 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" |  | 2024-10
000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0033 | 0 | 131242-WSW41-MI-C-0033 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000762 | 2024-10-14 | 2024-10-14 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" |  | 2024-10
000763 | 00 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 0 | 131242-WST02-CD-I-0005 | 2024-10-15 | SSN Instrument List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-13 | 2025-02-13 | 87 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000763 | 2024-10-15 | 2025-10-27 | 1 | NAP | Approved with Comments | 2 | "SSN Instrument List " |  | 2024-10
000763 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 1 | 131242-WST02-CD-I-0005 | 2025-10-27 | SSN Instrument List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-11-14 | 2026-01-26 | 65 | Approved with Comments | YES | 2026-02-13 | NO | Resubmitted | 0 |  |  | 000763 | 2024-10-15 | 2025-10-27 | 1 | AWC | Approved with Comments | 2 | "SSN Instrument List " |  | 2025-10
000764 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 0 | 131242-WSD11-QA-I-0004 | 2024-10-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-15 | 2025-03-25 | 113 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000764 | 2024-10-17 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " |  | 2024-10
000764 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 1 | 131242-WSD11-QA-I-0004 | 2025-05-30 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-19 | 2025-06-04 | 3 | Approved with Comments | YES | 2025-06-24 | NO | Resubmitted | 0 |  |  | 000764 | 2024-10-17 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " |  | 2025-05
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614 | A | 131242-WSW41-DR-S-0310_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614 | A | 131242-WSW41-DR-S-0311_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614 | A | 131242-WSW41-DR-S-0312_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614 | A | 131242-WSW41-DR-S-0313_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614 | A | 131242-WSW41-DR-S-0314_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614 | A | 131242-WSW41-DR-S-0315_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0316_ST614 | A | 131242-WSW41-DR-S-0316_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0317_ST614 | A | 131242-WSW41-DR-S-0317_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614 | A | 131242-WSW41-DR-S-1100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614 | A | 131242-WSW41-DR-S-1101_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614 | A | 131242-WSW41-DR-S-1102_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614 | A | 131242-WSW41-DR-S-1103_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614 | A | 131242-WSW41-DR-S-1104_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614 | A | 131242-WSW41-DR-S-2100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614 | A | 131242-WSW41-DR-S-2101_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614 | A | 131242-WSW41-DR-S-3100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614 | A | 131242-WSW41-DR-S-5100_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614 | A | 131242-WSW41-DR-S-5101_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614 | A | 131242-WSW41-DR-S-5102_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614 | A | 131242-WSW41-DR-S-5103_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614 | A | 131242-WSW41-DR-S-8002_ST614 | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000765 | 2024-10-17 | 2024-10-17 | A | INF | For Information | 1 | "ST614 - SiteWide Pipe Rack 003" |  | 2024-10
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | CL | M | 5461 | 0 | 131242-WST02-CL-M-5461 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | 2 | AWC | Approved | 2 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2024-10
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | DR | M | 5461 | A | 131242-WST02-DR-M-5461 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2024-10
000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | DR | M | 5463 | A | 131242-WST02-DR-M-5463 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2024-10
000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | A.1 | 131242-WST02-DR-M-5461 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-12 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  | The Only comment is to get PE endorsement (Mech PE) | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2024-12
000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5463 | A.1 | 131242-WST02-DR-M-5463 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-06 | 2024-12-12 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | AWC | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2024-12
000766 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5461 | 2 | 131242-WST02-CL-M-5461 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 131 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | 2 | APP | Approved | 2 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2025-04
000766 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | C | 131242-WST02-DR-M-5461 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 131 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | APP | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2025-04
000766 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5463 | C | 131242-WST02-DR-M-5463 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | 131 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000766 | 2024-10-18 | 2025-04-04 | C | APP | Approved | 3 | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" |  | 2025-04
000767 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0017 | 0 | 131242-WSW41-RT-PM-0017 | 2024-10-19 | C4B Monthly Progress Report Number No.17 (09 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-11-18 | 2024-10-25 | 4 | Approved with Comments | YES | 2024-11-14 | NO | Resubmitted | 0 |  |  | 000767 | 2024-10-19 | 2024-10-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.17 (09 24) " |  | 2024-10
000768 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0046 | 0 | 131242-WSW41-LT-PM-0046 | 2024-10-21 | Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings | Rev (0): Received for information. lease refer to S.O. correspondence no. 289 dated 21 Jan 2025. | 2024-11-19 | 2025-11-20 | 283 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000768 | 2024-10-21 | 2024-10-21 | 0 | INF | For Information | 1 | "Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings" |  | 2024-10
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5501 | 0 | 131242-WST02-CL-P-5501 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 | 2025-04-30 00:00:00 | Pending model update, need PE endorsement | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" |  | 2024-10
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5511 | 0 | 131242-WST02-CL-P-5511 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" |  | 2024-10
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5521 | 0 | 131242-WST02-CL-P-5521 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" |  | 2024-10
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5531 | 0 | 131242-WST02-CL-P-5531 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" |  | 2024-10
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5541 | 0 | 131242-WST02-CL-P-5541 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" |  | 2024-10
000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5551 | 0 | 131242-WST02-CL-P-5551 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | 65 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000769 | 2024-10-21 | 2024-10-21 | 0 | AWC | Approved with Comments | 1 | "SSN Dosing Pump Sizing Calculations" |  | 2024-10
000770 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | K | 0001 | 0 | 131242-WST02-CL-K-0001 | 2024-10-22 | SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs | Rev 0: Approved with comments. Please refer to comment sheet. | 2024-11-20 | 2024-11-21 | 22 | Approved with Comments | YES | 2024-12-11 | NO | Resubmitted | 0 |  |  | 000770 | 2024-10-22 | 2024-10-22 | 0 | AWC | Approved with Comments | 1 | "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" |  | 2024-10
000771 | 00 | Radha | QAQC | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-C-0008 | 2024-10-22 | Bored Piling Pile Eccentricity Reports (ECC 13 to 18) | For Information. Please find attached comment sheet. | 2024-11-20 | 2024-11-04 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000737&&000771 | 2024-09-27 | 2024-11-07 | 1 | INF | Approved | 3 | "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" && "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" |  | 2024-10
000772 | 00 | Qili | Process | NA | 131242 | WST02 | RT | E | 0006 | 0 | 131242-WST02-RT-E-0006 | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | 109 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000772 | 2024-10-23 | 2024-10-23 | 0 | AWC | Approved with Comments | 1 | "SSN Hazardous Area Assessment Report" |  | 2024-10
000772 | 00 | Qili | Process | NA | 131242 | WST02 | DR | E | 8001 | A | 131242-WST02-DR-E-8001 | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | 109 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000772 | 2024-10-23 | 2024-10-23 | A | AWC | Approved with Comments | 1 | "SSN Hazardous Area Assessment Report" |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | A | 131242-WSW41-DR-S-0310_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | A | 131242-WSW41-DR-S-0311_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | A | 131242-WSW41-DR-S-0312_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | A | 131242-WSW41-DR-S-0313_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | A | 131242-WSW41-DR-S-0314_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | A | 131242-WSW41-DR-S-0315_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0316_ST614_BCA | A | 131242-WSW41-DR-S-0316_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773 | 2024-10-23 | 2024-10-23 | A | INF | For Information | 1 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0317_ST614_BCA | A | 131242-WSW41-DR-S-0317_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773 | 2024-10-23 | 2024-10-23 | A | INF | For Information | 1 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | A | 131242-WSW41-DR-S-1100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | A | 131242-WSW41-DR-S-1101_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | A | 131242-WSW41-DR-S-1102_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | A | 131242-WSW41-DR-S-1103_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | A | 131242-WSW41-DR-S-1104_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | A | 131242-WSW41-DR-S-2100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | A | 131242-WSW41-DR-S-2101_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | A | 131242-WSW41-DR-S-3100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | A | 131242-WSW41-DR-S-5100_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | A | 131242-WSW41-DR-S-5101_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | A | 131242-WSW41-DR-S-5102_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | A | 131242-WSW41-DR-S-5103_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | A | 131242-WSW41-DR-S-8002_ST614_BCA | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | 38 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2024-10
000774 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 0 | 131242-WSW41-DS-E-1386 | 2024-10-23 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-21 | 2024-11-21 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000774 | 2024-10-23 | 2024-12-20 | 1 | AWC | Rejected | 2 | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" |  | 2024-10
000774 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 1 | 131242-WSW41-DS-E-1386 | 2024-12-20 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 1: Rejected. Wrong comment reply sheet has been attached. | 2025-01-10 | 2025-02-18 | 42 | Rejected | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000774 | 2024-10-23 | 2024-12-20 | 1 | REJ | Rejected | 2 | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" |  | 2024-12
000775 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 0 | 131242-WSW41-MS-C-0019 | 2024-10-23 | MSRA for RC Wall | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-11-15 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000775 | 2024-10-23 | 2024-12-19 | 1 | AWC | Approved with Comments | 3 | "MSRA for RC Wall" |  | 2024-10
000775 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-C-0019 | 2024-11-26 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2024-12-16 | 2024-12-18 | 16 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000775 | 2024-10-23 | 2024-12-19 | 1 | AWC | Approved with Comments | 3 | "MSRA for RC Wall" |  | 2024-11
000775 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-C-0019 | 2024-12-19 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2025-01-09 | 2025-01-08 | 14 | Approved with Comments | YES | 2025-01-28 | NO | Resubmitted | 0 |  |  | 000775 | 2024-10-23 | 2024-12-19 | 1 | AWC | Approved with Comments | 3 | "MSRA for RC Wall" |  | 2024-12
000776 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0047 | 0 | 131242-WSW41-LT-PM-0047 | 2024-10-25 | Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works | Rejected. Please refer to S.O. correspondence no. 276 dated 7 January 2025. | 2024-11-25 | 2025-08-25 | 216 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000776 | 2024-10-25 | 2024-10-25 | 0 | REJ | Rejected | 1 | "Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works " |  | 2024-10
000777 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 0 | 131242-WSW41-VI-M-0010 | 2024-10-25 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-11-25 | 2024-11-27 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000777 | 2024-10-25 | 2025-01-11 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Spray Nozzles " |  | 2024-10
000777 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 1 | 131242-WSW41-VI-M-0010 | 2025-01-11 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000777 | 2024-10-25 | 2025-01-11 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Spray Nozzles " |  | 2025-01
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-M-1024 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 130 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" |  | 2024-10
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1025 | A | 131242-WST02-DR-M-1025 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 130 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000429&&000778 | 2024-04-09 | 2024-10-26 | A | AWC | Approved with Comments | 2 | "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Piping Support Plan Layout (Cast-In Supports)" |  | 2024-10
000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 2000 | A | 131242-WST02-DR-M-2000 | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | 130 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000778 | 2024-10-26 | 2024-10-26 | A | AWC | Approved with Comments | 1 | "SSN Piping Support Plan Layout (Cast-In Supports)" |  | 2024-10
000779 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 0001 | A | 131242-WST02-DR-M-0001 | 2024-10-26 | SSN Piping Drawing Index | Rev 0: For Information | 2024-11-25 | 2024-11-27 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000779 | 2024-10-26 | 2024-10-26 | A | INF | For Information | 1 | "SSN Piping Drawing Index" |  | 2024-10
000780 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0009 | 0 | 131242-WSW41-VI-S-0009 | 2024-10-26 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-20 | 17 | Approved with Comments | YES | 2024-12-10 | NO | Resubmitted | 0 |  |  | 000780 | 2024-10-26 | 2024-10-26 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " |  | 2024-10
000781 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-A-0002 | 2024-10-26 | Vendor Approval of Raised Floor – Hemsco Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-15 | 14 | Approved with Comments | YES | 2024-12-05 | NO | Resubmitted | 0 |  |  | 000781&&001325 | 2024-10-26 | 2025-05-28 | 0 | AWC | Approved | 2 | "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " |  | 2024-10
000782 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 0 | 131242-WSW41-QA-M-0021 | 2024-10-28 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 0: Not approved - Revise and Resubmit | 2024-11-26 | 2024-11-27 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000782 | 2024-10-28 | 2024-12-14 | 1 | NAP | Approved | 2 | "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" |  | 2024-10
000782 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 1 | 131242-WSW41-QA-M-0021 | 2024-12-14 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 1: Approved | 2025-01-03 | 2025-01-20 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000782 | 2024-10-28 | 2024-12-14 | 1 | APP | Approved | 2 | "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" |  | 2024-12
000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0001 | A | 131242-WSD11-DR-M-0001 | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000783 | 2024-10-28 | 2024-10-28 | A | INF | For Information | 1 | "THP Drawing Index" |  | 2024-10
000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0002 | A | 131242-WSD11-DR-M-0002 | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000783 | 2024-10-28 | 2024-10-28 | A | INF | For Information | 1 | "THP Drawing Index" |  | 2024-10
000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | A | 131242-WSD11-DR-M-5150 | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | 22 | Approved with Comments | YES | 2024-12-17 | NO | Resubmitted | 0 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" |  | 2024-10
000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | A | 131242-WSD11-DR-M-5160 | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | 22 | Approved with Comments | YES | 2024-12-17 | NO | Resubmitted | 0 |  |  | 000651&&000784 | 2024-10-28 | 2025-06-12 | B | AWC | Approved with Comments | 2 | "THP PC Pump GA Drawings" && "Ring Circulation Pump Drawing" |  | 2024-10
000785 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0016 | 0 | 131242-WSW41-PS-HS-0016 | 2024-10-28 | Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024 | For Information | 2024-11-26 | 2024-11-15 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000785 | 2024-10-28 | 2024-10-28 | 0 | INF | For Information | 1 | "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" |  | 2024-10
000786 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0010 | 0 | 131242-WSW41-RT-C-0010 | 2024-10-28 | Report of DFS (GUIDE 3) for PIPE RACKS | Rev.0: Approved with comments. Revise and resubmit. | 2024-11-26 | 2024-12-08 | 30 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000786 | 2024-10-28 | 2024-10-28 | 0 | AWC | Approved with Comments | 1 | "Report of DFS (GUIDE 3) for PIPE RACKS" |  | 2024-10
000787 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0011 | 0 | 131242-WSW41-RT-C-0011 | 2024-10-28 | Report of PROJECT SAFETY REVIEW for PIPE RACKS | For Information | 2024-11-26 | 2024-12-18 | 37 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000787 | 2024-10-28 | 2024-10-28 | 0 | INF | For Information | 1 | "Report of PROJECT SAFETY REVIEW for PIPE RACKS" |  | 2024-10
000788 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0016 | 0 | 131242-WSW41-PC-W-0016 | 2024-10-29 | Payment Claim No.16 | Rev(0): Approved. Please refer to S.O. Correspondence no. 244 dated 1 Nov 2024. | 2024-11-27 | 2024-11-07 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000788 | 2024-10-29 | 2024-10-29 | 0 | APP | Approved | 1 | "Payment Claim No.16" |  | 2024-10
000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9100 | A | 131242-WSD11-DR-M-9100 | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 26 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 | 2025-03-05 00:00:00 | 2nd priority (Shall update and submit under as built drawing) | 000789 | 2024-10-30 | 2024-10-30 | A | AWC | Approved with Comments | 1 | "THP Underground Piping and Cast in Details" |  | 2024-10
000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1190 | A | 131242-WSD11-DR-M-1190 | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | 26 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000789 | 2024-10-30 | 2024-10-30 | A | AWC | Approved with Comments | 1 | "THP Underground Piping and Cast in Details" |  | 2024-10
000790 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0012 | 0 | 131242-WSW41-RT-C-0012 | 2024-10-30 | Quarterly Safety Review Follow Up on ERSS | For Information | 2024-11-28 | 2024-11-15 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000790&&001420 | 2024-10-30 | 2025-07-01 | 1 | INF | Approved with Comments | 2 | "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " |  | 2024-10
000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0034 | 0 | 131242-WSW41-MI-C-0034 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000791 | 2024-10-31 | 2024-10-31 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" |  | 2024-10
000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0035 | 0 | 131242-WSW41-MI-C-0035 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000791 | 2024-10-31 | 2024-10-31 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" |  | 2024-10
000792 | 00 | PCM | PCM | NA | 131242 | WSW41 | MI | PM | 0017 | 0 | 131242-WSW41-MI-PM-0017 | 2024-10-31 | Monthly Progress Meeting Minutes 0017_20241023 | Rev. 0 - For Information | 2024-11-28 | 2024-11-07 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000792 | 2024-10-31 | 2024-10-31 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0017_20241023" |  | 2024-10
000793 | 00 | PCM | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-PM-0016 | 2024-10-31 | Monthly Progress Presentation No. 17 (1024) | For Information | 2024-11-28 | 2024-11-07 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000740&&000793 | 2024-10-01 | 2024-10-31 | 0 | INF | For Information | 2 | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" |  | 2024-10
000794 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0001 | 0 | 131242-WST02-VI-A-0001 | 2024-10-31 | Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-28 | 2024-11-25 | 17 | Approved with Comments | YES | 2024-12-13 | NO | Resubmitted | 0 |  |  | 000794 | 2024-10-31 | 2024-10-31 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" |  | 2024-10
000795 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0022 | 0 | 131242-WSW41-QA-M-0022 | 2024-11-01 | FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver) | Rev 0: Approved | 2024-11-29 | 2024-12-05 | 24 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000795 | 2024-11-01 | 2024-11-01 | 0 | APP | Approved | 1 | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" |  | 2024-11
000796 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0023 | 0 | 131242-WSW41-VI-E-0023 | 2024-11-02 | Vendor Approval of EICA Material and Accessories (Cable Gland) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-11-29 | 2024-11-24 | 15 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000796 | 2024-11-02 | 2024-11-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of EICA Material and Accessories (Cable Gland)" |  | 2024-11
000797 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0022 | 0 | 131242-WSW41-VI-E-0022 | 2024-11-02 | Preliminary Design and Vendor Approval of Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-29 | 2024-11-24 | 15 | Approved with Comments | YES | 2024-12-12 | NO | Resubmitted | 0 |  |  | 000797 | 2024-11-02 | 2024-11-02 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval of Unistrut Support" |  | 2024-11
000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | A | 131242-WST02-DR-M-5311 | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-28 00:00:00 | In Progress | 000798 | 2024-11-04 | 2025-04-17 | B | AWC | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" |  | 2024-11
000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5301 | A | 131242-WST02-DR-M-5301 | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | 23 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000798 | 2024-11-04 | 2025-04-17 | B | AWC | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" |  | 2024-11
000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | B | 131242-WST02-DR-M-5311 | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | 247 | Awaiting S.O.'s response | YES | 2025-06-04 | NO | Overdue | 0 |  |  | 000798 | 2024-11-04 | 2025-04-17 | B | PEN | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" |  | 2025-04
000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5301 | B | 131242-WST02-DR-M-5301 | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | 247 | Awaiting S.O.'s response | YES | 2025-06-04 | NO | Overdue | 113 |  |  | 000798 | 2024-11-04 | 2025-04-17 | B | PEN | Approved with Comments | 2 | "GA Drawing for Centrifugal Pump" |  | 2025-04
000799 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2001 | 0 | 131242-WSW41-VI-M-2001 | 2024-11-05 | Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package | Rev 0: Approved | 2024-12-03 | 2024-12-05 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000799 | 2024-11-05 | 2024-11-05 | 0 | APP | Approved | 1 | "Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618 | A | 131242-WSD11-DR-S-2300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618 | A | 131242-WSD11-DR-S-3300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3301_ST618 | A | 131242-WSD11-DR-S-3301_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618 | A | 131242-WSD11-DR-S-5300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618 | A | 131242-WSD11-DR-S-5301_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618 | A | 131242-WSD11-DR-S-5302_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618 | A | 131242-WSD11-DR-S-5303_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618 | A | 131242-WSD11-DR-S-5304_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618 | A | 131242-WSD11-DR-S-5305_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618 | A | 131242-WSD11-DR-S-5306_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618 | A | 131242-WSD11-DR-S-5307_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618 | A | 131242-WSD11-DR-S-5308_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618 | A | 131242-WSD11-DR-S-5309_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618 | A | 131242-WSD11-DR-S-5310_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8001_ST618 | A | 131242-WSD11-DR-S-8001_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618 | A | 131242-WSD11-DR-S-0302_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618 | A | 131242-WSD11-DR-S-1300_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618 | A | 131242-WSD11-DR-S-1301_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618 | A | 131242-WSD11-DR-S-1302_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618 | A | 131242-WSD11-DR-S-1303_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618 | A | 131242-WSD11-DR-S-1304_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618 | A | 131242-WSD11-DR-S-1305_ST618 | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | 23 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000800 | 2024-11-06 | 2024-11-06 | A | AWC | Approved with Comments | 1 | "ST618- THP Train 1 & 2 Conceptual" |  | 2024-11
000801 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0048 | 0 | 131242-WSW41-LT-PM-0048 | 2024-11-06 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024) | Rev (0): Received for information. Please refer to S.O. correspondence no. 333 dated 17 April 2025. | 2024-12-04 | 2025-11-20 | 271 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000801 | 2024-11-06 | 2024-11-06 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024)" |  | 2024-11
000802 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 0 | 131242-WSW41-VI-M-0008 | 2024-11-06 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-04 | 2024-12-05 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000802 | 2024-11-06 | 2025-06-16 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" |  | 2024-11
000802 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 1 | 131242-WSW41-VI-M-0008 | 2025-01-26 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-04-27 | 65 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000802 | 2024-11-06 | 2025-06-16 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" |  | 2025-01
000802 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 2 | 131242-WSW41-VI-M-0008 | 2025-06-16 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 2: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-11-24 | 115 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000802 | 2024-11-06 | 2025-06-16 | 2 | AWC | Approved with Comments | 3 | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" |  | 2025-06
000803 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0049 | 0 | 131242-WSW41-CD-IM-0049 | 2024-11-08 | Submission of BIM Coordination VCM Model (Oct 2024) | For Information | 2024-12-06 | 2024-11-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000803 | 2024-11-08 | 2024-11-08 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (Oct 2024)" |  | 2024-11
000804 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0018 | 0 | 131242-WSW41-RT-PM-0018 | 2024-11-09 | C4B Monthly Progress Report Number No.18 (10 24) | Rev. 0 - Approved with comments (need to re-submit / see attached comments sheet) | 2024-12-06 | 2024-12-03 | 16 | Approved with Comments | YES | 2024-12-23 | NO | Resubmitted | 0 |  |  | 000804 | 2024-11-09 | 2024-11-09 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.18 (10 24) " |  | 2024-11
000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0004 | 0 | 131242-WST02-CL-S-0004 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 | 16 | Approved with Comments | YES | 2024-12-23 | NO | Resubmitted | 0 |  |  | 000805 | 2024-11-11 | 2024-11-11 | 0 | AWC | Approved with Comments | 1 | "Anchor bolt Details for pipe supports for post drill and Cast-in type" |  | 2024-11
000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0005 | 0 | 131242-WST02-CL-S-0005 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 | 16 | Approved with Comments | YES | 2024-12-23 | NO | Resubmitted | 0 |  |  | 000805 | 2024-11-11 | 2024-11-11 | 0 | AWC | Approved with Comments | 1 | "Anchor bolt Details for pipe supports for post drill and Cast-in type" |  | 2024-11
000806 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 0 | 131242-WSW41-VI-M-0030 | 2024-11-11 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-09 | 2024-12-05 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-21 00:00:00 | In progress. as SO comment s/n.4, provide Vendor product presentation slides to SO on 14 Feb, will resubmit | 000806 | 2024-11-11 | 2025-03-20 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" |  | 2024-11
000806 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 1 | 131242-WSW41-VI-M-0030 | 2025-03-20 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-11-24 | 177 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000806 | 2024-11-11 | 2025-03-20 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" |  | 2025-03
000807 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 0 | 131242-WSW41-DS-E-1388 | 2024-11-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-21 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000807 | 2024-11-12 | 2025-03-12 | 1 | AWC | Approved | 2 | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" |  | 2024-11
000807 | 01 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 1 | 131242-WSW41-DS-E-1388 | 2025-03-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 1: Approved. | 2025-04-01 | 2025-05-05 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000807 | 2024-11-12 | 2025-03-12 | 1 | APP | Approved | 2 | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" |  | 2025-03
000808 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1387 | 0 | 131242-WSW41-DS-E-1387 | 2024-11-12 | Sample board submission for SS Cable ladder, trays & accessories (United U-Li) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-25 | 9 | Approved with Comments | YES | 2024-12-13 | NO | Resubmitted | 0 |  |  | 000808 | 2024-11-12 | 2024-11-12 | 0 | AWC | Approved with Comments | 1 | "Sample board submission for SS Cable ladder, trays & accessories (United U-Li)" |  | 2024-11
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1000 | A | 131242-WST02-DR-A-1000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000471&&000809&&001604&&001924 | 2024-05-13 | 2026-02-03 | A.2 | INF | Not Approved | 5 | "NEA Waiver Submission of SSN Plant" && "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" |  | 2024-11
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" |  | 2024-11
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2000 | A | 131242-WST02-DR-A-2000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000809&&001604&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 4 | "SSN Overall Area Layout And Sections" && "Shop Drawing for Louvre Door and Window" && "SSN URA Submission" |  | 2024-11
000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 3000 | B | 131242-WST02-DR-A-3000 | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000809&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN Overall Area Layout And Sections" && "SSN URA Submission" |  | 2024-11
000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1003 | A | 131242-WST02-DR-A-1003 | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" |  | 2024-11
000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2002 | A | 131242-WST02-DR-A-2002 | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000810&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 001 Layout and Elevation" && "SSN URA Submission" |  | 2024-11
000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1004 | A | 131242-WST02-DR-A-1004 | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" |  | 2024-11
000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2003 | A | 131242-WST02-DR-A-2003 | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000811&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 002 Layout and Elevation" && "SSN URA Submission" |  | 2024-11
000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1009 | A | 131242-WST02-DR-A-1009 | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" |  | 2024-11
000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2007 | A | 131242-WST02-DR-A-2007 | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | 18 | For Information | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000812&&001924 | 2024-11-13 | 2026-02-03 | A.2 | INF | Not Approved | 3 | "SSN_Shelter 003 Layout and Elevation" && "SSN URA Submission" |  | 2024-11
000813 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 0 | 131242-WSW41-QA-M-0023 | 2024-11-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-05 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000813 | 2024-11-14 | 2025-10-23 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" |  | 2024-11
000813 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 1 | 131242-WSW41-QA-M-0023 | 2025-10-23 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-12 | 2025-12-23 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000813 | 2024-11-14 | 2025-10-23 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" |  | 2025-10
000814 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0019 | 0 | 131242-WSW41-QA-C-0019 | 2024-11-14 | Monthly Concrete Cube Records for Structural works for August 2024 | For Information | 2024-12-12 | 2024-12-07 | 17 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000814 | 2024-11-14 | 2024-11-14 | 0 | INF | For Information | 1 | "Monthly Concrete Cube Records for Structural works for August 2024" |  | 2024-11
000815 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0004 | 0 | 131242-WSW41-MS-M-0004 | 2024-11-15 | MSRA and SWP for Installation of Manway | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-05 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000815 | 2024-11-15 | 2024-11-15 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Installation of Manway" |  | 2024-11
000816 | 00 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0005 | 0 | 131242-WSW41-VI-I-0005 | 2024-11-16 | Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech) | Rev 0: Rejected. Based on CES request. | 2024-12-13 | 2024-12-05 | 13 | Rejected | NO |  | YES | Resubmitted | 0 |  | Email sent on 25 Nov 24 | 000816 | 2024-11-16 | 2024-11-16 | 0 | REJ | Rejected | 1 | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" |  | 2024-11
000817 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0024 | 0 | 131242-WSW41-VI-E-0024 | 2024-11-16 | Preliminary Design and Vendor Approval – HDMANN Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-13 | 2024-12-06 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000817 | 2024-11-16 | 2024-11-16 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval – HDMANN Unistrut Support" |  | 2024-11
000818 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0003 | 0 | 131242-WSW41-MS-M-0003 | 2024-11-16 | MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-06 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000818 | 2024-11-16 | 2024-11-16 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " |  | 2024-11
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001 | A | 131242-WSD11-DR-A-1001 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 2 | "THP Layout, Elevations and Section Details" && "THP BCA BP Submission" |  | 2024-11
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A | 131242-WSD11-DR-A-1002 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" |  | 2024-11
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A | 131242-WSD11-DR-A-1003 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" |  | 2024-11
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A | 131242-WSD11-DR-A-2000 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" |  | 2024-11
000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A | 131242-WSD11-DR-A-3000 | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | 43 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000819&&001893&&001931 | 2024-11-18 | 2026-01-05 | A | INF | For Information | 3 | "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" && "THP BCA BP Submission" |  | 2024-11
000820 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5000 | A | 131242-WSD11-DR-A-5000 | 2024-11-18 | THP Door and Finishes Schedules | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-18 | 22 | Not Approved | YES | 2025-01-07 | NO | Resubmitted | 0 |  |  | 000820 | 2024-11-18 | 2024-11-18 | A | NAP | Not Approved | 1 | "THP Door and Finishes Schedules" |  | 2024-11
000821 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5006 | A | 131242-WSD11-DR-A-5006 | 2024-11-18 | THP Corridor & Stair Compartment Waterproofing Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-21 | 25 | Not Approved | YES | 2025-01-09 | NO | Resubmitted | 0 |  |  | 000821 | 2024-11-18 | 2024-11-18 | A | NAP | Not Approved | 1 | "THP Corridor & Stair Compartment Waterproofing Details" |  | 2024-11
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5001 | A | 131242-WSD11-DR-A-5001 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" |  | 2024-11
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5002 | A | 131242-WSD11-DR-A-5002 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" |  | 2024-11
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5003 | A | 131242-WSD11-DR-A-5003 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" |  | 2024-11
000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5004 | A | 131242-WSD11-DR-A-5004 | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | 15 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000822 | 2024-11-18 | 2024-11-18 | A | AWC | Approved with Comments | 1 | "THP Handrail Layout and Cad Ladder Details" |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609 | D | 131242-WST00-DR-S-8004_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0300_ST609 | D | 131242-WST02-DR-S-0300_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0301_ST609 | D | 131242-WST02-DR-S-0301_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0303_ST609 | D | 131242-WST02-DR-S-0303_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0304_ST609 | D | 131242-WST02-DR-S-0304_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0305_ST609 | D | 131242-WST02-DR-S-0305_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0306_ST609 | D | 131242-WST02-DR-S-0306_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0307_ST609 | D | 131242-WST02-DR-S-0307_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0308_ST609 | D | 131242-WST02-DR-S-0308_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0309_ST609 | D | 131242-WST02-DR-S-0309_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1100_ST609 | D | 131242-WST02-DR-S-1100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1101_ST609 | D | 131242-WST02-DR-S-1101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1102_ST609 | D | 131242-WST02-DR-S-1102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1103_ST609 | D | 131242-WST02-DR-S-1103_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2100_ST609 | D | 131242-WST02-DR-S-2100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2101_ST609 | D | 131242-WST02-DR-S-2101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2102_ST609 | D | 131242-WST02-DR-S-2102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3100_ST609 | D | 131242-WST02-DR-S-3100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3101_ST609 | D | 131242-WST02-DR-S-3101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3102_ST609 | D | 131242-WST02-DR-S-3102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5100_ST609 | D | 131242-WST02-DR-S-5100_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5101_ST609 | D | 131242-WST02-DR-S-5101_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5102_ST609 | D | 131242-WST02-DR-S-5102_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5103_ST609 | D | 131242-WST02-DR-S-5103_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5104_ST609 | D | 131242-WST02-DR-S-5104_ST609 | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | 42 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000823 | 2024-11-19 | 2024-11-19 | D | INF | For Information | 1 | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-S-0300_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | A | 131242-WSD11-DR-S-0301_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | A | 131242-WSD11-DR-S-1000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | A | 131242-WSD11-DR-S-1001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | A | 131242-WSD11-DR-S-1002_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | A | 131242-WSD11-DR-S-1003_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | A | 131242-WSD11-DR-S-2000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | A | 131242-WSD11-DR-S-2001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | A | 131242-WSD11-DR-S-3000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | A | 131242-WSD11-DR-S-3001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | A | 131242-WSD11-DR-S-3002_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | A | 131242-WSD11-DR-S-5000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | A | 131242-WSD11-DR-S-5001_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | A | 131242-WSD11-DR-S-5002_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | A | 131242-WSD11-DR-S-5003_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | A | 131242-WSD11-DR-S-5004_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | A | 131242-WSD11-DR-S-5005_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | A | 131242-WSD11-DR-S-5006_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | A | 131242-WSD11-DR-S-8000_ST617 | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | 14 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 1 |  |  | 000386&&000824 | 2024-07-04 | 2024-11-19 | A | AWC | Approved with Comments | 3 | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 -THP PLATFORM 01 & 02" |  | 2024-11
000825 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-C-0021 | 2024-11-20 | Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm | For Information | 2024-12-18 | 2024-11-27 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000825&&000952 | 2024-11-20 | 2025-01-04 | 0 | INF | For Information | 2 | "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" |  | 2024-11
000826 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 0 | 131242-WSD11-RT-E-0002 | 2024-11-20 | THP Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 00:00:00 |  | 000826 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Load Flow Study Report" |  | 2024-11
000826 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 1 | 131242-WSD11-RT-E-0002 | 2025-03-25 | THP Load Flow Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000826 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Load Flow Study Report" |  | 2025-03
000827 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 0 | 131242-WSD11-RT-E-0003 | 2024-11-20 | THP Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 00:00:00 |  | 000827 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Short Circuit Study Report" |  | 2024-11
000827 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 1 | 131242-WSD11-RT-E-0003 | 2025-03-25 | THP Short Circuit Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | 30 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 000827 | 2024-11-20 | 2025-03-25 | 1 | AWC | Approved with Comments | 2 | "THP Short Circuit Study Report" |  | 2025-03
000828 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 0 | 131242-WSW41-MS-M-0005 | 2024-11-21 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-05 | 10 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000828 | 2024-11-21 | 2024-12-11 | 1 | NAP | Approved with Comments | 2 | "MSRA and SWP for Delivery of 2000kVA Transformer " |  | 2024-11
000828 | 01 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 1 | 131242-WSW41-MS-M-0005 | 2024-12-11 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2024-12-30 | 13 | Approved with Comments | YES | 2025-01-17 | NO | Resubmitted | 0 |  |  | 000828 | 2024-11-21 | 2024-12-11 | 1 | AWC | Approved with Comments | 2 | "MSRA and SWP for Delivery of 2000kVA Transformer " |  | 2024-12
000829 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5006 | A | 131242-WST02-DR-A-5006 | 2024-11-21 | Fire Seal Detail | Rev.0: Not approved. Please revise and resubmit. | 2024-12-19 | 2024-12-06 | 11 | Not Approved | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000829 | 2024-11-21 | 2024-11-21 | A | NAP | Not Approved | 1 | "Fire Seal Detail" |  | 2024-11
000830 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0020 | 0 | 131242-WSW41-QA-C-0020 | 2024-11-21 | Monthly Concrete Cube Records for Structural works for September 2024 | For information. | 2024-12-19 | 2024-11-27 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000830 | 2024-11-21 | 2024-11-21 | 0 | INF | For Information | 1 | "Monthly Concrete Cube Records for Structural works for September 2024" |  | 2024-11
000831 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | A | 131242-WST02-DR-A-5003 | 2024-11-22 | SSN_CAT Ladder | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-08 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2024-11-22 | 2025-08-19 | D | NAP | Not Approved | 3 | "SSN_CAT Ladder " |  | 2024-11
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | - | 131242-WST02-DR-A-5003 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2024-11-22 | 2025-08-19 | D | NAP | Not Approved | 3 | "SSN_CAT Ladder " |  | 2025-04
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1007 | A | 131242-WST02-DR-A-1007 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2025-04-04 | 2025-04-04 | A | NAP | Not Approved | 1 | "SSN_CAT Ladder " |  | 2025-04
000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1008 | A | 131242-WST02-DR-A-1008 | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000831 | 2025-04-04 | 2025-04-04 | A | NAP | Not Approved | 1 | "SSN_CAT Ladder " |  | 2025-04
000831 | 02 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | D | 131242-WST02-DR-A-5003 | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | 41 | Not Approved | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 000831 | 2024-11-22 | 2025-08-19 | D | NAP | Not Approved | 3 | "SSN_CAT Ladder " |  | 2025-08
000831 | 02 | Anna | CSA | NA | PE report | NA | RT | A | NA | C | PE report-NA-RT-A-NA | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | 41 | Not Approved | YES | 2025-11-04 | NO | Resubmitted | 0 |  |  | 000831 | 2025-08-19 | 2025-08-19 | C | NAP | Not Approved | 1 | "SSN_CAT Ladder " |  | 2025-08
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1002 | A | 131242-WST02-DR-A-1002 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | AWC | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" |  | 2024-11
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 2001 | A | 131242-WST02-DR-A-2001 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832&&001924 | 2024-11-22 | 2026-02-03 | A.2 | AWC | Not Approved | 3 | "SSN Electrical Building Archi Drawing" && "SSN URA Submission" |  | 2024-11
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5004 | A | 131242-WST02-DR-A-5004 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832 | 2024-11-22 | 2024-11-22 | A | AWC | Approved with Comments | 1 | "SSN Electrical Building Archi Drawing" |  | 2024-11
000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5005 | A | 131242-WST02-DR-A-5005 | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000832 | 2024-11-22 | 2024-11-22 | A | AWC | Approved with Comments | 1 | "SSN Electrical Building Archi Drawing" |  | 2024-11
000833 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 5002 | A | 131242-WST02-DR-A-5002 | 2024-11-22 | SSN Door Window Schedule | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" |  | 2024-11
000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | B | 131242-WST02-DR-A-5002 | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" |  | 2025-02
000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5007 | A | 131242-WST02-DR-A-5007 | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2025-02-18 | 2025-02-18 | A | AWC | Approved with Comments | 1 | "SSN Door Window Schedule" |  | 2025-02
000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-A-5002 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" |  | 2025-08
000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5001 | A.2 | 131242-WST02-DR-A-5001 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000833 | 2025-08-19 | 2025-11-21 | A.2 | AWC | Approved with Comments | 2 | "SSN Door Window Schedule" |  | 2025-08
000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-A-5002 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 | 9 | Approved with Comments | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 000833 | 2024-11-22 | 2025-11-21 | A.2 | AWC | Approved with Comments | 4 | "SSN Door Window Schedule" |  | 2025-11
000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5001 | A.2 | 131242-WST02-DR-A-5001 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 | 9 | Approved with Comments | YES | 2025-12-24 | NO | Resubmitted | 0 |  |  | 000833 | 2025-08-19 | 2025-11-21 | A.2 | AWC | Approved with Comments | 2 | "SSN Door Window Schedule" |  | 2025-11
000834 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001 | 2024-11-22 | SSN Railing Layout | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-20 | 2024-12-07 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000809&&000834&&001625&&001924 | 2024-11-13 | 2026-02-03 | A.2 | AWC | Not Approved | 7 | "SSN Overall Area Layout And Sections" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" |  | 2024-11
000835 | 00 | Franklin | CSA | NA | 131242 | WST02 | DR | C | 1025 | A | 131242-WST02-DR-C-1025 | 2024-11-22 | SSN Pavement Plan | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-08 | 11 | Approved with Comments | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000835&&002018 | 2024-11-22 | 2026-02-24 | A | AWC | Approved with Comments | 2 | "SSN Pavement Plan" && "C4B SSN Drain Hydraulic Calculation" |  | 2024-11
000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5400 | A | 131242-WST02-DR-S-5400 | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 | 10 | Not Approved | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | F | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" |  | 2024-11
000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1400 | A | 131242-WST02-DR-S-1400 | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 | 10 | Not Approved | YES | 2024-12-26 | NO | Resubmitted | 0 |  |  | 000753&&000836&&001730&&001914 | 2024-10-10 | 2025-12-18 | H | NAP | Not Approved | 4 | "SSN- Biomass separator footing detail" && "SSN Wall Mounted Pipe Support Design" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" |  | 2024-11
000837 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 0 | 131242-WSD11-CL-S-0005 | 2024-11-22 | Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check | Approved | 2024-12-20 | 2024-12-06 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000446&&000837 | 2024-04-19 | 2024-11-22 | 0 | APP | Approved | 5 | "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" |  | 2024-11
000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0034 | 0 | 131242-WSD11-MI-P-0034 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000838 | 2024-11-22 | 2024-11-22 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" |  | 2024-11
000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0035 | 0 | 131242-WSD11-MI-P-0035 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 | 9 | For Information | YES | 2024-12-25 | NO | Resubmitted | 0 |  |  | 000838 | 2024-11-22 | 2024-11-22 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" |  | 2024-11
000839 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0020 | 0 | 131242-WSW41-MS-C-0020 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold | Approved | 2024-12-20 | 2024-12-18 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000839 | 2024-11-23 | 2024-11-23 | 0 | APP | Approved | 1 | "MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold" |  | 2024-11
000840 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0021 | 0 | 131242-WSW41-MS-C-0021 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold | Approved | 2024-12-20 | 2024-12-07 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000840 | 2024-11-23 | 2024-11-23 | 0 | APP | Approved | 1 | "MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold" |  | 2024-11
000841 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0022 | 0 | 131242-WSW41-MS-C-0022 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold | Approved | 2024-12-20 | 2024-12-18 | 17 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000841 | 2024-11-23 | 2024-11-23 | 0 | APP | Approved | 1 | "MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold" |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST619 | A | 131242-WSD11-DR-S-0304_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0305_ST619 | A | 131242-WSD11-DR-S-0305_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619 | A | 131242-WSD11-DR-S-1100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619 | A | 131242-WSD11-DR-S-1101_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619 | A | 131242-WSD11-DR-S-2100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619 | A | 131242-WSD11-DR-S-3100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619 | A | 131242-WSD11-DR-S-5100_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619 | A | 131242-WSD11-DR-S-5101_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619 | A | 131242-WSD11-DR-S-8002_ST619 | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000842 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST619 " |  | 2024-11
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1500_ST611 | A | 131242-WST02-DR-S-1500_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000843 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" |  | 2024-11
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5500_ST611 | A | 131242-WST02-DR-S-5500_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000843 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" |  | 2024-11
000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5501_ST611 | A | 131242-WST02-DR-S-5501_ST611 | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000843 | 2024-11-25 | 2024-11-25 | A | AWC | Approved with Comments | 1 | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" |  | 2024-11
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-S-1501 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" |  | 2024-11
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3500 | A | 131242-WSD11-DR-S-3500 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" |  | 2024-11
000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1500 | A | 131242-WSD11-DR-S-1500 | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | AWC | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" |  | 2024-11
000844 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment reply | NA | 131242-WSD11-DR-S-comment reply | 2025-08-22 | THP Courtyard RC Plinth Detail | Rev.1: For Information | 2025-09-11 | 2025-09-17 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000844 | 2025-08-22 | 2025-08-22 | NA | INF | For Information | 1 | "THP Courtyard RC Plinth Detail" |  | 2025-08
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-S-1501 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | REJ | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" |  | 2024-12
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3500 | A | 131242-WSD11-DR-S-3500 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | REJ | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" |  | 2024-12
000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1500 | A | 131242-WSD11-DR-S-1500 | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000844&&000845&&001363 | 2024-11-25 | 2025-09-24 | G | REJ | Approved with Comments | 5 | "THP Courtyard RC Plinth Detail" && " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" |  | 2024-12
000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1505_Superceded | A | 131242-WSD11-DR-S-1505_Superceded | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-13 | 2024-12-18 | 17 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000845 | 2024-11-25 | 2024-11-25 | A | REJ | Rejected | 1 | " THP Courtyard Equipment Anchor Bolt Details" |  | 2024-11
000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3505_Superceded | A | 131242-WSD11-DR-S-3505_Superceded | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-23 | 2024-12-18 | 17 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000845 | 2024-11-25 | 2024-11-25 | A | REJ | Rejected | 1 | " THP Courtyard Equipment Anchor Bolt Details" |  | 2024-11
000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1505 | A | 131242-WSD11-DR-S-1505 | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-08 | 2025-02-12 | 40 | Approved with Comments | YES | 2025-03-04 | NO | Resubmitted | 0 |  |  | 000845 | 2024-12-18 | 2024-12-18 | A | AWC | Approved with Comments | 1 | " THP Courtyard Equipment Anchor Bolt Details" |  | 2024-12
000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3505 | A | 131242-WSD11-DR-S-3505 | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-16 | 2025-02-12 | 40 | Approved with Comments | YES | 2025-03-04 | NO | Resubmitted | 0 |  |  | 000845 | 2024-12-18 | 2024-12-18 | A | AWC | Approved with Comments | 1 | " THP Courtyard Equipment Anchor Bolt Details" |  | 2024-12
000846 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 0 | 131242-WST02-DS-M-5481 | 2024-11-28 | Data Sheet for Hyperbolic Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-07 00:00:00 | In progress: 1). await TVU to confirm motor area (safety zone or not, Qili checking w TUV, will discuss with SO this Friday); 2). needTenwit confirm anchor bolt detail in C&S Dwg -> in 2 weeks | 000846 | 2024-11-28 | 2025-03-27 | 1 | AWC | Approved | 2 | "Data Sheet for Hyperbolic Mixer" |  | 2024-11
000846 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 1 | 131242-WST02-DS-M-5481 | 2025-03-27 | Data Sheet for Hyperbolic Mixer | Rev 1: Approved | 2025-04-16 | 2025-04-27 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000846 | 2024-11-28 | 2025-03-27 | 1 | APP | Approved | 2 | "Data Sheet for Hyperbolic Mixer" |  | 2025-03
000847 | 00 | Yibo/ Qili | Mech | NA | 131242 | WST02 | CL | P | 5481 | 0 | 131242-WST02-CL-P-5481 | 2024-11-28 | SSN Hyperbolic Mixer CFD | Rev 0: Not approved - Revise and Resubmit | 2024-12-27 | 2024-12-14 | 12 | Not Approved | YES | 2025-01-02 | NO | Resubmitted | 0 |  | To be handled by Process (QiLi), will be VO for revised CFD version | 000847 | 2024-11-28 | 2024-11-28 | 0 | NAP | Not Approved | 1 | "SSN Hyperbolic Mixer CFD" |  | 2024-11
000848 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0014 | 0 | 131242-WST02-VI-E-0014 | 2024-11-28 | Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-05 | 5 | Approved with Comments | YES | 2024-12-25 | NO | Resubmitted | 0 |  | To follow-up with HDMANN. | 000848 | 2024-11-28 | 2024-11-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" |  | 2024-11
000849 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 0 | 131242-WST02-RT-E-0007 | 2024-11-28 | SSN Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 |  | 000849 | 2024-11-28 | 2025-05-04 | 1 | AWC | Approved with Comments | 2 | "SSN Load Flow Study Report" |  | 2024-11
000849 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 1 | 131242-WST02-RT-E-0007 | 2025-05-04 | SSN Load Flow Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-22 | 2025-05-30 | 19 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 000849 | 2024-11-28 | 2025-05-04 | 1 | AWC | Approved with Comments | 2 | "SSN Load Flow Study Report" |  | 2025-05
000850 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 0 | 131242-WST02-RT-E-0008 | 2024-11-28 | SSN Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 |  | 000850 | 2024-11-28 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "SSN Short Circuit Study Report" |  | 2024-11
000850 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 1 | 131242-WST02-RT-E-0008 | 2025-05-30 | SSN Short Circuit Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-06-19 | 2025-07-23 | 38 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 000850 | 2024-11-28 | 2025-05-30 | 1 | AWC | Approved with Comments | 2 | "SSN Short Circuit Study Report" |  | 2025-05
000851 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0036 | 0 | 131242-WSW41-MI-C-0036 | 2024-11-28 | CSA Meeting Minutes 0036_14112024 | For Information | 2024-12-27 | 2024-12-07 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000851 | 2024-11-28 | 2024-11-28 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0036_14112024" |  | 2024-11
000852 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0013 | 0 | 131242-WSW41-RT-C-0013 | 2024-11-28 | Quarterly Safety Review Follow Up on SSN RC Works | For Information | 2024-12-27 | 2024-12-07 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000852&&001420 | 2024-11-28 | 2025-07-01 | 1 | INF | Approved with Comments | 2 | "Quarterly Safety Review Follow Up on SSN RC Works" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " |  | 2024-11
000853 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0022 | 0 | 131242-WST02-VI-I-0022 | 2024-11-28 | Vendor approval of SSN Package (Autosampler) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-27 | 2025-03-14 | 76 | Approved with Comments | YES | 2025-04-03 | NO | Resubmitted | 0 |  |  | 000853 | 2024-11-28 | 2024-11-28 | 0 | AWC | Approved with Comments | 1 | "Vendor approval of SSN Package (Autosampler) " |  | 2024-11
000854 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0003 | 0 | 131242-WST02-VI-A-0003 | 2024-11-28 | Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd. | Approved | 2024-12-27 | 2024-12-07 | 7 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000854 | 2024-11-28 | 2024-11-28 | 0 | APP | Approved | 1 | "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." |  | 2024-11
000855 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-A-0004 | 2024-11-28 | Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd. | Approved | 2024-12-27 | 2024-12-05 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000855&&001327 | 2024-11-28 | 2025-05-28 | 0 | APP | Approved | 2 | "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " |  | 2024-11
000856 | 00 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 0 | 131242-WST02-QA-A-0003 | 2024-11-29 | 2Hrs Fire rated AAC Blocks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2024-12-06 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000856 | 2024-11-29 | 2024-12-20 | 1 | NAP | Approved | 2 | "2Hrs Fire rated AAC Blocks" |  | 2024-11
000856 | 01 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 1 | 131242-WST02-QA-A-0003 | 2024-12-20 | 2Hrs Fire rated AAC Blocks | Rev.1: Approved | 2025-01-10 | 2025-01-02 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000856 | 2024-11-29 | 2024-12-20 | 1 | APP | Approved | 2 | "2Hrs Fire rated AAC Blocks" |  | 2024-12
000857 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 0 | 131242-WSW41-DS-I-0001 | 2024-11-29 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-30 | 2025-03-25 | 82 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000857 | 2024-11-29 | 2025-09-15 | 1 | AWC | Approved with Comments | 2 | "SSN and THP ICA, ELV and Communication Cable datasheet and specification" |  | 2024-11
000857 | 01 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 1 | 131242-WSW41-DS-I-0001 | 2025-09-15 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-10-03 | 2025-12-02 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000857 | 2024-11-29 | 2025-09-15 | 1 | AWC | Approved with Comments | 2 | "SSN and THP ICA, ELV and Communication Cable datasheet and specification" |  | 2025-09
000858 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0008 | 0 | 131242-WSW41-QA-E-0008 | 2024-11-30 | FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-12-30 | 2024-12-14 | 10 | Approved with Comments | YES | 2025-01-02 | NO | Resubmitted | 0 |  |  | 000858 | 2024-11-30 | 2024-11-30 | 0 | AWC | Approved with Comments | 1 | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5218 | A | 131242-WST02-SD-S-5218 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5219 | A | 131242-WST02-SD-S-5219 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5220 | A | 131242-WST02-SD-S-5220 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5221 | A | 131242-WST02-SD-S-5221 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5223 | A | 131242-WST02-SD-S-5223 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5224 | A | 131242-WST02-SD-S-5224 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1201 | A | 131242-WST02-SD-S-1201 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1202 | A | 131242-WST02-SD-S-1202 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1203 | A.1 | 131242-WST02-SD-S-1203 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A.1 | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1204 | A | 131242-WST02-SD-S-1204 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5212 | A | 131242-WST02-SD-S-5212 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5213 | A | 131242-WST02-SD-S-5213 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5214 | A | 131242-WST02-SD-S-5214 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5215 | A | 131242-WST02-SD-S-5215 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5216 | A | 131242-WST02-SD-S-5216 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5217 | A | 131242-WST02-SD-S-5217 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | 33 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000859 | 2024-11-30 | 2024-11-30 | A | AWC | Approved with Comments | 1 | "SSN Wall Shop Drawing" |  | 2024-11
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1027 | A | 131242-WST02-DR-C-1027 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 66 | Not Approved | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000860 | 2024-11-30 | 2024-11-30 | A | NAP | Not Approved | 1 | "SSN-Rain Water Drainage Layout and Detail Design" |  | 2024-11
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1026 | A | 131242-WST02-DR-C-1026 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 66 | Not Approved | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000860 | 2024-11-30 | 2024-11-30 | A | NAP | Not Approved | 1 | "SSN-Rain Water Drainage Layout and Detail Design" |  | 2024-11
000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5008 | A | 131242-WST02-DR-C-5008 | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | 66 | Not Approved | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000860 | 2024-11-30 | 2024-11-30 | A | NAP | Not Approved | 1 | "SSN-Rain Water Drainage Layout and Detail Design" |  | 2024-11
000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210 | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001572 | 2024-11-30 | 2025-12-14 | A | NAP | Approved | 4 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard Sump Design (Updates)" |  | 2024-11
000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200 | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | NAP | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" |  | 2024-11
000861 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | cmmt sheet | NA | 131242-WSD11-DR-S-cmmt sheet | 2025-09-15 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-25 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000861 | 2025-09-15 | 2025-09-15 | NA | INF | For Information | 1 | "THP- Valve Pit, Sump and Kerb Detail" |  | 2025-09
000862 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0018 | 0 | 131242-WSW41-PS-PM-0018 | 2024-11-30 | Monthly Progress Presentation No. 18 (1124) | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000862 | 2024-11-30 | 2024-11-30 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 18 (1124)" |  | 2024-11
000863 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0018 | 0 | 131242-WSW41-MI-PM-0018 | 2024-11-30 | Monthly Progress Meeting Minutes 0018_20241113 | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000863 | 2024-11-30 | 2024-11-30 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0018_20241113" |  | 2024-11
000864 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0031 | 0 | 131242-WSW41-VI-M-0031 | 2024-12-02 | Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2024-06-12 | 0 | Approved with Comments | YES | 2024-07-02 | NO | Resubmitted | 0 |  |  | 000864 | 2024-12-02 | 2024-12-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd." |  | 2024-12
000865 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 0 | 131242-WSW41-PC-W-0017 | 2024-12-02 | Payment Claim No.17 | As requested by C4BJV to reject this submittal and resubmit. | 2024-12-31 | 2024-12-03 | 1 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000865 | 2024-12-02 | 2024-12-03 | 1 | REJ | Approved | 2 | "Payment Claim No.17" |  | 2024-12
000865 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 1 | 131242-WSW41-PC-W-0017 | 2024-12-03 | Payment Claim No.17 | Rev(1): Approved. Please refer to S.O. correspondence no 259 3 Dec 2024. | 2024-12-23 | 2025-01-08 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000865 | 2024-12-02 | 2024-12-03 | 1 | APP | Approved | 2 | "Payment Claim No.17" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | A | 131242-WST02-DR-EP-3008 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | A | 131242-WST02-DR-EP-3009 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | A | 131242-WST02-DR-EP-3010 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | A | 131242-WST02-DR-EP-3011 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | A | 131242-WST02-DR-EP-3012 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | A | 131242-WST02-DR-EP-3013 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | A | 131242-WST02-DR-EP-3014 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | A | 131242-WST02-DR-EP-3015 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | A | 131242-WST02-DR-EP-3016 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | A | 131242-WST02-DR-EP-3017 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | A | 131242-WST02-DR-EP-3018 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | A | 131242-WST02-DR-EP-3019 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | A | 131242-WST02-DR-EP-3020 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | A | 131242-WST02-DR-EP-3021 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | A | 131242-WST02-DR-EP-3022 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | A | 131242-WST02-DR-EP-3023 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | A | 131242-WST02-DR-EP-7110 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | A | 131242-WST02-DR-EP-7111 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | A | 131242-WST02-DR-EP-7112 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | A | 131242-WST02-DR-EP-7113 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | A | 131242-WST02-DR-EP-7114 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | A | 131242-WST02-DR-EP-7115 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | A | 131242-WST02-DR-EP-7116 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | A | 131242-WST02-DR-EP-7117 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | A | 131242-WST02-DR-EP-7118 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | A | 131242-WST02-DR-EP-7119 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | A | 131242-WST02-DR-EP-7120 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | A | 131242-WST02-DR-EP-7121 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | A | 131242-WST02-DR-EP-7122 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | A | 131242-WST02-DR-EP-7123 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | A | 131242-WST02-DR-EP-7124 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | A | 131242-WST02-DR-EP-7125 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | A | 131242-WST02-DR-EP-7126 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | A | 131242-WST02-DR-EP-7127 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | A | 131242-WST02-DR-EI-7040 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | A | 131242-WST02-DR-EI-7041 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | A | 131242-WST02-DR-EI-7042 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | A | 131242-WST02-DR-EI-7043 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | A | 131242-WST02-DR-EI-7044 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | A | 131242-WST02-DR-EI-7045 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | A | 131242-WST02-DR-EI-7046 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | A | 131242-WST02-DR-EI-7047 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | A | 131242-WST02-DR-EI-7048 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | A | 131242-WST02-DR-EI-7049 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | A | 131242-WST02-DR-EI-7050 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | A | 131242-WST02-DR-EI-7051 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | A | 131242-WST02-DR-EI-7052 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | A | 131242-WST02-DR-EI-7053 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | A | 131242-WST02-DR-EI-7054 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | A | 131242-WST02-DR-EI-7055 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | A | 131242-WST02-DR-EI-7060 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | A | 131242-WST02-DR-EI-7061 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | A | 131242-WST02-DR-EI-7062 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | A | 131242-WST02-DR-EI-7063 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | A | 131242-WST02-DR-EI-7064 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | A | 131242-WST02-DR-EI-7065 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | A | 131242-WST02-DR-EI-7066 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | A | 131242-WST02-DR-EI-7067 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | A | 131242-WST02-DR-EI-7068 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | A | 131242-WST02-DR-EI-7069 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | A | 131242-WST02-DR-EI-7070 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | A | 131242-WST02-DR-EI-7071 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | A | 131242-WST02-DR-EI-7072 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | A | 131242-WST02-DR-EI-7073 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | A | 131242-WST02-DR-EI-7074 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | A | 131242-WST02-DR-EI-7075 | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2024-12
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | B | 131242-WST02-DR-EI-7040 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | B | 131242-WST02-DR-EI-7041 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | B | 131242-WST02-DR-EI-7042 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | B | 131242-WST02-DR-EI-7043 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | B | 131242-WST02-DR-EI-7044 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | B | 131242-WST02-DR-EI-7045 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | B | 131242-WST02-DR-EI-7046 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | B | 131242-WST02-DR-EI-7047 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | B | 131242-WST02-DR-EI-7048 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | B | 131242-WST02-DR-EI-7049 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | B | 131242-WST02-DR-EI-7050 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | B | 131242-WST02-DR-EI-7051 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | B | 131242-WST02-DR-EI-7052 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | B | 131242-WST02-DR-EI-7053 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | B | 131242-WST02-DR-EI-7054 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | B | 131242-WST02-DR-EI-7055 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | B | 131242-WST02-DR-EI-7056 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | B | 131242-WST02-DR-EI-7057 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | B | 131242-WST02-DR-EI-7058 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | B | 131242-WST02-DR-EI-7060 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | B | 131242-WST02-DR-EI-7061 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | B | 131242-WST02-DR-EI-7062 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | B | 131242-WST02-DR-EI-7063 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | B | 131242-WST02-DR-EI-7064 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | B | 131242-WST02-DR-EI-7065 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | B | 131242-WST02-DR-EI-7066 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | B | 131242-WST02-DR-EI-7067 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | B | 131242-WST02-DR-EI-7068 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | B | 131242-WST02-DR-EI-7069 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | B | 131242-WST02-DR-EI-7070 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | B | 131242-WST02-DR-EI-7071 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | B | 131242-WST02-DR-EI-7072 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | B | 131242-WST02-DR-EI-7073 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | B | 131242-WST02-DR-EI-7074 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | B | 131242-WST02-DR-EI-7075 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | B | 131242-WST02-DR-EI-7076 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | B | 131242-WST02-DR-EI-7077 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | B | 131242-WST02-DR-EI-7078 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | NAP | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | B | 131242-WST02-DR-EP-3008 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | B | 131242-WST02-DR-EP-3009 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | B | 131242-WST02-DR-EP-3010 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | B | 131242-WST02-DR-EP-3011 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | NAP | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | B | 131242-WST02-DR-EP-3012 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | B | 131242-WST02-DR-EP-3013 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | B | 131242-WST02-DR-EP-3014 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | B | 131242-WST02-DR-EP-3015 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | B | 131242-WST02-DR-EP-3016 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | B | 131242-WST02-DR-EP-3017 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | B | 131242-WST02-DR-EP-3018 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | B | 131242-WST02-DR-EP-3019 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | B | 131242-WST02-DR-EP-3020 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | B | 131242-WST02-DR-EP-3021 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | B | 131242-WST02-DR-EP-3022 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | B | 131242-WST02-DR-EP-3023 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | B | 131242-WST02-DR-EP-7110 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | B | 131242-WST02-DR-EP-7111 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | B | 131242-WST02-DR-EP-7112 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | B | 131242-WST02-DR-EP-7113 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | B | 131242-WST02-DR-EP-7114 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | B | 131242-WST02-DR-EP-7115 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | B | 131242-WST02-DR-EP-7116 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | B | 131242-WST02-DR-EP-7117 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | B | 131242-WST02-DR-EP-7118 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | B | 131242-WST02-DR-EP-7119 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | B | 131242-WST02-DR-EP-7120 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | B | 131242-WST02-DR-EP-7121 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | B | 131242-WST02-DR-EP-7122 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | B | 131242-WST02-DR-EP-7123 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | B | 131242-WST02-DR-EP-7124 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | B | 131242-WST02-DR-EP-7125 | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | 4 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | NAP | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | C | 131242-WST02-DR-EI-7040 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | C | 131242-WST02-DR-EI-7041 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | C | 131242-WST02-DR-EI-7042 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | C | 131242-WST02-DR-EI-7043 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | C | 131242-WST02-DR-EI-7044 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | C | 131242-WST02-DR-EI-7045 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | C | 131242-WST02-DR-EI-7046 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | C | 131242-WST02-DR-EI-7047 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | C | 131242-WST02-DR-EI-7048 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | C | 131242-WST02-DR-EI-7049 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | C | 131242-WST02-DR-EI-7050 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | C | 131242-WST02-DR-EI-7051 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | C | 131242-WST02-DR-EI-7052 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | C | 131242-WST02-DR-EI-7053 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | C | 131242-WST02-DR-EI-7054 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | C | 131242-WST02-DR-EI-7055 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | C | 131242-WST02-DR-EI-7056 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | C | 131242-WST02-DR-EI-7057 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | C | 131242-WST02-DR-EI-7058 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | C | 131242-WST02-DR-EI-7060 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | C | 131242-WST02-DR-EI-7061 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | C | 131242-WST02-DR-EI-7062 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | C | 131242-WST02-DR-EI-7063 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | C | 131242-WST02-DR-EI-7064 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | C | 131242-WST02-DR-EI-7065 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | C | 131242-WST02-DR-EI-7066 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | C | 131242-WST02-DR-EI-7067 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | C | 131242-WST02-DR-EI-7068 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | C | 131242-WST02-DR-EI-7069 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | C | 131242-WST02-DR-EI-7070 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | C | 131242-WST02-DR-EI-7071 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | C | 131242-WST02-DR-EI-7072 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | C | 131242-WST02-DR-EI-7073 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | C | 131242-WST02-DR-EI-7074 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | C | 131242-WST02-DR-EI-7075 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | C | 131242-WST02-DR-EI-7076 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | C | 131242-WST02-DR-EI-7077 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | C | 131242-WST02-DR-EI-7078 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | C | 131242-WST02-DR-EP-3008 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | C | 131242-WST02-DR-EP-3009 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | C | 131242-WST02-DR-EP-3010 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | C | 131242-WST02-DR-EP-3011 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | C | 131242-WST02-DR-EP-3012 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | C | 131242-WST02-DR-EP-3013 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | C | 131242-WST02-DR-EP-3014 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | C | 131242-WST02-DR-EP-3015 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | C | 131242-WST02-DR-EP-3016 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | C | 131242-WST02-DR-EP-3017 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | C | 131242-WST02-DR-EP-3018 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | C | 131242-WST02-DR-EP-3019 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | C | 131242-WST02-DR-EP-3020 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | C | 131242-WST02-DR-EP-3021 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | C | 131242-WST02-DR-EP-3022 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | C | 131242-WST02-DR-EP-3023 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | C | 131242-WST02-DR-EP-7110 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | C | 131242-WST02-DR-EP-7111 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | C | 131242-WST02-DR-EP-7112 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | C | 131242-WST02-DR-EP-7113 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | C | 131242-WST02-DR-EP-7114 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | C | 131242-WST02-DR-EP-7115 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | C | 131242-WST02-DR-EP-7116 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | C | 131242-WST02-DR-EP-7117 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | C | 131242-WST02-DR-EP-7118 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | C | 131242-WST02-DR-EP-7119 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | C | 131242-WST02-DR-EP-7120 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | C | 131242-WST02-DR-EP-7121 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | C | 131242-WST02-DR-EP-7122 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | C | 131242-WST02-DR-EP-7123 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | C | 131242-WST02-DR-EP-7124 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | C | 131242-WST02-DR-EP-7125 | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-03
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | D | 131242-WST02-DR-EI-7040 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | D | 131242-WST02-DR-EI-7041 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | D | 131242-WST02-DR-EI-7042 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | D | 131242-WST02-DR-EI-7043 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | D | 131242-WST02-DR-EI-7044 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | D | 131242-WST02-DR-EI-7045 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | D | 131242-WST02-DR-EI-7046 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | D | 131242-WST02-DR-EI-7047 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | D | 131242-WST02-DR-EI-7048 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | D | 131242-WST02-DR-EI-7049 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | D | 131242-WST02-DR-EI-7050 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | D | 131242-WST02-DR-EI-7051 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | D | 131242-WST02-DR-EI-7052 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | D | 131242-WST02-DR-EI-7053 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | D | 131242-WST02-DR-EI-7054 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | D | 131242-WST02-DR-EI-7055 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | D | 131242-WST02-DR-EI-7056 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | D | 131242-WST02-DR-EI-7057 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | D | 131242-WST02-DR-EI-7058 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | D | 131242-WST02-DR-EI-7060 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | D | 131242-WST02-DR-EI-7061 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | D | 131242-WST02-DR-EI-7062 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | D | 131242-WST02-DR-EI-7063 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | D | 131242-WST02-DR-EI-7064 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | D | 131242-WST02-DR-EI-7065 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | D | 131242-WST02-DR-EI-7066 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | D | 131242-WST02-DR-EI-7067 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | D | 131242-WST02-DR-EI-7068 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | D | 131242-WST02-DR-EI-7069 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | D | 131242-WST02-DR-EI-7070 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | D | 131242-WST02-DR-EI-7071 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | D | 131242-WST02-DR-EI-7072 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | D | 131242-WST02-DR-EI-7073 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | D | 131242-WST02-DR-EI-7074 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | D | 131242-WST02-DR-EI-7075 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | D | 131242-WST02-DR-EI-7076 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | D | 131242-WST02-DR-EI-7077 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | D | 131242-WST02-DR-EI-7078 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2025-03-07 | 2025-07-01 | D | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | D | 131242-WST02-DR-EP-3008 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | D | 131242-WST02-DR-EP-3009 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | D | 131242-WST02-DR-EP-3010 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | D | 131242-WST02-DR-EP-3011 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000605&&000866 | 2024-11-21 | 2025-07-01 | D | AWC | Approved with Comments | 7 | "SSN LVSG 0101AB Single Line Diagram" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | D | 131242-WST02-DR-EP-3012 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | D | 131242-WST02-DR-EP-3013 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | D | 131242-WST02-DR-EP-3014 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | D | 131242-WST02-DR-EP-3015 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | D | 131242-WST02-DR-EP-3016 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | D | 131242-WST02-DR-EP-3017 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | D | 131242-WST02-DR-EP-3018 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | D | 131242-WST02-DR-EP-3019 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | D | 131242-WST02-DR-EP-3020 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | D | 131242-WST02-DR-EP-3021 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | D | 131242-WST02-DR-EP-3022 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | D | 131242-WST02-DR-EP-3023 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | D | 131242-WST02-DR-EP-7110 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | D | 131242-WST02-DR-EP-7111 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | D | 131242-WST02-DR-EP-7112 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | D | 131242-WST02-DR-EP-7113 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | D | 131242-WST02-DR-EP-7114 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | D | 131242-WST02-DR-EP-7115 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | D | 131242-WST02-DR-EP-7116 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | D | 131242-WST02-DR-EP-7117 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | D | 131242-WST02-DR-EP-7118 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | D | 131242-WST02-DR-EP-7119 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | D | 131242-WST02-DR-EP-7120 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | D | 131242-WST02-DR-EP-7121 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | D | 131242-WST02-DR-EP-7122 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | D | 131242-WST02-DR-EP-7123 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | D | 131242-WST02-DR-EP-7124 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | D | 131242-WST02-DR-EP-7125 | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | 69 | Approved with Comments | YES | 2025-10-24 | NO | Resubmitted | 0 |  |  | 000866 | 2024-12-02 | 2025-07-01 | D | AWC | Approved with Comments | 4 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" |  | 2025-07
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | A | 131242-WST02-DR-EP-3038 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-08-21 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | A | 131242-WST02-DR-EP-3039 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | A | 131242-WST02-DR-EP-3040 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | A | 131242-WST02-DR-EP-3041 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | A | 131242-WST02-DR-EP-3042 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | A | 131242-WST02-DR-EP-3043 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | A | 131242-WST02-DR-EP-3044 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | A | 131242-WST02-DR-EP-3045 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | A | 131242-WST02-DR-EP-3046 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | A | 131242-WST02-DR-EP-3047 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | A | 131242-WST02-DR-EP-3048 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | A | 131242-WST02-DR-EP-3049 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | A | 131242-WST02-DR-EP-3050 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | A | 131242-WST02-DR-EP-3051 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | A | 131242-WST02-DR-EP-7136 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | A | 131242-WST02-DR-EP-7137 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | A | 131242-WST02-DR-EP-7138 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | A | 131242-WST02-DR-EP-7139 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | A | 131242-WST02-DR-EP-7140 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | A | 131242-WST02-DR-EP-7141 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | A | 131242-WST02-DR-EI-7120 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | A | 131242-WST02-DR-EI-7121 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | A | 131242-WST02-DR-EI-7122 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | A | 131242-WST02-DR-EI-7123 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | A | 131242-WST02-DR-EI-7124 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | A | 131242-WST02-DR-EI-7125 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | A | 131242-WST02-DR-EI-7126 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | A | 131242-WST02-DR-EI-7127 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | A | 131242-WST02-DR-EI-7128 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | A | 131242-WST02-DR-EI-7140 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | A | 131242-WST02-DR-EI-7141 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | A | 131242-WST02-DR-EI-7142 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | A | 131242-WST02-DR-EI-7143 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | A | 131242-WST02-DR-EI-7144 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | A | 131242-WST02-DR-EI-7145 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | A | 131242-WST02-DR-EI-7146 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | A | 131242-WST02-DR-EI-7147 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | A | 131242-WST02-DR-EI-7148 | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | 49 | Approved with Comments | YES | 2025-02-27 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2024-12
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | B | 131242-WST02-DR-EP-3038 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-08-21 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | B | 131242-WST02-DR-EP-3039 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | B | 131242-WST02-DR-EP-3040 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | B | 131242-WST02-DR-EP-3041 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | B | 131242-WST02-DR-EP-3042 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | B | 131242-WST02-DR-EP-3043 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | B | 131242-WST02-DR-EP-3044 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | B | 131242-WST02-DR-EP-3045 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | B | 131242-WST02-DR-EP-3046 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | B | 131242-WST02-DR-EP-3047 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | B | 131242-WST02-DR-EP-3048 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | B | 131242-WST02-DR-EP-3049 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | B | 131242-WST02-DR-EP-3050 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | B | 131242-WST02-DR-EP-3051 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | B | 131242-WST02-DR-EP-7136 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | B | 131242-WST02-DR-EP-7137 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | B | 131242-WST02-DR-EP-7138 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | B | 131242-WST02-DR-EP-7139 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | B | 131242-WST02-DR-EP-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | B | 131242-WST02-DR-EP-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | B | 131242-WST02-DR-EI-7120 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | B | 131242-WST02-DR-EI-7121 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | B | 131242-WST02-DR-EI-7122 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | B | 131242-WST02-DR-EI-7123 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | B | 131242-WST02-DR-EI-7124 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | B | 131242-WST02-DR-EI-7125 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | B | 131242-WST02-DR-EI-7126 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | B | 131242-WST02-DR-EI-7127 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | B | 131242-WST02-DR-EI-7128 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | B | 131242-WST02-DR-EI-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | B | 131242-WST02-DR-EI-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | B | 131242-WST02-DR-EI-7142 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | B | 131242-WST02-DR-EI-7143 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | B | 131242-WST02-DR-EI-7144 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | B | 131242-WST02-DR-EI-7145 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | B | 131242-WST02-DR-EI-7146 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | B | 131242-WST02-DR-EI-7147 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | B | 131242-WST02-DR-EI-7148 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7149 | B | 131242-WST02-DR-EI-7149 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000867 | 2025-03-28 | 2025-03-28 | B | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | C | 131242-WST02-DR-EP-3038 | 2025-08-21 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 29 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000867 | 2024-12-02 | 2025-08-21 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-08
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | C | 131242-WST02-DR-EP-3039 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | C | 131242-WST02-DR-EP-3040 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | C | 131242-WST02-DR-EP-3041 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | C | 131242-WST02-DR-EP-3042 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | C | 131242-WST02-DR-EP-3043 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | C | 131242-WST02-DR-EP-3044 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | C | 131242-WST02-DR-EP-3045 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | C | 131242-WST02-DR-EP-3046 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | C | 131242-WST02-DR-EP-3047 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | C | 131242-WST02-DR-EP-3048 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | C | 131242-WST02-DR-EP-3049 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | C | 131242-WST02-DR-EP-3050 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | C | 131242-WST02-DR-EP-3051 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | C | 131242-WST02-DR-EP-7136 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | C | 131242-WST02-DR-EP-7137 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | C | 131242-WST02-DR-EP-7138 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | C | 131242-WST02-DR-EP-7139 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | C | 131242-WST02-DR-EP-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | C | 131242-WST02-DR-EP-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | C | 131242-WST02-DR-EI-7120 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | C | 131242-WST02-DR-EI-7121 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | C | 131242-WST02-DR-EI-7122 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | C | 131242-WST02-DR-EI-7123 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | C | 131242-WST02-DR-EI-7124 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | C | 131242-WST02-DR-EI-7125 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | C | 131242-WST02-DR-EI-7126 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | C | 131242-WST02-DR-EI-7127 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | C | 131242-WST02-DR-EI-7128 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | C | 131242-WST02-DR-EI-7140 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | C | 131242-WST02-DR-EI-7141 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | C | 131242-WST02-DR-EI-7142 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | C | 131242-WST02-DR-EI-7143 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | C | 131242-WST02-DR-EI-7144 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | C | 131242-WST02-DR-EI-7145 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | C | 131242-WST02-DR-EI-7146 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | C | 131242-WST02-DR-EI-7147 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | C | 131242-WST02-DR-EI-7148 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 29 |  |  | 000867 | 2024-12-02 | 2025-03-28 | B | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7149 | C | 131242-WST02-DR-EI-7149 | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | 133 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 000867 | 2025-03-28 | 2025-03-28 | B | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" |  | 2025-03
000868 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 0 | 131242-WSW41-SP-C-0022 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-31 | 2025-01-08 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000868 | 2024-12-02 | 2025-02-20 | 2 | NAP | Approved | 3 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" |  | 2024-12
000868 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 1 | 131242-WSW41-SP-C-0022 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-17 | 55 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000868 | 2024-12-02 | 2025-02-20 | 2 | AWC | Approved | 3 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" |  | 2024-12
000868 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 2 | 131242-WSW41-SP-C-0022 | 2025-02-20 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R2: Approved | 2025-03-12 | 2025-03-04 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000868 | 2024-12-02 | 2025-02-20 | 2 | APP | Approved | 3 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" |  | 2025-02
000869 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 0 | 131242-WSW41-SP-C-0023 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R0: Not Approved. Please refer to comment sheet for resubmission | 2024-12-31 | 2025-01-08 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000869 | 2024-12-02 | 2024-12-02 | 0 | NAP | Not Approved | 2 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" |  | 2024-12
000869 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 1 | 131242-WSW41-SP-C-0023 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R1:Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-03 | 45 | Approved with Comments | YES | 2025-02-21 | NO | Resubmitted | 0 |  |  | 000869 | 2024-12-02 | 2024-12-02 | 0 | AWC | Not Approved | 2 | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | A | 131242-WST02-DR-EP-3024 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | A | 131242-WST02-DR-EP-3025 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | A | 131242-WST02-DR-EP-3026 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | A | 131242-WST02-DR-EP-3027 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | A | 131242-WST02-DR-EP-3028 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | A | 131242-WST02-DR-EP-3029 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | A | 131242-WST02-DR-EP-3030 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | A | 131242-WST02-DR-EP-3031 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | A | 131242-WST02-DR-EP-3032 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | A | 131242-WST02-DR-EP-3033 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | A | 131242-WST02-DR-EP-3034 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | A | 131242-WST02-DR-EP-3035 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | A | 131242-WST02-DR-EI-7080 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | A | 131242-WST02-DR-EI-7081 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | A | 131242-WST02-DR-EI-7082 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | A | 131242-WST02-DR-EI-7083 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | A | 131242-WST02-DR-EI-7084 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | A | 131242-WST02-DR-EI-7085 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | A | 131242-WST02-DR-EI-7086 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | A | 131242-WST02-DR-EI-7087 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | A | 131242-WST02-DR-EI-7088 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | A | 131242-WST02-DR-EI-7089 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | A | 131242-WST02-DR-EI-7090 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | A | 131242-WST02-DR-EI-7091 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | A | 131242-WST02-DR-EI-7100 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | A | 131242-WST02-DR-EI-7101 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | A | 131242-WST02-DR-EI-7102 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | A | 131242-WST02-DR-EI-7103 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | A | 131242-WST02-DR-EI-7104 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | A | 131242-WST02-DR-EI-7105 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | A | 131242-WST02-DR-EI-7106 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | A | 131242-WST02-DR-EI-7107 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | A | 131242-WST02-DR-EI-7108 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | A | 131242-WST02-DR-EI-7109 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | A | 131242-WST02-DR-EI-7110 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | A | 131242-WST02-DR-EI-7111 | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2024-12
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | B | 131242-WST02-DR-EP-3024 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBA |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | B | 131242-WST02-DR-EP-3025 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | B | 131242-WST02-DR-EP-3026 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | B | 131242-WST02-DR-EP-3027 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | B | 131242-WST02-DR-EP-3028 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | B | 131242-WST02-DR-EP-3029 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | B | 131242-WST02-DR-EP-3030 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | B | 131242-WST02-DR-EP-3031 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | B | 131242-WST02-DR-EP-3032 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | B | 131242-WST02-DR-EP-3033 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | B | 131242-WST02-DR-EP-3034 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | B | 131242-WST02-DR-EP-3035 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | B | 131242-WST02-DR-EP-7126 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | B | 131242-WST02-DR-EP-7127 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7128 | B | 131242-WST02-DR-EP-7128 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7129 | B | 131242-WST02-DR-EP-7129 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7130 | B | 131242-WST02-DR-EP-7130 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7131 | B | 131242-WST02-DR-EP-7131 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7132 | B | 131242-WST02-DR-EP-7132 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7133 | B | 131242-WST02-DR-EP-7133 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7134 | B | 131242-WST02-DR-EP-7134 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7135 | B | 131242-WST02-DR-EP-7135 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | B | 131242-WST02-DR-EI-7080 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | B | 131242-WST02-DR-EI-7081 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | B | 131242-WST02-DR-EI-7082 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | B | 131242-WST02-DR-EI-7083 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | B | 131242-WST02-DR-EI-7084 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | B | 131242-WST02-DR-EI-7085 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | B | 131242-WST02-DR-EI-7086 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | B | 131242-WST02-DR-EI-7087 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | B | 131242-WST02-DR-EI-7088 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | B | 131242-WST02-DR-EI-7089 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | B | 131242-WST02-DR-EI-7090 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | B | 131242-WST02-DR-EI-7091 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7092 | B | 131242-WST02-DR-EI-7092 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | B | 131242-WST02-DR-EI-7100 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | B | 131242-WST02-DR-EI-7101 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | B | 131242-WST02-DR-EI-7102 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | B | 131242-WST02-DR-EI-7103 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | B | 131242-WST02-DR-EI-7104 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | B | 131242-WST02-DR-EI-7105 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | B | 131242-WST02-DR-EI-7106 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | B | 131242-WST02-DR-EI-7107 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | B | 131242-WST02-DR-EI-7108 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | B | 131242-WST02-DR-EI-7109 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | B | 131242-WST02-DR-EI-7110 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | B | 131242-WST02-DR-EI-7111 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7112 | B | 131242-WST02-DR-EI-7112 | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-04
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | C | 131242-WST02-DR-EP-3024 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | C | 131242-WST02-DR-EP-3025 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | C | 131242-WST02-DR-EP-3026 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | C | 131242-WST02-DR-EP-3027 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | C | 131242-WST02-DR-EP-3028 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | C | 131242-WST02-DR-EP-3029 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | C | 131242-WST02-DR-EP-3030 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | C | 131242-WST02-DR-EP-3031 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | C | 131242-WST02-DR-EP-3032 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | C | 131242-WST02-DR-EP-3033 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | C | 131242-WST02-DR-EP-3034 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | C | 131242-WST02-DR-EP-3035 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | C | 131242-WST02-DR-EP-7126 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | C | 131242-WST02-DR-EP-7127 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000866&&000870 | 2024-12-02 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7128 | C | 131242-WST02-DR-EP-7128 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7129 | C | 131242-WST02-DR-EP-7129 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7130 | C | 131242-WST02-DR-EP-7130 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7131 | C | 131242-WST02-DR-EP-7131 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7132 | C | 131242-WST02-DR-EP-7132 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7133 | C | 131242-WST02-DR-EP-7133 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7134 | C | 131242-WST02-DR-EP-7134 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7135 | C | 131242-WST02-DR-EP-7135 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | C | 131242-WST02-DR-EI-7080 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | C | 131242-WST02-DR-EI-7081 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | C | 131242-WST02-DR-EI-7082 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | C | 131242-WST02-DR-EI-7083 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | C | 131242-WST02-DR-EI-7084 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | C | 131242-WST02-DR-EI-7085 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | C | 131242-WST02-DR-EI-7086 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | C | 131242-WST02-DR-EI-7087 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | C | 131242-WST02-DR-EI-7088 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | C | 131242-WST02-DR-EI-7089 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | C | 131242-WST02-DR-EI-7090 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | C | 131242-WST02-DR-EI-7091 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7092 | C | 131242-WST02-DR-EI-7092 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | C | 131242-WST02-DR-EI-7100 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | C | 131242-WST02-DR-EI-7101 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | C | 131242-WST02-DR-EI-7102 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | C | 131242-WST02-DR-EI-7103 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | C | 131242-WST02-DR-EI-7104 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | C | 131242-WST02-DR-EI-7105 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | C | 131242-WST02-DR-EI-7106 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | C | 131242-WST02-DR-EI-7107 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | C | 131242-WST02-DR-EI-7108 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | C | 131242-WST02-DR-EI-7109 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | C | 131242-WST02-DR-EI-7110 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | C | 131242-WST02-DR-EI-7111 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2024-12-03 | 2025-07-24 | C | AWC | Approved with Comments | 3 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7112 | C | 131242-WST02-DR-EI-7112 | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | 116 | Approved with Comments | YES | 2026-01-22 | NO | Resubmitted | 0 |  |  | 000870 | 2025-04-08 | 2025-07-24 | C | AWC | Approved with Comments | 2 | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" |  | 2025-07
000871 | 00 | Thet Myo | QAQC | NA | 131242 | WSD11 | MM | S | 0001 | 0 | 131242-WSD11-MM-S-0001 | 2024-12-03 | THP Courtyard SCDF Consultation Letter | For Information | 2025-01-01 | 2024-11-14 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000871 | 2024-12-03 | 2024-12-03 | 0 | INF | For Information | 1 | "THP Courtyard SCDF Consultation Letter" |  | 2024-12
000872 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0026 | 0 | 131242-WSW41-QA-M-0026 | 2024-12-04 | Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-02 | 2024-12-14 | 8 | Approved with Comments | YES | 2025-01-02 | NO | Resubmitted | 0 |  |  | 000872 | 2024-12-04 | 2024-12-04 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" |  | 2024-12
000873 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0009 | 0 | 131242-WST02-QA-E-0009 | 2024-12-04 | FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-02 | 2024-12-23 | 13 | Approved with Comments | YES | 2025-01-10 | NO | Resubmitted | 0 |  |  | 000873 | 2024-12-04 | 2024-12-04 | 0 | AWC | Approved with Comments | 1 | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " |  | 2024-12
000874 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 0 | 131242-WST02-CL-P-5431 | 2024-12-04 | SSN Catchpot Sizing Calculation | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-02 | 2025-01-08 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | comments received on 14 Feb | 000874 | 2024-12-04 | 2025-07-14 | 2 | AWC | Approved with Comments | 3 | "SSN Catchpot Sizing Calculation " |  | 2024-12
000874 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 1 | 131242-WST02-CL-P-5431 | 2025-03-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-28 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000874 | 2024-12-04 | 2025-07-14 | 2 | AWC | Approved with Comments | 3 | "SSN Catchpot Sizing Calculation " |  | 2025-03
000874 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 2 | 131242-WST02-CL-P-5431 | 2025-07-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-01 | 2025-09-17 | 47 | Approved with Comments | YES | 2025-10-07 | NO | Resubmitted | 0 |  |  | 000874 | 2024-12-04 | 2025-07-14 | 2 | AWC | Approved with Comments | 3 | "SSN Catchpot Sizing Calculation " |  | 2025-07
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | E | 131242-WST00-DR-S-8005_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | E | 131242-WST02-DR-S-0302_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0310_ST608_BCA | E | 131242-WST02-DR-S-0310_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000875 | 2024-12-05 | 2024-12-05 | E | INF | For Information | 1 | "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0311_ST608_BCA | E | 131242-WST02-DR-S-0311_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000875 | 2024-12-05 | 2024-12-05 | E | INF | For Information | 1 | "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0312_ST608_BCA | E | 131242-WST02-DR-S-0312_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000875 | 2024-12-05 | 2024-12-05 | E | INF | For Information | 1 | "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | E | 131242-WST02-DR-S-1200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | E | 131242-WST02-DR-S-1201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | E | 131242-WST02-DR-S-1202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | E | 131242-WST02-DR-S-1203_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | E | 131242-WST02-DR-S-1204_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | E | 131242-WST02-DR-S-1205_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | E | 131242-WST02-DR-S-2200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | E | 131242-WST02-DR-S-2201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | E | 131242-WST02-DR-S-2202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | E | 131242-WST02-DR-S-2203_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | E | 131242-WST02-DR-S-3200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | E | 131242-WST02-DR-S-3201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | E | 131242-WST02-DR-S-3202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | E | 131242-WST02-DR-S-5200_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | E | 131242-WST02-DR-S-5201_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | E | 131242-WST02-DR-S-5202_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | E | 131242-WST02-DR-S-5203_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | E | 131242-WST02-DR-S-5204_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | E | 131242-WST02-DR-S-5205_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | E | 131242-WST02-DR-S-5206_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | E | 131242-WST02-DR-S-5207_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | E | 131242-WST02-DR-S-5208_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | E | 131242-WST02-DR-S-5209_ST608_BCA | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000742&&000875 | 2024-10-04 | 2024-12-05 | E | INF | For Information | 2 | "BCA submission of ST608 – SSN Shelters (for Information) " && "BCA approval of ST608 - SSN Shelter" |  | 2024-12
000876 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 0 | 131242-WST02-QA-A-0001 | 2024-12-05 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-03 | 2024-12-23 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000876 | 2024-12-05 | 2025-04-11 | 1 | AWC | Approved with Comments | 2 | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" |  | 2024-12
000876 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 1 | 131242-WST02-QA-A-0001 | 2025-04-11 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Approved with Comments | 2025-05-01 | 2025-06-09 | 41 | Approved with Comments | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 000876 | 2024-12-05 | 2025-04-11 | 1 | AWC | Approved with Comments | 2 | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" |  | 2025-04
000877 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0051 | 0 | 131242-WSW41-LT-PM-0051 | 2024-12-07 | CV of Team Member (CSEM) | Rev 0: Accepted for Information. | 2025-01-06 | 2025-03-25 | 76 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000877 | 2024-12-07 | 2024-12-07 | 0 | INF | For Information | 1 | "CV of Team Member (CSEM)" |  | 2024-12
000878 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0052 | 0 | 131242-WSW41-LT-PM-0052 | 2024-12-07 | Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3) | Rev (0): Rejected. Please refer to S.O. correspondence no. 397 dated 10 Sep 25. | 2025-01-06 | 2025-09-23 | 206 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000878 | 2024-12-07 | 2024-12-07 | 0 | REJ | Rejected | 1 | "Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3)" |  | 2024-12
000879 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | NA | 0 | 131242-WSW41-CD-IM-NA | 2024-12-09 | VCM Model Submission | For Information. | 2025-01-07 | 2024-12-23 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000879&&001888&&001941&&002009 | 2024-12-09 | 2026-02-09 | 0 | INF | For Information | 4 | "VCM Model Submission" && " VCM Submission for 2025-11" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" |  | 2024-12
000880 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5391 | 0 | 131242-WST02-CL-P-5391 | 2024-12-10 | Sampling Pump Calculation | Rev 0: Approved | 2025-01-08 | 2025-04-27 | 99 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000880 | 2024-12-10 | 2024-12-10 | 0 | APP | Approved | 1 | "Sampling Pump Calculation" |  | 2024-12
000881 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 0 | 131242-WSW41-QA-M-0025 | 2024-12-10 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-08 | 2025-01-20 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000881 | 2024-12-10 | 2025-03-13 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" |  | 2024-12
000881 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 1 | 131242-WSW41-QA-M-0025 | 2025-03-13 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Approved | 2025-04-02 | 2025-05-19 | 47 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000881 | 2024-12-10 | 2025-03-13 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" |  | 2025-03
000882 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0005 | 0 | 131242-WST02-VI-E-0005 | 2024-12-10 | Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-08 | 2024-12-23 | 9 | Approved with Comments | YES | 2025-01-10 | NO | Resubmitted | 0 |  | To follow-up with Jebsen and Jessen. | 000882 | 2024-12-10 | 2024-12-10 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" |  | 2024-12
000883 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0008 | 0 | 131242-WST02-QA-A-0008 | 2024-12-10 | Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-08 | 2024-12-23 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000883 | 2024-12-10 | 2024-12-10 | 0 | APP | Approved | 1 | "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " |  | 2024-12
000884 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0007 | 0 | 131242-WST02-QA-A-0007 | 2024-12-11 | Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-09 | 2024-12-23 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000884 | 2024-12-11 | 2024-12-11 | 0 | APP | Approved | 1 | "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " |  | 2024-12
000885 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 0 | 131242-WSW41-QA-S-0010 | 2024-12-11 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.0: As requested by CES to reject this submission. | 2025-01-09 | 2024-12-14 | 3 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000885 | 2024-12-11 | 2024-12-18 | 1 | REJ | Approved with Comments | 2 | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" |  | 2024-12
000885 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 1 | 131242-WSW41-QA-S-0010 | 2024-12-18 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.1: Approved with comments. Please refer comment sheet for resubmission. | 2025-01-08 | 2024-12-23 | 3 | Approved with Comments | YES | 2025-01-10 | NO | Resubmitted | 0 |  |  | 000885 | 2024-12-11 | 2024-12-18 | 1 | AWC | Approved with Comments | 2 | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" |  | 2024-12
000886 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | I | 0006 | 0 | 131242-WSW41-VI-I-0006 | 2024-12-11 | Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-09 | 2025-01-08 | 20 | Approved with Comments | YES | 2025-01-28 | NO | Resubmitted | 0 |  |  | 000886 | 2024-12-11 | 2024-12-11 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" |  | 2024-12
000887 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0017 | 0 | 131242-WSW41-PS-HS-0017 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Sept 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2025-01-10 | 2024-12-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000887 | 2024-12-12 | 2024-12-12 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Sept 2024" |  | 2024-12
000888 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0018 | 0 | 131242-WSW41-PS-HS-0018 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Oct 2024 | Rev 0: Scoring confirmed to be at 60/100 | 2025-01-10 | 2024-12-30 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000888 | 2024-12-12 | 2024-12-12 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Oct 2024" |  | 2024-12
000889 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-M-0027 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-01-20 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000889 | 2024-12-12 | 2024-12-12 | 0 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" |  | 2024-12
000889 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-M-0027 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 1: Approved. | 2025-01-02 | 2025-12-23 | 268 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000889 | 2024-12-12 | 2024-12-12 | 0 | APP | Approved with Comments | 2 | "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" |  | 2024-12
000890 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0019 | 0 | 131242-WSW41-RT-PM-0019 | 2024-12-13 | C4B Monthly Progress Report Number No.19 (11 24) | Rev. 0 - Approved with comments (see attached comment sheet / need to re-submit) | 2025-01-13 | 2025-01-16 | 24 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000890 | 2024-12-13 | 2024-12-13 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.19 (11 24) " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | A | 131242-WSW41-DR-M-5201 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-25 00:00:00 | Pending vendor resubmission - Jash | 000891 | 2024-12-13 | 2025-03-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5202 | A | 131242-WSW41-DR-M-5202 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5203 | A | 131242-WSW41-DR-M-5203 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5204 | A | 131242-WSW41-DR-M-5204 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5205 | A | 131242-WSW41-DR-M-5205 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5206 | A | 131242-WSW41-DR-M-5206 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5207 | A | 131242-WSW41-DR-M-5207 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5208 | A | 131242-WSW41-DR-M-5208 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5209 | A | 131242-WSW41-DR-M-5209 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5210 | A | 131242-WSW41-DR-M-5210 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5211 | A | 131242-WSW41-DR-M-5211 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5212 | A | 131242-WSW41-DR-M-5212 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5213 | A | 131242-WSW41-DR-M-5213 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5214 | A | 131242-WSW41-DR-M-5214 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5215 | A | 131242-WSW41-DR-M-5215 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5216 | A | 131242-WSW41-DR-M-5216 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5217 | A | 131242-WSW41-DR-M-5217 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5218 | A | 131242-WSW41-DR-M-5218 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5219 | A | 131242-WSW41-DR-M-5219 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5220 | A | 131242-WSW41-DR-M-5220 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5221 | A | 131242-WSW41-DR-M-5221 | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | 21 | Approved with Comments | YES | 2025-01-30 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2024-12
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | B | 131242-WSW41-DR-M-5201 | 2025-03-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 18 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 | 2025-02-25 00:00:00 | Pending vendor resubmission - Jash | 000891 | 2024-12-13 | 2025-03-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-03
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5202 | B | 131242-WSW41-DR-M-5202 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5203 | B | 131242-WSW41-DR-M-5203 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5204 | B | 131242-WSW41-DR-M-5204 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5205 | B | 131242-WSW41-DR-M-5205 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5206 | B | 131242-WSW41-DR-M-5206 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5207 | B | 131242-WSW41-DR-M-5207 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5208 | B | 131242-WSW41-DR-M-5208 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5209 | B | 131242-WSW41-DR-M-5209 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5210 | B | 131242-WSW41-DR-M-5210 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5211 | B | 131242-WSW41-DR-M-5211 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5212 | B | 131242-WSW41-DR-M-5212 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5213 | B | 131242-WSW41-DR-M-5213 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5214 | B | 131242-WSW41-DR-M-5214 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5215 | B | 131242-WSW41-DR-M-5215 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5216 | B | 131242-WSW41-DR-M-5216 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5217 | B | 131242-WSW41-DR-M-5217 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5218 | B | 131242-WSW41-DR-M-5218 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5219 | B | 131242-WSW41-DR-M-5219 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5220 | B | 131242-WSW41-DR-M-5220 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5221 | B | 131242-WSW41-DR-M-5221 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2024-12-13 | 2025-01-13 | B | AWC | Approved with Comments | 2 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5222 | A | 131242-WSW41-DR-M-5222 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5223 | A | 131242-WSW41-DR-M-5223 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5224 | A | 131242-WSW41-DR-M-5224 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5225 | A | 131242-WSW41-DR-M-5225 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5226 | A | 131242-WSW41-DR-M-5226 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5227 | A | 131242-WSW41-DR-M-5227 | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | 61 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000891 | 2025-01-13 | 2025-01-13 | A | AWC | Approved with Comments | 1 | "GA drawing for Metallic Knife Gate Valves " |  | 2025-01
000892 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0037 | 0 | 131242-WSW41-MI-C-0037 | 2024-12-13 | CSA Meeting Minutes 0037_28112024 | For Information | 2025-01-13 | 2024-12-30 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000892 | 2024-12-13 | 2024-12-13 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0037_28112024" |  | 2024-12
000893 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0023 | 0 | 131242-WST02-VI-I-0023 | 2024-12-13 | Vendor Approval of SSN Package (Rotameter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-14 | 65 | Approved with Comments | YES | 2025-04-03 | NO | Resubmitted | 0 |  |  | 000893 | 2024-12-13 | 2024-12-13 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of SSN Package (Rotameter)" |  | 2024-12
000894 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0050 | 0 | 131242-WSW41-LT-PM-0050 | 2024-12-13 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025. | 2025-01-13 | 2025-08-25 | 181 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000894 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" |  | 2024-12
000895 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 0 | 131242-WSW41-DS-E-1390 | 2024-12-13 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2024-12-23 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000895 | 2024-12-13 | 2025-02-14 | 1 | AWC | Approved | 2 | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" |  | 2024-12
000895 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 1 | 131242-WSW41-DS-E-1390 | 2025-02-14 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 1: Approved. | 2025-03-06 | 2025-04-27 | 51 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000895 | 2024-12-13 | 2025-02-14 | 1 | APP | Approved | 2 | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" |  | 2025-02
000896 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 0 | 131242-WSW41-DS-E-1389 | 2024-12-13 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000896 | 2024-12-13 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" |  | 2024-12
000896 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 1 | 131242-WSW41-DS-E-1389 | 2025-03-06 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-26 | 2025-04-27 | 37 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000896 | 2024-12-13 | 2025-03-06 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" |  | 2025-03
000897 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-E-1391 | 2024-12-13 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000897 | 2024-12-13 | 2025-03-11 | 0 | AWC | Approved | 2 | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" |  | 2024-12
000897 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-E-1391 | 2025-03-11 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 1: Approved. | 2025-03-31 | 2025-05-05 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000897 | 2024-12-13 | 2025-03-11 | 0 | APP | Approved | 2 | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" |  | 2025-03
000898 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-C-0023 | 2024-12-13 | MSRA and SWP for Installation of AAC Block Wall | Approved | 2025-01-13 | 2025-01-08 | 18 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000898&&001044 | 2024-12-13 | 2025-02-16 | 0 | APP | Approved | 2 | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" |  | 2024-12
000899 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0030 | 0 | 131242-WST02-DS-M-0030 | 2024-12-13 | Data Sheet for Blower Discharge Sliencer | Rev 0: Approved | 2025-01-13 | 2025-03-04 | 57 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000899 | 2024-12-13 | 2024-12-13 | 0 | APP | Approved | 1 | "Data Sheet for Blower Discharge Sliencer" |  | 2024-12
000900 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 0 | 131242-WST02-DS-I -0002 | 2024-12-13 | Datasheet for Electromagnetic Flowmeter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-25 | 72 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000900 | 2024-12-13 | 2025-06-26 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Electromagnetic Flowmeter" |  | 2024-12
000900 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 1 | 131242-WST02-DS-I -0002 | 2025-06-26 | Datasheet for Electromagnetic Flowmeter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-16 | 2025-07-28 | 22 | Approved with Comments | YES | 2025-08-15 | NO | Resubmitted | 0 |  |  | 000900 | 2024-12-13 | 2025-06-26 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Electromagnetic Flowmeter" |  | 2025-06
000901 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0009 | 0 | 131242-WST02-QA-A-0009 | 2024-12-13 | Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh | For Information | 2025-01-13 | 2024-12-23 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000901 | 2024-12-13 | 2024-12-13 | 0 | INF | For Information | 1 | "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" |  | 2024-12
000902 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004_Withdraw | 0 | 131242-WSD11-QA-N-0004_Withdraw | 2024-12-13 | Instrument Differential Pressure Switch SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000902 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Instrument Differential Pressure Switch SAT" |  | 2024-12
000903 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005_Withdraw | 0 | 131242-WSD11-QA-N-0005_Withdraw | 2024-12-13 | Instrument Pressure Transmitter SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000903 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Instrument Pressure Transmitter SAT" |  | 2024-12
000904 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006_Withdraw | 0 | 131242-WSD11-QA-N-0006_Withdraw | 2024-12-13 | Penumatic on/ off Valve SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000904 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Penumatic on/ off Valve SAT" |  | 2024-12
000905 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002_Withdraw | 0 | 131242-WSD11-QA-N-0002_Withdraw | 2024-12-13 | Air Compresspor SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000905 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Air Compresspor SAT" |  | 2024-12
000906 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003_Withdraw | 0 | 131242-WSD11-QA-N-0003_Withdraw | 2024-12-13 | Air Dryer SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | 40 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000906 | 2024-12-13 | 2024-12-13 | 0 | REJ | Rejected | 1 | "Air Dryer SAT" |  | 2024-12
000907 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 0 | 131242-WST02-RT-E-0009 | 2024-12-16 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | 46 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000907 | 2024-12-16 | 2026-01-20 | 1 | AWC | Approved with Comments | 2 | "SSN Harmonics Study Report" |  | 2024-12
000907 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 1 | 131242-WST02-RT-E-0009 | 2026-01-20 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 000907 | 2024-12-16 | 2026-01-20 | 1 | PEN | Approved with Comments | 2 | "SSN Harmonics Study Report" |  | 2026-01
000908 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0004 | 0 | 131242-WSD11-RT-E-0004 | 2024-12-16 | THP Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | 46 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000908 | 2024-12-16 | 2024-12-16 | 0 | AWC | Approved with Comments | 1 | "THP Harmonics Study Report" |  | 2024-12
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A | 131242-WSW41-DR-M-5128 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 00:00:00 | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" |  | 2024-12
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A | 131242-WSW41-DR-M-5129 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard- SWPR" |  | 2024-12
000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5130 | A | 131242-WSW41-DR-M-5130 | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" |  | 2024-12
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A.1 | 131242-WSW41-DR-M-5128 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-27 00:00:00 | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" |  | 2025-03
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.1 | 131242-WSW41-DR-M-5129 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard- SWPR" |  | 2025-03
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5130 | A.1 | 131242-WSW41-DR-M-5130 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-03-13 | A.1 | AWC | Approved with Comments | 2 | "Pipe Support Standard- SWPR" |  | 2025-03
000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-M-5100 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | 14 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000297&&000909 | 2024-02-01 | 2025-03-13 | A.1 | AWC | Approved with Comments | 3 | "Pipe Support Standard - General Notes" && "Standard Pipe Support - For All Area " && "Pipe Support Standard- SWPR" |  | 2025-03
000909 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.2 | 131242-WSW41-DR-M-5129 | 2025-06-25 | Pipe Support Standard- SWPR | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | 73 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000909 | 2024-12-16 | 2025-06-25 | A.2 | AWC | Approved with Comments | 3 | "Pipe Support Standard- SWPR" |  | 2025-06
000910 | 00 | David | Mech | NA | 131242 | WSW41 | DS | M | 5341 | 0 | 131242-WSW41-DS-M-5341 | 2024-12-17 | Data Sheet of Auto Lubrication Unit for centrifugal pump | Rev 0: Not approved - Revise and Resubmit | 2025-01-15 | 2025-01-20 | 24 | Not Approved | YES | 2025-02-07 | NO | Resubmitted | 0 | 2025-03-28 00:00:00 | In Progress | 000910 | 2024-12-17 | 2024-12-17 | 0 | NAP | Not Approved | 1 | "Data Sheet of Auto Lubrication Unit for centrifugal pump" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A | 131242-WST02-DR-M-5401 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-28 00:00:00 | In Progress | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5402 | A | 131242-WST02-DR-M-5402 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5403 | A | 131242-WST02-DR-M-5403 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5404 | A | 131242-WST02-DR-M-5404 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5405 | A | 131242-WST02-DR-M-5405 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5416 | A | 131242-WST02-DR-M-5416 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5417 | A | 131242-WST02-DR-M-5417 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5419 | A | 131242-WST02-DR-M-5419 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5420 | A | 131242-WST02-DR-M-5420 | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | AWC | Approved | 2 | "GA Drawing for FRP Tank" |  | 2024-12
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A.1 | 131242-WST02-DR-M-5401 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5402 | A.1 | 131242-WST02-DR-M-5402 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5403 | A.1 | 131242-WST02-DR-M-5403 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5404 | A.1 | 131242-WST02-DR-M-5404 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5405 | A.1 | 131242-WST02-DR-M-5405 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5406 | A.1 | 131242-WST02-DR-M-5406 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5407 | A.1 | 131242-WST02-DR-M-5407 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5408 | A.1 | 131242-WST02-DR-M-5408 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5416 | A.1 | 131242-WST02-DR-M-5416 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5417 | A.1 | 131242-WST02-DR-M-5417 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5418 | A.1 | 131242-WST02-DR-M-5418 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5419 | A.1 | 131242-WST02-DR-M-5419 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5420 | A.1 | 131242-WST02-DR-M-5420 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2024-12-17 | 2025-04-01 | A.1 | APP | Approved | 2 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5421 | A.1 | 131242-WST02-DR-M-5421 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" |  | 2025-04
000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5422 | A.1 | 131242-WST02-DR-M-5422 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000911 | 2025-04-01 | 2025-04-01 | A.1 | APP | Approved | 1 | "GA Drawing for FRP Tank" |  | 2025-04
000912 | 00 | Max | Project | NA | 131242 | WST02 | RT | S | 0001 | 0 | 131242-WST02-RT-S-0001 | 2024-12-18 | Safety Review Report for SSN Structures | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-16 | 2025-01-16 | 21 | Approved with Comments | YES | 2025-02-05 | NO | Resubmitted | 0 |  |  | 000912 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Safety Review Report for SSN Structures" |  | 2024-12
000913 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0010 | 0 | 131242-WST02-QA-E-0010 | 2024-12-18 | FAT report for Earth cable, LV Power cable (Unwitnessed) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-02-18 | 44 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000913 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "FAT report for Earth cable, LV Power cable (Unwitnessed)" |  | 2024-12
000914 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0028 | 0 | 131242-WSD11-QA-M-0028 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | 64 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000914 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI)" |  | 2024-12
000915 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0024 | 0 | 131242-WSD11-QA-M-0024 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | 64 | Approved with Comments | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 000915 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " |  | 2024-12
000916 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0013 | 0 | 131242-WSD11-CL-P-0013 | 2024-12-18 | THP G2D Plant Hydraulic Network Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-04-27 | 93 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000916 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "THP G2D Plant Hydraulic Network Calculation" |  | 2024-12
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | A | 131242-WST02-DR-M-5501 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2024-12
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5511 | A | 131242-WST02-DR-M-5511 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2024-12
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5521 | A | 131242-WST02-DR-M-5521 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2024-12
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5531 | A | 131242-WST02-DR-M-5531 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2024-12
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5541 | A | 131242-WST02-DR-M-5541 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2024-12
000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5551 | A | 131242-WST02-DR-M-5551 | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | 54 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | AWC | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2024-12
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | B | 131242-WST02-DR-M-5501 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-03 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2025-06
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5511 | B | 131242-WST02-DR-M-5511 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2025-06
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5521 | B | 131242-WST02-DR-M-5521 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2025-06
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5531 | B | 131242-WST02-DR-M-5531 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2025-06
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5541 | B | 131242-WST02-DR-M-5541 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2025-06
000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5551 | B | 131242-WST02-DR-M-5551 | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | 205 | Awaiting S.O.'s response | YES | 2025-07-31 | NO | Overdue | 0 |  |  | 000917 | 2024-12-18 | 2025-06-15 | B | PEN | Approved with Comments | 2 | "GA Drawing for Dosing Pump" |  | 2025-06
000918 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 0 | 131242-WST02-CL-BF-8000 | 2024-12-18 | Hydraulic Calculation (HOSEREEL) | Rev 0: Not approved - Revise and Resubmit | 2025-01-16 | 2025-01-24 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000918 | 2024-12-18 | 2025-02-19 | 1 | NAP | Approved with Comments | 2 | "Hydraulic Calculation (HOSEREEL)" |  | 2024-12
000918 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 1 | 131242-WST02-CL-BF-8000 | 2025-02-19 | Hydraulic Calculation (HOSEREEL) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-11 | 2025-03-18 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000918 | 2024-12-18 | 2025-02-19 | 1 | AWC | Approved with Comments | 2 | "Hydraulic Calculation (HOSEREEL)" |  | 2025-02
000919 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 0 | 131242-WSW41-LT-PM-0053 | 2024-12-19 | CV of Team Member (T&C Manager) | Rejected as requested by Contractor | 2025-01-17 | 2024-12-27 | 6 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000919 | 2024-12-19 | 2024-12-27 | 1 | REJ | Approved with Comments | 2 | "CV of Team Member (T&C Manager)" |  | 2024-12
000919 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 1 | 131242-WSW41-LT-PM-0053 | 2024-12-27 | CV of Team Member (T&C Manager) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-21 | 60 | Approved with Comments | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 000919 | 2024-12-19 | 2024-12-27 | 1 | AWC | Approved with Comments | 2 | "CV of Team Member (T&C Manager)" |  | 2024-12
000920 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0006 | 0 | 131242-WSW41-MS-E-0006 | 2024-12-18 | Installation of Cable Container Support System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the attached file for comments. | 2025-01-16 | 2025-12-17 | 260 | Approved with Comments | YES | 2026-01-06 | NO | Resubmitted | 0 |  |  | 000920 | 2024-12-18 | 2024-12-18 | 0 | AWC | Approved with Comments | 1 | "Installation of Cable Container Support System" |  | 2024-12
000921 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 0 | 131242-WSW41-VI-M-2004 | 2024-12-19 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-17 | 2025-03-10 | 57 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000921 | 2024-12-19 | 2025-04-01 | 1 | AWC | Approved | 2 | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" |  | 2024-12
000921 | 01 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 1 | 131242-WSW41-VI-M-2004 | 2025-04-01 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000921 | 2024-12-19 | 2025-04-01 | 1 | APP | Approved | 2 | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" |  | 2025-04
000922 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1393 | 0 | 131242-WST02-DS-E-1393 | 2024-12-19 | Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000922 | 2024-12-19 | 2024-12-19 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) " |  | 2024-12
000923 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1392 | 0 | 131242-WST02-DS-E-1392 | 2024-12-19 | Sample Board Submission for SS Cable Ladder, Accessories (United U-LI) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | 43 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000923 | 2024-12-19 | 2024-12-19 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for SS Cable Ladder, Accessories (United U-LI)" |  | 2024-12
000924 | 00 | Yuen Fatt | Project | NA | 131242 | WSD11 | VI | M | 0032 | 0 | 131242-WSD11-VI-M-0032 | 2024-12-20 | Vendor Approval of Ducting - CES_Salcon Sdn Bhd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-20 | 2025-01-09 | 14 | Approved with Comments | YES | 2025-01-29 | NO | Resubmitted | 0 |  |  | 000924 | 2024-12-20 | 2024-12-20 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Ducting - CES_Salcon Sdn Bhd" |  | 2024-12
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5351 | A | 131242-WST02-DR-M-5351 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | AWC | Approved with Comments | 1 | "PC Pump GA Drawing " |  | 2024-12
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5361 | A | 131242-WST02-DR-M-5361 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | PEN | Awaiting S.O.'s response | 1 | "PC Pump GA Drawing " |  | 2024-12
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5371 | A | 131242-WST02-DR-M-5371 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | PEN | Awaiting S.O.'s response | 1 | "PC Pump GA Drawing " |  | 2024-12
000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5381 | A | 131242-WST02-DR-M-5381 | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | 90 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000925 | 2024-12-23 | 2024-12-23 | A | PEN | Awaiting S.O.'s response | 1 | "PC Pump GA Drawing " |  | 2024-12
000926 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0012 | 0 | 131242-WST02-VI-E-0012 | 2024-12-23 | Vendor Approval - Passive Harmonic Filter | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-01-21 | 2025-01-19 | 20 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000926 | 2024-12-23 | 2024-12-23 | 0 | REJ | Rejected | 1 | "Vendor Approval - Passive Harmonic Filter" |  | 2024-12
000927 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-E-0011 | 2024-12-23 | FAT Report for Cable Ladder 1st Batch (United ULI) | Rev 0: Approved. | 2025-01-21 | 2025-02-18 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000927&&001087 | 2024-12-23 | 2025-03-05 | 0 | APP | Approved | 2 | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" |  | 2024-12
000928 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0018 | 0 | 131242-WSW41-PC-W-0018 | 2024-12-24 | Payment Claim No.18 | Rev(0): Approved. Please refer to S.O. correspondence no. 273 dated 26 Dec 2024. | 2025-01-22 | 2025-01-08 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000928 | 2024-12-24 | 2024-12-24 | 0 | APP | Approved | 1 | "Payment Claim No.18" |  | 2024-12
000929 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0030 | 0 | 131242-WSW41-QA-M-0030 | 2024-12-24 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-22 | 2025-03-11 | 55 | Approved with Comments | YES | 2025-03-31 | NO | Resubmitted | 0 |  |  | 000929 | 2024-12-24 | 2024-12-24 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" |  | 2024-12
000930 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0031 | 0 | 131242-WSD11-QA-M-0031 | 2024-12-26 | Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) | Rev 0: Approved | 2025-01-23 | 2025-03-11 | 53 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000930 | 2024-12-26 | 2024-12-26 | 0 | APP | Approved | 1 | "Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) " |  | 2024-12
000931 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | A | 131242-WST02-DR-M-5601 | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-24 | 2025-03-04 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000931&&001051 | 2024-12-27 | 2025-05-26 | B | AWC | Approved | 3 | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" |  | 2024-12
000931 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | B | 131242-WST02-DR-M-5601 | 2025-05-26 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 |  | 220 | Awaiting S.O.'s response | YES | 2025-07-11 | NO | Overdue | 0 |  |  | 000931&&001051 | 2024-12-27 | 2025-05-26 | B | PEN | Approved | 3 | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" |  | 2025-05
000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0011 | 0 | 131242-WSD11-OM-M-0011 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | 51 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000932 | 2024-12-27 | 2024-12-27 | 0 | INF | For Information | 1 | "O&M manual for Air Dryer and Air Compressor" |  | 2024-12
000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0010 | 0 | 131242-WSD11-OM-M-0010 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | 51 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000932 | 2024-12-27 | 2024-12-27 | 0 | INF | For Information | 1 | "O&M manual for Air Dryer and Air Compressor" |  | 2024-12
000933 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601_WITHDRAW | A | 131242-WST02-DR-M-5601_WITHDRAW | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Rejected Submittal 931 include the same content and is already reviewed. | 2025-01-24 | 2025-03-04 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000933 | 2024-12-27 | 2024-12-27 | A | REJ | Rejected | 1 | "Screen General Arrangement Drawing" |  | 2024-12
000934 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5136 | 0 | 131242-WST02-DR-M-5136 | 2024-12-31 | Blower Name Plate Drawing | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000934 | 2024-12-31 | 2024-12-31 | 0 | APP | Approved | 1 | "Blower Name Plate Drawing " |  | 2024-12
000935 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0010 | 0 | 131242-WST02-QA-A-0010 | 2024-12-31 | Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-01-28 | 2025-02-24 | 39 | Approved with Comments | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 000935 | 2024-12-31 | 2024-12-31 | 0 | AWC | Approved with Comments | 1 | "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" |  | 2024-12
000936 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0012 | 0 | 131242-WSW41-QA-E-0012 | 2024-12-31 | FAT Report for Power Cable, Control Cable, MV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-28 | 2025-01-20 | 14 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000936 | 2024-12-31 | 2024-12-31 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Power Cable, Control Cable, MV Cable" |  | 2024-12
000937 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0034 | 0 | 131242-WSW41-QA-M-0034 | 2024-12-31 | Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000937 | 2024-12-31 | 2024-12-31 | 0 | APP | Approved | 1 | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" |  | 2024-12
000938 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0035 | 0 | 131242-WSW41-QA-M-0035 | 2024-12-31 | Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | 70 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000938 | 2024-12-31 | 2024-12-31 | 0 | APP | Approved | 1 | "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" |  | 2024-12
000939 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0032 | 0 | 131242-WSW41-QA-M-0032 | 2025-01-02 | QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details) | Rev 0: Approved | 2025-01-30 | 2025-04-27 | 82 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000939 | 2025-01-02 | 2025-01-02 | 0 | APP | Approved | 1 | "QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details)" |  | 2025-01
000940 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0029 | 0 | 131242-WSW41-QA-M-0029 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating | Rev 0: Approved | 2025-01-30 | 2025-04-08 | 68 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000940 | 2025-01-02 | 2025-01-02 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" |  | 2025-01
000941 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 0 | 131242-WSW41-QA-M-0033 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Rev 0: Not approved - Revise and Resubmit | 2025-01-30 | 2025-03-18 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000941 | 2025-01-02 | 2025-04-21 | 1 | NAP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" |  | 2025-01
000941 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 1 | 131242-WSW41-QA-M-0033 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Approved | 2025-05-09 | 2025-05-19 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000941 | 2025-01-02 | 2025-04-21 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" |  | 2025-04
000942 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 0 | 131242-WSW41-SH-M-1004 | 2025-01-02 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 | TBC | SO comment: Please furnish GA drawings in TWRP format. (vendor not able to provide) | 000942 | 2025-01-02 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" |  | 2025-01
000942 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 1 | 131242-WSW41-SH-M-1004 | 2025-06-16 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2025-09-04 | 58 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 000942 | 2025-01-02 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" |  | 2025-06
000943 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | E | 0001 | 0 | 131242-WSW41-DS-E-0001 | 2025-01-03 | Datasheet for Unistrut Supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000943 | 2025-01-03 | 2025-01-03 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Unistrut Supports" |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1300 | A | 131242-WSW41-DR-E-1300 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1301 | A | 131242-WSW41-DR-E-1301 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1302 | A | 131242-WSW41-DR-E-1302 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1303 | A | 131242-WSW41-DR-E-1303 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1304 | A | 131242-WSW41-DR-E-1304 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1305 | A | 131242-WSW41-DR-E-1305 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1306 | A | 131242-WSW41-DR-E-1306 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1307 | A | 131242-WSW41-DR-E-1307 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1308 | A | 131242-WSW41-DR-E-1308 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1309 | A | 131242-WSW41-DR-E-1309 | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | 49 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000944 | 2025-01-03 | 2025-01-03 | A | AWC | Approved with Comments | 1 | "Drawing Submission for Unistrut EICA Cable tray supports " |  | 2025-01
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-S-1600_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | D | 131242-WST02-DR-S-1601_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | D | 131242-WST02-DR-S-5600_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-S-5601_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | D | 131242-WST02-DR-S-5602_ST611_BCA | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609_BCA | E | 131242-WST00-DR-S-8004_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1100__ST609_BCA | E | 131242-WST02-DR-S-1100__ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0300__ST609_BCA | E | 131242-WST02-DR-S-0300__ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0301_ST609_BCA | E | 131242-WST02-DR-S-0301_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0303_ST609_BCA | E | 131242-WST02-DR-S-0303_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0304_ST609_BCA | E | 131242-WST02-DR-S-0304_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0305_ST609_BCA | E | 131242-WST02-DR-S-0305_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0306_ST609_BCA | E | 131242-WST02-DR-S-0306_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0307_ST609_BCA | E | 131242-WST02-DR-S-0307_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0308_ST609_BCA | E | 131242-WST02-DR-S-0308_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0309_ST609_BCA | E | 131242-WST02-DR-S-0309_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1101_ST609_BCA | E | 131242-WST02-DR-S-1101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1102_ST609_BCA | E | 131242-WST02-DR-S-1102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1103_ST609_BCA | E | 131242-WST02-DR-S-1103_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2100_ST609_BCA | E | 131242-WST02-DR-S-2100_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2101_ST609_BCA | E | 131242-WST02-DR-S-2101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2102_ST609_BCA | E | 131242-WST02-DR-S-2102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3100_ST609_BCA | E | 131242-WST02-DR-S-3100_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3101_ST609_BCA | E | 131242-WST02-DR-S-3101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3102_ST609_BCA | E | 131242-WST02-DR-S-3102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5100_ST609_BCA | E | 131242-WST02-DR-S-5100_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5101_ST609_BCA | E | 131242-WST02-DR-S-5101_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5102_ST609_BCA | E | 131242-WST02-DR-S-5102_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5103_ST609_BCA | E | 131242-WST02-DR-S-5103_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5104_ST609_BCA | E | 131242-WST02-DR-S-5104_ST609_BCA | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000946 | 2025-01-03 | 2025-01-03 | E | INF | For Information | 1 | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | D | 131242-WSW41-DR-S-8002_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | D | 131242-WSW41-DR-S-1100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | D | 131242-WSW41-DR-S-0310_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | D | 131242-WSW41-DR-S-0311_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | C | 131242-WSW41-DR-S-0312_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | C | 131242-WSW41-DR-S-0313_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | C | 131242-WSW41-DR-S-0314_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | C | 131242-WSW41-DR-S-0315_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | C | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | D | 131242-WSW41-DR-S-1101_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | D | 131242-WSW41-DR-S-1102_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | D | 131242-WSW41-DR-S-1103_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | D | 131242-WSW41-DR-S-1104_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1105_ST614_BCA | D | 131242-WSW41-DR-S-1105_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000947 | 2025-01-03 | 2025-01-03 | D | INF | For Information | 1 | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1106_ST614_BCA | D | 131242-WSW41-DR-S-1106_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000947 | 2025-01-03 | 2025-01-03 | D | INF | For Information | 1 | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | D | 131242-WSW41-DR-S-2100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | D | 131242-WSW41-DR-S-2101_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | D | 131242-WSW41-DR-S-3100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | D | 131242-WSW41-DR-S-5100_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | D | 131242-WSW41-DR-S-5101_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | D | 131242-WSW41-DR-S-5102_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | D | 131242-WSW41-DR-S-5103_ST614_BCA | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000773&&000947 | 2024-10-23 | 2025-01-03 | D | INF | For Information | 2 | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " && "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " |  | 2025-01
000948 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | RT | C | 0014 | 0 | 131242-WSW41-RT-C-0014 | 2025-01-03 | Bored Piling Pile Eccentricity Reports (ECC 19 & 20) | For Information. Please refer comment sheet. | 2025-01-31 | 2025-01-12 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000948 | 2025-01-03 | 2025-01-03 | 0 | INF | For Information | 1 | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" |  | 2025-01
000949 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 0 | 131242-WSW41-MS-E-0007 | 2025-01-03 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-01-31 | 2025-01-24 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000949 | 2025-01-03 | 2025-02-27 | 1 | NAP | Approved with Comments | 2 | "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" |  | 2025-01
000949 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 1 | 131242-WSW41-MS-E-0007 | 2025-02-27 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-27 | 42 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000949 | 2025-01-03 | 2025-02-27 | 1 | AWC | Approved with Comments | 2 | "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" |  | 2025-02
000950 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0005 | 0 | 131242-WST02-VI-A-0005 | 2025-01-03 | Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd. | Approved | 2025-01-31 | 2025-01-16 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000950 | 2025-01-03 | 2025-01-03 | 0 | APP | Approved | 1 | "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." |  | 2025-01
000951 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0011 | 0 | 131242-WST02-QA-A-0011 | 2025-01-04 | Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-01-31 | 2025-02-03 | 20 | Approved with Comments | YES | 2025-02-21 | NO | Resubmitted | 0 |  |  | 000951 | 2025-01-04 | 2025-01-04 | 0 | AWC | Approved with Comments | 1 | "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" |  | 2025-01
000952 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-C-0021 | 2025-01-04 | Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024 | For information. | 2025-01-31 | 2025-01-24 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000825&&000952 | 2024-11-20 | 2025-01-04 | 0 | INF | For Information | 2 | "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" |  | 2025-01
000953 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1003 | 0 | 131242-WSW41-SH-M-1003 | 2025-01-07 | C4B Knife Gate Valve List & Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-04 | 2025-04-08 | 65 | Approved with Comments | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 000953 | 2025-01-07 | 2025-01-07 | 0 | AWC | Approved with Comments | 1 | "C4B Knife Gate Valve List & Datasheet" |  | 2025-01
000954 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 0 | 131242-WSW41-VI-M-1013 | 2025-01-07 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 0: Not approved - Revise and Resubmit | 2025-02-04 | 2025-02-12 | 26 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000954 | 2025-01-07 | 2025-06-17 | 2 | REJ | Approved | 3 | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" |  | 2025-01
000954 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 1 | 131242-WSW41-VI-M-1013 | 2025-03-27 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-04-11 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 | Pending vendor clarification - Breen | 000954 | 2025-01-07 | 2025-06-17 | 2 | AWC | Approved | 3 | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" |  | 2025-03
000954 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 2 | 131242-WSW41-VI-M-1013 | 2025-06-17 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 2: Approved | 2025-07-07 | 2025-07-28 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000954 | 2025-01-07 | 2025-06-17 | 2 | APP | Approved | 3 | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" |  | 2025-06
000955 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0036 | 0 | 131242-WSW41-QA-M-0036 | 2025-01-07 | FAT/MDR Report for Side Manway (9 no;) | Rev 0: Approved | 2025-02-04 | 2025-03-25 | 55 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000955 | 2025-01-07 | 2025-01-07 | 0 | APP | Approved | 1 | "FAT/MDR Report for Side Manway (9 no;)" |  | 2025-01
000956 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0051 | 0 | 131242-WSW41-CD-IM-0051 | 2025-01-08 | Submission of BIM Coordination VCM Model (Dec 2024) | For Information. Score= 71/100 | 2025-02-05 | 2025-01-24 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000956 | 2025-01-08 | 2025-01-08 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (Dec 2024)" |  | 2025-01
000957 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0038 | 0 | 131242-WSW41-MI-C-0038 | 2025-01-09 | CSA Meeting Minutes 0038_12122024 | For information. | 2025-02-06 | 2025-01-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000957 | 2025-01-09 | 2025-01-09 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0038_12122024" |  | 2025-01
000958 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0038 | 0 | 131242-WST02-QA-M-0038 | 2025-01-09 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch) | Rev 0: Approved | 2025-02-06 | 2025-03-25 | 53 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000958 | 2025-01-09 | 2025-01-09 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" |  | 2025-01
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0006 | A | 131242-WSD11-CL-S-0006 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000959 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system <2m" |  | 2025-01
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1602 | A | 131242-WSD11-DR-S-1602 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000959 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system <2m" |  | 2025-01
000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5602 | A | 131242-WSD11-DR-S-5602 | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000959 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system <2m" |  | 2025-01
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007 | A | 131242-WSD11-CL-S-0007 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960&&001945 | 2025-01-10 | 2026-01-12 | 1 | AWC | Approved with Comments | 2 | "Support design for compressed Air system >2m" && "G2D Pipe Support_Report from QPD" |  | 2025-01
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600 | A | 131242-WSD11-DR-S-5600 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" |  | 2025-01
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601 | A | 131242-WSD11-DR-S-5601 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" |  | 2025-01
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600 | A | 131242-WSD11-DR-S-1600 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" |  | 2025-01
000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601 | A | 131242-WSD11-DR-S-1601 | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | 27 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 000960 | 2025-01-10 | 2025-01-10 | A | AWC | Approved with Comments | 1 | "Support design for compressed Air system >2m" |  | 2025-01
000961 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 0 | 131242-WSD11-DS-I-0004 | 2025-01-10 | Datasheet for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-05 00:00:00 |  | 000961 | 2025-01-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Pressure Transmitter" |  | 2025-01
000961 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 1 | 131242-WSD11-DS-I-0004 | 2025-03-17 | Datasheet for Pressure Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | 37 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 000961 | 2025-01-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Pressure Transmitter" |  | 2025-03
000962 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 0 | 131242-WSD11-QA-M-0039 | 2025-01-10 | FAT report for THP Train 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-20 | 29 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | AWC | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" |  | 2025-01
000962 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 1 | 131242-WSD11-QA-M-0039 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rejected, as requested by contractor via email dated 8 Dec 2025. They will resubmit ZIP files with clear descriptive folder names instead of individual file | 2025-12-26 | 2025-12-08 | 0 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | REJ | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" |  | 2025-12
000962 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 2 | 131242-WSD11-QA-M-0039 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2025-12-23 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | AWC | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" |  | 2025-12
000962 | 03 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 3 | 131242-WSD11-QA-M-0039 | 2026-01-06 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000962 | 2025-01-10 | 2026-01-06 | 3 | PEN | Rejected | 4 | "FAT report for THP Train 1 (Part-1)" |  | 2026-01
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-S-5601_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | D | 131242-WST02-DR-S-5602_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-S-1600_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | D | 131242-WST02-DR-S-1601_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | D | 131242-WST02-DR-S-5600_ST611_BCA | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000945&&000963 | 2025-01-03 | 2025-01-11 | D | INF | For Information | 2 | "BCA submission of ST611 (Pipe Support More Than 2m)" && "BCA Approval of ST611 (Pipe Support more than 2m)" |  | 2025-01
000964 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 0 | 131242-WSD11-SP-I-0004 | 2025-01-11 | Functional Design Specification (Air Compressor System) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-04 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000964 | 2025-01-11 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "Functional Design Specification (Air Compressor System)" |  | 2025-01
000964 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 1 | 131242-WSD11-SP-I-0004 | 2025-06-04 | Functional Design Specification (Air Compressor System) | R1: Approved with comments. No resubmittal is required at this moment. The resubmittal is required only if any changes during the detailing. | 2025-06-24 | 2025-07-02 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000964 | 2025-01-11 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "Functional Design Specification (Air Compressor System)" |  | 2025-06
000964 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 2 | 131242-WSD11-SP-I-0004 | 2025-08-12 | Functional Design Specification (Air Compressor System) | R2: Approved with comments. However, no resubmission at this stage unless there is a change to the document. | 2025-09-01 | 2025-10-08 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000964 | 2025-01-11 | 2025-08-12 | 2 | AWC | Approved with Comments | 3 | "Functional Design Specification (Air Compressor System)" |  | 2025-08
000965 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0036 | 0 | 131242-WSW41-MI-P-0036 | 2025-01-11 | Process & MEICA Meeting Minutes 0036_21112024 | For Information | 2025-02-07 | 2025-01-16 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000965 | 2025-01-11 | 2025-01-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0036_21112024" |  | 2025-01
000966 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0037 | 0 | 131242-WSW41-MI-P-0037 | 2025-01-11 | Process & MEICA Meeting Minutes 0037_05122024 | For Information | 2025-02-07 | 2025-01-16 | 3 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000966 | 2025-01-11 | 2025-01-11 | 0 | INF | For Information | 1 | "Process & MEICA Meeting Minutes 0037_05122024" |  | 2025-01
000967 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 0 | 131242-WST02-DS-I-0005 | 2025-01-11 | Datasheet for pH Transmitter & Sensor | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000967 | 2025-01-11 | 2025-08-15 | 1 | NAP | Approved with Comments | 2 | "Datasheet for pH Transmitter & Sensor " |  | 2025-01
000967 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 1 | 131242-WST02-DS-I-0005 | 2025-08-15 | Datasheet for pH Transmitter & Sensor | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-11-26 | 73 | Approved with Comments | YES | 2025-12-16 | NO | Resubmitted | 0 |  |  | 000967 | 2025-01-11 | 2025-08-15 | 1 | AWC | Approved with Comments | 2 | "Datasheet for pH Transmitter & Sensor " |  | 2025-08
000968 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 0 | 131242-WST02-QA-A-0012 | 2025-01-11 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-02-24 | 30 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000968 | 2025-01-11 | 2025-04-23 | 1 | NAP | Not Approved | 3 | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" |  | 2025-01
000968 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-A-0012 | 2025-03-10 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-14 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000968 | 2025-01-11 | 2025-04-23 | 1 | NAP | Not Approved | 3 | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" |  | 2025-03
000968 | 02 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-A-0012 | 2025-04-23 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.2: Not Approved. Please refer to comment sheet for resubmission | 2025-05-13 | 2025-04-28 | 3 | Not Approved | YES | 2025-05-16 | NO | Resubmitted | 0 |  |  | 000968 | 2025-01-11 | 2025-04-23 | 1 | NAP | Not Approved | 3 | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" |  | 2025-04
000969 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | I | 0005 | 0 | 131242-WSW41-QA-I-0005 | 2025-01-13 | FAT report for Power cable, Control Cable, Instrument Cable (Witness) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-02-10 | 2025-01-20 | 5 | Approved with Comments | YES | 2025-02-07 | NO | Resubmitted | 0 |  |  | 000969 | 2025-01-13 | 2025-01-13 | 0 | AWC | Approved with Comments | 1 | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " |  | 2025-01
000970 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0013 | 0 | 131242-WSW41-QA-E-0013 | 2025-01-13 | FAT report for SS Unistrut Support, Accessories (HDMANN) | Rev 0: Approved with comments. Resubmission not required. Please refer to attached file for comments as noted. | 2025-02-10 | 2025-03-02 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000970 | 2025-01-13 | 2025-01-13 | 0 | AWC | Approved with Comments | 1 | "FAT report for SS Unistrut Support, Accessories (HDMANN) " |  | 2025-01
000971 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0014 | 0 | 131242-WSW41-QA-E-0014 | 2025-01-13 | FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000971 | 2025-01-13 | 2025-01-13 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" |  | 2025-01
000972 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0015 | 0 | 131242-WST02-QA-E-0015 | 2025-01-13 | FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | 26 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000972 | 2025-01-13 | 2025-01-13 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" |  | 2025-01
000973 | 00 | Franklin | CSA | NA | 131242 | WSW41 | CN | S | 0002 | 0 | 131242-WSW41-CN-S-0002 | 2025-01-13 | Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-10 | 2025-02-24 | 30 | Approved with Comments | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 000973 | 2025-01-13 | 2025-01-13 | 0 | AWC | Approved with Comments | 1 | "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" |  | 2025-01
000974 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0040 | 0 | 131242-WSW41-QA-M-0040 | 2025-01-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) | Rev 0: Approved | 2025-02-11 | 2025-03-18 | 45 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000974 | 2025-01-14 | 2025-01-14 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " |  | 2025-01
000975 | 00 | K. Balaji | Mech | NA | 131242 | WSW41 | MS | M | 0006 | 0 | 131242-WSW41-MS-M-0006 | 2025-01-14 | Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 | Rev 0: Approved | 2025-02-11 | 2025-04-11 | 63 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000975 | 2025-01-14 | 2025-01-14 | 0 | APP | Approved | 1 | "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " |  | 2025-01
000976 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 0 | 131242-WSD11-QA-M-0041 | 2025-01-15 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-12 | 2025-02-20 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000976 | 2025-01-15 | 2026-01-06 | 2 | AWC | Approved with Comments | 3 | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" |  | 2025-01
000976 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 1 | 131242-WSD11-QA-M-0041 | 2025-12-09 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-29 | 2025-12-23 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000976 | 2025-01-15 | 2026-01-06 | 2 | AWC | Approved with Comments | 3 | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" |  | 2025-12
000976 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 2 | 131242-WSD11-QA-M-0041 | 2026-01-06 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  | 59 | Awaiting S.O.'s response | YES | 2026-02-23 | NO | Overdue | 0 |  |  | 000976 | 2025-01-15 | 2026-01-06 | 2 | PEN | Approved with Comments | 3 | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" |  | 2026-01
000977 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0024 | 0 | 131242-WSW41-SP-C-0024 | 2025-01-15 | Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-12 | 2025-03-04 | 34 | Approved with Comments | YES | 2025-03-24 | NO | Resubmitted | 0 |  |  | 000977 | 2025-01-15 | 2025-01-15 | 0 | AWC | Approved with Comments | 1 | "Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd)" |  | 2025-01
000978 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0043 | 0 | 131242-WST02-QA-M-0043 | 2025-01-16 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch) | Rev 0: Approved | 2025-02-13 | 2025-03-25 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000978 | 2025-01-16 | 2025-01-16 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch)" |  | 2025-01
000979 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0019 | 0 | 131242-WSW41-PS-PM-0019 | 2025-01-16 | Monthly Progress Presentation No. 19 (1224) | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000979 | 2025-01-16 | 2025-01-16 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 19 (1224)" |  | 2025-01
000980 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0019 | 0 | 131242-WSW41-MI-PM-0019 | 2025-01-16 | Monthly Progress Meeting Minutes 0019_20241217 | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 | 2 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000980 | 2025-01-16 | 2025-01-16 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0019_20241217" |  | 2025-01
000981 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0002 | 0 | 131242-WSW41-RT-HS-0002 | 2025-01-16 | Final Investigation Report (Incident on Leg Injury) | For Information | 2025-02-13 | 2025-12-23 | 243 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000981 | 2025-01-16 | 2025-01-16 | 0 | INF | For Information | 1 | "Final Investigation Report (Incident on Leg Injury)" |  | 2025-01
000982 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0022 | 0 | 131242-WSW41-QA-C-0022 | 2025-01-16 | Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-02-13 | 2025-02-24 | 27 | Approved with Comments | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 000982 | 2025-01-16 | 2025-01-16 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" |  | 2025-01
000983 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 0 | 131242-WSD11-QA-M-0042 | 2025-01-16 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-02-20 | 25 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000983 | 2025-01-16 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" |  | 2025-01
000983 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 1 | 131242-WSD11-QA-M-0042 | 2025-12-02 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000983 | 2025-01-16 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" |  | 2025-12
000984 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 0 | 131242-WSW41-VI-M-1014 | 2025-01-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-01-20 | 2 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000984 | 2025-01-16 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" |  | 2025-01
000984 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 1 | 131242-WSW41-VI-M-1014 | 2025-06-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-06-23 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000984 | 2025-01-16 | 2025-06-16 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" |  | 2025-06
000985 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0044 | 0 | 131242-WSW41-QA-M-0044 | 2025-01-17 | Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-14 | 2025-04-27 | 71 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 000985 | 2025-01-17 | 2025-01-17 | 0 | AWC | Approved with Comments | 1 | "Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd " |  | 2025-01
000986 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0020 | 0 | 131242-WSW41-RT-PM-0020 | 2025-01-19 | C4B Monthly Progress Report Number No.20 (12 24) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-02-14 | 2025-02-03 | 10 | Approved with Comments | YES | 2025-02-21 | NO | Resubmitted | 0 |  |  | 000986 | 2025-01-19 | 2025-01-19 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.20 (12 24) " |  | 2025-01
000987 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0024 | 0 | 131242-WSW41-MS-C-0024 | 2025-01-20 | MSRA and SWP for Waterproofing Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-17 | 2025-02-17 | 20 | Approved with Comments | YES | 2025-03-07 | NO | Resubmitted | 0 |  |  | 000987 | 2025-01-20 | 2025-01-20 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Waterproofing Work" |  | 2025-01
000988 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 0 | 131242-WSW41-VI-M-2005 | 2025-01-20 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-28 00:00:00 |  | 000988 | 2025-01-20 | 2025-06-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" |  | 2025-01
000988 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 1 | 131242-WSW41-VI-M-2005 | 2025-06-18 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-08 | 2026-01-07 | 145 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000988 | 2025-01-20 | 2025-06-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" |  | 2025-06
000989 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 0 | 131242-WSW41-VI-M-2002 | 2025-01-20 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-01-24 | 4 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" |  | 2025-01
000989 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002 | 2025-02-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-04-02 | 26 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" |  | 2025-02
000989 | 02 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002 | 2025-04-17 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-05-07 | 2025-05-21 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-02-21 00:00:00 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | AWC | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" |  | 2025-04
000989 | 03 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002 | 2025-08-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-09-12 |  | 155 | Awaiting S.O.'s response | YES | 2025-10-10 | NO | Overdue | 0 | 2025-02-21 00:00:00 |  | 000989 | 2025-01-20 | 2025-08-25 | 1 | PEN | Approved with Comments | 4 | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" |  | 2025-08
000990 | 00 | Prachi | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-P-0014 | 2025-01-20 | THP Steam Pressure Loss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | 185 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000990&&001007 | 2025-01-20 | 2025-01-26 | 0 | APP | Approved | 2 | "THP Steam Pressure Loss Calculation" && "Process Gas Hydraulic Calculation" |  | 2025-01
000991 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0011 | 0 | 131242-WST02-CL-P-0011 | 2025-01-20 | SSN Compressed Air Headloss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | 185 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000991 | 2025-01-20 | 2025-01-20 | 0 | APP | Approved | 1 | "SSN Compressed Air Headloss Calculation" |  | 2025-01
000992 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-M-0025 | 2025-01-20 | Air Compressor On Off Valve Data sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000992 | 2025-01-20 | 2025-03-07 | 0 | AWC | Approved | 2 | "Air Compressor On Off Valve Data sheet" |  | 2025-01
000992 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-M-0025 | 2025-03-07 | Air Compressor On Off Valve Data sheet | Rev 1: Approved | 2025-03-27 | 2025-07-08 | 87 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000992 | 2025-01-20 | 2025-03-07 | 0 | APP | Approved | 2 | "Air Compressor On Off Valve Data sheet" |  | 2025-03
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 0 | 131242-WSD11-QA-N-0005 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 0 | 131242-WSD11-QA-N-0006 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 0 | 131242-WSD11-QA-N-0009 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-01
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-03
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-03
000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-03
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | AWC | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | 10 | Approved with Comments | YES | 2025-05-12 | NO | Resubmitted | 0 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | AWC | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2025-04
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | PEN | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | PEN | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 1 | PEN | Approved with Comments | 4 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | 43 | Awaiting S.O.'s response | YES | 2026-03-17 | NO | Overdue | 261 |  |  | 000993 | 2025-01-20 | 2026-01-28 | 0 | PEN | Approved with Comments | 3 | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " |  | 2026-01
000994 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 0 | 131242-WSD11-QA-N-0001 | 2025-01-20 | Commissioning Plan for THP Air Compressor System | Rev.0: Approved with Comments. Revise and resubmit. | 2025-02-17 | 2025-02-03 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000994 | 2025-01-20 | 2025-05-10 | 2 | AWC | Approved with Comments | 3 | "Commissioning Plan for THP Air Compressor System" |  | 2025-01
000994 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 1 | 131242-WSD11-QA-N-0001 | 2025-03-06 | Commissioning Plan for THP Air Compressor System | Rev.1: Approved with Comments. Resubmittal is required | 2025-03-26 | 2025-03-18 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 000994 | 2025-01-20 | 2025-05-10 | 2 | AWC | Approved with Comments | 3 | "Commissioning Plan for THP Air Compressor System" |  | 2025-03
000994 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 2 | 131242-WSD11-QA-N-0001 | 2025-05-10 | Commissioning Plan for THP Air Compressor System | Rev.2: Approved with Comments. Resubmittal is required | 2025-05-29 | 2025-06-04 | 17 | Approved with Comments | YES | 2025-06-24 | NO | Resubmitted | 0 |  |  | 000994 | 2025-01-20 | 2025-05-10 | 2 | AWC | Approved with Comments | 3 | "Commissioning Plan for THP Air Compressor System" |  | 2025-05
000995 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 0 | 131242-WSD11-DR-I-7209 | 2025-01-21 | THP Biosolids PMS Network Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-18 | 2025-03-31 | 49 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000995 | 2025-01-21 | 2025-04-09 | 1 | NAP | Approved with Comments | 2 | "THP Biosolids PMS Network Architecture Drawing" |  | 2025-01
000995 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 1 | 131242-WSD11-DR-I-7209 | 2025-04-09 | THP Biosolids PMS Network Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-29 | 2025-05-07 | 20 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 000995 | 2025-01-21 | 2025-04-09 | 1 | AWC | Approved with Comments | 2 | "THP Biosolids PMS Network Architecture Drawing" |  | 2025-04
000996 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 0001 | A | 131242-WSD11-DR-E-0001 | 2025-01-21 | THP Drawing Index for Cable Raceway and Room Layout | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2025-02-18 | 2025-03-13 | 37 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000996 | 2025-01-21 | 2025-01-21 | A | NAP | Not Approved | 1 | "THP Drawing Index for Cable Raceway and Room Layout" |  | 2025-01
000997 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0020 | 0 | 131242-WSD11-QA-E-0020 | 2025-01-22 | Electrical Documents for THP Train 1 & Train 2 (CAMBI) | Rev 0: Rejected. Please refer to attached file for comments. | 2025-02-19 | 2025-03-13 | 36 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 000997 | 2025-01-22 | 2025-01-22 | 0 | NAP | Not Approved | 1 | "Electrical Documents for THP Train 1 & Train 2 (CAMBI)" |  | 2025-01
000998 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 0 | 131242-WSW41-QA-A-0014 | 2025-01-22 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-19 | 2025-02-24 | 23 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 000998 | 2025-01-22 | 2025-03-10 | 1 | NAP | Not Approved | 2 | "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " |  | 2025-01
000998 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 1 | 131242-WSW41-QA-A-0014 | 2025-03-10 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-11 | 24 | Not Approved | YES | 2025-05-01 | NO | Resubmitted | 0 |  |  | 000998 | 2025-01-22 | 2025-03-10 | 1 | NAP | Not Approved | 2 | "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " |  | 2025-03
000999 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0013 | 0 | 131242-WSW41-QA-A-0013 | 2025-01-24 | Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd) | Approved | 2025-02-21 | 2025-02-24 | 21 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000999 | 2025-01-24 | 2025-01-24 | 0 | APP | Approved | 1 | "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" |  | 2025-01
001000 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 0 | 131242-WSW41-SP-C-0025 | 2025-01-24 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-13 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | NAP | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" |  | 2025-01
001000 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 1 | 131242-WSW41-SP-C-0025 | 2025-03-14 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-06 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | NAP | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" |  | 2025-03
001000 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 2 | 131242-WSW41-SP-C-0025 | 2025-04-08 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Approved with Comments | 2025-04-28 | 2025-05-16 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | AWC | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" |  | 2025-04
001000 | 03 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 3 | 131242-WSW41-SP-C-0025 | 2025-06-06 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.3: Approved | 2025-06-26 | 2025-07-04 | 20 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001000 | 2025-01-24 | 2025-06-06 | 3 | APP | Approved | 4 | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" |  | 2025-06
001001 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0026 | 0 | 131242-WSW41-SP-C-0026 | 2025-01-24 | Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information. | 2025-02-21 | 2025-02-20 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001001 | 2025-01-24 | 2025-01-24 | 0 | INF | For Information | 1 | "Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32)" |  | 2025-01
001002 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 0001 | A | 131242-WSD11-DR-B-0001 | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | 65 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001002 | 2025-01-26 | 2025-01-26 | A | INF | For Information | 1 | "Drawing Index (Building and Services Mech.)" |  | 2025-01
001002 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | B | 0001 | A | 131242-WST02-DR-B-0001 | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | 65 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001002 | 2025-01-26 | 2025-01-26 | A | PEN | Awaiting S.O.'s response | 1 | "Drawing Index (Building and Services Mech.)" |  | 2025-01
001003 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0054 | 0 | 131242-WSW41-LT-PM-0054 | 2025-01-26 | CV of Team member (Senior Planning Engineer) | Rev. 0 - Approved | 2025-02-21 | 2025-02-07 | 9 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001003 | 2025-01-26 | 2025-01-26 | 0 | APP | Approved | 1 | "CV of Team member (Senior Planning Engineer)" |  | 2025-01
001004 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0021 | 0 | 131242-WST02-QA-E-0021 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001004 | 2025-01-26 | 2025-01-26 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI)" |  | 2025-01
001005 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1394 | 0 | 131242-WST02-DS-E-1394 | 2025-01-26 | Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-03-02 | 25 | Approved with Comments | YES | 2025-03-20 | NO | Resubmitted | 0 |  |  | 001005 | 2025-01-26 | 2025-01-26 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd)" |  | 2025-01
001006 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 0 | 131242-WSD11-MS-N-0001 | 2025-01-26 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-21 | 2025-02-07 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001006 | 2025-01-26 | 2025-05-19 | 1 | AWC | Approved with Comments | 2 | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" |  | 2025-01
001006 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 1 | 131242-WSD11-MS-N-0001 | 2025-05-19 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-06 | 2025-07-02 | 32 | Approved with Comments | YES | 2025-07-22 | NO | Resubmitted | 0 |  |  | 001006 | 2025-01-26 | 2025-05-19 | 1 | AWC | Approved with Comments | 2 | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" |  | 2025-05
001007 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-P-0014 | 2025-01-26 | Process Gas Hydraulic Calculation | Rev 0: Approved. Please furnish PE Endorsement. | 2025-02-21 | 2025-10-06 | 180 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000990&&001007 | 2025-01-20 | 2025-01-26 | 0 | APP | Approved | 2 | "THP Steam Pressure Loss Calculation" && "Process Gas Hydraulic Calculation" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | A | 131242-WST02-SD-A-1010 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | A | 131242-WST02-SD-A-1011 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | A | 131242-WST02-SD-A-1012 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | A | 131242-WST02-SD-A-1013 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | A | 131242-WST02-SD-A-3006 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | A | 131242-WST02-SD-A-3007 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | A | 131242-WST02-SD-A-3008 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | A | 131242-WST02-SD-A-3009 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | A | 131242-WST02-SD-A-3010 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | A | 131242-WST02-SD-A-3011 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | A | 131242-WST02-SD-A-3012 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | A | 131242-WST02-SD-A-3013 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-01
001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST00 | DR | S | 0001 | A | 131242-WST00-DR-S-0001 | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | 15 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-01-26 | A | NAP | Not Approved | 1 | "Shop Drawings for Lintel and Stiffener " |  | 2025-01
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-A-1010 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-10 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | B | 131242-WST02-SD-A-1011 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | B | 131242-WST02-SD-A-1012 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | B | 131242-WST02-SD-A-1013 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-A-3006 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | B | 131242-WST02-SD-A-3007 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | B | 131242-WST02-SD-A-3008 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | B | 131242-WST02-SD-A-3009 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | B | 131242-WST02-SD-A-3010 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | B | 131242-WST02-SD-A-3011 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | B | 131242-WST02-SD-A-3012 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | B | 131242-WST02-SD-A-3013 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-03
001008 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | A | 0001_supporting docs | 1 | 131242-WSW41-QA-A-0001_supporting docs | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | 5 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001008 | 2025-03-21 | 2025-03-21 | 1 | NAP | Not Approved | 1 | "Shop Drawings for Block Wall" |  | 2025-03
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | C | 131242-WST02-SD-A-1010 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | C | 131242-WST02-SD-A-1011 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | C | 131242-WST02-SD-A-1012 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | C | 131242-WST02-SD-A-1013 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | C | 131242-WST02-SD-A-3006 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | C | 131242-WST02-SD-A-3007 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | C | 131242-WST02-SD-A-3008 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | C | 131242-WST02-SD-A-3009 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | C | 131242-WST02-SD-A-3010 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001008 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 3 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | C | 131242-WST02-SD-A-3011 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | C | 131242-WST02-SD-A-3012 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | C | 131242-WST02-SD-A-3013 | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | 23 | Not Approved | YES | 2025-10-03 | NO | Resubmitted | 125 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-08
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617_BCA | B | 131242-WSD11-DR-S-0300_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617_BCA | B | 131242-WSD11-DR-S-0301_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST617_BCA | B | 131242-WSD11-DR-S-0302_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0303_ST617_BCA | B | 131242-WSD11-DR-S-0303_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST617_BCA | B | 131242-WSD11-DR-S-0304_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0305_ST617_BCA | B | 131242-WSD11-DR-S-0305_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617_BCA | B | 131242-WSD11-DR-S-1000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617_BCA | B | 131242-WSD11-DR-S-1001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617_BCA | B | 131242-WSD11-DR-S-1002_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617_BCA | B | 131242-WSD11-DR-S-1003_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617_BCA | B | 131242-WSD11-DR-S-2000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617_BCA | B | 131242-WSD11-DR-S-2001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617_BCA | B | 131242-WSD11-DR-S-3000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617_BCA | B | 131242-WSD11-DR-S-3001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617_BCA | B | 131242-WSD11-DR-S-3002_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617_BCA | B | 131242-WSD11-DR-S-5000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617_BCA | B | 131242-WSD11-DR-S-5001_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617_BCA | B | 131242-WSD11-DR-S-5002_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617_BCA | B | 131242-WSD11-DR-S-5003_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617_BCA | B | 131242-WSD11-DR-S-5004_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617_BCA | B | 131242-WSD11-DR-S-5005_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617_BCA | B | 131242-WSD11-DR-S-5006_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617_BCA | B | 131242-WSD11-DR-S-8000_ST617_BCA | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001009 | 2025-01-26 | 2025-01-26 | B | AWC | Approved with Comments | 1 | "BCA Submission of ST617 (THP Platforms) " |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-S-0306_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | B | 131242-WSD11-DR-S-0307_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | B | 131242-WSD11-DR-S-0308_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | B | 131242-WSD11-DR-S-1100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | B | 131242-WSD11-DR-S-1101_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | B | 131242-WSD11-DR-S-2100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | B | 131242-WSD11-DR-S-3100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | B | 131242-WSD11-DR-S-5100_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | B | 131242-WSD11-DR-S-5101_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | B | 131242-WSD11-DR-S-8002_ST619_BCA | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | 18 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | AWC | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-01
001011 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0006 | 0 | 131242-WSD11-QA-I-0006 | 2025-01-26 | Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-21 | 2025-04-11 | 54 | Not Approved | YES | 2025-05-01 | NO | Resubmitted | 0 |  |  | 001011 | 2025-01-26 | 2025-01-26 | 0 | NAP | Not Approved | 1 | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" |  | 2025-01
001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7001 | A | 131242-WSD11-DR-BE-7001 | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | 47 | Rejected | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001012 | 2025-01-26 | 2025-01-26 | A | REJ | Rejected | 1 | "THP Compartmentalization Lighting and Ventilation Fan" |  | 2025-01
001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1005 | A | 131242-WSD11-DR-EL-1005 | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | 47 | Rejected | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001012 | 2025-01-26 | 2025-01-26 | A | REJ | Rejected | 1 | "THP Compartmentalization Lighting and Ventilation Fan" |  | 2025-01
001013 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0019 | 0 | 131242-WST02-QA-E-0019 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 | 16 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001013 | 2025-01-26 | 2025-01-26 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " |  | 2025-01
001014 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 0 | 131242-WSW41-QA-E-0016 | 2025-01-26 | ITP for Lightning Protection System Installation | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file and incorporate minor comments. | 2025-02-21 | 2025-03-13 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001014 | 2025-01-26 | 2025-03-14 | 1 | AWC | Approved | 2 | "ITP for Lightning Protection System Installation" |  | 2025-01
001014 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 1 | 131242-WSW41-QA-E-0016 | 2025-03-14 | ITP for Lightning Protection System Installation | Rev 1: Approved. | 2025-04-03 | 2025-05-07 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001014 | 2025-01-26 | 2025-03-14 | 1 | APP | Approved | 2 | "ITP for Lightning Protection System Installation" |  | 2025-03
001015 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0010 | 0 | 131242-WSW41-VI-S-0010 | 2025-02-03 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-03 | 2025-02-20 | 13 | Approved with Comments | YES | 2025-03-12 | NO | Resubmitted | 0 |  |  | 001015 | 2025-02-03 | 2025-02-03 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." |  | 2025-02
001016 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0019 | 0 | 131242-WSW41-PC-W-0019 | 2025-02-03 | Payment Claim No.19 | Rev (0): Approved. Please refer to S.O. Correspondence no. 291 dated 5 Feb 2025. | 2025-03-03 | 2025-02-17 | 10 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001016 | 2025-02-03 | 2025-02-03 | 0 | APP | Approved | 1 | "Payment Claim No.19" |  | 2025-02
001017 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BH | 7000 | A | 131242-WSD11-DR-BH-7000 | 2025-02-03 | THP Protected Corridor Fan Control Circuit Diagram | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-03-03 | 2025-04-27 | 60 | Rejected | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001017 | 2025-02-03 | 2025-02-03 | A | REJ | Rejected | 1 | "THP Protected Corridor Fan Control Circuit Diagram" |  | 2025-02
001018 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 0 | 131242-WSD11-QA-M-0047 | 2025-02-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-03 | 2025-03-25 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001018 | 2025-02-03 | 2025-07-03 | 1 | AWC | Approved | 2 | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" |  | 2025-02
001018 | 01 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 1 | 131242-WSD11-QA-M-0047 | 2025-07-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 1: Approved | 2025-07-23 | 2025-12-23 | 123 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001018 | 2025-02-03 | 2025-07-03 | 1 | APP | Approved | 2 | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" |  | 2025-07
001019 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0045 | 0 | 131242-WSW41-QA-M-0045 | 2025-02-03 | WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd | Rev 0: For Information | 2025-03-03 | 2025-04-27 | 60 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001019 | 2025-02-03 | 2025-02-03 | 0 | INF | For Information | 1 | "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" |  | 2025-02
001020 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 0 | 131242-WST02-DS-E-1395 | 2025-02-04 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-04 | 2025-03-02 | 19 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001020 | 2025-02-04 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" |  | 2025-02
001020 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 1 | 131242-WST02-DS-E-1395 | 2025-03-14 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | 36 | Approved with Comments | YES | 2025-05-23 | NO | Resubmitted | 0 |  |  | 001020 | 2025-02-04 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" |  | 2025-03
001021 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0048 | 0 | 131242-WST02-QA-M-0048 | 2025-02-05 | FAT Report for Air Blowers (Aerzen) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | 34 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 001021 | 2025-02-05 | 2025-02-05 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Air Blowers (Aerzen)" |  | 2025-02
001022 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0016 | 0 | 131242-WSW41-QA-A-0016 | 2025-02-06 | Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-06 | 2025-02-18 | 8 | Approved with Comments | YES | 2025-03-10 | NO | Resubmitted | 0 |  |  | 001022 | 2025-02-06 | 2025-02-06 | 0 | AWC | Approved with Comments | 1 | "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" |  | 2025-02
001023 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-C-0025 | 2025-02-07 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-03-02 | 16 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | NAP | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" |  | 2025-02
001023 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-C-0025 | 2025-03-10 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Approved with Comments | 2025-03-28 | 2025-06-11 | 67 | Approved with Comments | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | AWC | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" |  | 2025-03
001024 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0023 | 0 | 131242-WSW41-QA-C-0023 | 2025-02-07 | Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024 | For information. | 2025-03-07 | 2025-02-18 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001024 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" |  | 2025-02
001025 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0015 | 0 | 131242-WST02-QA-A-0015 | 2025-02-07 | Sample Board Submission for Roof Waterproofing (G-Concept) | For information. Please provide technical data sheet for the proposed system and submit shop drawings for approval. | 2025-03-07 | 2025-02-24 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001025 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | "Sample Board Submission for Roof Waterproofing (G-Concept)" |  | 2025-02
001026 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1014 | 0 | 131242-WST02-SD-A-1014 | 2025-02-07 | Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-02-24 | 11 | Not Approved | YES | 2025-03-14 | NO | Resubmitted | 0 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | A | 131242-WSD11-DR-EI-7040 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | A | 131242-WSD11-DR-EI-7041 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | A | 131242-WSD11-DR-EI-7042 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | A | 131242-WSD11-DR-EI-7043 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | A | 131242-WSD11-DR-EI-7044 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | A | 131242-WSD11-DR-EI-7045 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | A | 131242-WSD11-DR-EI-7046 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | A | 131242-WSD11-DR-EI-7047 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | A | 131242-WSD11-DR-EI-7048 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | A | 131242-WSD11-DR-EI-7049 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | A | 131242-WSD11-DR-EI-7050 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | A | 131242-WSD11-DR-EI-7060 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | A | 131242-WSD11-DR-EI-7061 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | A | 131242-WSD11-DR-EI-7062 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | A | 131242-WSD11-DR-EI-7063 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | A | 131242-WSD11-DR-EI-7064 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | A | 131242-WSD11-DR-EI-7065 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | A | 131242-WSD11-DR-EI-7066 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | A | 131242-WSD11-DR-EI-7067 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | A | 131242-WSD11-DR-EI-7068 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | A | 131242-WSD11-DR-EI-7069 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | A | 131242-WSD11-DR-EI-7070 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | A | 131242-WSD11-DR-EP-3014 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | A | 131242-WSD11-DR-EP-3015 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | A | 131242-WSD11-DR-EP-3016 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | A | 131242-WSD11-DR-EP-3017 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | A | 131242-WSD11-DR-EP-3018 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | A | 131242-WSD11-DR-EP-3019 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | A | 131242-WSD11-DR-EP-3020 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | A | 131242-WSD11-DR-EP-3021 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | A | 131242-WSD11-DR-EP-3022 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | A | 131242-WSD11-DR-EP-3023 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | A | 131242-WSD11-DR-EP-3024 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | A | 131242-WSD11-DR-EP-3025 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | A | 131242-WSD11-DR-EP-3026 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | A | 131242-WSD11-DR-EP-3027 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | A | 131242-WSD11-DR-EP-7110 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | A | 131242-WSD11-DR-EP-7111 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | A | 131242-WSD11-DR-EP-7112 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | A | 131242-WSD11-DR-EP-7113 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | A | 131242-WSD11-DR-EP-7114 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | A | 131242-WSD11-DR-EP-7115 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | A | 131242-WSD11-DR-EP-7116 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | A | 131242-WSD11-DR-EP-7117 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | A | 131242-WSD11-DR-EP-7118 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | A | 131242-WSD11-DR-EP-7119 | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-02
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | B | 131242-WSD11-DR-EI-7040 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | B | 131242-WSD11-DR-EI-7041 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | B | 131242-WSD11-DR-EI-7042 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | B | 131242-WSD11-DR-EI-7043 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | B | 131242-WSD11-DR-EI-7044 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | B | 131242-WSD11-DR-EI-7045 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | B | 131242-WSD11-DR-EI-7046 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | B | 131242-WSD11-DR-EI-7047 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | B | 131242-WSD11-DR-EI-7048 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | B | 131242-WSD11-DR-EI-7049 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | B | 131242-WSD11-DR-EI-7050 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | B | 131242-WSD11-DR-EI-7060 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | B | 131242-WSD11-DR-EI-7061 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | B | 131242-WSD11-DR-EI-7062 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | B | 131242-WSD11-DR-EI-7063 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | B | 131242-WSD11-DR-EI-7064 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | B | 131242-WSD11-DR-EI-7065 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | B | 131242-WSD11-DR-EI-7066 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | B | 131242-WSD11-DR-EI-7067 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | B | 131242-WSD11-DR-EI-7068 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | B | 131242-WSD11-DR-EI-7069 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | B | 131242-WSD11-DR-EI-7070 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | B | 131242-WSD11-DR-EP-3014 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | B | 131242-WSD11-DR-EP-3015 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | B | 131242-WSD11-DR-EP-3016 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | B | 131242-WSD11-DR-EP-3017 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | B | 131242-WSD11-DR-EP-3018 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | B | 131242-WSD11-DR-EP-3019 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | B | 131242-WSD11-DR-EP-3020 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | B | 131242-WSD11-DR-EP-3021 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | B | 131242-WSD11-DR-EP-3022 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | B | 131242-WSD11-DR-EP-3023 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | B | 131242-WSD11-DR-EP-3024 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | B | 131242-WSD11-DR-EP-3025 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | B | 131242-WSD11-DR-EP-3026 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | B | 131242-WSD11-DR-EP-3027 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | B | 131242-WSD11-DR-EP-7110 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | B | 131242-WSD11-DR-EP-7111 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | B | 131242-WSD11-DR-EP-7112 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | B | 131242-WSD11-DR-EP-7113 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | B | 131242-WSD11-DR-EP-7114 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | B | 131242-WSD11-DR-EP-7115 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | B | 131242-WSD11-DR-EP-7116 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | B | 131242-WSD11-DR-EP-7117 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | B | 131242-WSD11-DR-EP-7118 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | B | 131242-WSD11-DR-EP-7119 | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | NAP | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-05
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | C | 131242-WSD11-DR-EI-7040 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | C | 131242-WSD11-DR-EI-7041 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | C | 131242-WSD11-DR-EI-7042 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | C | 131242-WSD11-DR-EI-7043 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | C | 131242-WSD11-DR-EI-7044 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | C | 131242-WSD11-DR-EI-7045 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | C | 131242-WSD11-DR-EI-7046 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | C | 131242-WSD11-DR-EI-7047 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | C | 131242-WSD11-DR-EI-7048 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | C | 131242-WSD11-DR-EI-7049 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | C | 131242-WSD11-DR-EI-7050 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | C | 131242-WSD11-DR-EI-7060 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | C | 131242-WSD11-DR-EI-7061 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | C | 131242-WSD11-DR-EI-7062 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | C | 131242-WSD11-DR-EI-7063 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | C | 131242-WSD11-DR-EI-7064 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | C | 131242-WSD11-DR-EI-7065 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | C | 131242-WSD11-DR-EI-7066 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | C | 131242-WSD11-DR-EI-7067 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | C | 131242-WSD11-DR-EI-7068 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | C | 131242-WSD11-DR-EI-7069 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | C | 131242-WSD11-DR-EI-7070 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | C | 131242-WSD11-DR-EP-3014 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | C | 131242-WSD11-DR-EP-3015 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | C | 131242-WSD11-DR-EP-3016 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | C | 131242-WSD11-DR-EP-3017 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | C | 131242-WSD11-DR-EP-3018 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | C | 131242-WSD11-DR-EP-3019 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | C | 131242-WSD11-DR-EP-3020 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | C | 131242-WSD11-DR-EP-3021 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | C | 131242-WSD11-DR-EP-3022 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | C | 131242-WSD11-DR-EP-3023 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | C | 131242-WSD11-DR-EP-3024 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | C | 131242-WSD11-DR-EP-3025 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | C | 131242-WSD11-DR-EP-3026 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | C | 131242-WSD11-DR-EP-3027 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | C | 131242-WSD11-DR-EP-7110 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | C | 131242-WSD11-DR-EP-7111 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | C | 131242-WSD11-DR-EP-7112 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | C | 131242-WSD11-DR-EP-7113 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | C | 131242-WSD11-DR-EP-7114 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | C | 131242-WSD11-DR-EP-7115 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | C | 131242-WSD11-DR-EP-7116 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | C | 131242-WSD11-DR-EP-7117 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | C | 131242-WSD11-DR-EP-7118 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | C | 131242-WSD11-DR-EP-7119 | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | 11 | Approved with Comments | YES | 2025-09-09 | NO | Resubmitted | 0 |  |  | 001027 | 2025-02-07 | 2025-08-05 | C | AWC | Approved with Comments | 3 | "THP-MCC-0001AB MCC Drawings" |  | 2025-08
001028 | 00 | Zora | CSA | NA | 131242 | NA | NA | NA | FOR INFORMATION | 0 | 131242-NA-NA-NA-FOR INFORMATION | 2025-02-07 | BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters | For information. | 2025-03-07 | 2025-02-18 | 7 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001028 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | "BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters " |  | 2025-02
001029 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 0 | 131242-WSW41-QA-M-0037 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Rev 0: Not approved - Revise and Resubmit | 2025-03-07 | 2025-03-25 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001029 | 2025-02-07 | 2025-04-21 | 1 | NAP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " |  | 2025-02
001029 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 1 | 131242-WSW41-QA-M-0037 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Approved | 2025-05-09 | 2025-05-12 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001029 | 2025-02-07 | 2025-04-21 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " |  | 2025-04
001030 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 0 | 131242-WSW41-QA-M-0046 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-27 | 56 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001030 | 2025-02-07 | 2025-06-18 | 1 | AWC | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" |  | 2025-02
001030 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 1 | 131242-WSW41-QA-M-0046 | 2025-06-18 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-08 | 2025-09-08 | 58 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001030 | 2025-02-07 | 2025-06-18 | 1 | APP | Approved | 2 | "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" |  | 2025-06
001031 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0009 | 0 | 131242-WST02-CL-P-0009 | 2025-02-07 | SSN Energy Consumption Computation | Rev 0: For Information | 2025-03-07 | 2025-10-06 | 171 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001031 | 2025-02-07 | 2025-02-07 | 0 | INF | For Information | 1 | " SSN Energy Consumption Computation" |  | 2025-02
001032 | 00 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 0 | 131242-WST02-SP-P-0002 | 2025-02-07 | SSN Aeration Blower Control Philosophy | Rev0: approved with comments, resubmission is required. | 2025-03-07 | 2025-03-13 | 24 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001032 | 2025-02-07 | 2025-06-04 | 1 | AWC | Approved with Comments | 2 | "SSN Aeration Blower Control Philosophy" |  | 2025-02
001032 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 1 | 131242-WST02-SP-P-0002 | 2025-06-04 | SSN Aeration Blower Control Philosophy | Rev1: approved with comments, resubmission is required. | 2025-06-24 | 2025-07-02 | 20 | Approved with Comments | YES | 2025-07-22 | NO | Resubmitted | 0 |  |  | 001032 | 2025-02-07 | 2025-06-04 | 1 | AWC | Approved with Comments | 2 | "SSN Aeration Blower Control Philosophy" |  | 2025-06
001033 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 0 | 131242-WSD11-VI-I-0004 | 2025-02-10 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-10 | 2025-02-13 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 | 2025-03-05 00:00:00 |  | 001033 | 2025-02-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" |  | 2025-02
001033 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 1 | 131242-WSD11-VI-I-0004 | 2025-03-17 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | 37 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001033 | 2025-02-10 | 2025-03-17 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" |  | 2025-03
001034 | 00 | Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-IM-0052 | 2025-02-10 | Submission of BIM Coordination VCM Model (Jan 2025) | For Information. Score= 70/100 | 2025-03-10 | 2025-02-20 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 000163&&001034 | 2025-02-10 | 2025-12-16 | 0 | INF | Approved with Comments | 2 | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" |  | 2025-02
001035 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0049 | 0 | 131242-WSD11-QA-M-0049 | 2025-02-10 | FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch) | Rev 0: Approved | 2025-03-10 | 2025-03-25 | 31 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001035 | 2025-02-10 | 2025-02-10 | 0 | APP | Approved | 1 | "FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch)" |  | 2025-02
001036 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | A | 0017 | 0 | 131242-WST02-QA-A-0017 | 2025-02-11 | Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | For information. | 2025-03-11 | 2025-02-24 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001036 | 2025-02-11 | 2025-02-11 | 0 | INF | For Information | 1 | "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" |  | 2025-02
001037 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0055 | 0 | 131242-WSW41-LT-PM-0055 | 2025-02-11 | EOT Notice Letter for ST617 & ST619 | Rev (0): For Information. Please refer to S.O. correspondence no. 327 dated 14 April 2025. | 2025-03-11 | 2025-04-27 | 54 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001037 | 2025-02-11 | 2025-02-11 | 0 | INF | For Information | 1 | "EOT Notice Letter for ST617 & ST619" |  | 2025-02
001038 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0004 | 0 | 131242-WSW41-PO-E-0004 | 2025-02-11 | Unppriced PO for YHW | Rev 0: For Information. | 2025-03-11 | 2025-03-13 | 22 | For Information | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001038 | 2025-02-11 | 2025-02-11 | 0 | INF | For Information | 1 | "Unppriced PO for YHW" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A | 131242-WSD11-DR-B-1003 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.2 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 3000 | A1 | 131242-WSD11-DR-BH-3000 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1000 | A1 | 131242-WSD11-DR-BH-1000 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1001 | A1 | 131242-WSD11-DR-BH-1001 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1002 | A1 | 131242-WSD11-DR-BH-1002 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1002 | A | 131242-WSD11-DR-BF-1002 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3001 | A | 131242-WSD11-DR-BF-3001 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | NAP | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-02
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | CL | BH | 8000 | 0 | 131242-WSD11-CL-BH-8000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-06-04 | 2025-06-04 | 0 | AWC | Approved with Comments | 1 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A.2 | 131242-WSD11-DR-B-1003 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.2 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 3000 | A.3 | 131242-WSD11-DR-BH-3000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1000 | A.3 | 131242-WSD11-DR-BH-1000 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1001 | A.3 | 131242-WSD11-DR-BH-1001 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1002 | A.3 | 131242-WSD11-DR-BH-1002 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A.3 | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1002 | A | 131242-WSD11-DR-BF-1002 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3001 | A | 131242-WSD11-DR-BF-3001 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | 31 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001039 | 2025-02-12 | 2025-06-04 | A | AWC | Approved with Comments | 2 | "THP Protected Corridor Area-Building Service (Mechanical)" |  | 2025-06
001040 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 0 | 131242-WSD11-QA-E-0023 | 2025-02-12 | FAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. | 2025-03-12 | 2025-03-13 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001040 | 2025-02-12 | 2025-03-27 | 1 | AWC | Approved with Comments | 2 | "FAT Report for WSD11-MCC-0101A&B" |  | 2025-02
001040 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 1 | 131242-WSD11-QA-E-0023 | 2025-03-27 | FAT Report for WSD11-MCC-0101A&B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-05-07 | 29 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001040 | 2025-02-12 | 2025-03-27 | 1 | AWC | Approved with Comments | 2 | "FAT Report for WSD11-MCC-0101A&B" |  | 2025-03
001041 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 0 | 131242-WSW41-QA-M-0051 | 2025-02-13 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Rev 0: Not approved - Revise and Resubmit | 2025-03-13 | 2025-02-18 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001041 | 2025-02-13 | 2025-03-24 | 1 | NAP | Approved | 2 | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" |  | 2025-02
001041 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 1 | 131242-WSW41-QA-M-0051 | 2025-03-24 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Approved | 2025-04-11 | 2025-05-19 | 40 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001041 | 2025-02-13 | 2025-03-24 | 1 | APP | Approved | 2 | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" |  | 2025-03
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-A-3006 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | B | 131242-WST02-SD-A-3011 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | B | 131242-WST02-SD-A-3012 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | B | 131242-WST02-SD-A-3013 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-A-1010 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | B | 131242-WST02-SD-A-1011 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | B | 131242-WST02-SD-A-1012 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | B | 131242-WST02-SD-A-1013 | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | 25 | Not Approved | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001008&&001042 | 2025-01-26 | 2025-08-13 | C | NAP | Not Approved | 4 | "Shop Drawings for Lintel and Stiffener " && "Shop Drawings for Block Wall" && "Lintel and Stiffener Shop Drawings" |  | 2025-02
001043 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 0 | 131242-WSW41-VI-M-1007 | 2025-02-14 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-04-05 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001043 | 2025-02-14 | 2025-06-09 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Plastic Valves (GF)" |  | 2025-02
001043 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 1 | 131242-WSW41-VI-M-1007 | 2025-06-09 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-20 | 9 | Approved with Comments | YES | 2025-07-10 | NO | Resubmitted | 0 |  |  | 001043 | 2025-02-14 | 2025-06-09 | 1 | AWC | Approved with Comments | 2 | "Preliminary design and Vendor Approval – Plastic Valves (GF)" |  | 2025-06
001044 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-C-0023 | 2025-02-16 | MSRA, SWP for Site Wide Pipe Rack Installation | Approved | 2025-03-14 | 2025-12-17 | 217 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000898&&001044 | 2024-12-13 | 2025-02-16 | 0 | APP | Approved | 2 | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-S-0306_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | B | 131242-WSD11-DR-S-0307_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | B | 131242-WSD11-DR-S-0308_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | B | 131242-WSD11-DR-S-1100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | B | 131242-WSD11-DR-S-1101_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | B | 131242-WSD11-DR-S-2100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | B | 131242-WSD11-DR-S-3100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | B | 131242-WSD11-DR-S-5100_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | B | 131242-WSD11-DR-S-5101_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | B | 131242-WSD11-DR-S-8002_ST619_BCA | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | 1 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001010&&001045 | 2025-01-26 | 2025-02-17 | B | INF | For Information | 2 | "BCA Submission of ST619 (THP Pipe Rack)" && "BCA Approval of ST619 (THP Pipe Rack)" |  | 2025-02
001046 | 00 | Jun | HSE | NA | 131242 | WSW41 | MS | E | 0008 | 0 | 131242-WSW41-MS-E-0008 | 2025-02-17 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-03-17 | 20 | Approved with Comments | YES | 2025-04-04 | NO | Resubmitted | 0 |  |  | 001046 | 2025-02-17 | 2025-02-17 | 0 | AWC | Approved with Comments | 1 | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" |  | 2025-02
001047 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0021 | 0 | 131242-WSW41-RT-PM-0021 | 2025-02-17 | C4B Monthly Progress Report Number No.21 (01 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-03-17 | 2025-03-13 | 18 | Approved with Comments | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001047 | 2025-02-17 | 2025-02-17 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.21 (01 25) " |  | 2025-02
001048 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0020 | 0 | 131242-WSW41-PS-PM-0020 | 2025-02-18 | Monthly Progress Presentation No. 20 (0125) | Rev. 0 - For Information | 2025-03-18 | 2025-02-18 | 0 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001048 | 2025-02-18 | 2025-02-18 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 20 (0125)" |  | 2025-02
001049 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0020 | 0 | 131242-WSW41-MI-PM-0020 | 2025-02-18 | Monthly Progress Meeting Minutes 0020_20250122 | Rev. 0 - For Information | 2025-03-18 | 2025-02-24 | 4 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001049 | 2025-02-18 | 2025-02-18 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0020_20250122" |  | 2025-02
001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | A | 131242-WST02-SD-A-1014 | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 | 17 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001026&&001050&&001356 | 2025-02-07 | 2025-08-27 | C | NAP | Approved with Comments | 5 | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " |  | 2025-02
001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | A | 131242-WST02-SD-A-3014 | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 | 17 | Not Approved | YES | 2025-04-02 | NO | Resubmitted | 0 |  |  | 001050&&001356 | 2025-02-18 | 2025-08-27 | D | NAP | Approved with Comments | 5 | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " |  | 2025-02
001051 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 0 | 131242-WST02-DS-M-5601 | 2025-02-18 | Data Sheet for Parabolic Screen | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-03-04 | 10 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001051 | 2025-02-18 | 2025-04-01 | 1 | AWC | Approved | 2 | "Data Sheet for Parabolic Screen" |  | 2025-02
001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 1 | 131242-WST02-DS-M-5601 | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001051 | 2025-02-18 | 2025-04-01 | 1 | APP | Approved | 2 | "Data Sheet for Parabolic Screen" |  | 2025-04
001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | F | 131242-WST02-DR-M-5601 | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | 134 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000931&&001051 | 2024-12-27 | 2025-05-26 | B | APP | Approved | 3 | "Screen General Arrangement Drawing" && "Data Sheet for Parabolic Screen" |  | 2025-04
001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3203 | A | 131242-WST02-DR-E-3203 | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | 35 | Not Approved | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 001052 | 2025-02-18 | 2025-02-18 | A | NAP | Not Approved | 1 | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " |  | 2025-02
001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3204 | A | 131242-WST02-DR-E-3204 | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | 35 | Not Approved | YES | 2025-04-28 | NO | Resubmitted | 0 |  |  | 001052 | 2025-02-18 | 2025-02-18 | A | NAP | Not Approved | 1 | "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_BCA | B | 131242-WSD11-DR-S-0300_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_BCA | B | 131242-WSD11-DR-S-0301_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_BCA | B | 131242-WSD11-DR-S-0302_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0303_BCA | B | 131242-WSD11-DR-S-0303_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0304_BCA | B | 131242-WSD11-DR-S-0304_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0305_BCA | B | 131242-WSD11-DR-S-0305_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_BCA | B | 131242-WSD11-DR-S-1000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_BCA | B | 131242-WSD11-DR-S-1001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_BCA | B | 131242-WSD11-DR-S-1002_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_BCA | B | 131242-WSD11-DR-S-1003_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_BCA | B | 131242-WSD11-DR-S-2000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_BCA | B | 131242-WSD11-DR-S-2001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_BCA | B | 131242-WSD11-DR-S-3000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_BCA | B | 131242-WSD11-DR-S-3001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_BCA | B | 131242-WSD11-DR-S-3002_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_BCA | B | 131242-WSD11-DR-S-5000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_BCA | B | 131242-WSD11-DR-S-5001_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_BCA | B | 131242-WSD11-DR-S-5002_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_BCA | B | 131242-WSD11-DR-S-5003_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_BCA | B | 131242-WSD11-DR-S-5004_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_BCA | B | 131242-WSD11-DR-S-5005_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_BCA | B | 131242-WSD11-DR-S-5006_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_BCA | B | 131242-WSD11-DR-S-8000_BCA | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001053 | 2025-02-18 | 2025-02-18 | B | INF | For Information | 1 | "BCA Approval of ST617 (THP Platform 01 & 02)" |  | 2025-02
001054 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0018 | 0 | 131242-WSW41-QA-A-0018 | 2025-02-18 | Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works | Rev.0:Approved. Please submit MSRA. | 2025-03-18 | 2025-02-24 | 4 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001054 | 2025-02-18 | 2025-02-18 | 0 | APP | Approved | 1 | "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" |  | 2025-02
001055 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0022 | 0 | 131242-WSW41-QA-E-0022 | 2025-02-18 | Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 55 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001055 | 2025-02-18 | 2025-02-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" |  | 2025-02
001056 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0017 | 0 | 131242-WSW41-QA-E-0017 | 2025-02-18 | Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 55 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001056 | 2025-02-18 | 2025-02-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" |  | 2025-02
001057 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0018 | 0 | 131242-WSW41-QA-E-0018 | 2025-02-18 | Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | 55 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001057 | 2025-02-18 | 2025-02-18 | 0 | AWC | Approved with Comments | 1 | "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" |  | 2025-02
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-S-1600_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | D | 131242-WSD11-DR-S-1601_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | D | 131242-WSD11-DR-S-5600_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | D | 131242-WSD11-DR-S-5601_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007_ST620_BCA | 1 | 131242-WSD11-CL-S-0007_ST620_BCA | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | 16 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058 | 2025-02-19 | 2025-02-19 | 1 | INF | For Information | 1 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001059 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0050 | 0 | 131242-WST02-QA-M-0050 | 2025-02-19 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch) | Rev 0: Approved | 2025-03-19 | 2025-04-27 | 48 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001059 | 2025-02-19 | 2025-02-19 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch)" |  | 2025-02
001060 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0052 | 0 | 131242-WSD11-QA-M-0052 | 2025-02-19 | Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-02 | 30 | Approved with Comments | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001060 | 2025-02-19 | 2025-02-19 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system" |  | 2025-02
001061 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 0 | 131242-WSD11-QA-E-0024 | 2025-02-20 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-20 | 2025-02-25 | 3 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | NAP | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" |  | 2025-02
001061 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 1 | 131242-WSD11-QA-E-0024 | 2025-03-10 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-02 | 17 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | AWC | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" |  | 2025-03
001061 | 02 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 2 | 131242-WSD11-QA-E-0024 | 2025-04-11 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-05-01 | 2025-05-12 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | AWC | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" |  | 2025-04
001061 | 03 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 3 | 131242-WSD11-QA-E-0024 | 2025-05-02 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-05-12 | 6 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | AWC | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" |  | 2025-05
001061 | 04 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 4 | 131242-WSD11-QA-E-0024 | 2025-06-28 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 4: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-07-17 | 2025-07-23 | 17 | Rejected | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001061 | 2025-02-20 | 2025-06-28 | 4 | REJ | Rejected | 5 | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" |  | 2025-06
001062 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0007 | 0 | 131242-WSD11-QA-I-0007 | 2025-02-20 | Inspection and Test plan for THP air Compressor System Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-03-20 | 2025-05-30 | 71 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001062 | 2025-02-20 | 2025-02-20 | 0 | AWC | Approved with Comments | 1 | "Inspection and Test plan for THP air Compressor System Pressure Transmitter " |  | 2025-02
001063 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | E | 0001 | A | 131242-WST02-DR-E-0001 | 2025-02-21 | SSN Drawing Index (Cable Tray Layout) | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-03-21 | 2025-05-06 | 52 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001063 | 2025-02-21 | 2025-02-21 | A | REJ | Rejected | 1 | "SSN Drawing Index (Cable Tray Layout)" |  | 2025-02
001064 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 0001 | A | 131242-WST02-DR-I-0001 | 2025-02-21 | SSN Drawing Index (Instrument Layout) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-21 | 2025-05-07 | 53 | Not Approved | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001064 | 2025-02-21 | 2025-02-21 | A | NAP | Not Approved | 1 | "SSN Drawing Index (Instrument Layout)" |  | 2025-02
001065 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0053 | 0 | 131242-WSD11-QA-M-0053 | 2025-02-21 | Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton) | Rev 0: Approved | 2025-03-21 | 2025-04-02 | 28 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001065 | 2025-02-21 | 2025-02-21 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton)" |  | 2025-02
001066 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0026 | 0 | 131242-WSW41-VI-M-0026 | 2025-02-21 | Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-21 | 2025-04-02 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001066 | 2025-02-21 | 2025-02-21 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks)" |  | 2025-02
001067 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0026 | 0 | 131242-WSD11-DS-M-0026 | 2025-02-21 | Data Sheet for Steam Sparger G2D Inlet Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-21 | 2025-04-28 | 46 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 |  |  | 001067 | 2025-02-21 | 2025-02-21 | 0 | AWC | Approved with Comments | 1 | "Data Sheet for Steam Sparger G2D Inlet Control Valve" |  | 2025-02
001068 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-C-0025 | 2025-02-24 | MSRA, SWP for Box Out Concreting | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-24 | 2025-03-18 | 16 | Not Approved | YES | 2025-04-07 | NO | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | NAP | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" |  | 2025-02
001068 | 01 | Kumar | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-C-0025 | 2025-03-28 | MSRA, SWP for Box Out Concreting | R1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-04-15 | 12 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001023&&001068 | 2025-02-07 | 2025-03-28 | 1 | NAP | Not Approved | 4 | "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" && "MSRA, SWP for Box Out Concreting" |  | 2025-03
001069 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0013 | 0 | 131242-WSW41-PO-M-0013 | 2025-02-24 | Unpriced PO for CSEL Pipes (MUSG) | Rev 0: For Information. | 2025-03-24 | 2025-03-27 | 23 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001069 | 2025-02-24 | 2025-02-24 | 0 | INF | For Information | 1 | "Unpriced PO for CSEL Pipes (MUSG)" |  | 2025-02
001070 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0005 | 0 | 131242-WSW41-PO-E-0005 | 2025-02-24 | Unpriced PO for Cable Raceway (United-U Li) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001070 | 2025-02-24 | 2025-02-24 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Raceway (United-U Li) " |  | 2025-02
001071 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0006 | 0 | 131242-WSW41-PO-E-0006 | 2025-02-24 | Unpriced PO for Cable Raceway (Jebsen & Jessen) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001071 | 2025-02-24 | 2025-02-24 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" |  | 2025-02
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0039 | 0 | 131242-WSW41-MI-C-0039 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001072 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" |  | 2025-02
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0040 | 0 | 131242-WSW41-MI-C-0040 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001072 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" |  | 2025-02
001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0041 | 0 | 131242-WSW41-MI-C-0041 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001072 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" |  | 2025-02
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 7000 | A | 131242-WSD11-DR-BF-7000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | AWC | Approved with Comments | 2 | "THP-Dry Riser System" && "Dry Riser Installation Details" |  | 2025-02
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000292&&001073&&001902 | 2025-02-25 | 2025-12-16 | A1 | AWC | Approved with Comments | 4 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" && "Dry Riser Installation Details" |  | 2025-02
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" |  | 2025-02
001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000 | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | 20 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 000292&&001073 | 2025-02-25 | 2025-11-28 | A | AWC | Approved with Comments | 3 | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP-Dry Riser System" |  | 2025-02
001074 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0025 | 0 | 131242-WSD11-QA-E-0025 | 2025-02-26 | FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch | Rev 0: Approved. | 2025-03-26 | 2025-05-06 | 49 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001074 | 2025-02-26 | 2025-02-26 | 0 | APP | Approved | 1 | "FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch" |  | 2025-02
001075 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0020 | 0 | 131242-WST02-QA-A-0020 | 2025-02-27 | Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd) | For Information | 2025-03-27 | 2025-04-11 | 31 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001075 | 2025-02-27 | 2025-02-27 | 0 | APP | Approved | 1 | "Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd)" |  | 2025-02
001076 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8000 | 0 | 131242-WST02-CL-BH-8000 | 2025-02-27 | Fan Static Load Calculation (SSN Electrical Building) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-25 | 18 | Approved with Comments | YES | 2025-04-14 | NO | Resubmitted | 0 |  |  | 001076 | 2025-02-27 | 2025-02-27 | 0 | AWC | Approved with Comments | 1 | "Fan Static Load Calculation (SSN Electrical Building)" |  | 2025-02
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-S-1600_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | D | 131242-WSD11-DR-S-1601_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | D | 131242-WSD11-DR-S-5600_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | D | 131242-WSD11-DR-S-5601_ST620_BCA | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | 9 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001058&&001077 | 2025-02-19 | 2025-02-28 | D | INF | For Information | 2 | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" |  | 2025-02
001078 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 0 | 131242-WST02-QA-A-0019 | 2025-02-28 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-06 | 26 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001078 | 2025-02-28 | 2025-04-09 | 1 | NAP | Not Approved | 2 | "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" |  | 2025-02
001078 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 1 | 131242-WST02-QA-A-0019 | 2025-04-09 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-29 | 2025-05-27 | 34 | Not Approved | YES | 2025-06-16 | NO | Resubmitted | 0 |  |  | 001078 | 2025-02-28 | 2025-04-09 | 1 | NAP | Not Approved | 2 | "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" |  | 2025-04
001079 | 00 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5751 | 0 | 131242-WST02-CL-P-5751 | 2025-02-28 | C4B SSN Pressure Reducing Valve Calculations | Rev 0: Approved | 2025-03-28 | 2025-04-28 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001079 | 2025-02-28 | 2025-02-28 | 0 | APP | Approved | 1 | "C4B SSN Pressure Reducing Valve Calculations" |  | 2025-02
001080 | 00 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 0 | 131242-WST02-DS-M-5751 | 2025-02-28 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-28 | 41 | Approved with Comments | YES | 2025-05-16 | NO | Resubmitted | 0 |  |  | 001080 | 2025-02-28 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "C4B SSN Pressure Reducing Valve Datasheet" |  | 2025-02
001080 | 01 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 1 | 131242-WST02-DS-M-5751 | 2025-07-07 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 52 |  |  | 001080 | 2025-02-28 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "C4B SSN Pressure Reducing Valve Datasheet" |  | 2025-07
001081 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 0 | 131242-WSD11-VI-M-0003 | 2025-03-03 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-31 | 2025-03-04 | 1 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001081 | 2025-03-03 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" |  | 2025-03
001081 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 1 | 131242-WSD11-VI-M-0003 | 2025-03-14 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-02 | 13 | Approved with Comments | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001081 | 2025-03-03 | 2025-03-14 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" |  | 2025-03
001082 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | S | 0010 | 0 | 131242-WST02-VI-S-0010 | 2025-03-03 | Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-31 | 2025-04-02 | 22 | Not Approved | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001082 | 2025-03-03 | 2025-03-03 | 0 | NAP | Not Approved | 1 | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." |  | 2025-03
001083 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0024 | 0 | 131242-WSD11-DS-M-0024 | 2025-03-04 | Ring Circulation Pump Data Sheet | Rev 0: Approved | 2025-04-01 | 2025-10-06 | 154 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001083 | 2025-03-04 | 2025-03-04 | 0 | APP | Approved | 1 | "Ring Circulation Pump Data Sheet" |  | 2025-03
001084 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0028 | 0 | 131242-WSD11-CL-P-0028 | 2025-03-04 | Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-07-08 | 90 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 001084 | 2025-03-04 | 2025-03-04 | 0 | AWC | Approved with Comments | 1 | "Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 0301 | A1 | 131242-WSW41-SD-S-0301 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1101 | A1 | 131242-WSW41-SD-S-1101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1102 | A1 | 131242-WSW41-SD-S-1102 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1103 | A1 | 131242-WSW41-SD-S-1103 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1104 | A1 | 131242-WSW41-SD-S-1104 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1105 | A1 | 131242-WSW41-SD-S-1105 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1106 | A1 | 131242-WSW41-SD-S-1106 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1107 | A1 | 131242-WSW41-SD-S-1107 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1108 | A1 | 131242-WSW41-SD-S-1108 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2100 | A1 | 131242-WSW41-SD-S-2100 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2101 | A1 | 131242-WSW41-SD-S-2101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2102 | A1 | 131242-WSW41-SD-S-2102 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 3100 | A1 | 131242-WSW41-SD-S-3100 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 000581&&001085&&001906 | 2024-07-23 | 2025-12-17 | X | NAP | Not Approved | 3 | "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 3101 | A1 | 131242-WSW41-SD-S-3101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5100 | A1 | 131242-WSW41-SD-S-5100 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5101 | A1 | 131242-WSW41-SD-S-5101 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5102 | A1 | 131242-WSW41-SD-S-5102 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5103 | A1 | 131242-WSW41-SD-S-5103 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5104 | A1 | 131242-WSW41-SD-S-5104 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5105 | A1 | 131242-WSW41-SD-S-5105 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5106 | A1 | 131242-WSW41-SD-S-5106 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085 | 2025-03-04 | 2025-03-04 | A1 | NAP | Not Approved | 1 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" |  | 2025-03
001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 8002 | A1 | 131242-WSW41-SD-S-8002 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | 69 | Not Approved | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001085&&001906 | 2025-03-04 | 2025-12-17 | X | NAP | Not Approved | 2 | "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "As Built Drawing for ST619 (THP Pipe Rack PR-01)" |  | 2025-03
001086 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0055 | 0 | 131242-WST02-QA-M-0055 | 2025-03-04 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch) | Rev 0: Approved | 2025-04-01 | 2025-04-30 | 41 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001086 | 2025-03-04 | 2025-03-04 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch)" |  | 2025-03
001087 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-E-0011 | 2025-03-05 | FAT report for Cable Ladder 1st batch (United ULI) | For information | 2025-04-02 | 2025-05-05 | 43 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000927&&001087 | 2024-12-23 | 2025-03-05 | 0 | APP | Approved | 2 | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" |  | 2025-03
001088 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0033 | 0 | 131242-WSD11-VI-M-0033 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001088 | 2025-03-05 | 2025-03-05 | 0 | REJ | Rejected | 1 | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED" |  | 2025-03
001089 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0034 | 0 | 131242-WSD11-VI-M-0034 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001089 | 2025-03-05 | 2025-03-05 | 0 | REJ | Rejected | 1 | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD " |  | 2025-03
001090 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0035 | 0 | 131242-WSD11-VI-M-0035 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | 9 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001090 | 2025-03-05 | 2025-03-05 | 0 | REJ | Rejected | 1 | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES" |  | 2025-03
001091 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0054 | 0 | 131242-WSW41-QA-M-0054 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-03-25 | 13 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001091 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL)" |  | 2025-03
001092 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0028 | 0 | 131242-WSD11-DS-M-0028 | 2025-03-06 | Manual Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | 152 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001092 | 2025-03-06 | 2025-03-06 | 0 | APP | Approved | 1 | "Manual Gate Valve Data Sheet (Cambi Supply)" |  | 2025-03
001093 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0029 | 0 | 131242-WSD11-DS-M-0029 | 2025-03-06 | Manual Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | 152 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001093 | 2025-03-06 | 2025-03-06 | 0 | APP | Approved | 1 | "Manual Ball Valve Data Sheet (Cambi Supply)" |  | 2025-03
001094 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0030 | 0 | 131242-WSD11-DS-M-0030 | 2025-03-06 | Manual Globe Valve Data Sheet (Cambi Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | 88 | Approved with Comments | YES | 2025-07-28 | NO | Resubmitted | 0 |  |  | 001094 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "Manual Globe Valve Data Sheet (Cambi Supply)" |  | 2025-03
001095 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1395 | 0 | 131242-WSW41-DS-E-1395 | 2025-03-06 | Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) | Rev 0: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001095 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) " |  | 2025-03
001096 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0056 | 0 | 131242-WST02-QA-M-0056 | 2025-03-06 | FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved | 2025-04-03 | 2025-03-21 | 11 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001096 | 2025-03-06 | 2025-03-06 | 0 | APP | Approved | 1 | "FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant)" |  | 2025-03
001097 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0026 | 0 | 131242-WSD11-QA-I-0026 | 2025-03-06 | FAT report for Pressure transmitter (Air compressor) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-05-30 | 61 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001097 | 2025-03-06 | 2025-03-06 | 0 | AWC | Approved with Comments | 1 | "FAT report for Pressure transmitter (Air compressor)" |  | 2025-03
001098 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0014 | 0 | 131242-WSW41-PO-M-0014 | 2025-03-06 | Unpriced PO for HDPE Pipes (AGRU) | Rev 0 for information | 2025-04-03 | 2025-03-27 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001098 | 2025-03-06 | 2025-03-06 | 0 | INF | For Information | 1 | "Unpriced PO for HDPE Pipes (AGRU) " |  | 2025-03
001099 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 0 | 131242-WST02-CD-I-0009 | 2025-03-06 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | 33 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001099 | 2025-03-06 | 2025-08-19 | 2 | AWC | Approved with Comments | 3 | "SSN -RIO PANEL 0001A/0001B- I/O List " |  | 2025-03
001099 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 1 | 131242-WST02-CD-I-0009 | 2025-06-16 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | 18 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001099 | 2025-03-06 | 2025-08-19 | 2 | AWC | Approved with Comments | 3 | "SSN -RIO PANEL 0001A/0001B- I/O List " |  | 2025-06
001099 | 02 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 2 | 131242-WST02-CD-I-0009 | 2025-08-19 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-23 | 25 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001099 | 2025-03-06 | 2025-08-19 | 2 | AWC | Approved with Comments | 3 | "SSN -RIO PANEL 0001A/0001B- I/O List " |  | 2025-08
001100 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 0 | 131242-WST02-CD-I-0008 | 2025-03-06 | SSN Aeration Blowers I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | 33 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001100 | 2025-03-06 | 2025-07-11 | 1 | NAP | Approved with Comments | 2 | "SSN Aeration Blowers I/O List" |  | 2025-03
001100 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 1 | 131242-WST02-CD-I-0008 | 2025-07-11 | SSN Aeration Blowers I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001100 | 2025-03-06 | 2025-07-11 | 1 | AWC | Approved with Comments | 2 | "SSN Aeration Blowers I/O List" |  | 2025-07
001101 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0011 | 0 | 131242-WST02-RT-E-0011 | 2025-03-07 | SSN Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | 43 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001101 | 2025-03-07 | 2025-03-07 | 0 | AWC | Approved with Comments | 1 | "SSN Motor Starting Study Report " |  | 2025-03
001102 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0006 | 0 | 131242-WSD11-RT-E-0006 | 2025-03-07 | THP Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | 43 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001102 | 2025-03-07 | 2025-03-07 | 0 | AWC | Approved with Comments | 1 | "THP Motor Starting Study Report " |  | 2025-03
001103 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0032 | 0 | 131242-WSD11-DS-M-0032 | 2025-03-07 | ON OFF Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001103 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Gate Valve Data Sheet (Cambi Supply)" |  | 2025-03
001104 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0033 | 0 | 131242-WSD11-DS-M-0033 | 2025-03-07 | ON OFF Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001104 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Ball Valve Data Sheet (Cambi Supply)" |  | 2025-03
001105 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0034 | 0 | 131242-WSD11-DS-M-0034 | 2025-03-07 | ON OFF Ball Valve PN25 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001105 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Ball Valve PN25 Data Sheet (Cambi Supply)" |  | 2025-03
001106 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0035 | 0 | 131242-WSD11-DS-M-0035 | 2025-03-07 | ON OFF Ball Valve PN40 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | 151 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001106 | 2025-03-07 | 2025-03-07 | 0 | APP | Approved | 1 | "ON OFF Ball Valve PN40 Data Sheet (Cambi Supply)" |  | 2025-03
001107 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0022 | 0 | 131242-WSW41-RT-PM-0022 | 2025-03-10 | C4B Monthly Progress Report Number No.22 (02 25) | Rev. 0 - Approved with comments (need to re-submit / see attached comment sheet) | 2025-04-07 | 2025-03-27 | 13 | Approved with Comments | YES | 2025-04-16 | NO | Resubmitted | 0 |  |  | 001107 | 2025-03-10 | 2025-03-10 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.22 (02 25) " |  | 2025-03
001108 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 0 | 131242-WST02-VI-B-0003 | 2025-03-10 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001108 | 2025-03-10 | 2025-08-22 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" |  | 2025-03
001108 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 1 | 131242-WST02-VI-B-0003 | 2025-08-22 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-11 |  | 156 | Awaiting S.O.'s response | YES | 2025-10-09 | NO | Overdue | 0 |  |  | 001108 | 2025-03-10 | 2025-08-22 | 1 | PEN | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" |  | 2025-08
001109 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 0 | 131242-WST02-VI-B-0002 | 2025-03-10 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 | 11 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001109 | 2025-03-10 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" |  | 2025-03
001109 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 1 | 131242-WST02-VI-B-0002 | 2025-04-18 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-08 | 2025-05-06 | 12 | Approved with Comments | YES | 2025-05-26 | NO | Resubmitted | 0 |  |  | 001109 | 2025-03-10 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" |  | 2025-04
001110 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0053 | 0 | 131242-WSW41-CD-IM-0053 | 2025-03-10 | Submission of BIM Coordination VCM Model (Feb 2025) | For information. | 2025-04-07 | 2025-03-25 | 11 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001110 | 2025-03-10 | 2025-03-10 | 0 | INF | For Information | 1 | " Submission of BIM Coordination VCM Model (Feb 2025) " |  | 2025-03
001111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0020 | 0 | 131242-WSW41-PC-W-0020 | 2025-03-10 | Payment Claim No.20 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-04-07 | 2025-04-27 | 35 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001111 | 2025-03-10 | 2025-03-10 | 0 | INF | For Information | 1 | "Payment Claim No.20" |  | 2025-03
001112 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 0 | 131242-WST02-DR-I-7209 | 2025-03-10 | SSN PMS Network Architecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-07 | 2025-05-07 | 42 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001112 | 2025-03-10 | 2025-08-07 | 1 | NAP | Approved with Comments | 2 | "SSN PMS Network Architecture Drawings" |  | 2025-03
001112 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 1 | 131242-WST02-DR-I-7209 | 2025-08-07 | SSN PMS Network Architecture Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-23 | 55 | Approved with Comments | YES | 2025-11-12 | NO | Resubmitted | 0 |  |  | 001112 | 2025-03-10 | 2025-08-07 | 1 | AWC | Approved with Comments | 2 | "SSN PMS Network Architecture Drawings" |  | 2025-08
001113 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 0 | 131242-WST02-VI-BP-0001 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-04-07 | 2025-03-28 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001113 | 2025-03-10 | 2026-02-05 | 2 | NAP | Not Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" |  | 2025-03
001113 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 1 | 131242-WST02-VI-BP-0001 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-03-28 | 2025-05-29 | 58 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001113 | 2025-03-10 | 2026-02-05 | 2 | NAP | Not Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" |  | 2025-03
001113 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 2 | 131242-WST02-VI-BP-0001 | 2026-02-05 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2026-02-25 |  | 37 | Awaiting S.O.'s response | YES | 2026-03-25 | NO | Overdue | 0 |  |  | 001113 | 2025-03-10 | 2026-02-05 | 2 | PEN | Not Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" |  | 2026-02
001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3015 | A | 131242-WST02-SD-A-3015 | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 | 16 | Not Approved | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001114&&001356 | 2025-03-11 | 2025-06-12 | A | NAP | Not Approved | 2 | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " |  | 2025-03
001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1015 | A | 131242-WST02-SD-A-1015 | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 | 16 | Not Approved | YES | 2025-04-22 | NO | Resubmitted | 0 |  |  | 001114 | 2025-03-11 | 2025-03-11 | A | NAP | Not Approved | 1 | "Shop Drawings for Siphonic System (Fast Flow)" |  | 2025-03
001115 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0007 | 0 | 131242-WSW41-PO-E-0007 | 2025-03-11 | Unpriced PO for Cable Support System (Jiangsu HDMann) | Rev 0: For Information. | 2025-04-08 | 2025-04-27 | 34 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001115 | 2025-03-11 | 2025-03-11 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Support System (Jiangsu HDMann) " |  | 2025-03
001116 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0057 | 0 | 131242-WSD11-QA-M-0057 | 2025-03-12 | FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-09 | 2025-03-21 | 7 | Approved with Comments | YES | 2025-04-10 | NO | Resubmitted | 0 |  |  | 001116 | 2025-03-12 | 2025-03-12 | 0 | AWC | Approved with Comments | 1 | "FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) " |  | 2025-03
001117 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 0 | 131242-WST02-CD-I-0010 | 2025-03-12 | SSN -RIO PANEL 0202- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-09 | 2025-04-22 | 29 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001117 | 2025-03-12 | 2025-06-18 | 1 | NAP | Approved with Comments | 2 | "SSN -RIO PANEL 0202- I/O List" |  | 2025-03
001117 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 1 | 131242-WST02-CD-I-0010 | 2025-06-18 | SSN -RIO PANEL 0202- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-09-02 | 54 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001117 | 2025-03-12 | 2025-06-18 | 1 | AWC | Approved with Comments | 2 | "SSN -RIO PANEL 0202- I/O List" |  | 2025-06
001118 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2007 | 0 | 131242-WSW41-VI-M-2007 | 2025-03-12 | Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-07-08 | 84 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001118 | 2025-03-12 | 2025-03-12 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain" |  | 2025-03
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_LTA_NPKS | A | 131242-WSD11-DR-A-1002_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" |  | 2025-03
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_LTA_NPKS | A | 131242-WSD11-DR-A-1003_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" |  | 2025-03
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_LTA_NPKS | A | 131242-WSD11-DR-A-1004_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" |  | 2025-03
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_LTA_NPKS | A | 131242-WSD11-DR-A-2000_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" |  | 2025-03
001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_LTA_NPKS | A | 131242-WSD11-DR-A-3000_LTA_NPKS | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001119 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP LTA Submission" |  | 2025-03
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_PUB | A | 131242-WSD11-DR-A-1002_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" |  | 2025-03
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_PUB | A | 131242-WSD11-DR-A-1003_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" |  | 2025-03
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_PUB | A | 131242-WSD11-DR-A-1004_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" |  | 2025-03
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_PUB | A | 131242-WSD11-DR-A-2000_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" |  | 2025-03
001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_PUB | A | 131242-WSD11-DR-A-3000_PUB | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001120 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP PUB Submission" |  | 2025-03
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_NEA | A | 131242-WSD11-DR-A-1002_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" |  | 2025-03
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_NEA | A | 131242-WSD11-DR-A-1003_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" |  | 2025-03
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_NEA | A | 131242-WSD11-DR-A-1004_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" |  | 2025-03
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_NEA | A | 131242-WSD11-DR-A-2000_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" |  | 2025-03
001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_NEA | A | 131242-WSD11-DR-A-3000_NEA | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | 65 | Not Approved | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001121 | 2025-03-12 | 2025-03-12 | A | NAP | Not Approved | 1 | "THP NEA Submission" |  | 2025-03
001122 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0056 | 0 | 131242-WSW41-LT-PM-0056 | 2025-03-13 | NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings | For Information. Please refer to S.O. correspondence no. 353 dated 28 May 2025. | 2025-04-10 | 2025-08-25 | 117 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001122 | 2025-03-13 | 2025-03-13 | 0 | INF | For Information | 1 | "NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings" |  | 2025-03
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | A | 131242-WST02-DR-M-5484 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-03
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5481 | A | 131242-WST02-DR-M-5481 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-03
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5482 | A | 131242-WST02-DR-M-5482 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-03
001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5483 | A | 131242-WST02-DR-M-5483 | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-03
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | B | 131242-WST02-DR-M-5484 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-07
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5481 | B | 131242-WST02-DR-M-5481 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-07
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5482 | B | 131242-WST02-DR-M-5482 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-07
001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5483 | B | 131242-WST02-DR-M-5483 | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | 149 | Approved with Comments | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001123 | 2025-03-13 | 2025-07-07 | B | AWC | Approved with Comments | 2 | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" |  | 2025-07
001124 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 5483 | 0 | 131242-WSD11-QA-M-5483 | 2025-03-14 | Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON) | Rev 0: Approved | 2025-04-11 | 2025-07-08 | 82 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001124 | 2025-03-14 | 2025-03-14 | 0 | APP | Approved | 1 | "Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON)" |  | 2025-03
001125 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2003 | 0 | 131242-WSW41-VI-M-2003 | 2025-03-14 | Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-11 | 2025-04-27 | 31 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001125 | 2025-03-14 | 2025-03-14 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen)" |  | 2025-03
001126 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0026 | 0 | 131242-WSW41-MS-C-0026 | 2025-03-14 | SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd. | R0: As communicated, CES would like to withdraw the submittal as CES has no intention to use the proposed materials for grouting. Hence, this submittal is rejected and no resubmission is required. | 2025-04-11 | 2025-06-04 | 58 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001126 | 2025-03-14 | 2025-03-14 | 0 | REJ | Rejected | 1 | "SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd." |  | 2025-03
001127 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0005 | 0 | 131242-WSD11-DS-I-0005 | 2025-03-17 | Datasheet for Differential Pressure Switch (Compressed Air System) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-14 | 2025-07-10 | 83 | Approved with Comments | YES | 2025-07-30 | NO | Resubmitted | 0 |  |  | 001127 | 2025-03-17 | 2025-03-17 | 0 | AWC | Approved with Comments | 1 | "Datasheet for Differential Pressure Switch (Compressed Air System)" |  | 2025-03
001128 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0019 | 0 | 131242-WSW41-PS-HS-0019 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Nov 2024 | Rev 0: Scoring confirmed to be at 70/100 | 2025-04-14 | 2025-03-25 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001128 | 2025-03-17 | 2025-03-17 | 0 | APP | Approved | 1 | "Incentive/ Disincentive Audit Scheme for Nov 2024" |  | 2025-03
001129 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | B | 0005 | 0 | 131242-WST02-VI-B-0005 | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-03-25 | 5 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001129 | 2025-03-18 | 2025-03-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " |  | 2025-03
001129 | 01 | Yuen Fatt | Project | NA | 131242 | NA | NA | NA | Cmt reply sheet | NA | 131242-NA-NA-NA-Cmt reply sheet | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 1: Approved | 2025-04-07 | 2025-05-06 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001129 | 2025-03-18 | 2025-03-18 | NA | APP | Approved | 1 | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " |  | 2025-03
001130 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0020 | 0 | 131242-WSW41-PS-HS-0020 | 2025-03-18 | Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025 | Rev 0: Noted for information | 2025-04-15 | 2025-03-25 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001130 | 2025-03-18 | 2025-03-18 | 0 | APP | Approved | 1 | "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" |  | 2025-03
001131 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 0 | 131242-WST02-RT-S-0002 | 2025-03-18 | Safety Review Report for Sitewide Pipe Rack | Approved with Comments | 2025-04-15 | 2025-05-13 | 40 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001131 | 2025-03-18 | 2025-06-18 | 1 | AWC | Approved | 2 | "Safety Review Report for Sitewide Pipe Rack" |  | 2025-03
001131 | 01 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 1 | 131242-WST02-RT-S-0002 | 2025-06-18 | Safety Review Report for Sitewide Pipe Rack | R1: Approved | 2025-07-08 | 2025-07-07 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001131 | 2025-03-18 | 2025-06-18 | 1 | APP | Approved | 2 | "Safety Review Report for Sitewide Pipe Rack" |  | 2025-06
001132 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 0 | 131242-WST02-QA-EI-0026 | 2025-03-18 | FAT Procedure for LVSG Panels (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-05-07 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001132 | 2025-03-18 | 2025-05-23 | 1 | AWC | Approved | 2 | "FAT Procedure for LVSG Panels (Sunlight)" |  | 2025-03
001132 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 1 | 131242-WST02-QA-EI-0026 | 2025-05-23 | FAT Procedure for LVSG Panels (Sunlight) | Rev 1: Approved. | 2025-06-12 | 2025-07-14 | 36 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001132 | 2025-03-18 | 2025-05-23 | 1 | APP | Approved | 2 | "FAT Procedure for LVSG Panels (Sunlight)" |  | 2025-05
001133 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0027 | 0 | 131242-WST02-QA-EI-0027 | 2025-03-18 | FAT Procedure for MDB Panels (Sunlight) | Approved with Comments | 2025-04-15 | 2025-05-21 | 46 | Approved with Comments | YES | 2025-06-10 | NO | Resubmitted | 0 |  |  | 001133 | 2025-03-18 | 2025-03-18 | 0 | AWC | Approved with Comments | 1 | " FAT Procedure for MDB Panels (Sunlight)" |  | 2025-03
001134 | 00 | Max | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 0 | 131242-WSD11-RT-S-0001 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-12 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001134 | 2025-03-18 | 2025-03-18 | 0 | NAP | Not Approved | 2 | "Report of DFS (GUIDE 3) for THP Trains Installation" |  | 2025-03
001134 | 01 | Htet Nu | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 1 | 131242-WSD11-RT-S-0001 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-07 | 2025-07-17 | 87 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001134 | 2025-03-18 | 2025-03-18 | 0 | AWC | Not Approved | 2 | "Report of DFS (GUIDE 3) for THP Trains Installation" |  | 2025-03
001135 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5801 | A | 131242-WST02-DS-M-5801 | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | 82 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001135 | 2025-03-20 | 2025-03-20 | A | AWC | Approved with Comments | 1 | "SSN Spray Nozzle datasheet and drawing" |  | 2025-03
001135 | 00 | Qili | Process | NA | 131242 | WST02 | DR | M | 5801 | 0 | 131242-WST02-DR-M-5801 | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | 82 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001135 | 2025-03-20 | 2025-03-20 | 0 | AWC | Approved with Comments | 1 | "SSN Spray Nozzle datasheet and drawing" |  | 2025-03
001136 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | A | 5000 | A | 131242-WSW41-DR-A-5000 | 2025-03-20 | Sitewide Piperack Handrail and Cad Ladder Layout and Details | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | 34 | Not Approved | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001136 | 2025-03-20 | 2025-03-20 | A | NAP | Not Approved | 1 | "Sitewide Piperack Handrail and Cad Ladder Layout and Details " |  | 2025-03
001137 | 00 | Radha | QAQC | NA | 131101 | WSW41 | MM | C | 0002 | 0 | 131101-WSW41-MM-C-0002 | 2025-03-20 | Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | 34 | Approved with Comments | YES | 2025-05-27 | NO | Resubmitted | 0 |  |  | 001137 | 2025-03-20 | 2025-03-20 | 0 | AWC | Approved with Comments | 1 | "Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall)" |  | 2025-03
001138 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0028 | 0 | 131242-WSW41-QA-E-0028 | 2025-03-20 | FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI) | Approved | 2025-04-17 | 2025-05-06 | 33 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001138 | 2025-03-20 | 2025-03-20 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" |  | 2025-03
001139 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 0 | 131242-WSW41-VI-M-2006 | 2025-03-20 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-04-05 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001139 | 2025-03-20 | 2025-05-05 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" |  | 2025-03
001139 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 1 | 131242-WSW41-VI-M-2006 | 2025-05-05 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | 235 | Awaiting S.O.'s response | YES | 2025-06-20 | NO | Overdue | 0 |  |  | 001139 | 2025-03-20 | 2025-05-05 | 1 | PEN | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" |  | 2025-05
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | A | 131242-WST02-DR-EI-7160 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7161 | A | 131242-WST02-DR-EI-7161 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7162 | A | 131242-WST02-DR-EI-7162 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7163 | A | 131242-WST02-DR-EI-7163 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7164 | A | 131242-WST02-DR-EI-7164 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7165 | A | 131242-WST02-DR-EI-7165 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7166 | A | 131242-WST02-DR-EI-7166 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7167 | A | 131242-WST02-DR-EI-7167 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7180 | A | 131242-WST02-DR-EI-7180 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7181 | A | 131242-WST02-DR-EI-7181 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7182 | A | 131242-WST02-DR-EI-7182 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7183 | A | 131242-WST02-DR-EI-7183 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7184 | A | 131242-WST02-DR-EI-7184 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7185 | A | 131242-WST02-DR-EI-7185 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7186 | A | 131242-WST02-DR-EI-7186 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7187 | A | 131242-WST02-DR-EI-7187 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3052 | A | 131242-WST02-DR-EP-3052 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3053 | A | 131242-WST02-DR-EP-3053 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3054 | A | 131242-WST02-DR-EP-3054 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3055 | A | 131242-WST02-DR-EP-3055 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3056 | A | 131242-WST02-DR-EP-3056 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3057 | A | 131242-WST02-DR-EP-3057 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3058 | A | 131242-WST02-DR-EP-3058 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3059 | A | 131242-WST02-DR-EP-3059 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3060 | A | 131242-WST02-DR-EP-3060 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3061 | A | 131242-WST02-DR-EP-3061 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3062 | A | 131242-WST02-DR-EP-3062 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3063 | A | 131242-WST02-DR-EP-3063 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3064 | A | 131242-WST02-DR-EP-3064 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3065 | A | 131242-WST02-DR-EP-3065 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7142 | A | 131242-WST02-DR-EP-7142 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7143 | A | 131242-WST02-DR-EP-7143 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7144 | A | 131242-WST02-DR-EP-7144 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7145 | A | 131242-WST02-DR-EP-7145 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7146 | A | 131242-WST02-DR-EP-7146 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7147 | A | 131242-WST02-DR-EP-7147 | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-03
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | B | 131242-WST02-DR-EI-7160 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7161 | B | 131242-WST02-DR-EI-7161 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7162 | B | 131242-WST02-DR-EI-7162 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7163 | B | 131242-WST02-DR-EI-7163 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7164 | B | 131242-WST02-DR-EI-7164 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7165 | B | 131242-WST02-DR-EI-7165 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7166 | B | 131242-WST02-DR-EI-7166 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7167 | B | 131242-WST02-DR-EI-7167 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7180 | B | 131242-WST02-DR-EI-7180 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7181 | B | 131242-WST02-DR-EI-7181 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7182 | B | 131242-WST02-DR-EI-7182 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7183 | B | 131242-WST02-DR-EI-7183 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7184 | B | 131242-WST02-DR-EI-7184 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7185 | B | 131242-WST02-DR-EI-7185 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7186 | B | 131242-WST02-DR-EI-7186 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7187 | B | 131242-WST02-DR-EI-7187 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3052 | B | 131242-WST02-DR-EP-3052 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3053 | B | 131242-WST02-DR-EP-3053 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3054 | B | 131242-WST02-DR-EP-3054 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3055 | B | 131242-WST02-DR-EP-3055 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3056 | B | 131242-WST02-DR-EP-3056 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3057 | B | 131242-WST02-DR-EP-3057 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3058 | B | 131242-WST02-DR-EP-3058 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3059 | B | 131242-WST02-DR-EP-3059 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3060 | B | 131242-WST02-DR-EP-3060 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3061 | B | 131242-WST02-DR-EP-3061 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3062 | B | 131242-WST02-DR-EP-3062 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3063 | B | 131242-WST02-DR-EP-3063 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3064 | B | 131242-WST02-DR-EP-3064 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3065 | B | 131242-WST02-DR-EP-3065 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7142 | B | 131242-WST02-DR-EP-7142 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7143 | B | 131242-WST02-DR-EP-7143 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7144 | B | 131242-WST02-DR-EP-7144 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7145 | B | 131242-WST02-DR-EP-7145 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7146 | B | 131242-WST02-DR-EP-7146 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7147 | B | 131242-WST02-DR-EP-7147 | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | 46 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001140 | 2025-03-21 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-1001A.B SLD, Schem and GA Drawings" |  | 2025-07
001141 | 00 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 0 | 131242-WST02-VI-I-0024 | 2025-03-21 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-18 | 20 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001141 | 2025-03-21 | 2025-04-30 | 1 | NAP | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" |  | 2025-03
001141 | 01 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 1 | 131242-WST02-VI-I-0024 | 2025-04-30 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-04 | 25 | Approved with Comments | YES | 2025-06-24 | NO | Resubmitted | 0 |  |  | 001141 | 2025-03-21 | 2025-04-30 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" |  | 2025-04
001142 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 0 | 131242-WST02-CD-I-0011 | 2025-03-21 | SSN -RIO PANEL 0401- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-22 | 22 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001142 | 2025-03-21 | 2025-06-25 | 1 | NAP | Approved with Comments | 2 | "SSN -RIO PANEL 0401- I/O List" |  | 2025-03
001142 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 1 | 131242-WST02-CD-I-0011 | 2025-06-25 | SSN -RIO PANEL 0401- I/O List | Rev 1: Approved with Comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-15 | 58 | Approved with Comments | YES | 2025-10-03 | NO | Resubmitted | 0 |  |  | 001142 | 2025-03-21 | 2025-06-25 | 1 | AWC | Approved with Comments | 2 | "SSN -RIO PANEL 0401- I/O List" |  | 2025-06
001143 | 00 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 0 | 131242-WSD11-MS-M-0007 | 2025-03-21 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Rev 0: Not approved - Revise and Resubmit. Refer to comments provided during MSRA briefing meeting dated 28th March 2025 and 4 April 2025. | 2025-04-18 | 2025-04-05 | 11 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001143 | 2025-03-21 | 2025-04-10 | 1 | NAP | Approved | 2 | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " |  | 2025-03
001143 | 01 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 1 | 131242-WSD11-MS-M-0007 | 2025-04-10 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Approved | 2025-04-30 | 2025-05-21 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001143 | 2025-03-21 | 2025-04-10 | 1 | APP | Approved | 2 | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " |  | 2025-04
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-IP-1001 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1002 | B | 131242-WST02-DR-IP-1002 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1003 | B | 131242-WST02-DR-IP-1003 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1004 | B | 131242-WST02-DR-IP-1004 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1005 | B | 131242-WST02-DR-IP-1005 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1006 | B | 131242-WST02-DR-IP-1006 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1007 | B | 131242-WST02-DR-IP-1007 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1008 | B | 131242-WST02-DR-IP-1008 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1009 | B | 131242-WST02-DR-IP-1009 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1010 | B | 131242-WST02-DR-IP-1010 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1011 | B | 131242-WST02-DR-IP-1011 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1012 | B | 131242-WST02-DR-IP-1012 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1013 | B | 131242-WST02-DR-IP-1013 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1014 | B | 131242-WST02-DR-IP-1014 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1015 | B | 131242-WST02-DR-IP-1015 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1016 | B | 131242-WST02-DR-IP-1016 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1017 | B | 131242-WST02-DR-IP-1017 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1018 | B | 131242-WST02-DR-IP-1018 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1019 | B | 131242-WST02-DR-IP-1019 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1020 | B | 131242-WST02-DR-IP-1020 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1021 | B | 131242-WST02-DR-IP-1021 | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-03
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-IP-1001 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1002 | B | 131242-WST02-DR-IP-1002 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1003 | B | 131242-WST02-DR-IP-1003 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1004 | B | 131242-WST02-DR-IP-1004 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1005 | B | 131242-WST02-DR-IP-1005 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1006 | B | 131242-WST02-DR-IP-1006 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1007 | B | 131242-WST02-DR-IP-1007 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1008 | B | 131242-WST02-DR-IP-1008 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1009 | B | 131242-WST02-DR-IP-1009 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1010 | B | 131242-WST02-DR-IP-1010 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1011 | B | 131242-WST02-DR-IP-1011 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1012 | B | 131242-WST02-DR-IP-1012 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1013 | B | 131242-WST02-DR-IP-1013 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1014 | B | 131242-WST02-DR-IP-1014 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1015 | B | 131242-WST02-DR-IP-1015 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1016 | B | 131242-WST02-DR-IP-1016 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1017 | B | 131242-WST02-DR-IP-1017 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1018 | B | 131242-WST02-DR-IP-1018 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1019 | B | 131242-WST02-DR-IP-1019 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1020 | B | 131242-WST02-DR-IP-1020 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1021 | B | 131242-WST02-DR-IP-1021 | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001144 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN ECCP-1000- GA & Wiring Diagram" |  | 2025-08
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | B | 131242-WST02-DR-IP-1051 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1052 | B | 131242-WST02-DR-IP-1052 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1053 | B | 131242-WST02-DR-IP-1053 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1054 | B | 131242-WST02-DR-IP-1054 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1055 | B | 131242-WST02-DR-IP-1055 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1056 | B | 131242-WST02-DR-IP-1056 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1057 | B | 131242-WST02-DR-IP-1057 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1058 | B | 131242-WST02-DR-IP-1058 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1059 | B | 131242-WST02-DR-IP-1059 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1060 | B | 131242-WST02-DR-IP-1060 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1061 | B | 131242-WST02-DR-IP-1061 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1062 | B | 131242-WST02-DR-IP-1062 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1063 | B | 131242-WST02-DR-IP-1063 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1064 | B | 131242-WST02-DR-IP-1064 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1065 | B | 131242-WST02-DR-IP-1065 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1066 | B | 131242-WST02-DR-IP-1066 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1067 | B | 131242-WST02-DR-IP-1067 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1068 | B | 131242-WST02-DR-IP-1068 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1069 | B | 131242-WST02-DR-IP-1069 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1070 | B | 131242-WST02-DR-IP-1070 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1071 | B | 131242-WST02-DR-IP-1071 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1072 | B | 131242-WST02-DR-IP-1072 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1073 | B | 131242-WST02-DR-IP-1073 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1074 | B | 131242-WST02-DR-IP-1074 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1075 | B | 131242-WST02-DR-IP-1075 | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | NAP | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-03
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | C | 131242-WST02-DR-IP-1051 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1052 | C | 131242-WST02-DR-IP-1052 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1053 | C | 131242-WST02-DR-IP-1053 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1054 | C | 131242-WST02-DR-IP-1054 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1055 | C | 131242-WST02-DR-IP-1055 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1056 | C | 131242-WST02-DR-IP-1056 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1057 | C | 131242-WST02-DR-IP-1057 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1058 | C | 131242-WST02-DR-IP-1058 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1059 | C | 131242-WST02-DR-IP-1059 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1060 | C | 131242-WST02-DR-IP-1060 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1061 | C | 131242-WST02-DR-IP-1061 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1062 | C | 131242-WST02-DR-IP-1062 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1063 | C | 131242-WST02-DR-IP-1063 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1064 | C | 131242-WST02-DR-IP-1064 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1065 | C | 131242-WST02-DR-IP-1065 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1066 | C | 131242-WST02-DR-IP-1066 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1067 | C | 131242-WST02-DR-IP-1067 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1068 | C | 131242-WST02-DR-IP-1068 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1069 | C | 131242-WST02-DR-IP-1069 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1070 | C | 131242-WST02-DR-IP-1070 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1071 | C | 131242-WST02-DR-IP-1071 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1072 | C | 131242-WST02-DR-IP-1072 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1073 | C | 131242-WST02-DR-IP-1073 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1074 | C | 131242-WST02-DR-IP-1074 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1075 | C | 131242-WST02-DR-IP-1075 | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | 31 | Approved with Comments | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001145 | 2025-03-21 | 2025-08-19 | C | AWC | Approved with Comments | 2 | "SSN RIO 0001A GA & Wiring Diagram" |  | 2025-08
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-IP-1101 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1102 | B | 131242-WST02-DR-IP-1102 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1103 | B | 131242-WST02-DR-IP-1103 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1104 | B | 131242-WST02-DR-IP-1104 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1105 | B | 131242-WST02-DR-IP-1105 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1106 | B | 131242-WST02-DR-IP-1106 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1107 | B | 131242-WST02-DR-IP-1107 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1108 | B | 131242-WST02-DR-IP-1108 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1109 | B | 131242-WST02-DR-IP-1109 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1110 | B | 131242-WST02-DR-IP-1110 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1111 | B | 131242-WST02-DR-IP-1111 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1112 | B | 131242-WST02-DR-IP-1112 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1113 | B | 131242-WST02-DR-IP-1113 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1114 | B | 131242-WST02-DR-IP-1114 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1115 | B | 131242-WST02-DR-IP-1115 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1116 | B | 131242-WST02-DR-IP-1116 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1117 | B | 131242-WST02-DR-IP-1117 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1118 | B | 131242-WST02-DR-IP-1118 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1119 | B | 131242-WST02-DR-IP-1119 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1120 | B | 131242-WST02-DR-IP-1120 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1121 | B | 131242-WST02-DR-IP-1121 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1122 | B | 131242-WST02-DR-IP-1122 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1123 | B | 131242-WST02-DR-IP-1123 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1124 | B | 131242-WST02-DR-IP-1124 | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | NAP | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-03
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-IP-1101 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1102 | B | 131242-WST02-DR-IP-1102 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1103 | B | 131242-WST02-DR-IP-1103 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1104 | B | 131242-WST02-DR-IP-1104 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1105 | B | 131242-WST02-DR-IP-1105 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1106 | B | 131242-WST02-DR-IP-1106 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1107 | B | 131242-WST02-DR-IP-1107 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1108 | B | 131242-WST02-DR-IP-1108 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1109 | B | 131242-WST02-DR-IP-1109 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1110 | B | 131242-WST02-DR-IP-1110 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1111 | B | 131242-WST02-DR-IP-1111 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1112 | B | 131242-WST02-DR-IP-1112 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1113 | B | 131242-WST02-DR-IP-1113 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1114 | B | 131242-WST02-DR-IP-1114 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1115 | B | 131242-WST02-DR-IP-1115 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1116 | B | 131242-WST02-DR-IP-1116 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1117 | B | 131242-WST02-DR-IP-1117 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1118 | B | 131242-WST02-DR-IP-1118 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1119 | B | 131242-WST02-DR-IP-1119 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1120 | B | 131242-WST02-DR-IP-1120 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1121 | B | 131242-WST02-DR-IP-1121 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1122 | B | 131242-WST02-DR-IP-1122 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1123 | B | 131242-WST02-DR-IP-1123 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1124 | B | 131242-WST02-DR-IP-1124 | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | 36 | Approved with Comments | YES | 2025-10-28 | NO | Resubmitted | 0 |  |  | 001146 | 2025-03-21 | 2025-08-19 | B | AWC | Approved with Comments | 2 | "SSN RIO 0001B GA & Wiring Diagram" |  | 2025-08
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | B | 131242-WST02-DR-IP-1151 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1152 | B | 131242-WST02-DR-IP-1152 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1153 | B | 131242-WST02-DR-IP-1153 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1154 | B | 131242-WST02-DR-IP-1154 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1155 | B | 131242-WST02-DR-IP-1155 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1156 | B | 131242-WST02-DR-IP-1156 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1157 | B | 131242-WST02-DR-IP-1157 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1158 | B | 131242-WST02-DR-IP-1158 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1159 | B | 131242-WST02-DR-IP-1159 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1160 | B | 131242-WST02-DR-IP-1160 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1161 | B | 131242-WST02-DR-IP-1161 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1162 | B | 131242-WST02-DR-IP-1162 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1163 | B | 131242-WST02-DR-IP-1163 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1164 | B | 131242-WST02-DR-IP-1164 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1165 | B | 131242-WST02-DR-IP-1165 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1166 | B | 131242-WST02-DR-IP-1166 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1167 | B | 131242-WST02-DR-IP-1167 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1168 | B | 131242-WST02-DR-IP-1168 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1169 | B | 131242-WST02-DR-IP-1169 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1170 | B | 131242-WST02-DR-IP-1170 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1171 | B | 131242-WST02-DR-IP-1171 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1172 | B | 131242-WST02-DR-IP-1172 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1173 | B | 131242-WST02-DR-IP-1173 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1174 | B | 131242-WST02-DR-IP-1174 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1175 | B | 131242-WST02-DR-IP-1175 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1176 | B | 131242-WST02-DR-IP-1176 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1177 | B | 131242-WST02-DR-IP-1177 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1178 | B | 131242-WST02-DR-IP-1178 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1179 | B | 131242-WST02-DR-IP-1179 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1180 | B | 131242-WST02-DR-IP-1180 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1181 | B | 131242-WST02-DR-IP-1181 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1182 | B | 131242-WST02-DR-IP-1182 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1183 | B | 131242-WST02-DR-IP-1183 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1184 | B | 131242-WST02-DR-IP-1184 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1185 | B | 131242-WST02-DR-IP-1185 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1186 | B | 131242-WST02-DR-IP-1186 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1187 | B | 131242-WST02-DR-IP-1187 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1188 | B | 131242-WST02-DR-IP-1188 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1189 | B | 131242-WST02-DR-IP-1189 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1190 | B | 131242-WST02-DR-IP-1190 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1191 | B | 131242-WST02-DR-IP-1191 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1192 | B | 131242-WST02-DR-IP-1192 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1193 | B | 131242-WST02-DR-IP-1193 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1194 | B | 131242-WST02-DR-IP-1194 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1195 | B | 131242-WST02-DR-IP-1195 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1196 | B | 131242-WST02-DR-IP-1196 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1197 | B | 131242-WST02-DR-IP-1197 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1198 | B | 131242-WST02-DR-IP-1198 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1199 | B | 131242-WST02-DR-IP-1199 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1200 | B | 131242-WST02-DR-IP-1200 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1201 | B | 131242-WST02-DR-IP-1201 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1202 | B | 131242-WST02-DR-IP-1202 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1203 | B | 131242-WST02-DR-IP-1203 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1204 | B | 131242-WST02-DR-IP-1204 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1205 | B | 131242-WST02-DR-IP-1205 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1206 | B | 131242-WST02-DR-IP-1206 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1207 | B | 131242-WST02-DR-IP-1207 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1208 | B | 131242-WST02-DR-IP-1208 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1209 | B | 131242-WST02-DR-IP-1209 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1210 | B | 131242-WST02-DR-IP-1210 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1211 | B | 131242-WST02-DR-IP-1211 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1212 | B | 131242-WST02-DR-IP-1212 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1213 | B | 131242-WST02-DR-IP-1213 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1214 | B | 131242-WST02-DR-IP-1214 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1215 | B | 131242-WST02-DR-IP-1215 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1216 | B | 131242-WST02-DR-IP-1216 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1217 | B | 131242-WST02-DR-IP-1217 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1218 | B | 131242-WST02-DR-IP-1218 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1219 | B | 131242-WST02-DR-IP-1219 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1220 | B | 131242-WST02-DR-IP-1220 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1221 | B | 131242-WST02-DR-IP-1221 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1222 | B | 131242-WST02-DR-IP-1222 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1223 | B | 131242-WST02-DR-IP-1223 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1224 | B | 131242-WST02-DR-IP-1224 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1225 | B | 131242-WST02-DR-IP-1225 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1226 | B | 131242-WST02-DR-IP-1226 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1227 | B | 131242-WST02-DR-IP-1227 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1228 | B | 131242-WST02-DR-IP-1228 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1229 | B | 131242-WST02-DR-IP-1229 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1230 | B | 131242-WST02-DR-IP-1230 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1231 | B | 131242-WST02-DR-IP-1231 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1232 | B | 131242-WST02-DR-IP-1232 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1233 | B | 131242-WST02-DR-IP-1233 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1234 | B | 131242-WST02-DR-IP-1234 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1235 | B | 131242-WST02-DR-IP-1235 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1236 | B | 131242-WST02-DR-IP-1236 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1237 | B | 131242-WST02-DR-IP-1237 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1238 | B | 131242-WST02-DR-IP-1238 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1239 | B | 131242-WST02-DR-IP-1239 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1240 | B | 131242-WST02-DR-IP-1240 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1241 | B | 131242-WST02-DR-IP-1241 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1242 | B | 131242-WST02-DR-IP-1242 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1243 | B | 131242-WST02-DR-IP-1243 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1244 | B | 131242-WST02-DR-IP-1244 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1245 | B | 131242-WST02-DR-IP-1245 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1246 | B | 131242-WST02-DR-IP-1246 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1247 | B | 131242-WST02-DR-IP-1247 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1248 | B | 131242-WST02-DR-IP-1248 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1249 | B | 131242-WST02-DR-IP-1249 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1250 | B | 131242-WST02-DR-IP-1250 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1251 | B | 131242-WST02-DR-IP-1251 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1252 | B | 131242-WST02-DR-IP-1252 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1253 | B | 131242-WST02-DR-IP-1253 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1254 | B | 131242-WST02-DR-IP-1254 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1255 | B | 131242-WST02-DR-IP-1255 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1256 | B | 131242-WST02-DR-IP-1256 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1257 | B | 131242-WST02-DR-IP-1257 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1258 | B | 131242-WST02-DR-IP-1258 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1259 | B | 131242-WST02-DR-IP-1259 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1260 | B | 131242-WST02-DR-IP-1260 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1261 | B | 131242-WST02-DR-IP-1261 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1262 | B | 131242-WST02-DR-IP-1262 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1263 | B | 131242-WST02-DR-IP-1263 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1264 | B | 131242-WST02-DR-IP-1264 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1265 | B | 131242-WST02-DR-IP-1265 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1266 | B | 131242-WST02-DR-IP-1266 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1267 | B | 131242-WST02-DR-IP-1267 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1268 | B | 131242-WST02-DR-IP-1268 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1269 | B | 131242-WST02-DR-IP-1269 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1270 | B | 131242-WST02-DR-IP-1270 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1271 | B | 131242-WST02-DR-IP-1271 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1272 | B | 131242-WST02-DR-IP-1272 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1273 | B | 131242-WST02-DR-IP-1273 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1274 | B | 131242-WST02-DR-IP-1274 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1275 | B | 131242-WST02-DR-IP-1275 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1276 | B | 131242-WST02-DR-IP-1276 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1277 | B | 131242-WST02-DR-IP-1277 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1278 | B | 131242-WST02-DR-IP-1278 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1279 | B | 131242-WST02-DR-IP-1279 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1280 | B | 131242-WST02-DR-IP-1280 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1281 | B | 131242-WST02-DR-IP-1281 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1282 | B | 131242-WST02-DR-IP-1282 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1283 | B | 131242-WST02-DR-IP-1283 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1284 | B | 131242-WST02-DR-IP-1284 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1285 | B | 131242-WST02-DR-IP-1285 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1286 | B | 131242-WST02-DR-IP-1286 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1287 | B | 131242-WST02-DR-IP-1287 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1288 | B | 131242-WST02-DR-IP-1288 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1289 | B | 131242-WST02-DR-IP-1289 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1290 | B | 131242-WST02-DR-IP-1290 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1291 | B | 131242-WST02-DR-IP-1291 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1292 | B | 131242-WST02-DR-IP-1292 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1293 | B | 131242-WST02-DR-IP-1293 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1294 | B | 131242-WST02-DR-IP-1294 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1295 | B | 131242-WST02-DR-IP-1295 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1296 | B | 131242-WST02-DR-IP-1296 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1297 | B | 131242-WST02-DR-IP-1297 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1298 | B | 131242-WST02-DR-IP-1298 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1299 | B | 131242-WST02-DR-IP-1299 | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-03
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | C | 131242-WST02-DR-IP-1151 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1152 | C | 131242-WST02-DR-IP-1152 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1153 | C | 131242-WST02-DR-IP-1153 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1154 | C | 131242-WST02-DR-IP-1154 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1155 | C | 131242-WST02-DR-IP-1155 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1156 | C | 131242-WST02-DR-IP-1156 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1157 | C | 131242-WST02-DR-IP-1157 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1158 | C | 131242-WST02-DR-IP-1158 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1159 | C | 131242-WST02-DR-IP-1159 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1160 | C | 131242-WST02-DR-IP-1160 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1161 | C | 131242-WST02-DR-IP-1161 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1162 | C | 131242-WST02-DR-IP-1162 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1163 | C | 131242-WST02-DR-IP-1163 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1164 | C | 131242-WST02-DR-IP-1164 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1165 | C | 131242-WST02-DR-IP-1165 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1166 | C | 131242-WST02-DR-IP-1166 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1167 | C | 131242-WST02-DR-IP-1167 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1168 | C | 131242-WST02-DR-IP-1168 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1169 | C | 131242-WST02-DR-IP-1169 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1170 | C | 131242-WST02-DR-IP-1170 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1171 | C | 131242-WST02-DR-IP-1171 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1172 | C | 131242-WST02-DR-IP-1172 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1173 | C | 131242-WST02-DR-IP-1173 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1174 | C | 131242-WST02-DR-IP-1174 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1175 | C | 131242-WST02-DR-IP-1175 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1176 | C | 131242-WST02-DR-IP-1176 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1177 | C | 131242-WST02-DR-IP-1177 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1178 | C | 131242-WST02-DR-IP-1178 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1179 | C | 131242-WST02-DR-IP-1179 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1180 | C | 131242-WST02-DR-IP-1180 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1181 | C | 131242-WST02-DR-IP-1181 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1182 | C | 131242-WST02-DR-IP-1182 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1183 | C | 131242-WST02-DR-IP-1183 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1184 | C | 131242-WST02-DR-IP-1184 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1185 | C | 131242-WST02-DR-IP-1185 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1186 | C | 131242-WST02-DR-IP-1186 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1187 | C | 131242-WST02-DR-IP-1187 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1188 | C | 131242-WST02-DR-IP-1188 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1189 | C | 131242-WST02-DR-IP-1189 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1190 | C | 131242-WST02-DR-IP-1190 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1191 | C | 131242-WST02-DR-IP-1191 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1192 | C | 131242-WST02-DR-IP-1192 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1193 | C | 131242-WST02-DR-IP-1193 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1194 | C | 131242-WST02-DR-IP-1194 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1195 | C | 131242-WST02-DR-IP-1195 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1196 | C | 131242-WST02-DR-IP-1196 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1197 | C | 131242-WST02-DR-IP-1197 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1198 | C | 131242-WST02-DR-IP-1198 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1199 | C | 131242-WST02-DR-IP-1199 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1200 | C | 131242-WST02-DR-IP-1200 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1201 | C | 131242-WST02-DR-IP-1201 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1202 | C | 131242-WST02-DR-IP-1202 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1203 | C | 131242-WST02-DR-IP-1203 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1204 | C | 131242-WST02-DR-IP-1204 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1205 | C | 131242-WST02-DR-IP-1205 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1206 | C | 131242-WST02-DR-IP-1206 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1207 | C | 131242-WST02-DR-IP-1207 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1208 | C | 131242-WST02-DR-IP-1208 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1209 | C | 131242-WST02-DR-IP-1209 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1210 | C | 131242-WST02-DR-IP-1210 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1211 | C | 131242-WST02-DR-IP-1211 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1212 | C | 131242-WST02-DR-IP-1212 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1213 | C | 131242-WST02-DR-IP-1213 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1214 | C | 131242-WST02-DR-IP-1214 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1215 | C | 131242-WST02-DR-IP-1215 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1216 | C | 131242-WST02-DR-IP-1216 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1217 | C | 131242-WST02-DR-IP-1217 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1218 | C | 131242-WST02-DR-IP-1218 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1219 | C | 131242-WST02-DR-IP-1219 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1220 | C | 131242-WST02-DR-IP-1220 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1221 | C | 131242-WST02-DR-IP-1221 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1222 | C | 131242-WST02-DR-IP-1222 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1223 | C | 131242-WST02-DR-IP-1223 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1224 | C | 131242-WST02-DR-IP-1224 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1225 | C | 131242-WST02-DR-IP-1225 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1226 | C | 131242-WST02-DR-IP-1226 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1227 | C | 131242-WST02-DR-IP-1227 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1228 | C | 131242-WST02-DR-IP-1228 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1229 | C | 131242-WST02-DR-IP-1229 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1230 | C | 131242-WST02-DR-IP-1230 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1231 | C | 131242-WST02-DR-IP-1231 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1232 | C | 131242-WST02-DR-IP-1232 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1233 | C | 131242-WST02-DR-IP-1233 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1234 | C | 131242-WST02-DR-IP-1234 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1235 | C | 131242-WST02-DR-IP-1235 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1236 | C | 131242-WST02-DR-IP-1236 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1237 | C | 131242-WST02-DR-IP-1237 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1238 | C | 131242-WST02-DR-IP-1238 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1239 | C | 131242-WST02-DR-IP-1239 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1240 | C | 131242-WST02-DR-IP-1240 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1241 | C | 131242-WST02-DR-IP-1241 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1242 | C | 131242-WST02-DR-IP-1242 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1243 | C | 131242-WST02-DR-IP-1243 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1244 | C | 131242-WST02-DR-IP-1244 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1245 | C | 131242-WST02-DR-IP-1245 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1246 | C | 131242-WST02-DR-IP-1246 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1247 | C | 131242-WST02-DR-IP-1247 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1248 | C | 131242-WST02-DR-IP-1248 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1249 | C | 131242-WST02-DR-IP-1249 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1250 | C | 131242-WST02-DR-IP-1250 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1251 | C | 131242-WST02-DR-IP-1251 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1252 | C | 131242-WST02-DR-IP-1252 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1253 | C | 131242-WST02-DR-IP-1253 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1254 | C | 131242-WST02-DR-IP-1254 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1255 | C | 131242-WST02-DR-IP-1255 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1256 | C | 131242-WST02-DR-IP-1256 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1257 | C | 131242-WST02-DR-IP-1257 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1258 | C | 131242-WST02-DR-IP-1258 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1259 | C | 131242-WST02-DR-IP-1259 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1260 | C | 131242-WST02-DR-IP-1260 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1261 | C | 131242-WST02-DR-IP-1261 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1262 | C | 131242-WST02-DR-IP-1262 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1263 | C | 131242-WST02-DR-IP-1263 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1264 | C | 131242-WST02-DR-IP-1264 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1265 | C | 131242-WST02-DR-IP-1265 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1266 | C | 131242-WST02-DR-IP-1266 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1267 | C | 131242-WST02-DR-IP-1267 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1268 | C | 131242-WST02-DR-IP-1268 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1269 | C | 131242-WST02-DR-IP-1269 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1270 | C | 131242-WST02-DR-IP-1270 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1271 | C | 131242-WST02-DR-IP-1271 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1272 | C | 131242-WST02-DR-IP-1272 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1273 | C | 131242-WST02-DR-IP-1273 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1274 | C | 131242-WST02-DR-IP-1274 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1275 | C | 131242-WST02-DR-IP-1275 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1276 | C | 131242-WST02-DR-IP-1276 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1277 | C | 131242-WST02-DR-IP-1277 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1278 | C | 131242-WST02-DR-IP-1278 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1279 | C | 131242-WST02-DR-IP-1279 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1280 | C | 131242-WST02-DR-IP-1280 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1281 | C | 131242-WST02-DR-IP-1281 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1282 | C | 131242-WST02-DR-IP-1282 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1283 | C | 131242-WST02-DR-IP-1283 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1284 | C | 131242-WST02-DR-IP-1284 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1285 | C | 131242-WST02-DR-IP-1285 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1286 | C | 131242-WST02-DR-IP-1286 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1287 | C | 131242-WST02-DR-IP-1287 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1288 | C | 131242-WST02-DR-IP-1288 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1289 | C | 131242-WST02-DR-IP-1289 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1290 | C | 131242-WST02-DR-IP-1290 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1291 | C | 131242-WST02-DR-IP-1291 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1292 | C | 131242-WST02-DR-IP-1292 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1293 | C | 131242-WST02-DR-IP-1293 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1294 | C | 131242-WST02-DR-IP-1294 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1295 | C | 131242-WST02-DR-IP-1295 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1296 | C | 131242-WST02-DR-IP-1296 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1297 | C | 131242-WST02-DR-IP-1297 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1298 | C | 131242-WST02-DR-IP-1298 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1299 | C | 131242-WST02-DR-IP-1299 | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001147 | 2025-03-21 | 2025-07-29 | C | NAP | Not Approved | 2 | "SSN RIO 0201 GA & Wiring Diagram" |  | 2025-07
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-IP-1351 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1352 | B | 131242-WST02-DR-IP-1352 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1353 | B | 131242-WST02-DR-IP-1353 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1354 | B | 131242-WST02-DR-IP-1354 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1355 | B | 131242-WST02-DR-IP-1355 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1356 | B | 131242-WST02-DR-IP-1356 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1357 | B | 131242-WST02-DR-IP-1357 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1358 | B | 131242-WST02-DR-IP-1358 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1359 | B | 131242-WST02-DR-IP-1359 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1360 | B | 131242-WST02-DR-IP-1360 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1361 | B | 131242-WST02-DR-IP-1361 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1362 | B | 131242-WST02-DR-IP-1362 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1363 | B | 131242-WST02-DR-IP-1363 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1364 | B | 131242-WST02-DR-IP-1364 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1365 | B | 131242-WST02-DR-IP-1365 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1366 | B | 131242-WST02-DR-IP-1366 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1367 | B | 131242-WST02-DR-IP-1367 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1368 | B | 131242-WST02-DR-IP-1368 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1369 | B | 131242-WST02-DR-IP-1369 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1370 | B | 131242-WST02-DR-IP-1370 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1371 | B | 131242-WST02-DR-IP-1371 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1372 | B | 131242-WST02-DR-IP-1372 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1373 | B | 131242-WST02-DR-IP-1373 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1374 | B | 131242-WST02-DR-IP-1374 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1375 | B | 131242-WST02-DR-IP-1375 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1376 | B | 131242-WST02-DR-IP-1376 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1377 | B | 131242-WST02-DR-IP-1377 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1378 | B | 131242-WST02-DR-IP-1378 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1379 | B | 131242-WST02-DR-IP-1379 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1380 | B | 131242-WST02-DR-IP-1380 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1381 | B | 131242-WST02-DR-IP-1381 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1382 | B | 131242-WST02-DR-IP-1382 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1383 | B | 131242-WST02-DR-IP-1383 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1384 | B | 131242-WST02-DR-IP-1384 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1385 | B | 131242-WST02-DR-IP-1385 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1386 | B | 131242-WST02-DR-IP-1386 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1387 | B | 131242-WST02-DR-IP-1387 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1388 | B | 131242-WST02-DR-IP-1388 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1389 | B | 131242-WST02-DR-IP-1389 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1390 | B | 131242-WST02-DR-IP-1390 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1391 | B | 131242-WST02-DR-IP-1391 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1392 | B | 131242-WST02-DR-IP-1392 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1393 | B | 131242-WST02-DR-IP-1393 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1394 | B | 131242-WST02-DR-IP-1394 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1395 | B | 131242-WST02-DR-IP-1395 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1396 | B | 131242-WST02-DR-IP-1396 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1397 | B | 131242-WST02-DR-IP-1397 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1398 | B | 131242-WST02-DR-IP-1398 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1399 | B | 131242-WST02-DR-IP-1399 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1400 | B | 131242-WST02-DR-IP-1400 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1401 | B | 131242-WST02-DR-IP-1401 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1402 | B | 131242-WST02-DR-IP-1402 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1403 | B | 131242-WST02-DR-IP-1403 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1404 | B | 131242-WST02-DR-IP-1404 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1405 | B | 131242-WST02-DR-IP-1405 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1406 | B | 131242-WST02-DR-IP-1406 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1407 | B | 131242-WST02-DR-IP-1407 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1408 | B | 131242-WST02-DR-IP-1408 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1409 | B | 131242-WST02-DR-IP-1409 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1410 | B | 131242-WST02-DR-IP-1410 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1411 | B | 131242-WST02-DR-IP-1411 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1412 | B | 131242-WST02-DR-IP-1412 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1413 | B | 131242-WST02-DR-IP-1413 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1414 | B | 131242-WST02-DR-IP-1414 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1415 | B | 131242-WST02-DR-IP-1415 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1416 | B | 131242-WST02-DR-IP-1416 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1417 | B | 131242-WST02-DR-IP-1417 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1418 | B | 131242-WST02-DR-IP-1418 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1419 | B | 131242-WST02-DR-IP-1419 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1420 | B | 131242-WST02-DR-IP-1420 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1421 | B | 131242-WST02-DR-IP-1421 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1422 | B | 131242-WST02-DR-IP-1422 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1423 | B | 131242-WST02-DR-IP-1423 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1424 | B | 131242-WST02-DR-IP-1424 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1425 | B | 131242-WST02-DR-IP-1425 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1426 | B | 131242-WST02-DR-IP-1426 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1427 | B | 131242-WST02-DR-IP-1427 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1428 | B | 131242-WST02-DR-IP-1428 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1429 | B | 131242-WST02-DR-IP-1429 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1430 | B | 131242-WST02-DR-IP-1430 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1431 | B | 131242-WST02-DR-IP-1431 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1432 | B | 131242-WST02-DR-IP-1432 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1433 | B | 131242-WST02-DR-IP-1433 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1434 | B | 131242-WST02-DR-IP-1434 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1435 | B | 131242-WST02-DR-IP-1435 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1436 | B | 131242-WST02-DR-IP-1436 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1437 | B | 131242-WST02-DR-IP-1437 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1438 | B | 131242-WST02-DR-IP-1438 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1439 | B | 131242-WST02-DR-IP-1439 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1440 | B | 131242-WST02-DR-IP-1440 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1441 | B | 131242-WST02-DR-IP-1441 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1442 | B | 131242-WST02-DR-IP-1442 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1443 | B | 131242-WST02-DR-IP-1443 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1444 | B | 131242-WST02-DR-IP-1444 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1445 | B | 131242-WST02-DR-IP-1445 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1446 | B | 131242-WST02-DR-IP-1446 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1447 | B | 131242-WST02-DR-IP-1447 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1448 | B | 131242-WST02-DR-IP-1448 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1449 | B | 131242-WST02-DR-IP-1449 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1450 | B | 131242-WST02-DR-IP-1450 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1451 | B | 131242-WST02-DR-IP-1451 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1452 | B | 131242-WST02-DR-IP-1452 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1453 | B | 131242-WST02-DR-IP-1453 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1454 | B | 131242-WST02-DR-IP-1454 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1455 | B | 131242-WST02-DR-IP-1455 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1456 | B | 131242-WST02-DR-IP-1456 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1457 | B | 131242-WST02-DR-IP-1457 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1458 | B | 131242-WST02-DR-IP-1458 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1459 | B | 131242-WST02-DR-IP-1459 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1460 | B | 131242-WST02-DR-IP-1460 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1461 | B | 131242-WST02-DR-IP-1461 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1462 | B | 131242-WST02-DR-IP-1462 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1463 | B | 131242-WST02-DR-IP-1463 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1464 | B | 131242-WST02-DR-IP-1464 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1465 | B | 131242-WST02-DR-IP-1465 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1466 | B | 131242-WST02-DR-IP-1466 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1467 | B | 131242-WST02-DR-IP-1467 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1468 | B | 131242-WST02-DR-IP-1468 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1469 | B | 131242-WST02-DR-IP-1469 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1470 | B | 131242-WST02-DR-IP-1470 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1471 | B | 131242-WST02-DR-IP-1471 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1472 | B | 131242-WST02-DR-IP-1472 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1473 | B | 131242-WST02-DR-IP-1473 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1474 | B | 131242-WST02-DR-IP-1474 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1475 | B | 131242-WST02-DR-IP-1475 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1476 | B | 131242-WST02-DR-IP-1476 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1477 | B | 131242-WST02-DR-IP-1477 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1478 | B | 131242-WST02-DR-IP-1478 | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | 79 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-03
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-IP-1351 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1352 | B | 131242-WST02-DR-IP-1352 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1353 | B | 131242-WST02-DR-IP-1353 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1354 | B | 131242-WST02-DR-IP-1354 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1355 | B | 131242-WST02-DR-IP-1355 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1356 | B | 131242-WST02-DR-IP-1356 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1357 | B | 131242-WST02-DR-IP-1357 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1358 | B | 131242-WST02-DR-IP-1358 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1359 | B | 131242-WST02-DR-IP-1359 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1360 | B | 131242-WST02-DR-IP-1360 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1361 | B | 131242-WST02-DR-IP-1361 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1362 | B | 131242-WST02-DR-IP-1362 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1363 | B | 131242-WST02-DR-IP-1363 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1364 | B | 131242-WST02-DR-IP-1364 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1365 | B | 131242-WST02-DR-IP-1365 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1366 | B | 131242-WST02-DR-IP-1366 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1367 | B | 131242-WST02-DR-IP-1367 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1368 | B | 131242-WST02-DR-IP-1368 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1369 | B | 131242-WST02-DR-IP-1369 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1370 | B | 131242-WST02-DR-IP-1370 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1371 | B | 131242-WST02-DR-IP-1371 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1372 | B | 131242-WST02-DR-IP-1372 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1373 | B | 131242-WST02-DR-IP-1373 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1374 | B | 131242-WST02-DR-IP-1374 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1375 | B | 131242-WST02-DR-IP-1375 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1376 | B | 131242-WST02-DR-IP-1376 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1377 | B | 131242-WST02-DR-IP-1377 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1378 | B | 131242-WST02-DR-IP-1378 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1379 | B | 131242-WST02-DR-IP-1379 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1380 | B | 131242-WST02-DR-IP-1380 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1381 | B | 131242-WST02-DR-IP-1381 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1382 | B | 131242-WST02-DR-IP-1382 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1383 | B | 131242-WST02-DR-IP-1383 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1384 | B | 131242-WST02-DR-IP-1384 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1385 | B | 131242-WST02-DR-IP-1385 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1386 | B | 131242-WST02-DR-IP-1386 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1387 | B | 131242-WST02-DR-IP-1387 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1388 | B | 131242-WST02-DR-IP-1388 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1389 | B | 131242-WST02-DR-IP-1389 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1390 | B | 131242-WST02-DR-IP-1390 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1391 | B | 131242-WST02-DR-IP-1391 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1392 | B | 131242-WST02-DR-IP-1392 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1393 | B | 131242-WST02-DR-IP-1393 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1394 | B | 131242-WST02-DR-IP-1394 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1395 | B | 131242-WST02-DR-IP-1395 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1396 | B | 131242-WST02-DR-IP-1396 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1397 | B | 131242-WST02-DR-IP-1397 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1398 | B | 131242-WST02-DR-IP-1398 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1399 | B | 131242-WST02-DR-IP-1399 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1400 | B | 131242-WST02-DR-IP-1400 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1401 | B | 131242-WST02-DR-IP-1401 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1402 | B | 131242-WST02-DR-IP-1402 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1403 | B | 131242-WST02-DR-IP-1403 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1404 | B | 131242-WST02-DR-IP-1404 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1405 | B | 131242-WST02-DR-IP-1405 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1406 | B | 131242-WST02-DR-IP-1406 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1407 | B | 131242-WST02-DR-IP-1407 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1408 | B | 131242-WST02-DR-IP-1408 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1409 | B | 131242-WST02-DR-IP-1409 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1410 | B | 131242-WST02-DR-IP-1410 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1411 | B | 131242-WST02-DR-IP-1411 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1412 | B | 131242-WST02-DR-IP-1412 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1413 | B | 131242-WST02-DR-IP-1413 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1414 | B | 131242-WST02-DR-IP-1414 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1415 | B | 131242-WST02-DR-IP-1415 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1416 | B | 131242-WST02-DR-IP-1416 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1417 | B | 131242-WST02-DR-IP-1417 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1418 | B | 131242-WST02-DR-IP-1418 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1419 | B | 131242-WST02-DR-IP-1419 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1420 | B | 131242-WST02-DR-IP-1420 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1421 | B | 131242-WST02-DR-IP-1421 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1422 | B | 131242-WST02-DR-IP-1422 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1423 | B | 131242-WST02-DR-IP-1423 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1424 | B | 131242-WST02-DR-IP-1424 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1425 | B | 131242-WST02-DR-IP-1425 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1426 | B | 131242-WST02-DR-IP-1426 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1427 | B | 131242-WST02-DR-IP-1427 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1428 | B | 131242-WST02-DR-IP-1428 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1429 | B | 131242-WST02-DR-IP-1429 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1430 | B | 131242-WST02-DR-IP-1430 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1431 | B | 131242-WST02-DR-IP-1431 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1432 | B | 131242-WST02-DR-IP-1432 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1433 | B | 131242-WST02-DR-IP-1433 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1434 | B | 131242-WST02-DR-IP-1434 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1435 | B | 131242-WST02-DR-IP-1435 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1436 | B | 131242-WST02-DR-IP-1436 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1437 | B | 131242-WST02-DR-IP-1437 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1438 | B | 131242-WST02-DR-IP-1438 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1439 | B | 131242-WST02-DR-IP-1439 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1440 | B | 131242-WST02-DR-IP-1440 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1441 | B | 131242-WST02-DR-IP-1441 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1442 | B | 131242-WST02-DR-IP-1442 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1443 | B | 131242-WST02-DR-IP-1443 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1444 | B | 131242-WST02-DR-IP-1444 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1445 | B | 131242-WST02-DR-IP-1445 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1446 | B | 131242-WST02-DR-IP-1446 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1447 | B | 131242-WST02-DR-IP-1447 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1448 | B | 131242-WST02-DR-IP-1448 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1449 | B | 131242-WST02-DR-IP-1449 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1450 | B | 131242-WST02-DR-IP-1450 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1451 | B | 131242-WST02-DR-IP-1451 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1452 | B | 131242-WST02-DR-IP-1452 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1453 | B | 131242-WST02-DR-IP-1453 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1454 | B | 131242-WST02-DR-IP-1454 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1455 | B | 131242-WST02-DR-IP-1455 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1456 | B | 131242-WST02-DR-IP-1456 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1457 | B | 131242-WST02-DR-IP-1457 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1458 | B | 131242-WST02-DR-IP-1458 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1459 | B | 131242-WST02-DR-IP-1459 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1460 | B | 131242-WST02-DR-IP-1460 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1461 | B | 131242-WST02-DR-IP-1461 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1462 | B | 131242-WST02-DR-IP-1462 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1463 | B | 131242-WST02-DR-IP-1463 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1464 | B | 131242-WST02-DR-IP-1464 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1465 | B | 131242-WST02-DR-IP-1465 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1466 | B | 131242-WST02-DR-IP-1466 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1467 | B | 131242-WST02-DR-IP-1467 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1468 | B | 131242-WST02-DR-IP-1468 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1469 | B | 131242-WST02-DR-IP-1469 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1470 | B | 131242-WST02-DR-IP-1470 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1471 | B | 131242-WST02-DR-IP-1471 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1472 | B | 131242-WST02-DR-IP-1472 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1473 | B | 131242-WST02-DR-IP-1473 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1474 | B | 131242-WST02-DR-IP-1474 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1475 | B | 131242-WST02-DR-IP-1475 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1476 | B | 131242-WST02-DR-IP-1476 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1477 | B | 131242-WST02-DR-IP-1477 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1478 | B | 131242-WST02-DR-IP-1478 | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | 97 | Not Approved | YES | 2025-12-31 | NO | Resubmitted | 0 |  |  | 001148 | 2025-03-21 | 2025-07-29 | B | NAP | Not Approved | 2 | "SSN RIO 0202 GA & Wiring Diagram" |  | 2025-07
001149 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | B | 1397 | 0 | 131242-WSW41-DS-B-1397 | 2025-03-21 | Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance) | Approved | 2025-04-18 | 2025-05-25 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001149 | 2025-03-21 | 2025-03-21 | 0 | APP | Approved | 1 | "Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance)" |  | 2025-03
001150 | 00 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 0 | 131242-WSD11-RT-S-0002 | 2025-03-24 | Report of Project Safety Review for THP Trains Installation | Approved with Comments | 2025-04-21 | 2025-05-13 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001150 | 2025-03-24 | 2025-09-03 | 2 | AWC | Approved with Comments | 3 | "Report of Project Safety Review for THP Trains Installation" |  | 2025-03
001150 | 01 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 1 | 131242-WSD11-RT-S-0002 | 2025-06-18 | Report of Project Safety Review for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-08 | 2025-07-04 | 12 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001150 | 2025-03-24 | 2025-09-03 | 2 | AWC | Approved with Comments | 3 | "Report of Project Safety Review for THP Trains Installation" |  | 2025-06
001150 | 02 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 2 | 131242-WSD11-RT-S-0002 | 2025-09-03 | Report of Project Safety Review for THP Trains Installation | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-10-14 | 29 | Approved with Comments | YES | 2025-11-03 | NO | Resubmitted | 0 |  |  | 001150 | 2025-03-24 | 2025-09-03 | 2 | AWC | Approved with Comments | 3 | "Report of Project Safety Review for THP Trains Installation" |  | 2025-09
001151 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0059 | 0 | 131242-WSW41-QA-M-0059 | 2025-03-24 | FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch) | NA | 2025-04-21 | 2025-09-02 | 116 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001151 | 2025-03-24 | 2025-03-24 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" |  | 2025-03
001152 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0028 | 0 | 131242-WSW41-SP-C-0028 | 2025-03-24 | Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) | Approved | 2025-04-21 | 2025-05-09 | 34 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001152 | 2025-03-24 | 2025-03-24 | 0 | APP | Approved | 1 | "Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) " |  | 2025-03
001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | CL | S | 0003 | 0 | 131242-WST02-CL-S-0003 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001153 | 2025-03-24 | 2025-03-24 | 0 | APP | Approved | 1 | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" |  | 2025-03
001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | DR | S | 5603 | A.3 | 131242-WST02-DR-S-5603 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001153&&001528 | 2025-03-24 | 2025-07-24 | A | APP | Not Approved | 2 | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " |  | 2025-03
001154 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 0 | 131242-WST02-VI-BF-0001 | 2025-03-24 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-04-21 | 2025-05-06 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001154 | 2025-03-24 | 2025-08-12 | 2 | NAP | Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" |  | 2025-03
001154 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 1 | 131242-WST02-VI-BF-0001 | 2025-06-04 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-06-24 | 2025-07-08 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001154 | 2025-03-24 | 2025-08-12 | 2 | NAP | Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" |  | 2025-06
001154 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 2 | 131242-WST02-VI-BF-0001 | 2025-08-12 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-09-01 | 2026-01-05 | 104 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001154 | 2025-03-24 | 2025-08-12 | 2 | APP | Approved | 3 | "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" |  | 2025-08
001155 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 0 | 131242-WST02-CD-I-0012 | 2025-03-24 | SSN -RIO PANEL 0203- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-21 | 2025-04-27 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001155 | 2025-03-24 | 2025-06-25 | 1 | NAP | Approved with Comments | 2 | "SSN -RIO PANEL 0203- I/O List " |  | 2025-03
001155 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 1 | 131242-WST02-CD-I-0012 | 2025-06-25 | SSN -RIO PANEL 0203- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-02 | 49 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001155 | 2025-03-24 | 2025-06-25 | 1 | AWC | Approved with Comments | 2 | "SSN -RIO PANEL 0203- I/O List " |  | 2025-06
001156 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | A | 0005 | 0 | 131242-WSW41-MS-A-0005 | 2025-03-24 | MSRA for Waterproofing Works | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-21 | 2025-04-15 | 16 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001156 | 2025-03-24 | 2025-03-24 | 0 | NAP | Not Approved | 1 | "MSRA for Waterproofing Works" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | A | 131242-WST02-DR-EI-7200 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7201 | A | 131242-WST02-DR-EI-7201 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7202 | A | 131242-WST02-DR-EI-7202 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7203 | A | 131242-WST02-DR-EI-7203 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7204 | A | 131242-WST02-DR-EI-7204 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7205 | A | 131242-WST02-DR-EI-7205 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7206 | A | 131242-WST02-DR-EI-7206 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7207 | A | 131242-WST02-DR-EI-7207 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7208 | A | 131242-WST02-DR-EI-7208 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7209 | A | 131242-WST02-DR-EI-7209 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7220 | A | 131242-WST02-DR-EI-7220 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7221 | A | 131242-WST02-DR-EI-7221 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7222 | A | 131242-WST02-DR-EI-7222 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7223 | A | 131242-WST02-DR-EI-7223 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7224 | A | 131242-WST02-DR-EI-7224 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7225 | A | 131242-WST02-DR-EI-7225 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7226 | A | 131242-WST02-DR-EI-7226 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7227 | A | 131242-WST02-DR-EI-7227 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7228 | A | 131242-WST02-DR-EI-7228 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7229 | A | 131242-WST02-DR-EI-7229 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3066 | A | 131242-WST02-DR-EP-3066 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3067 | A | 131242-WST02-DR-EP-3067 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3068 | A | 131242-WST02-DR-EP-3068 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3069 | A | 131242-WST02-DR-EP-3069 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3070 | A | 131242-WST02-DR-EP-3070 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3071 | A | 131242-WST02-DR-EP-3071 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3072 | A | 131242-WST02-DR-EP-3072 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3073 | A | 131242-WST02-DR-EP-3073 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3074 | A | 131242-WST02-DR-EP-3074 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3075 | A | 131242-WST02-DR-EP-3075 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3076 | A | 131242-WST02-DR-EP-3076 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3077 | A | 131242-WST02-DR-EP-3077 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3078 | A | 131242-WST02-DR-EP-3078 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3079 | A | 131242-WST02-DR-EP-3079 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7148 | A | 131242-WST02-DR-EP-7148 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7149 | A | 131242-WST02-DR-EP-7149 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7150 | A | 131242-WST02-DR-EP-7150 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7151 | A | 131242-WST02-DR-EP-7151 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7152 | A | 131242-WST02-DR-EP-7152 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7153 | A | 131242-WST02-DR-EP-7153 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7154 | A | 131242-WST02-DR-EP-7154 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7155 | A | 131242-WST02-DR-EP-7155 | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | NAP | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-03
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | B | 131242-WST02-DR-EI-7200 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7201 | B | 131242-WST02-DR-EI-7201 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7202 | B | 131242-WST02-DR-EI-7202 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7203 | B | 131242-WST02-DR-EI-7203 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7204 | B | 131242-WST02-DR-EI-7204 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7205 | B | 131242-WST02-DR-EI-7205 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7206 | B | 131242-WST02-DR-EI-7206 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7207 | B | 131242-WST02-DR-EI-7207 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7208 | B | 131242-WST02-DR-EI-7208 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7209 | B | 131242-WST02-DR-EI-7209 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7220 | B | 131242-WST02-DR-EI-7220 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7221 | B | 131242-WST02-DR-EI-7221 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7222 | B | 131242-WST02-DR-EI-7222 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7223 | B | 131242-WST02-DR-EI-7223 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7224 | B | 131242-WST02-DR-EI-7224 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7225 | B | 131242-WST02-DR-EI-7225 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7226 | B | 131242-WST02-DR-EI-7226 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7227 | B | 131242-WST02-DR-EI-7227 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7228 | B | 131242-WST02-DR-EI-7228 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7229 | B | 131242-WST02-DR-EI-7229 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3066 | B | 131242-WST02-DR-EP-3066 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3067 | B | 131242-WST02-DR-EP-3067 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3068 | B | 131242-WST02-DR-EP-3068 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3069 | B | 131242-WST02-DR-EP-3069 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3070 | B | 131242-WST02-DR-EP-3070 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3071 | B | 131242-WST02-DR-EP-3071 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3072 | B | 131242-WST02-DR-EP-3072 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3073 | B | 131242-WST02-DR-EP-3073 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3074 | B | 131242-WST02-DR-EP-3074 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3075 | B | 131242-WST02-DR-EP-3075 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3076 | B | 131242-WST02-DR-EP-3076 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3077 | B | 131242-WST02-DR-EP-3077 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3078 | B | 131242-WST02-DR-EP-3078 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3079 | B | 131242-WST02-DR-EP-3079 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7148 | B | 131242-WST02-DR-EP-7148 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7149 | B | 131242-WST02-DR-EP-7149 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7150 | B | 131242-WST02-DR-EP-7150 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7151 | B | 131242-WST02-DR-EP-7151 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7152 | B | 131242-WST02-DR-EP-7152 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7153 | B | 131242-WST02-DR-EP-7153 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7154 | B | 131242-WST02-DR-EP-7154 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7155 | B | 131242-WST02-DR-EP-7155 | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | 33 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001157 | 2025-03-25 | 2025-07-21 | B | AWC | Approved with Comments | 2 | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" |  | 2025-07
001158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0010 | 0 | 131242-WST02-RT-E-0010 | 2025-03-25 | SSN Protection Coordination Study Report | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-22 | 2025-05-27 | 45 | Approved with Comments | YES | 2025-06-16 | NO | Resubmitted | 0 |  |  | 001158 | 2025-03-25 | 2025-03-25 | 0 | AWC | Approved with Comments | 1 | "SSN Protection Coordination Study Report" |  | 2025-03
001159 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0005 | 0 | 131242-WSD11-RT-E-0005 | 2025-03-25 | THP Protection Coordination Study Report | : Rev 0: Approved with comments. To revise and resubmit | 2025-04-22 | 2025-05-27 | 45 | Approved with Comments | YES | 2025-06-16 | NO | Resubmitted | 0 |  |  | 001159 | 2025-03-25 | 2025-03-25 | 0 | AWC | Approved with Comments | 1 | "THP Protection Coordination Study Report" |  | 2025-03
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7201 | A | 131242-WSD11-DR-I-7201 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " |  | 2025-03
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7202 | A | 131242-WSD11-DR-I-7202 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " |  | 2025-03
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7203 | A | 131242-WSD11-DR-I-7203 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " |  | 2025-03
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7204 | A | 131242-WSD11-DR-I-7204 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " |  | 2025-03
001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7205 | A | 131242-WSD11-DR-I-7205 | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | 37 | Approved with Comments | YES | 2025-06-04 | NO | Resubmitted | 0 |  |  | 001160 | 2025-03-25 | 2025-03-25 | A | AWC | Approved with Comments | 1 | "THP UPS DB SLD Drawing " |  | 2025-03
001161 | 00 | Charles | CSA | NA | 131242 | WSW41 | MS | A | 0001 | 0 | 131242-WSW41-MS-A-0001 | 2025-03-25 | MSRA and SWP for MEICA OPENING on Block-wall | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 | 15 | Approved with Comments | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001161 | 2025-03-25 | 2025-03-25 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for MEICA OPENING on Block-wall " |  | 2025-03
001162 | 00 | N.Kumar | CSA | NA | 131242 | WSW41 | MS | C | 0027 | 0 | 131242-WSW41-MS-C-0027 | 2025-03-25 | Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 | 15 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001162 | 2025-03-25 | 2025-03-25 | 0 | NAP | Not Approved | 1 | "Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) " |  | 2025-03
001163 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0008 | 0 | 131242-WSW41-PO-E-0008 | 2025-03-25 | Unpriced PO for Cable Raceway (Jiangsu HDMann) | Rev 0: For information. | 2025-04-22 | 2025-05-06 | 30 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001163 | 2025-03-25 | 2025-03-25 | 0 | INF | For Information | 1 | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" |  | 2025-03
001164 | 00 | Aaron | CSA | NA | 131242 | WSW41 | VI | A | 0005 | 0 | 131242-WSW41-VI-A-0005 | 2025-03-25 | Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd) | R0: Approved | 2025-04-22 | 2025-04-15 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001164 | 2025-03-25 | 2025-03-25 | 0 | APP | Approved | 1 | "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | A | 131242-WST02-DR-IC-3001 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3002 | A | 131242-WST02-DR-IC-3002 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3003 | A | 131242-WST02-DR-IC-3003 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3004 | A | 131242-WST02-DR-IC-3004 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3005 | A | 131242-WST02-DR-IC-3005 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3006 | A | 131242-WST02-DR-IC-3006 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3007 | A | 131242-WST02-DR-IC-3007 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3008 | A | 131242-WST02-DR-IC-3008 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3009 | A | 131242-WST02-DR-IC-3009 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3010 | A | 131242-WST02-DR-IC-3010 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3011 | A | 131242-WST02-DR-IC-3011 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3012 | A | 131242-WST02-DR-IC-3012 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3013 | A | 131242-WST02-DR-IC-3013 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3014 | A | 131242-WST02-DR-IC-3014 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3015 | A | 131242-WST02-DR-IC-3015 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3016 | A | 131242-WST02-DR-IC-3016 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3017 | A | 131242-WST02-DR-IC-3017 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3018 | A | 131242-WST02-DR-IC-3018 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3019 | A | 131242-WST02-DR-IC-3019 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3020 | A | 131242-WST02-DR-IC-3020 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3021 | A | 131242-WST02-DR-IC-3021 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3022 | A | 131242-WST02-DR-IC-3022 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3023 | A | 131242-WST02-DR-IC-3023 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3024 | A | 131242-WST02-DR-IC-3024 | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | 18 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-03
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | B | 131242-WST02-DR-IC-3001 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3002 | B | 131242-WST02-DR-IC-3002 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3003 | B | 131242-WST02-DR-IC-3003 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3004 | B | 131242-WST02-DR-IC-3004 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3005 | B | 131242-WST02-DR-IC-3005 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3006 | B | 131242-WST02-DR-IC-3006 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3007 | B | 131242-WST02-DR-IC-3007 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3008 | B | 131242-WST02-DR-IC-3008 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3009 | B | 131242-WST02-DR-IC-3009 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3010 | B | 131242-WST02-DR-IC-3010 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3011 | B | 131242-WST02-DR-IC-3011 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3012 | B | 131242-WST02-DR-IC-3012 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3013 | B | 131242-WST02-DR-IC-3013 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3014 | B | 131242-WST02-DR-IC-3014 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3015 | B | 131242-WST02-DR-IC-3015 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3016 | B | 131242-WST02-DR-IC-3016 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3017 | B | 131242-WST02-DR-IC-3017 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3018 | B | 131242-WST02-DR-IC-3018 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3019 | B | 131242-WST02-DR-IC-3019 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3020 | B | 131242-WST02-DR-IC-3020 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3021 | B | 131242-WST02-DR-IC-3021 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3022 | B | 131242-WST02-DR-IC-3022 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3023 | B | 131242-WST02-DR-IC-3023 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3024 | B | 131242-WST02-DR-IC-3024 | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | 77 | Not Approved | YES | 2025-12-29 | NO | Resubmitted | 0 |  |  | 001165 | 2025-03-25 | 2025-08-22 | B | NAP | Not Approved | 2 | "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" |  | 2025-08
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | A | 131242-WST02-DR-IP-2101 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2102 | A | 131242-WST02-DR-IP-2102 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2103 | A | 131242-WST02-DR-IP-2103 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2104 | A | 131242-WST02-DR-IP-2104 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2105 | A | 131242-WST02-DR-IP-2105 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2106 | A | 131242-WST02-DR-IP-2106 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2107 | A | 131242-WST02-DR-IP-2107 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2108 | A | 131242-WST02-DR-IP-2108 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2109 | A | 131242-WST02-DR-IP-2109 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2110 | A | 131242-WST02-DR-IP-2110 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2111 | A | 131242-WST02-DR-IP-2111 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2112 | A | 131242-WST02-DR-IP-2112 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2113 | A | 131242-WST02-DR-IP-2113 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2114 | A | 131242-WST02-DR-IP-2114 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2115 | A | 131242-WST02-DR-IP-2115 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2116 | A | 131242-WST02-DR-IP-2116 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2117 | A | 131242-WST02-DR-IP-2117 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2118 | A | 131242-WST02-DR-IP-2118 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | NAP | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2119 | A | 131242-WST02-DR-IP-2119 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-03-25 | A | NAP | Not Approved | 1 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2120 | A | 131242-WST02-DR-IP-2120 | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | 24 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-03-25 | A | NAP | Not Approved | 1 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-03
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | D | 131242-WST02-DR-IP-2101 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-02 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2102 | D | 131242-WST02-DR-IP-2102 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2103 | D | 131242-WST02-DR-IP-2103 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2104 | D | 131242-WST02-DR-IP-2104 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2105 | D | 131242-WST02-DR-IP-2105 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2106 | D | 131242-WST02-DR-IP-2106 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2107 | D | 131242-WST02-DR-IP-2107 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2108 | D | 131242-WST02-DR-IP-2108 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2109 | D | 131242-WST02-DR-IP-2109 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2110 | D | 131242-WST02-DR-IP-2110 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2111 | D | 131242-WST02-DR-IP-2111 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2112 | D | 131242-WST02-DR-IP-2112 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2113 | D | 131242-WST02-DR-IP-2113 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2114 | D | 131242-WST02-DR-IP-2114 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2115 | D | 131242-WST02-DR-IP-2115 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2116 | D | 131242-WST02-DR-IP-2116 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2117 | D | 131242-WST02-DR-IP-2117 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2118 | D | 131242-WST02-DR-IP-2118 | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | 31 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001166 | 2025-03-25 | 2025-12-15 | D | AWC | Approved with Comments | 2 | "SSN Panel (FIOP) - GA & Wiring Drawings" |  | 2025-12
001167 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 0 | 131242-WSD11-DS-I-0006 | 2025-03-25 | Datasheet for Electromagnetic Flow Meter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-07-10 | 77 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001167 | 2025-03-25 | 2025-10-16 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Electromagnetic Flow Meter " |  | 2025-03
001167 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 1 | 131242-WSD11-DS-I-0006 | 2025-10-16 | Datasheet for Electromagnetic Flow Meter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-27 | 30 | Approved with Comments | YES | 2025-12-17 | NO | Resubmitted | 0 |  |  | 001167 | 2025-03-25 | 2025-10-16 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Electromagnetic Flow Meter " |  | 2025-10
001168 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0006 | 0 | 131242-WST02-VI-A-0006 | 2025-03-26 | Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd. | Approved | 2025-04-23 | 2025-04-11 | 12 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001168 | 2025-03-26 | 2025-03-26 | 0 | APP | Approved | 1 | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." |  | 2025-03
001169 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0058 | 0 | 131242-WSW41-LT-PM-0058 | 2025-03-26 | Consent to Potential Acquisition of CES Construction by OKH | For Information | 2025-04-23 | 2025-04-05 | 8 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001169 | 2025-03-26 | 2025-03-26 | 0 | INF | For Information | 1 | "Consent to Potential Acquisition of CES Construction by OKH " |  | 2025-03
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 0 | 131242-WST02-CL-P-5701 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-03
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5702 | 0 | 131242-WST02-CL-P-5702 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-03
001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5703 | 0 | 131242-WST02-CL-P-5703 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-03
001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5701 | 0 | 131242-WST02-DS-M-5701 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-03
001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5702 | 0 | 131242-WST02-DS-M-5702 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-03
001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5703 | 0 | 131242-WST02-DS-M-5703 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | 22 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | AWC | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-03
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 1 | 131242-WST02-CL-P-5701 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 0 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-07
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5702 | 1 | 131242-WST02-CL-P-5702 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-07
001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5703 | 1 | 131242-WST02-CL-P-5703 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-07
001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5701 | 1 | 131242-WST02-DS-M-5701 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-07
001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5702 | 1 | 131242-WST02-DS-M-5702 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-07
001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5703 | 1 | 131242-WST02-DS-M-5703 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-22 | NO | Overdue | 53 |  |  | 001170 | 2025-03-27 | 2025-07-07 | 1 | PEN | Approved with Comments | 2 | "SSN FCV Calculation and Datasheet" |  | 2025-07
001171 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 0 | 131242-WSD11-DS-I-0007 | 2025-03-27 | Datasheet for Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | 77 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001171 | 2025-03-27 | 2025-10-16 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Level Transmitter" |  | 2025-03
001171 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 1 | 131242-WSD11-DS-I-0007 | 2025-10-16 | Datasheet for Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-05 | 14 | Approved with Comments | YES | 2025-11-25 | NO | Resubmitted | 0 |  |  | 001171 | 2025-03-27 | 2025-10-16 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Level Transmitter" |  | 2025-10
001172 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 0 | 131242-WST02-DS-M-5391 | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | 1 | AWC | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" |  | 2025-03
001172 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5391 | A | 131242-WST02-DR-M-5391 | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | 39 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | B | AWC | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" |  | 2025-03
001172 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 1 | 131242-WST02-DS-M-5391 | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-06 |  | 115 | Awaiting S.O.'s response | YES | 2025-12-04 | NO | Overdue | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | 1 | PEN | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" |  | 2025-10
001172 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5391 | B | 131242-WST02-DR-M-5391 | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-14 |  | 115 | Awaiting S.O.'s response | YES | 2025-12-04 | NO | Overdue | 0 |  |  | 001172 | 2025-03-27 | 2025-10-18 | B | PEN | Approved with Comments | 2 | "Datasheet & GA drawing for sampling pump" |  | 2025-10
001173 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 0 | 131242-WSD11-DS-I-0011 | 2025-03-27 | Datasheet for Temperature Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | 77 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001173 | 2025-03-27 | 2026-01-21 | 1 | NAP | Not Approved | 3 | "Datasheet for Temperature Transmitter " |  | 2025-03
001173 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1_Superceded | 131242-WSD11-DS-I-0011 | 2025-10-27 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2025-11-14 | 2025-12-09 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001173 | 2025-03-27 | 2026-01-21 | 1 | NAP | Not Approved | 3 | "Datasheet for Temperature Transmitter " |  | 2025-10
001173 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1 | 131242-WSD11-DS-I-0011 | 2026-01-21 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2026-02-10 |  | 48 | Awaiting S.O.'s response | YES | 2026-03-10 | NO | Overdue | 0 |  |  | 001173 | 2025-03-27 | 2026-01-21 | 1 | PEN | Not Approved | 3 | "Datasheet for Temperature Transmitter " |  | 2026-01
001174 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-E-0029 | 2025-03-27 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-24 | 2025-06-17 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001174 | 2025-03-27 | 2025-07-10 | 0 | AWC | Approved with Comments | 2 | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " |  | 2025-03
001174 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-E-0029 | 2025-07-10 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached filed for comments. | 2025-07-30 | 2025-07-17 | 5 | Approved with Comments | YES | 2025-08-06 | NO | Resubmitted | 0 |  |  | 001174 | 2025-03-27 | 2025-07-10 | 0 | AWC | Approved with Comments | 2 | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " |  | 2025-07
001175 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0060 | 0 | 131242-WSW41-QA-M-0060 | 2025-03-27 | FAT Report for Compressor Pipe support in Bio solid building | NA | 2025-04-24 | 2025-09-02 | 113 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001175 | 2025-03-27 | 2025-03-27 | 0 | AWC | Approved with Comments | 1 | " FAT Report for Compressor Pipe support in Bio solid building" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | A | 131242-WST02-DR-IP-1025 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | A | 131242-WST02-DR-IP-1026 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | A | 131242-WST02-DR-IP-1027 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | A | 131242-WST02-DR-IP-1028 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | A | 131242-WST02-DR-IP-1029 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | A | 131242-WST02-DR-IP-1030 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | A | 131242-WST02-DR-IP-1031 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | A | 131242-WST02-DR-IP-1032 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | A | 131242-WST02-DR-IP-1033 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | A | 131242-WST02-DR-IP-1034 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | A | 131242-WST02-DR-IP-1035 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | A | 131242-WST02-DR-IP-1036 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | A | 131242-WST02-DR-IP-1037 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | A | 131242-WST02-DR-IP-1038 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | A | 131242-WST02-DR-IP-1039 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | A | 131242-WST02-DR-IP-1040 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | A | 131242-WST02-DR-IP-1041 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | A | 131242-WST02-DR-IP-1042 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | A | 131242-WST02-DR-IP-1043 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | A | 131242-WST02-DR-IP-1044 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | A | 131242-WST02-DR-IP-1045 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | A | 131242-WST02-DR-IP-1046 | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | 28 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-03
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-IP-1025 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | B | 131242-WST02-DR-IP-1026 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | B | 131242-WST02-DR-IP-1027 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | B | 131242-WST02-DR-IP-1028 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | B | 131242-WST02-DR-IP-1029 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | B | 131242-WST02-DR-IP-1030 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | B | 131242-WST02-DR-IP-1031 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | B | 131242-WST02-DR-IP-1032 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | B | 131242-WST02-DR-IP-1033 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | B | 131242-WST02-DR-IP-1034 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | B | 131242-WST02-DR-IP-1035 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | B | 131242-WST02-DR-IP-1036 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | B | 131242-WST02-DR-IP-1037 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | B | 131242-WST02-DR-IP-1038 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | B | 131242-WST02-DR-IP-1039 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | B | 131242-WST02-DR-IP-1040 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | B | 131242-WST02-DR-IP-1041 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | B | 131242-WST02-DR-IP-1042 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | B | 131242-WST02-DR-IP-1043 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | B | 131242-WST02-DR-IP-1044 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | B | 131242-WST02-DR-IP-1045 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | B | 131242-WST02-DR-IP-1046 | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | 58 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-07
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-IP-1025 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | B | 131242-WST02-DR-IP-1026 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | B | 131242-WST02-DR-IP-1027 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | B | 131242-WST02-DR-IP-1028 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | B | 131242-WST02-DR-IP-1029 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | B | 131242-WST02-DR-IP-1030 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | B | 131242-WST02-DR-IP-1031 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | B | 131242-WST02-DR-IP-1032 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | B | 131242-WST02-DR-IP-1033 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | B | 131242-WST02-DR-IP-1034 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | B | 131242-WST02-DR-IP-1035 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | B | 131242-WST02-DR-IP-1036 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | B | 131242-WST02-DR-IP-1037 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | B | 131242-WST02-DR-IP-1038 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | B | 131242-WST02-DR-IP-1039 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | B | 131242-WST02-DR-IP-1040 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | B | 131242-WST02-DR-IP-1041 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | B | 131242-WST02-DR-IP-1042 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | B | 131242-WST02-DR-IP-1043 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | B | 131242-WST02-DR-IP-1044 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | B | 131242-WST02-DR-IP-1045 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | B | 131242-WST02-DR-IP-1046 | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | 21 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001176 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (ECCP-1001)- GA & Wiring Drawings" |  | 2025-11
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | A | 131242-WST02-DR-IP-1901 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | A | 131242-WST02-DR-IP-1902 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | A | 131242-WST02-DR-IP-1903 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | A | 131242-WST02-DR-IP-1904 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | A | 131242-WST02-DR-IP-1905 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | A | 131242-WST02-DR-IP-1906 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | A | 131242-WST02-DR-IP-1907 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | A | 131242-WST02-DR-IP-1908 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | A | 131242-WST02-DR-IP-1909 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | A | 131242-WST02-DR-IP-1910 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | A | 131242-WST02-DR-IP-1911 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | A | 131242-WST02-DR-IP-1912 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | A | 131242-WST02-DR-IP-1913 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | A | 131242-WST02-DR-IP-1914 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | A | 131242-WST02-DR-IP-1915 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | A | 131242-WST02-DR-IP-1916 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | A | 131242-WST02-DR-IP-1917 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | A | 131242-WST02-DR-IP-1918 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | A | 131242-WST02-DR-IP-1919 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | A | 131242-WST02-DR-IP-1920 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | A | 131242-WST02-DR-IP-1921 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | A | 131242-WST02-DR-IP-1922 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | A | 131242-WST02-DR-IP-1923 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | A | 131242-WST02-DR-IP-1924 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | A | 131242-WST02-DR-IP-1925 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | A | 131242-WST02-DR-IP-1926 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | A | 131242-WST02-DR-IP-1927 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | A | 131242-WST02-DR-IP-1928 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | A | 131242-WST02-DR-IP-1929 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | A | 131242-WST02-DR-IP-1930 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | A | 131242-WST02-DR-IP-1931 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | A | 131242-WST02-DR-IP-1932 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | A | 131242-WST02-DR-IP-1933 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | A | 131242-WST02-DR-IP-1934 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | A | 131242-WST02-DR-IP-1935 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | A | 131242-WST02-DR-IP-1936 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | A | 131242-WST02-DR-IP-1937 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | A | 131242-WST02-DR-IP-1938 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | A | 131242-WST02-DR-IP-1939 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | A | 131242-WST02-DR-IP-1940 | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | 35 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-03
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | B | 131242-WST02-DR-IP-1917 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | B | 131242-WST02-DR-IP-1918 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | B | 131242-WST02-DR-IP-1919 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | B | 131242-WST02-DR-IP-1920 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | B | 131242-WST02-DR-IP-1921 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | B | 131242-WST02-DR-IP-1922 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | B | 131242-WST02-DR-IP-1923 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | B | 131242-WST02-DR-IP-1924 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | B | 131242-WST02-DR-IP-1925 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | B | 131242-WST02-DR-IP-1926 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | B | 131242-WST02-DR-IP-1927 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | B | 131242-WST02-DR-IP-1928 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | B | 131242-WST02-DR-IP-1929 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | B | 131242-WST02-DR-IP-1930 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | B | 131242-WST02-DR-IP-1931 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | B | 131242-WST02-DR-IP-1932 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | B | 131242-WST02-DR-IP-1933 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | B | 131242-WST02-DR-IP-1934 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | B | 131242-WST02-DR-IP-1935 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | B | 131242-WST02-DR-IP-1936 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | B | 131242-WST02-DR-IP-1937 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | B | 131242-WST02-DR-IP-1938 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | B | 131242-WST02-DR-IP-1939 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | B | 131242-WST02-DR-IP-1940 | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | 53 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-07
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001177&&001536 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 4 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | B | 131242-WST02-DR-IP-1917 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | B | 131242-WST02-DR-IP-1918 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | B | 131242-WST02-DR-IP-1919 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | B | 131242-WST02-DR-IP-1920 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | B | 131242-WST02-DR-IP-1921 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | B | 131242-WST02-DR-IP-1922 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | B | 131242-WST02-DR-IP-1923 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | B | 131242-WST02-DR-IP-1924 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | B | 131242-WST02-DR-IP-1925 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | B | 131242-WST02-DR-IP-1926 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | B | 131242-WST02-DR-IP-1927 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | B | 131242-WST02-DR-IP-1928 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | B | 131242-WST02-DR-IP-1929 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | B | 131242-WST02-DR-IP-1930 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | B | 131242-WST02-DR-IP-1931 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | B | 131242-WST02-DR-IP-1932 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | B | 131242-WST02-DR-IP-1933 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | B | 131242-WST02-DR-IP-1934 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | B | 131242-WST02-DR-IP-1935 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | B | 131242-WST02-DR-IP-1936 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | B | 131242-WST02-DR-IP-1937 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | B | 131242-WST02-DR-IP-1938 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | B | 131242-WST02-DR-IP-1939 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | B | 131242-WST02-DR-IP-1940 | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001177 | 2025-03-28 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" |  | 2025-11
001178 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0061 | 0 | 131242-WSD11-QA-M-0061 | 2025-03-28 | Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI) | NA | 2025-04-25 | 2025-09-08 | 116 | Approved with Comments | YES | 2025-09-26 | NO | Resubmitted | 0 |  |  | 001178 | 2025-03-28 | 2025-03-28 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI)" |  | 2025-03
001179 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0008 | 0 | 131242-WSD11-DS-I-0008 | 2025-04-01 | Datasheet for Pressure Transmitter | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001179 | 2025-04-01 | 2025-10-16 | 1 | NAP | Not Approved | 2 | "Datasheet for Pressure Transmitter" |  | 2025-04
001179 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0008 | 1 | 131242-WSD11-DS-I-0008 | 2025-10-16 | Datasheet for Pressure Transmitter | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-12-02 | 33 | Not Approved | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001179 | 2025-04-01 | 2025-10-16 | 1 | NAP | Not Approved | 2 | "Datasheet for Pressure Transmitter" |  | 2025-10
001180 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0009 | 0 | 131242-WSD11-DS-I-0009 | 2025-04-01 | Datasheet for Tuning Fork Level Switch | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001180 | 2025-04-01 | 2025-09-10 | 1 | NAP | Not Approved | 2 | "Datasheet for Tuning Fork Level Switch " |  | 2025-04
001180 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0009 | 1 | 131242-WSD11-DS-I-0009 | 2025-09-10 | Datasheet for Tuning Fork Level Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-09-30 | 2025-12-02 | 59 | Not Approved | YES | 2025-12-22 | NO | Resubmitted | 0 |  |  | 001180 | 2025-04-01 | 2025-09-10 | 1 | NAP | Not Approved | 2 | "Datasheet for Tuning Fork Level Switch " |  | 2025-09
001181 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 0 | 131242-WSD11-DS-I-0010 | 2025-04-01 | Datasheet for Pressure Switch | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | 51 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001181 | 2025-04-01 | 2026-01-30 | 2 | NAP | Not Approved | 3 | "Datasheet for Pressure Switch" |  | 2025-04
001181 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 1 | 131242-WSD11-DS-I-0010 | 2025-09-10 | Datasheet for Pressure Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-30 | 2025-12-02 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001181 | 2025-04-01 | 2026-01-30 | 2 | NAP | Not Approved | 3 | "Datasheet for Pressure Switch" |  | 2025-09
001181 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 2 | 131242-WSD11-DS-I-0010 | 2026-01-30 | Datasheet for Pressure Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-19 |  | 41 | Awaiting S.O.'s response | YES | 2026-03-19 | NO | Overdue | 0 |  |  | 001181 | 2025-04-01 | 2026-01-30 | 2 | PEN | Not Approved | 3 | "Datasheet for Pressure Switch" |  | 2026-01
001182 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1017 | 0 | 131242-WSW41-VI-M-1017 | 2025-04-01 | Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-29 | 2025-06-23 | 59 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001182 | 2025-04-01 | 2025-04-01 | 0 | AWC | Approved with Comments | 1 | "Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe)" |  | 2025-04
001183 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1007 | 0 | 131242-WSW41-SH-M-1007 | 2025-04-01 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | Rev 0: Not approved - Revise and Resubmit | 2025-04-29 | 2025-06-23 | 59 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001183 | 2025-04-01 | 2025-07-22 | 1 | NAP | Approved | 2 | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" |  | 2025-04
001183 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1007 | 1 | 131242-WSW41-SH-M-1007 | 2025-07-22 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | Approved | 2025-08-11 | 2025-08-01 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001183 | 2025-04-01 | 2025-07-22 | 1 | APP | Approved | 2 | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" |  | 2025-07
001184 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0061 | 0 | 131242-WSW41-QA-M-0061 | 2025-04-02 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch) | Approved | 2025-04-30 | 2025-05-21 | 35 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001184 | 2025-04-02 | 2025-04-02 | 0 | APP | Approved | 1 | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch)" |  | 2025-04
001185 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0062 | 0 | 131242-WSW41-QA-M-0062 | 2025-04-02 | FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch) | NA | 2025-04-30 | 2025-09-02 | 109 | Approved with Comments | YES | 2025-09-22 | NO | Resubmitted | 0 |  |  | 001185 | 2025-04-02 | 2025-04-02 | 0 | AWC | Approved with Comments | 1 | "FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch)" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A1 | 131242-WST02-DR-A-1000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A1 | 131242-WST02-DR-A-1001_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A1 | 131242-WST02-DR-A-1002_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A1 | 131242-WST02-DR-A-1003_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A1 | 131242-WST02-DR-A-1004_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A1 | 131242-WST02-DR-A-1006_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A1 | 131242-WST02-DR-A-1009_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A1 | 131242-WST02-DR-A-2000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A1 | 131242-WST02-DR-A-2001_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A1 | 131242-WST02-DR-A-2002_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A1 | 131242-WST02-DR-A-2003_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A | 131242-WST02-DR-A-2007_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A | 131242-WST02-DR-A-3000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9000_BCA_BP | A1 | 131242-WST02-DR-A-9000_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2025-04-02 | A1 | NAP | Not Approved | 1 | "SSN BCA BP Submission" |  | 2025-04
001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9001_BCA_BP | A1 | 131242-WST02-DR-A-9001_BCA_BP | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | 50 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2025-04-02 | A1 | NAP | Not Approved | 1 | "SSN BCA BP Submission" |  | 2025-04
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-11-18 | 2026-01-20 | A | NAP | Not Approved | 3 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | 21 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-11
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-11-18 | 2026-01-20 | A | NAP | Not Approved | 3 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | 14 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | NAP | Not Approved | 4 | "SSN BCA BP Submission" |  | 2025-12
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.4 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-11-18 | 2026-01-20 | A | PEN | Not Approved | 3 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.1 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | 49 | Awaiting S.O.'s response | YES | 2026-03-09 | NO | Overdue | 0 |  |  | 001186 | 2025-04-02 | 2026-01-20 | A.2 | PEN | Not Approved | 4 | "SSN BCA BP Submission" |  | 2026-01
001187 | 00 | K Balaji | CSA | NA | 131242 | WSD11 | VI | S | 0001 | 0 | 131242-WSD11-VI-S-0001 | 2025-04-03 | Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-01 | 2025-04-15 | 8 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001187 | 2025-04-03 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" |  | 2025-04
001187 | 01 | K Balaji | CSA | NA | 131242 | WSD11 | VI | S | 0001 | 1 | 131242-WSD11-VI-S-0001 | 2025-04-18 | Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | Approved with Comments | 2025-05-08 | 2025-05-16 | 20 | Approved with Comments | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001187 | 2025-04-03 | 2025-04-18 | 1 | AWC | Approved with Comments | 2 | "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" |  | 2025-04
001188 | 00 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0001 | 0 | 131242-WST02-MM-E-0001 | 2025-04-03 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | Rev 0: Rejected. To revise and resubmit. | 2025-05-01 | 2025-05-30 | 41 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001188 | 2025-04-03 | 2025-07-22 | 1 | REJ | Not Approved | 2 | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " |  | 2025-04
001188 | 01 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0001 | 1 | 131242-WST02-MM-E-0001 | 2025-07-22 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | Rev 1: Not Approved. To revise and resubmit. Refer to the comment sheet, after incorporating comments, please submit hardcopy to S.O. prior to resubmission. | 2025-08-11 | 2025-10-01 | 51 | Not Approved | YES | 2025-10-21 | NO | Resubmitted | 0 |  |  | 001188 | 2025-04-03 | 2025-07-22 | 1 | NAP | Not Approved | 2 | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " |  | 2025-07
001189 | 00 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0002 | 0 | 131242-WST02-MM-E-0002 | 2025-04-03 | Memo-Installation Letter of TMS for Sivacon S8 | Rev 0: Accepted for Information | 2025-05-01 | 2025-05-05 | 22 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001189 | 2025-04-03 | 2025-04-03 | 0 | INF | For Information | 1 | "Memo-Installation Letter of TMS for Sivacon S8" |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7201 | A | 131242-WST02-DR-I-7201 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | AWC | Approved with Comments | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7202 | A | 131242-WST02-DR-I-7202 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7203 | A | 131242-WST02-DR-I-7203 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7204 | A | 131242-WST02-DR-I-7204 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7205 | A | 131242-WST02-DR-I-7205 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7206 | A | 131242-WST02-DR-I-7206 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7207 | A | 131242-WST02-DR-I-7207 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7208 | A | 131242-WST02-DR-I-7208 | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | 17 | Awaiting S.O.'s response | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001190 | 2025-04-03 | 2025-04-03 | A | PEN | Awaiting S.O.'s response | 1 | "SSN UPSDB SLD " |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | A | 131242-WST02-DR-IP-1941 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | A | 131242-WST02-DR-IP-1942 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | A | 131242-WST02-DR-IP-1943 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | A | 131242-WST02-DR-IP-1944 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | A | 131242-WST02-DR-IP-1945 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | A | 131242-WST02-DR-IP-1946 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | A | 131242-WST02-DR-IP-1947 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | A | 131242-WST02-DR-IP-1948 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | A | 131242-WST02-DR-IP-1949 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | A | 131242-WST02-DR-IP-1950 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | A | 131242-WST02-DR-IP-1951 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | A | 131242-WST02-DR-IP-1952 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | A | 131242-WST02-DR-IP-1953 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | A | 131242-WST02-DR-IP-1954 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | A | 131242-WST02-DR-IP-1955 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | A | 131242-WST02-DR-IP-1956 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | A | 131242-WST02-DR-IP-1957 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | A | 131242-WST02-DR-IP-1958 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | A | 131242-WST02-DR-IP-1959 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | A | 131242-WST02-DR-IP-1960 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | A | 131242-WST02-DR-IP-1961 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | A | 131242-WST02-DR-IP-1962 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | A | 131242-WST02-DR-IP-1963 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | A | 131242-WST02-DR-IP-1964 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | A | 131242-WST02-DR-IP-1965 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | A | 131242-WST02-DR-IP-1966 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | A | 131242-WST02-DR-IP-1967 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | A | 131242-WST02-DR-IP-1968 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | A | 131242-WST02-DR-IP-1969 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | A | 131242-WST02-DR-IP-1970 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | A | 131242-WST02-DR-IP-1971 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | A | 131242-WST02-DR-IP-1972 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | A | 131242-WST02-DR-IP-1973 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | A | 131242-WST02-DR-IP-1974 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | A | 131242-WST02-DR-IP-1975 | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-04
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | B | 131242-WST02-DR-IP-1941 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | B | 131242-WST02-DR-IP-1942 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | B | 131242-WST02-DR-IP-1943 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | B | 131242-WST02-DR-IP-1944 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | B | 131242-WST02-DR-IP-1945 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | B | 131242-WST02-DR-IP-1946 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | B | 131242-WST02-DR-IP-1947 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | B | 131242-WST02-DR-IP-1948 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | B | 131242-WST02-DR-IP-1949 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | B | 131242-WST02-DR-IP-1950 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | B | 131242-WST02-DR-IP-1951 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | B | 131242-WST02-DR-IP-1952 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | B | 131242-WST02-DR-IP-1953 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | B | 131242-WST02-DR-IP-1954 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | B | 131242-WST02-DR-IP-1955 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | B | 131242-WST02-DR-IP-1956 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | B | 131242-WST02-DR-IP-1957 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | B | 131242-WST02-DR-IP-1958 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | B | 131242-WST02-DR-IP-1959 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | B | 131242-WST02-DR-IP-1960 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | B | 131242-WST02-DR-IP-1961 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | B | 131242-WST02-DR-IP-1962 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | B | 131242-WST02-DR-IP-1963 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | B | 131242-WST02-DR-IP-1964 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | B | 131242-WST02-DR-IP-1965 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | B | 131242-WST02-DR-IP-1966 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | B | 131242-WST02-DR-IP-1967 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | B | 131242-WST02-DR-IP-1968 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | B | 131242-WST02-DR-IP-1969 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | B | 131242-WST02-DR-IP-1970 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | B | 131242-WST02-DR-IP-1971 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | B | 131242-WST02-DR-IP-1972 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | B | 131242-WST02-DR-IP-1973 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | B | 131242-WST02-DR-IP-1974 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | B | 131242-WST02-DR-IP-1975 | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-07
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | B | 131242-WST02-DR-IP-1941 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 0 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | B | 131242-WST02-DR-IP-1942 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | B | 131242-WST02-DR-IP-1943 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | B | 131242-WST02-DR-IP-1944 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | B | 131242-WST02-DR-IP-1945 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | B | 131242-WST02-DR-IP-1946 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | B | 131242-WST02-DR-IP-1947 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | B | 131242-WST02-DR-IP-1948 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | B | 131242-WST02-DR-IP-1949 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | B | 131242-WST02-DR-IP-1950 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | B | 131242-WST02-DR-IP-1951 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | B | 131242-WST02-DR-IP-1952 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | B | 131242-WST02-DR-IP-1953 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | B | 131242-WST02-DR-IP-1954 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | B | 131242-WST02-DR-IP-1955 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | B | 131242-WST02-DR-IP-1956 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | B | 131242-WST02-DR-IP-1957 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | B | 131242-WST02-DR-IP-1958 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | B | 131242-WST02-DR-IP-1959 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | B | 131242-WST02-DR-IP-1960 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | B | 131242-WST02-DR-IP-1961 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | B | 131242-WST02-DR-IP-1962 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | B | 131242-WST02-DR-IP-1963 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | B | 131242-WST02-DR-IP-1964 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | B | 131242-WST02-DR-IP-1965 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | B | 131242-WST02-DR-IP-1966 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | B | 131242-WST02-DR-IP-1967 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | B | 131242-WST02-DR-IP-1968 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | B | 131242-WST02-DR-IP-1969 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | B | 131242-WST02-DR-IP-1970 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | B | 131242-WST02-DR-IP-1971 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | B | 131242-WST02-DR-IP-1972 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | B | 131242-WST02-DR-IP-1973 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | B | 131242-WST02-DR-IP-1974 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | B | 131242-WST02-DR-IP-1975 | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | 51 | Approved with Comments | YES | 2026-02-16 | NO | Resubmitted | 35 |  |  | 001191 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0201) - GA & Schematic Drawings" && " SSN Panel RIO-205 - GA & Schematic Drawings" |  | 2025-11
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | A | 131242-WST02-DR-IP-2021 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | A | 131242-WST02-DR-IP-2022 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | A | 131242-WST02-DR-IP-2023 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | A | 131242-WST02-DR-IP-2024 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | A | 131242-WST02-DR-IP-2025 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | A | 131242-WST02-DR-IP-2026 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | A | 131242-WST02-DR-IP-2027 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | A | 131242-WST02-DR-IP-2028 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | A | 131242-WST02-DR-IP-2029 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | A | 131242-WST02-DR-IP-2030 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | A | 131242-WST02-DR-IP-2031 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | A | 131242-WST02-DR-IP-2032 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | A | 131242-WST02-DR-IP-2033 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | A | 131242-WST02-DR-IP-2034 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | A | 131242-WST02-DR-IP-2035 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | A | 131242-WST02-DR-IP-2036 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | A | 131242-WST02-DR-IP-2037 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | A | 131242-WST02-DR-IP-2038 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | A | 131242-WST02-DR-IP-2039 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | A | 131242-WST02-DR-IP-2040 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | A | 131242-WST02-DR-IP-2041 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | A | 131242-WST02-DR-IP-2042 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | A | 131242-WST02-DR-IP-2043 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | A | 131242-WST02-DR-IP-2044 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | A | 131242-WST02-DR-IP-2045 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | A | 131242-WST02-DR-IP-2046 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | A | 131242-WST02-DR-IP-2047 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | A | 131242-WST02-DR-IP-2048 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | A | 131242-WST02-DR-IP-2049 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | A | 131242-WST02-DR-IP-2050 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | A | 131242-WST02-DR-IP-2051 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | A | 131242-WST02-DR-IP-2052 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | A | 131242-WST02-DR-IP-2053 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | A | 131242-WST02-DR-IP-2054 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | A | 131242-WST02-DR-IP-2055 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | A | 131242-WST02-DR-IP-2056 | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-04
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | B | 131242-WST02-DR-IP-2021 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | B | 131242-WST02-DR-IP-2022 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | B | 131242-WST02-DR-IP-2023 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | B | 131242-WST02-DR-IP-2024 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | B | 131242-WST02-DR-IP-2025 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | B | 131242-WST02-DR-IP-2026 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | B | 131242-WST02-DR-IP-2027 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | B | 131242-WST02-DR-IP-2028 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | B | 131242-WST02-DR-IP-2029 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | B | 131242-WST02-DR-IP-2030 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | B | 131242-WST02-DR-IP-2031 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | B | 131242-WST02-DR-IP-2032 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | B | 131242-WST02-DR-IP-2033 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | B | 131242-WST02-DR-IP-2034 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | B | 131242-WST02-DR-IP-2035 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | B | 131242-WST02-DR-IP-2036 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | B | 131242-WST02-DR-IP-2037 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | B | 131242-WST02-DR-IP-2038 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | B | 131242-WST02-DR-IP-2039 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | B | 131242-WST02-DR-IP-2040 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | B | 131242-WST02-DR-IP-2041 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | B | 131242-WST02-DR-IP-2042 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | B | 131242-WST02-DR-IP-2043 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | B | 131242-WST02-DR-IP-2044 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | B | 131242-WST02-DR-IP-2045 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | B | 131242-WST02-DR-IP-2046 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | B | 131242-WST02-DR-IP-2047 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | B | 131242-WST02-DR-IP-2048 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | B | 131242-WST02-DR-IP-2049 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | B | 131242-WST02-DR-IP-2050 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | B | 131242-WST02-DR-IP-2051 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | B | 131242-WST02-DR-IP-2052 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | B | 131242-WST02-DR-IP-2053 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | B | 131242-WST02-DR-IP-2054 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | B | 131242-WST02-DR-IP-2055 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | B | 131242-WST02-DR-IP-2056 | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | 60 | Approved with Comments | YES | 2025-11-19 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-08
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | B | 131242-WST02-DR-IP-2021 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | B | 131242-WST02-DR-IP-2022 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | B | 131242-WST02-DR-IP-2023 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | B | 131242-WST02-DR-IP-2024 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | B | 131242-WST02-DR-IP-2025 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | B | 131242-WST02-DR-IP-2026 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | B | 131242-WST02-DR-IP-2027 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | B | 131242-WST02-DR-IP-2028 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | B | 131242-WST02-DR-IP-2029 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | B | 131242-WST02-DR-IP-2030 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | B | 131242-WST02-DR-IP-2031 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | B | 131242-WST02-DR-IP-2032 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | B | 131242-WST02-DR-IP-2033 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | B | 131242-WST02-DR-IP-2034 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | B | 131242-WST02-DR-IP-2035 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | B | 131242-WST02-DR-IP-2036 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | B | 131242-WST02-DR-IP-2037 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | B | 131242-WST02-DR-IP-2038 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | B | 131242-WST02-DR-IP-2039 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | B | 131242-WST02-DR-IP-2040 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | B | 131242-WST02-DR-IP-2041 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | B | 131242-WST02-DR-IP-2042 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | B | 131242-WST02-DR-IP-2043 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | B | 131242-WST02-DR-IP-2044 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | B | 131242-WST02-DR-IP-2045 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | B | 131242-WST02-DR-IP-2046 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | B | 131242-WST02-DR-IP-2047 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | B | 131242-WST02-DR-IP-2048 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | B | 131242-WST02-DR-IP-2049 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | B | 131242-WST02-DR-IP-2050 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | B | 131242-WST02-DR-IP-2051 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | B | 131242-WST02-DR-IP-2052 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | B | 131242-WST02-DR-IP-2053 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | B | 131242-WST02-DR-IP-2054 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | B | 131242-WST02-DR-IP-2055 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | B | 131242-WST02-DR-IP-2056 | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001192 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" |  | 2025-11
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | A | 131242-WST02-DR-IP-2061 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | A | 131242-WST02-DR-IP-2062 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | A | 131242-WST02-DR-IP-2063 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | A | 131242-WST02-DR-IP-2064 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | A | 131242-WST02-DR-IP-2065 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | A | 131242-WST02-DR-IP-2066 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | A | 131242-WST02-DR-IP-2067 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | A | 131242-WST02-DR-IP-2068 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | A | 131242-WST02-DR-IP-2069 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | A | 131242-WST02-DR-IP-2070 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | A | 131242-WST02-DR-IP-2071 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | A | 131242-WST02-DR-IP-2072 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | A | 131242-WST02-DR-IP-2073 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | A | 131242-WST02-DR-IP-2074 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | A | 131242-WST02-DR-IP-2075 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | A | 131242-WST02-DR-IP-2076 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | A | 131242-WST02-DR-IP-2077 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | A | 131242-WST02-DR-IP-2078 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | A | 131242-WST02-DR-IP-2079 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | A | 131242-WST02-DR-IP-2080 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | A | 131242-WST02-DR-IP-2081 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | A | 131242-WST02-DR-IP-2082 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | A | 131242-WST02-DR-IP-2083 | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | YES | 2025-06-05 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-04
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | B | 131242-WST02-DR-IP-2061 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-28 | 2025-09-23 | 55 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | B | 131242-WST02-DR-IP-2062 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | B | 131242-WST02-DR-IP-2063 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | B | 131242-WST02-DR-IP-2064 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | B | 131242-WST02-DR-IP-2065 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | B | 131242-WST02-DR-IP-2066 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | B | 131242-WST02-DR-IP-2067 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | B | 131242-WST02-DR-IP-2068 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | B | 131242-WST02-DR-IP-2069 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | B | 131242-WST02-DR-IP-2070 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | B | 131242-WST02-DR-IP-2071 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | B | 131242-WST02-DR-IP-2072 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | B | 131242-WST02-DR-IP-2073 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | B | 131242-WST02-DR-IP-2074 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | B | 131242-WST02-DR-IP-2075 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | B | 131242-WST02-DR-IP-2076 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | B | 131242-WST02-DR-IP-2077 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | B | 131242-WST02-DR-IP-2078 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | B | 131242-WST02-DR-IP-2079 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | B | 131242-WST02-DR-IP-2080 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | B | 131242-WST02-DR-IP-2081 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | B | 131242-WST02-DR-IP-2082 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | B | 131242-WST02-DR-IP-2083 | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | 55 | Approved with Comments | YES | 2025-10-13 | NO | Resubmitted | 33 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-07
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | B | 131242-WST02-DR-IP-2061 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | B | 131242-WST02-DR-IP-2062 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | B | 131242-WST02-DR-IP-2063 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | B | 131242-WST02-DR-IP-2064 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | B | 131242-WST02-DR-IP-2065 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | B | 131242-WST02-DR-IP-2066 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | B | 131242-WST02-DR-IP-2067 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | B | 131242-WST02-DR-IP-2068 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | B | 131242-WST02-DR-IP-2069 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | B | 131242-WST02-DR-IP-2070 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | B | 131242-WST02-DR-IP-2071 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | B | 131242-WST02-DR-IP-2072 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | B | 131242-WST02-DR-IP-2073 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | B | 131242-WST02-DR-IP-2074 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | B | 131242-WST02-DR-IP-2075 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | B | 131242-WST02-DR-IP-2076 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | B | 131242-WST02-DR-IP-2077 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | B | 131242-WST02-DR-IP-2078 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | B | 131242-WST02-DR-IP-2079 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | B | 131242-WST02-DR-IP-2080 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | B | 131242-WST02-DR-IP-2081 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | B | 131242-WST02-DR-IP-2082 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | B | 131242-WST02-DR-IP-2083 | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 35 |  |  | 001193 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" |  | 2025-11
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | A | 131242-WST02-DR-IP-1981 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | A | 131242-WST02-DR-IP-1982 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | A | 131242-WST02-DR-IP-1983 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | A | 131242-WST02-DR-IP-1984 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | A | 131242-WST02-DR-IP-1985 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | A | 131242-WST02-DR-IP-1986 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | A | 131242-WST02-DR-IP-1987 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | A | 131242-WST02-DR-IP-1988 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | A | 131242-WST02-DR-IP-1989 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | A | 131242-WST02-DR-IP-1990 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | A | 131242-WST02-DR-IP-1991 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | A | 131242-WST02-DR-IP-1992 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | A | 131242-WST02-DR-IP-1993 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | A | 131242-WST02-DR-IP-1994 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | A | 131242-WST02-DR-IP-1995 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | A | 131242-WST02-DR-IP-1996 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | A | 131242-WST02-DR-IP-1997 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | A | 131242-WST02-DR-IP-1998 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | A | 131242-WST02-DR-IP-1999 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | A | 131242-WST02-DR-IP-2000 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | A | 131242-WST02-DR-IP-2001 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | A | 131242-WST02-DR-IP-2002 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | A | 131242-WST02-DR-IP-2003 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | A | 131242-WST02-DR-IP-2004 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | A | 131242-WST02-DR-IP-2005 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | A | 131242-WST02-DR-IP-2006 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | A | 131242-WST02-DR-IP-2007 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | A | 131242-WST02-DR-IP-2008 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | A | 131242-WST02-DR-IP-2009 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | A | 131242-WST02-DR-IP-2010 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | A | 131242-WST02-DR-IP-2011 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | A | 131242-WST02-DR-IP-2012 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | A | 131242-WST02-DR-IP-2013 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | A | 131242-WST02-DR-IP-2014 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | A | 131242-WST02-DR-IP-2015 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | A | 131242-WST02-DR-IP-2016 | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | 31 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | NAP | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-04
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | B | 131242-WST02-DR-IP-1981 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | B | 131242-WST02-DR-IP-1982 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | B | 131242-WST02-DR-IP-1983 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | B | 131242-WST02-DR-IP-1984 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | B | 131242-WST02-DR-IP-1985 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | B | 131242-WST02-DR-IP-1986 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | B | 131242-WST02-DR-IP-1987 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | B | 131242-WST02-DR-IP-1988 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | B | 131242-WST02-DR-IP-1989 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | B | 131242-WST02-DR-IP-1990 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | B | 131242-WST02-DR-IP-1991 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | B | 131242-WST02-DR-IP-1992 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | B | 131242-WST02-DR-IP-1993 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | B | 131242-WST02-DR-IP-1994 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | B | 131242-WST02-DR-IP-1995 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | B | 131242-WST02-DR-IP-1996 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | B | 131242-WST02-DR-IP-1997 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | B | 131242-WST02-DR-IP-1998 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | B | 131242-WST02-DR-IP-1999 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | B | 131242-WST02-DR-IP-2000 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | B | 131242-WST02-DR-IP-2001 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | B | 131242-WST02-DR-IP-2002 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | B | 131242-WST02-DR-IP-2003 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | B | 131242-WST02-DR-IP-2004 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | B | 131242-WST02-DR-IP-2005 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | B | 131242-WST02-DR-IP-2006 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | B | 131242-WST02-DR-IP-2007 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | B | 131242-WST02-DR-IP-2008 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | B | 131242-WST02-DR-IP-2009 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | B | 131242-WST02-DR-IP-2010 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | B | 131242-WST02-DR-IP-2011 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | B | 131242-WST02-DR-IP-2012 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | B | 131242-WST02-DR-IP-2013 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | B | 131242-WST02-DR-IP-2014 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | B | 131242-WST02-DR-IP-2015 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | B | 131242-WST02-DR-IP-2016 | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | 52 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-07
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | B | 131242-WST02-DR-IP-1981 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | B | 131242-WST02-DR-IP-1982 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | B | 131242-WST02-DR-IP-1983 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | B | 131242-WST02-DR-IP-1984 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | B | 131242-WST02-DR-IP-1985 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | B | 131242-WST02-DR-IP-1986 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | B | 131242-WST02-DR-IP-1987 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | B | 131242-WST02-DR-IP-1988 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | B | 131242-WST02-DR-IP-1989 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | B | 131242-WST02-DR-IP-1990 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | B | 131242-WST02-DR-IP-1991 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | B | 131242-WST02-DR-IP-1992 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | B | 131242-WST02-DR-IP-1993 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | B | 131242-WST02-DR-IP-1994 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | B | 131242-WST02-DR-IP-1995 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | B | 131242-WST02-DR-IP-1996 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | B | 131242-WST02-DR-IP-1997 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | B | 131242-WST02-DR-IP-1998 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | B | 131242-WST02-DR-IP-1999 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | B | 131242-WST02-DR-IP-2000 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | B | 131242-WST02-DR-IP-2001 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | B | 131242-WST02-DR-IP-2002 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | B | 131242-WST02-DR-IP-2003 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | B | 131242-WST02-DR-IP-2004 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | B | 131242-WST02-DR-IP-2005 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | B | 131242-WST02-DR-IP-2006 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | B | 131242-WST02-DR-IP-2007 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | B | 131242-WST02-DR-IP-2008 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | B | 131242-WST02-DR-IP-2009 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | B | 131242-WST02-DR-IP-2010 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | B | 131242-WST02-DR-IP-2011 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | B | 131242-WST02-DR-IP-2012 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | B | 131242-WST02-DR-IP-2013 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | B | 131242-WST02-DR-IP-2014 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | B | 131242-WST02-DR-IP-2015 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | B | 131242-WST02-DR-IP-2016 | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | 20 | Approved with Comments | YES | 2026-01-02 | NO | Resubmitted | 0 |  |  | 001194 | 2025-04-03 | 2025-11-17 | B | AWC | Approved with Comments | 3 | "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && " SSN Panel RIO-208 - GA & Schematic Drawings" |  | 2025-11
001195 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 0 | 131242-WSW41-SH-M-1006 | 2025-04-03 | Manual Butterfly Valve | Rev 0: Not approved - Revise and Resubmit | 2025-05-01 | 2025-06-23 | 57 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001195 | 2025-04-03 | 2025-11-26 | 2 | NAP | Approved with Comments | 3 | "Manual Butterfly Valve " |  | 2025-04
001195 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 1 | 131242-WSW41-SH-M-1006 | 2025-08-06 | Manual Butterfly Valve | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-08-26 | 2025-09-04 | 21 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001195 | 2025-04-03 | 2025-11-26 | 2 | AWC | Approved with Comments | 3 | "Manual Butterfly Valve " |  | 2025-08
001195 | 02 | Joo Kwan | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 2 | 131242-WSW41-SH-M-1006 | 2025-11-26 | Manual Butterfly Valve | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-12-16 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001195 | 2025-04-03 | 2025-11-26 | 2 | PEN | Approved with Comments | 3 | "Manual Butterfly Valve " |  | 2025-11
001196 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0021 | 0 | 131242-WSW41-QA-A-0021 | 2025-04-03 | Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-01 | 2025-04-15 | 8 | Not Approved | YES | 2025-05-05 | NO | Resubmitted | 0 |  |  | 001196 | 2025-04-03 | 2025-04-03 | 0 | NAP | Not Approved | 1 | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" |  | 2025-04
001197 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0003 | 0 | 131242-WSW41-MS-A-0003 | 2025-04-03 | MSRA and SWP for Plastering and Skim Coat | Rev.0: Approved with comments. No resubmission is required. | 2025-05-01 | 2025-05-12 | 27 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001197 | 2025-04-03 | 2025-04-03 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Plastering and Skim Coat " |  | 2025-04
001198 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0004 | 0 | 131242-WSW41-MS-A-0004 | 2025-04-03 | MSRA and SWP for Floor Screeding and Tiles Laying | Rev.0: Approved with comments. | 2025-05-01 | 2025-05-12 | 27 | Approved with Comments | YES | 2025-05-30 | NO | Resubmitted | 0 |  |  | 001198 | 2025-04-03 | 2025-04-03 | 0 | AWC | Approved with Comments | 1 | "MSRA and SWP for Floor Screeding and Tiles Laying " |  | 2025-04
001199 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0068 | 0 | 131242-WST02-QA-M-0068 | 2025-04-03 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) | NA | 2025-05-01 | 2025-09-08 | 112 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001199 | 2025-04-03 | 2025-04-03 | 0 | APP | Approved | 1 | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) " |  | 2025-04
001200 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0028 | 0 | 131242-WSW41-VI-M-0028 | 2025-04-03 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | Approved with Comments | 2025-05-01 | 2025-05-21 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001200 | 2025-04-03 | 2025-07-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" |  | 2025-04
001200 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0028 | 1 | 131242-WSW41-VI-M-0028 | 2025-07-02 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-22 | 2026-01-07 | 135 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001200 | 2025-04-03 | 2025-07-02 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" |  | 2025-07
001201 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1015 | 0 | 131242-WSW41-VI-M-1015 | 2025-04-04 | Preliminary design and Vendor Approval – Strainer (Bliss) | Rev 0: Not approved - Revise and Resubmit | 2025-05-02 | 2025-06-23 | 56 | Not Approved | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001201 | 2025-04-04 | 2025-04-04 | 0 | NAP | Not Approved | 1 | "Preliminary design and Vendor Approval – Strainer (Bliss)" |  | 2025-04
001202 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0059 | 0 | 131242-WSW41-LT-PM-0059 | 2025-04-04 | Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors | Rev (0): Received for information. Please refer to S.O. correspondence no. 399 dated 10 Sep 2025. | 2025-05-02 | 2025-09-23 | 122 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001202 | 2025-04-04 | 2025-04-04 | 0 | INF | For Information | 1 | "Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors" |  | 2025-04
001203 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0007 | 0 | 131242-WSW41-MS-A-0007 | 2025-04-07 | MSRA, SWP for Door Installation | Approved | 2025-05-05 | 2025-04-15 | 6 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001203 | 2025-04-07 | 2025-04-07 | 0 | APP | Approved | 1 | "MSRA, SWP for Door Installation" |  | 2025-04
001204 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0021 | 0 | 131242-WSW41-PC-W-0021 | 2025-04-07 | Payment Claim No.21 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-05-05 | 2025-04-27 | 15 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001204 | 2025-04-07 | 2025-04-07 | 0 | INF | For Information | 1 | "Payment Claim No.21" |  | 2025-04
001205 | 00 | N. Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0024 | 0 | 131242-WSW41-QA-C-0024 | 2025-04-07 | Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) | Approved with Comments | 2025-05-05 | 2025-06-04 | 42 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001205 | 2025-04-07 | 2025-04-07 | 0 | AWC | Approved with Comments | 1 | "Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) " |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7000 | A | 131242-WSW41-DR-EI-7000 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7001 | A | 131242-WSW41-DR-EI-7001 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7002 | A | 131242-WSW41-DR-EI-7002 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3000 | A | 131242-WSW41-DR-EP-3000 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3001 | A | 131242-WSW41-DR-EP-3001 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3002 | A | 131242-WSW41-DR-EP-3002 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3003 | A | 131242-WSW41-DR-EP-3003 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3004 | A | 131242-WSW41-DR-EP-3004 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3005 | A | 131242-WSW41-DR-EP-3005 | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | 47 | Rejected | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001206 | 2025-04-07 | 2025-04-07 | A | REJ | Rejected | 1 | "LCS GA and Schematic Drawing" |  | 2025-04
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7400 | B | 131242-WSD11-DR-EI-7400 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7401 | B | 131242-WSD11-DR-EI-7401 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7402 | B | 131242-WSD11-DR-EI-7402 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3180 | B | 131242-WSD11-DR-EP-3180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3181 | B | 131242-WSD11-DR-EP-3181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3182 | B | 131242-WSD11-DR-EP-3182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3183 | B | 131242-WSD11-DR-EP-3183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3184 | B | 131242-WSD11-DR-EP-3184 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3185 | B | 131242-WSD11-DR-EP-3185 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3186 | B | 131242-WSD11-DR-EP-3186 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3187 | B | 131242-WSD11-DR-EP-3187 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3188 | B | 131242-WSD11-DR-EP-3188 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7180 | B | 131242-WSD11-DR-EP-7180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7181 | B | 131242-WSD11-DR-EP-7181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7182 | B | 131242-WSD11-DR-EP-7182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7183 | B | 131242-WSD11-DR-EP-7183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7400 | B | 131242-WST02-DR-EI-7400 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7401 | B | 131242-WST02-DR-EI-7401 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7402 | B | 131242-WST02-DR-EI-7402 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3180 | B | 131242-WST02-DR-EP-3180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3181 | B | 131242-WST02-DR-EP-3181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3182 | B | 131242-WST02-DR-EP-3182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3183 | B | 131242-WST02-DR-EP-3183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3184 | B | 131242-WST02-DR-EP-3184 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3185 | B | 131242-WST02-DR-EP-3185 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3186 | B | 131242-WST02-DR-EP-3186 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3187 | B | 131242-WST02-DR-EP-3187 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3188 | B | 131242-WST02-DR-EP-3188 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7180 | B | 131242-WST02-DR-EP-7180 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7181 | B | 131242-WST02-DR-EP-7181 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7182 | B | 131242-WST02-DR-EP-7182 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7183 | B | 131242-WST02-DR-EP-7183 | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | 61 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-07
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7400 | C | 131242-WSD11-DR-EI-7400 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7401 | C | 131242-WSD11-DR-EI-7401 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7402 | C | 131242-WSD11-DR-EI-7402 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3180 | C | 131242-WSD11-DR-EP-3180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3181 | C | 131242-WSD11-DR-EP-3181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3182 | C | 131242-WSD11-DR-EP-3182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3183 | C | 131242-WSD11-DR-EP-3183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3184 | C | 131242-WSD11-DR-EP-3184 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3185 | C | 131242-WSD11-DR-EP-3185 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3186 | C | 131242-WSD11-DR-EP-3186 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3187 | C | 131242-WSD11-DR-EP-3187 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3188 | C | 131242-WSD11-DR-EP-3188 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7180 | C | 131242-WSD11-DR-EP-7180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7181 | C | 131242-WSD11-DR-EP-7181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7182 | C | 131242-WSD11-DR-EP-7182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7183 | C | 131242-WSD11-DR-EP-7183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7400 | C | 131242-WST02-DR-EI-7400 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7401 | C | 131242-WST02-DR-EI-7401 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7402 | C | 131242-WST02-DR-EI-7402 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3180 | C | 131242-WST02-DR-EP-3180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3181 | C | 131242-WST02-DR-EP-3181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3182 | C | 131242-WST02-DR-EP-3182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3183 | C | 131242-WST02-DR-EP-3183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3184 | C | 131242-WST02-DR-EP-3184 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3185 | C | 131242-WST02-DR-EP-3185 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3186 | C | 131242-WST02-DR-EP-3186 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3187 | C | 131242-WST02-DR-EP-3187 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3188 | C | 131242-WST02-DR-EP-3188 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7180 | C | 131242-WST02-DR-EP-7180 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7181 | C | 131242-WST02-DR-EP-7181 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7182 | C | 131242-WST02-DR-EP-7182 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7183 | C | 131242-WST02-DR-EP-7183 | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | 99 | Approved with Comments | YES | 2026-03-16 | NO | Resubmitted | 0 |  |  | 001206 | 2025-07-08 | 2025-10-08 | C | AWC | Approved with Comments | 2 | "LCS GA and Schematic Drawing" |  | 2025-10
001207 | 00 | N Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0028 | 0 | 131242-WSW41-MS-C-0028 | 2025-04-07 | MSRA SWP for Concrete Coring | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-05 | 2025-05-12 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001207 | 2025-04-07 | 2025-05-18 | 1 | NAP | Approved with Comments | 2 | "MSRA SWP for Concrete Coring " |  | 2025-04
001207 | 01 | N Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0028 | 1 | 131242-WSW41-MS-C-0028 | 2025-05-18 | MSRA SWP for Concrete Coring | Rev.1: Approved with Comments: Please refer to comment sheet for resubmission. | 2025-06-05 | 2025-06-13 | 19 | Approved with Comments | YES | 2025-07-03 | NO | Resubmitted | 0 |  |  | 001207 | 2025-04-07 | 2025-05-18 | 1 | AWC | Approved with Comments | 2 | "MSRA SWP for Concrete Coring " |  | 2025-05
001208 | 00 | Aaron | CSA | NA | 131242 | WSW41 | SD | S | - | 0 | 131242-WSW41-SD-S-- | 2025-04-08 | Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614) | R0: For Information. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-06-30 | 59 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001208 | 2025-04-08 | 2025-04-08 | 0 | INF | For Information | 1 | "Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1101 | A | 131242-WST02-SD-S-1101 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1102 | A | 131242-WST02-SD-S-1102 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 2100 | A | 131242-WST02-SD-S-2100 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 2103 | A | 131242-WST02-SD-S-2103 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3100 | A | 131242-WST02-SD-S-3100 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5100 | A | 131242-WST02-SD-S-5100 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | NAP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5101 | A | 131242-WST02-SD-S-5101 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 000615&&001209 | 2024-08-05 | 2025-04-08 | A | NAP | Not Approved | 3 | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5105 | A | 131242-WST02-SD-S-5105 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8004 | A | 131242-WST02-SD-S-8004 | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | 84 | Not Approved | YES | 2025-08-22 | NO | Resubmitted | 0 |  |  | 001209 | 2025-04-08 | 2025-04-08 | A | NAP | Not Approved | 1 | "Steel Shop Drawings For SSN PR-001 (ST609)" |  | 2025-04
001210 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0054 | 0 | 131242-WSW41-CD-IM-0054 | 2025-04-08 | Submission of BIM Coordination VCM Model (Mar 2025) | For Information. Score= 71/100 | 2025-05-06 | 2025-04-27 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001210 | 2025-04-08 | 2025-04-08 | 0 | INF | For Information | 1 | " Submission of BIM Coordination VCM Model (Mar 2025) " |  | 2025-04
001211 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0015 | 0 | 131242-WSW41-PO-M-0015 | 2025-04-08 | Unpriced LOA for MEICA installer (Cyclect Engineering) | Rev 0: For Information | 2025-05-06 | 2025-10-06 | 129 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001211 | 2025-04-08 | 2025-04-08 | 0 | INF | For Information | 1 | "Unpriced LOA for MEICA installer (Cyclect Engineering)" |  | 2025-04
001212 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0023 | 0 | 131242-WSW41-RT-PM-0023 | 2025-04-09 | C4B Monthly Progress Report Number No.23 (03 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-05-07 | 2025-04-27 | 13 | Approved with Comments | YES | 2025-05-15 | NO | Resubmitted | 0 |  |  | 001212 | 2025-04-09 | 2025-04-09 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.23 (03 25) " |  | 2025-04
001213 | 00 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 0 | 131242-WSD11-CD-I-0005 | 2025-04-09 | Electrical Signal List for THP -MCC-0101A/0101B | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 | 2025-04-27 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001213&&001440 | 2025-04-09 | 2025-07-07 | 0 | NAP | Approved with Comments | 3 | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" |  | 2025-04
001213 | 01 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 1 | 131242-WSD11-CD-I-0005 | 2025-05-09 | Electrical Signal List for THP -MCC-0101A/0101B | Rev 1: Approved with comments. To revise and resubmit. | 2025-05-29 | 2025-06-17 | 27 | Approved with Comments | YES | 2025-07-07 | NO | Resubmitted | 0 |  |  | 001213&&001440 | 2025-04-09 | 2025-07-07 | 0 | AWC | Approved with Comments | 3 | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" |  | 2025-05
001214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0016 | 0 | 131242-WSW41-PO-M-0016 | 2025-04-09 | Unpriced LOA for Fire Protection System | Rev 0: For Information | 2025-05-07 | 2025-10-06 | 128 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001214 | 2025-04-09 | 2025-04-09 | 0 | INF | For Information | 1 | "Unpriced LOA for Fire Protection System" |  | 2025-04
001215 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0063 | 0 | 131242-WSD11-QA-M-0063 | 2025-04-09 | Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3 | Approved | 2025-05-07 | 2025-05-21 | 30 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001215 | 2025-04-09 | 2025-04-09 | 0 | APP | Approved | 1 | "Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3" |  | 2025-04
001216 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0067 | 0 | 131242-WSD11-QA-M-0067 | 2025-04-09 | Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 | Rev 0: Approved | 2025-05-07 | 2025-10-06 | 128 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001216 | 2025-04-09 | 2025-04-09 | 0 | APP | Approved | 1 | "Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 " |  | 2025-04
001217 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0029 | 0 | 131242-WSW41-QA-EI-0029 | 2025-04-10 | FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch | Approved | 2025-05-08 | 2025-05-12 | 22 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001217 | 2025-04-10 | 2025-04-10 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" |  | 2025-04
001218 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 1008 | 0 | 131242-WSW41-SH-M-1008 | 2025-04-10 | ON OFF Butterfly Valve Data sheet (OVS) | Rev 0: Not approved - Revise and Resubmit | 2025-05-08 | 2025-06-23 | 52 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001218 | 2025-04-10 | 2025-04-10 | 0 | NAP | Not Approved | 1 | "ON OFF Butterfly Valve Data sheet (OVS)" |  | 2025-04
001218 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | SH | M | 1008 | 1 | 131242-WST02-SH-M-1008 | 2025-07-11 | ON OFF Butterfly Valve Data sheet (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-31 | 2025-09-04 | 39 | Approved with Comments | YES | 2025-09-24 | NO | Resubmitted | 0 |  |  | 001218 | 2025-07-11 | 2025-07-11 | 1 | AWC | Approved with Comments | 1 | "ON OFF Butterfly Valve Data sheet (OVS)" |  | 2025-07
001219 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 0 | 131242-WST02-QA-BS-0001 | 2025-04-10 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | Not Approved - Revise and resubmit | 2025-05-08 | 2025-05-25 | 32 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" |  | 2025-04
001219 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 1 | 131242-WST02-QA-BS-0001 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | Not Approved - Revise and resubmit | 2025-07-22 | 2025-08-06 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" |  | 2025-07
001219 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 2 | 131242-WST02-QA-BS-0001 | 2025-08-19 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-08-28 | 7 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" |  | 2025-08
001219 | 03 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 3 | 131242-WST02-QA-BS-0001 | 2025-10-07 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-27 | 2025-12-05 | 43 | Not Approved | YES | 2025-12-25 | NO | Resubmitted | 0 |  |  | 001219 | 2025-04-10 | 2025-10-07 | 3 | NAP | Not Approved | 4 | "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" |  | 2025-10
001220 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0065 | 0 | 131242-WSW41-QA-M-0065 | 2025-04-10 | Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve | Approved | 2025-05-08 | 2025-05-21 | 29 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001220 | 2025-04-10 | 2025-04-10 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve" |  | 2025-04
001221 | 00 | N Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0025 | 0 | 131242-WSW41-QA-C-0025 | 2025-04-11 | Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces | Approved with Comments | 2025-05-09 | 2025-05-09 | 20 | Approved with Comments | YES | 2025-05-29 | NO | Resubmitted | 0 |  |  | 001221 | 2025-04-11 | 2025-04-11 | 0 | AWC | Approved with Comments | 1 | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" |  | 2025-04
001222 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0021 | 0 | 131242-WSW41-PS-HS-0021 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Dec 2024 | For Information | 2025-04-14 | 2025-05-12 | 40 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001222 | 2025-03-17 | 2025-03-17 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Dec 2024" |  | 2025-03
001223 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0022 | 0 | 131242-WSW41-PS-HS-0022 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Jan 2025 | For Information | 2025-04-14 | 2025-05-12 | 40 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001223 | 2025-03-17 | 2025-03-17 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Jan 2025" |  | 2025-03
001224 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0023 | 0 | 131242-WSW41-PS-HS-0023 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Feb 2025 | For Information | 2025-04-14 | 2025-05-12 | 40 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001224 | 2025-03-17 | 2025-03-17 | 0 | INF | For Information | 1 | "Incentive/ Disincentive Audit Scheme for Feb 2025" |  | 2025-03
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0042 | 0 | 131242-WSW41-MI-C-0042 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" |  | 2025-02
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0043 | 0 | 131242-WSW41-MI-C-0043 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" |  | 2025-02
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0044 | 0 | 131242-WSW41-MI-C-0044 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" |  | 2025-02
001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0045 | 0 | 131242-WSW41-MI-C-0045 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | 49 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001225 | 2025-02-25 | 2025-02-25 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" |  | 2025-02
001226 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5200 | A | 131242-WSW41-DR-S-5200 | 2025-04-14 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Not Approved - Revise and resubmit | 2025-05-12 | 2025-05-19 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001226&&001586 | 2025-04-14 | 2025-08-13 | E | NAP | Not Approved | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "SWPR _Platform A and B- Cat ladders" |  | 2025-04
001226 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1210 | A | 131242-WSW41-DR-S-1210 | 2025-04-14 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Not Approved - Revise and resubmit | 2025-05-12 | 2025-05-19 | 25 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001226 | 2025-04-14 | 2025-09-15 | B | NAP | Rejected | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " |  | 2025-04
001226 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | B | 131242-WSD11-DR-S-5200 | 2025-09-15 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Rev.1:Rejected. Resubmission is not required. | 2025-10-03 | 2025-10-15 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 000861&&001226&&001572 | 2024-11-30 | 2025-12-14 | A | REJ | Approved | 5 | "THP- Valve Pit, Sump and Kerb Detail" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" |  | 2025-09
001226 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1210 | B | 131242-WSW41-DR-S-1210 | 2025-09-15 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Rev.1:Rejected. Resubmission is not required. | 2025-10-03 | 2025-10-15 | 22 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001226 | 2025-04-14 | 2025-09-15 | B | REJ | Rejected | 2 | "THP Courtyard - Valve Pit, Sump and Kerb Detail " |  | 2025-09
001227 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | EI | 0011 | 0 | 131242-WSW41-MS-EI-0011 | 2025-04-14 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-12 | 2025-05-30 | 34 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001227 | 2025-04-14 | 2025-12-08 | 1 | AWC | Approved with Comments | 2 | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" |  | 2025-04
001227 | 01 | Bryan | EICA | NA | 131242 | WSW41 | MS | EI | 0011 | 1 | 131242-WSW41-MS-EI-0011 | 2025-12-08 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2026-02-20 | 54 | Approved with Comments | YES | 2026-03-12 | NO | Resubmitted | 0 |  |  | 001227 | 2025-04-14 | 2025-12-08 | 1 | AWC | Approved with Comments | 2 | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" |  | 2025-12
001228 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0029 | 0 | 131242-WSW41-SP-C-0029 | 2025-04-16 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-14 | 2025-05-07 | 15 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001228 | 2025-04-16 | 2025-06-27 | 1 | AWC | Approved | 2 | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" |  | 2025-04
001228 | 01 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0029 | 1 | 131242-WSW41-SP-C-0029 | 2025-06-27 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | R1: Approved | 2025-07-17 | 2025-07-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001228 | 2025-04-16 | 2025-06-27 | 1 | APP | Approved | 2 | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" |  | 2025-06
001229 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0006 | 0 | 131242-WST02-DS-I-0006 | 2025-04-16 | Datasheet for Tuning Fork Level Switch | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001229 | 2025-04-16 | 2025-12-08 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Tuning Fork Level Switch " |  | 2025-04
001229 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0006 | 1 | 131242-WST02-DS-I-0006 | 2025-12-08 | Datasheet for Tuning Fork Level Switch | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-26 | 2026-02-09 | 45 | Approved with Comments | YES | 2026-02-27 | NO | Resubmitted | 0 |  |  | 001229 | 2025-04-16 | 2025-12-08 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Tuning Fork Level Switch " |  | 2025-12
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3001 | A | 131242-WSD11-DR-IC-3001 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3002 | A | 131242-WSD11-DR-IC-3002 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3003 | A | 131242-WSD11-DR-IC-3003 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3004 | A | 131242-WSD11-DR-IC-3004 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3005 | A | 131242-WSD11-DR-IC-3005 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3006 | A | 131242-WSD11-DR-IC-3006 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3007 | A | 131242-WSD11-DR-IC-3007 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3008 | A | 131242-WSD11-DR-IC-3008 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3009 | A | 131242-WSD11-DR-IC-3009 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3010 | A | 131242-WSD11-DR-IC-3010 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3011 | A | 131242-WSD11-DR-IC-3011 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3012 | A | 131242-WSD11-DR-IC-3012 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3013 | A | 131242-WSD11-DR-IC-3013 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3014 | A | 131242-WSD11-DR-IC-3014 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3015 | A | 131242-WSD11-DR-IC-3015 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3016 | A | 131242-WSD11-DR-IC-3016 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3017 | A | 131242-WSD11-DR-IC-3017 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3018 | A | 131242-WSD11-DR-IC-3018 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3019 | A | 131242-WSD11-DR-IC-3019 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3020 | A | 131242-WSD11-DR-IC-3020 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3021 | A | 131242-WSD11-DR-IC-3021 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3022 | A | 131242-WSD11-DR-IC-3022 | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | 40 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-04
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3001 | A | 131242-WSD11-DR-IC-3001 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3002 | A | 131242-WSD11-DR-IC-3002 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3003 | A | 131242-WSD11-DR-IC-3003 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3004 | A | 131242-WSD11-DR-IC-3004 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3005 | A | 131242-WSD11-DR-IC-3005 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3006 | A | 131242-WSD11-DR-IC-3006 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3007 | A | 131242-WSD11-DR-IC-3007 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3008 | A | 131242-WSD11-DR-IC-3008 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3009 | A | 131242-WSD11-DR-IC-3009 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3010 | A | 131242-WSD11-DR-IC-3010 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3011 | A | 131242-WSD11-DR-IC-3011 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3012 | A | 131242-WSD11-DR-IC-3012 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3013 | A | 131242-WSD11-DR-IC-3013 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3014 | A | 131242-WSD11-DR-IC-3014 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3015 | A | 131242-WSD11-DR-IC-3015 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3016 | A | 131242-WSD11-DR-IC-3016 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3017 | A | 131242-WSD11-DR-IC-3017 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3018 | A | 131242-WSD11-DR-IC-3018 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3019 | A | 131242-WSD11-DR-IC-3019 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3020 | A | 131242-WSD11-DR-IC-3020 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3021 | A | 131242-WSD11-DR-IC-3021 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3022 | A | 131242-WSD11-DR-IC-3022 | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | 7 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001230 | 2025-04-16 | 2025-08-22 | A | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-08
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3001 | B | 131242-WSD11-DR-IP-3001 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3002 | B | 131242-WSD11-DR-IP-3002 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3003 | B | 131242-WSD11-DR-IP-3003 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3004 | B | 131242-WSD11-DR-IP-3004 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3005 | B | 131242-WSD11-DR-IP-3005 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3006 | B | 131242-WSD11-DR-IP-3006 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3007 | B | 131242-WSD11-DR-IP-3007 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3008 | B | 131242-WSD11-DR-IP-3008 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3009 | B | 131242-WSD11-DR-IP-3009 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3010 | B | 131242-WSD11-DR-IP-3010 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3011 | B | 131242-WSD11-DR-IP-3011 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3012 | B | 131242-WSD11-DR-IP-3012 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3013 | B | 131242-WSD11-DR-IP-3013 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3014 | B | 131242-WSD11-DR-IP-3014 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3015 | B | 131242-WSD11-DR-IP-3015 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3016 | B | 131242-WSD11-DR-IP-3016 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3017 | B | 131242-WSD11-DR-IP-3017 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3018 | B | 131242-WSD11-DR-IP-3018 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3019 | B | 131242-WSD11-DR-IP-3019 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3020 | B | 131242-WSD11-DR-IP-3020 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3021 | B | 131242-WSD11-DR-IP-3021 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3022 | B | 131242-WSD11-DR-IP-3022 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3023 | B | 131242-WSD11-DR-IP-3023 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3024 | B | 131242-WSD11-DR-IP-3024 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3025 | B | 131242-WSD11-DR-IP-3025 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | AWC | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3026 | B | 131242-WSD11-DR-IP-3026 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230 | 2025-11-11 | 2025-11-11 | B | AWC | Approved with Comments | 1 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3027 | B | 131242-WSD11-DR-IP-3027 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230 | 2025-11-11 | 2025-11-11 | B | AWC | Approved with Comments | 1 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-11
001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3028 | B | 131242-WSD11-DR-IP-3028 | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | 25 | Approved with Comments | YES | 2026-01-05 | NO | Resubmitted | 0 |  |  | 001230 | 2025-11-11 | 2025-11-11 | B | AWC | Approved with Comments | 1 | "THP WAP FFOTP_GA & Wiring Diagram" |  | 2025-11
001231 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0007 | 0 | 131242-WST02-DS-I-0007 | 2025-04-16 | Datasheet for Radar Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-05-14 | 2025-06-30 | 53 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001231 | 2025-04-16 | 2025-07-22 | 1 | NAP | Approved with Comments | 2 | "Datasheet for Radar Level Transmitter " |  | 2025-04
001231 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0007 | 1 | 131242-WST02-DS-I-0007 | 2025-07-22 | Datasheet for Radar Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-08-06 | 11 | Approved with Comments | YES | 2025-08-26 | NO | Resubmitted | 0 |  |  | 001231 | 2025-04-16 | 2025-07-22 | 1 | AWC | Approved with Comments | 2 | "Datasheet for Radar Level Transmitter " |  | 2025-07
001232 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0070 | 0 | 131242-WSD11-QA-M-0070 | 2025-04-17 | MSRA & SWP for NDT Activities | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-05-15 | 2025-10-06 | 122 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001232 | 2025-04-17 | 2025-04-17 | 0 | AWC | Approved with Comments | 1 | "MSRA & SWP for NDT Activities " |  | 2025-04
001233 | 00 | Balaji | EICA | NA | 131242 | WST02 | BQ | I | 0005 | 0 | 131242-WST02-BQ-I-0005 | 2025-04-17 | SSN ICA Cable List | Not Approved - Revise and resubmit | 2025-05-15 | 2025-06-11 | 39 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001233 | 2025-04-17 | 2025-10-28 | 1 | NAP | Not Approved | 2 | "SSN ICA Cable List " |  | 2025-04
001233 | 01 | Balaji | EICA | NA | 131242 | WST02 | BQ | I | 0005 | 1 | 131242-WST02-BQ-I-0005 | 2025-10-28 | SSN ICA Cable List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2026-01-26 | 64 | Not Approved | YES | 2026-02-13 | NO | Resubmitted | 0 |  |  | 001233 | 2025-04-17 | 2025-10-28 | 1 | NAP | Not Approved | 2 | "SSN ICA Cable List " |  | 2025-10
001234 | 00 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 0 | 131242-WST02-DS-BS-0003 | 2025-04-17 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | Rev 0: Not approved - Revise and Resubmit | 2025-05-15 | 2025-05-06 | 13 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001234 | 2025-04-17 | 2025-06-06 | 2 | NAP | Approved with Comments | 3 | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" |  | 2025-04
001234 | 01 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 1 | 131242-WST02-DS-BS-0003 | 2025-04-17 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | Rev 1: Not approved - Revise and Resubmit | 2025-05-07 | 2025-05-25 | 27 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001234 | 2025-04-17 | 2025-06-06 | 2 | NAP | Approved with Comments | 3 | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" |  | 2025-04
001234 | 02 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 2 | 131242-WST02-DS-BS-0003 | 2025-06-06 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-26 | 2025-07-04 | 20 | Approved with Comments | YES | 2025-07-24 | NO | Resubmitted | 0 |  |  | 001234 | 2025-04-17 | 2025-06-06 | 2 | AWC | Approved with Comments | 3 | "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" |  | 2025-06
001235 | 00 | Balaji | EICA | NA | 131242 | WSW41 | DR | IP | 1001 | A | 131242-WSW41-DR-IP-1001 | 2025-04-18 | Panel Base Frame Drawing | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-05-16 | 2025-06-11 | 38 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001235 | 2025-04-18 | 2025-04-18 | A | INF | For Information | 1 | "Panel Base Frame Drawing" |  | 2025-04
001236 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | DS | C | 0001 | 0 | 131242-WST02-DS-C-0001 | 2025-04-18 | Epoxy Coating System | Approved | 2025-05-16 | 2025-06-04 | 33 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001236 | 2025-04-18 | 2025-04-18 | 0 | APP | Approved | 1 | "Epoxy Coating System" |  | 2025-04
001237 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0030 | 0 | 131242-WSW41-QA-C-0030 | 2025-04-21 | Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps) | For Information | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001237 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" |  | 2025-04
001238 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0029 | 0 | 131242-WSW41-QA-C-0029 | 2025-04-21 | Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing | For Information | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001238 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" |  | 2025-04
001239 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0028 | 0 | 131242-WSW41-QA-C-0028 | 2025-04-21 | Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports) | For information | 2025-05-19 | 2025-06-04 | 32 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001239 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" |  | 2025-04
001240 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0027 | 0 | 131242-WSW41-QA-C-0027 | 2025-04-21 | Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps) | For Information | 2025-05-19 | 2025-05-30 | 29 | For Information | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001240 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" |  | 2025-04
001241 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0026 | 0 | 131242-WSW41-QA-C-0026 | 2025-04-21 | Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024 | For information | 2025-05-19 | 2025-05-16 | 19 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001241 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" |  | 2025-04
001242 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0021 | 0 | 131242-WSW41-PS-PM-0021 | 2025-04-21 | Monthly Progress Presentation No. 21 (0225) | For information and record. | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001242 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 21 (0225)" |  | 2025-04
001243 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0021 | 0 | 131242-WSW41-MI-PM-0021 | 2025-04-21 | Monthly Progress Meeting Minutes 0021_20250226 | For information and record. | 2025-05-19 | 2025-05-07 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001243 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0021_20250226" |  | 2025-04
001244 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0022 | 0 | 131242-WSW41-PS-PM-0022 | 2025-04-21 | Monthly Progress Presentation No. 22 (0325) | For information and record. | 2025-05-19 | 2025-05-05 | 10 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001244 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Presentation No. 22 (0325)" |  | 2025-04
001245 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0022 | 0 | 131242-WSW41-MI-PM-0022 | 2025-04-21 | Monthly Progress Meeting Minutes 0022_20250324 | For information and record | 2025-05-19 | 2025-05-07 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001245 | 2025-04-21 | 2025-04-21 | 0 | INF | For Information | 1 | "Monthly Progress Meeting Minutes 0022_20250324" |  | 2025-04
001246 | 00 | Danapal | QAQC | NA | 131242 | WSD11 | QA | I | 0009 | 0 | 131242-WSD11-QA-I-0009 | 2025-04-22 | FAT report for MCP panel WSD11-006-MCP-1000 | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-11 | 36 | Approved with Comments | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001246 | 2025-04-22 | 2025-04-22 | 0 | AWC | Approved with Comments | 1 | "FAT report for MCP panel WSD11-006-MCP-1000 " |  | 2025-04
001247 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0005 | 0 | 131242-WSD11-VI-I-0005 | 2025-04-22 | Vendor Approval for THP Electromagnetic Flowmeters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-30 | 49 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001247 | 2025-04-22 | 2025-04-22 | 0 | AWC | Approved with Comments | 1 | "Vendor Approval for THP Electromagnetic Flowmeters" |  | 2025-04
001248 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0046 | 0 | 131242-WSW41-MI-C-0046 | 2025-04-22 | CSA Meeting Minutes 0046_17042025 | For information. | 2025-05-20 | 2025-05-30 | 28 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001248 | 2025-04-22 | 2025-04-22 | 0 | INF | For Information | 1 | "CSA Meeting Minutes 0046_17042025" |  | 2025-04
001249 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0060 | 0 | 131242-WSW41-LT-PM-0060 | 2025-04-23 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building | Rev (0): Rejected. Please refer to S.O. correspondence no. 355 dated 3 June 2025. | 2025-05-21 | 2025-08-22 | 87 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001249 | 2025-04-23 | 2025-04-23 | 0 | REJ | Rejected | 1 | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building " |  | 2025-04
001250 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0066 | 0 | 131242-WSD11-QA-M-0066 | 2025-04-24 | FAT report for THP Sludge cooler B Stage 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-07-02 | 49 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001250 | 2025-04-24 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT report for THP Sludge cooler B Stage 1" |  | 2025-04
001250 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0066 | 1 | 131242-WSD11-QA-M-0066 | 2025-12-02 | FAT report for THP Sludge cooler B Stage 1 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001250 | 2025-04-24 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT report for THP Sludge cooler B Stage 1" |  | 2025-12
001251 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | C | 0031 | 0 | 131242-WST02-MS-C-0031 | 2025-04-24 | MSRA, SWP for Water Testing of Liquid Retaining Structure | Approved with Comments | 2025-05-22 | 2025-06-02 | 27 | Approved with Comments | YES | 2025-06-20 | NO | Resubmitted | 0 |  |  | 001251 | 2025-04-24 | 2025-04-24 | 0 | AWC | Approved with Comments | 1 | "MSRA, SWP for Water Testing of Liquid Retaining Structure" |  | 2025-04
001252 | 00 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0004 | 0 | 131242-WST02-DS-BS-0004 | 2025-04-25 | Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance | Not Approved - Revise and resubmit | 2025-05-23 | 2025-05-25 | 21 | Not Approved | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001252 | 2025-04-25 | 2025-04-25 | 0 | NAP | Not Approved | 1 | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " |  | 2025-04
001253 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | E | 0030 | 0 | 131242-WSW41-QA-E-0030 | 2025-04-25 | FAT Report for Control Cable and Power Cables | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-23 | 2025-05-30 | 25 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001253 | 2025-04-25 | 2025-04-25 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Control Cable and Power Cables" |  | 2025-04
001254 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | BQ | I | 0001 | 0 | 131242-WSD11-BQ-I-0001 | 2025-04-25 | THP ICA Cable List | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-23 | 2025-06-11 | 33 | Approved with Comments | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001254 | 2025-04-25 | 2025-04-25 | 0 | AWC | Approved with Comments | 1 | " THP ICA Cable List" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618_BCA | 0 | 131242-WSD11-DR-S-0302_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618_BCA | C | 131242-WSD11-DR-S-1300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618_BCA | C | 131242-WSD11-DR-S-1301_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618_BCA | C | 131242-WSD11-DR-S-1302_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618_BCA | C | 131242-WSD11-DR-S-1303_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618_BCA | C | 131242-WSD11-DR-S-1304_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618_BCA | C | 131242-WSD11-DR-S-1305_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1306_ST618_BCA | C | 131242-WSD11-DR-S-1306_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618_BCA | C | 131242-WSD11-DR-S-2300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618_BCA | C | 131242-WSD11-DR-S-3300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3301_ST618_BCA | C | 131242-WSD11-DR-S-3301_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255 | 2025-04-25 | 2025-04-25 | C | INF | For Information | 1 | "ST618 WD Response For THP Train Cambi Structures" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618_BCA | C | 131242-WSD11-DR-S-5300_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618_BCA | C | 131242-WSD11-DR-S-5301_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618_BCA | C | 131242-WSD11-DR-S-5302_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618_BCA | C | 131242-WSD11-DR-S-5303_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618_BCA | C | 131242-WSD11-DR-S-5304_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618_BCA | C | 131242-WSD11-DR-S-5305_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618_BCA | C | 131242-WSD11-DR-S-5306_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618_BCA | C | 131242-WSD11-DR-S-5307_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618_BCA | C | 131242-WSD11-DR-S-5308_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618_BCA | C | 131242-WSD11-DR-S-5309_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618_BCA | C | 131242-WSD11-DR-S-5310_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5311_ST618_BCA | C | 131242-WSD11-DR-S-5311_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5312_ST618_BCA | C | 131242-WSD11-DR-S-5312_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5313_ST618_BCA | C | 131242-WSD11-DR-S-5313_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5314_ST618_BCA | C | 131242-WSD11-DR-S-5314_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5315_ST618_BCA | C | 131242-WSD11-DR-S-5315_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5316_ST618_BCA | C | 131242-WSD11-DR-S-5316_ST618_BCA | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | 33 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001255&&001533 | 2025-04-25 | 2025-07-29 | C | INF | For Information | 2 | "ST618 WD Response For THP Train Cambi Structures" && "BCA Approval of ST618 (THP Train_Cambi Structures)" |  | 2025-04
001256 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0069 | 0 | 131242-WSD11-QA-M-0069 | 2025-04-28 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-26 | 2025-07-02 | 47 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001256 | 2025-04-28 | 2025-12-04 | 1 | AWC | Approved | 2 | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" |  | 2025-04
001256 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0069 | 1 | 131242-WSD11-QA-M-0069 | 2025-12-04 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | Rev 1: Approved | 2025-12-24 | 2025-12-23 | 13 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001256 | 2025-04-28 | 2025-12-04 | 1 | APP | Approved | 2 | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" |  | 2025-12
001257 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0068 | 0 | 131242-WSW41-QA-M-0068 | 2025-04-29 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-08-01 | 68 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001257 | 2025-04-29 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" |  | 2025-04
001257 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0068 | 1 | 131242-WSW41-QA-M-0068 | 2025-08-25 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-09-12 | 2025-12-23 | 86 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001257 | 2025-04-29 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" |  | 2025-08
001258 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0073 | 0 | 131242-WST02-QA-M-0073 | 2025-04-29 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-06-23 | 39 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001258 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant)" |  | 2025-04
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5731 | 0 | 131242-WST02-DS-M-5731 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" |  | 2025-04
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5732 | 0 | 131242-WST02-DS-M-5732 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" |  | 2025-04
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5733 | 0 | 131242-WST02-DS-M-5733 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" |  | 2025-04
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5734 | 0 | 131242-WST02-DS-M-5734 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" |  | 2025-04
001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5735 | 0 | 131242-WST02-DS-M-5735 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | 23 | Approved with Comments | YES | 2025-06-19 | NO | Resubmitted | 0 |  |  | 001259 | 2025-04-29 | 2025-04-29 | 0 | AWC | Approved with Comments | 1 | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" |  | 2025-04
001260 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0005 | 0 | 131242-WST02-QA-BS-0005 | 2025-04-30 | Inspection and test Plan for fire protection system | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-28 | 2025-05-30 | 22 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001260 | 2025-04-30 | 2025-07-04 | 1 | AWC | Approved | 2 | "Inspection and test Plan for fire protection system " |  | 2025-04
001260 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0005 | 1 | 131242-WST02-QA-BS-0005 | 2025-07-04 | Inspection and test Plan for fire protection system | R1: Approved | 2025-07-24 | 2025-12-29 | 126 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001260 | 2025-04-30 | 2025-07-04 | 1 | APP | Approved | 2 | "Inspection and test Plan for fire protection system " |  | 2025-07
001261 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0071 | 0 | 131242-WSD11-QA-M-0071 | 2025-04-30 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-28 | 2025-07-02 | 45 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001261 | 2025-04-30 | 2025-12-03 | 1 | AWC | Approved | 2 | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" |  | 2025-04
001261 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0071 | 1 | 131242-WSD11-QA-M-0071 | 2025-12-03 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | Rev 1: Approved | 2025-12-23 | 2025-12-23 | 14 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001261 | 2025-04-30 | 2025-12-03 | 1 | APP | Approved | 2 | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" |  | 2025-12
001262 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0006 | 0 | 131242-WST02-QA-BS-0006 | 2025-05-02 | Inspection and test Plan and Factory Acceptance Test for Public Address System | R0: Approved with comments. No resubmission is required. | 2025-05-30 | 2025-05-30 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001262 | 2025-05-02 | 2025-07-05 | 1 | AWC | Approved with Comments | 2 | "Inspection and test Plan and Factory Acceptance Test for Public Address System" |  | 2025-05
001262 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0006 | 1 | 131242-WST02-QA-BS-0006 | 2025-07-05 | Inspection and test Plan and Factory Acceptance Test for Public Address System | R0: Approved with comments. No resubmission is required. | 2025-07-24 |  | 190 | Awaiting S.O.'s response | YES | 2025-08-21 | NO | Overdue | 0 |  |  | 001262 | 2025-05-02 | 2025-07-05 | 1 | PEN | Approved with Comments | 2 | "Inspection and test Plan and Factory Acceptance Test for Public Address System" |  | 2025-07
001263 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0007 | 0 | 131242-WST02-QA-BS-0007 | 2025-05-02 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-30 | 2025-05-30 | 20 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001263 | 2025-05-02 | 2025-07-07 | 1 | AWC | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " |  | 2025-05
001263 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0007 | 1 | 131242-WST02-QA-BS-0007 | 2025-07-07 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | R1: Approved | 2025-07-25 | 2025-12-29 | 125 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001263 | 2025-05-02 | 2025-07-07 | 1 | APP | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " |  | 2025-07
001264 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | I | 0011 | 0 | 131242-WSW41-QA-I-0011 | 2025-05-02 | Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-05-30 | 2025-06-30 | 41 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001264 | 2025-05-02 | 2025-05-02 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " |  | 2025-05
001265 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0030 | 0 | 131242-WSW41-MS-C-0030 | 2025-05-04 | Application of Novolac Epoxy Coating | R0: Approved | 2025-05-30 | 2025-05-30 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001265 | 2025-05-04 | 2025-05-04 | 0 | APP | Approved | 1 | "Application of Novolac Epoxy Coating " |  | 2025-05
001266 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | E | 0014 | 0 | 131242-WSW41-MS-E-0014 | 2025-05-04 | MSRA for Protection Relay Replacement Works | Rev 0: Rejected. Resubmission not required, refer to attached file for comments to note | 2025-05-30 | 2025-06-17 | 31 | Rejected | NO |  | YES | Resubmitted | 0 |  |  | 001266 | 2025-05-04 | 2025-05-04 | 0 | REJ | Rejected | 1 | "MSRA for Protection Relay Replacement Works " |  | 2025-05
001267 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0031 | 0 | 131242-WSW41-QA-C-0031 | 2025-05-04 | Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 | For Information | 2025-05-30 | 2025-06-09 | 25 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001267 | 2025-05-04 | 2025-05-04 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " |  | 2025-05
001268 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0008 | 0 | 131242-WST02-QA-BS-0008 | 2025-05-04 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-30 | 2025-05-30 | 19 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001268 | 2025-05-04 | 2025-07-05 | 1 | NAP | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" |  | 2025-05
001268 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0008 | 1 | 131242-WST02-QA-BS-0008 | 2025-07-05 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-24 | 2025-09-23 | 56 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001268 | 2025-05-04 | 2025-07-05 | 1 | APP | Approved | 2 | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" |  | 2025-07
001269 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5487 | 0 | 131242-WST02-DS-M-5487 | 2025-05-04 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | Rev 0: For Information Only | 2025-05-30 | 2026-01-30 | 194 | For Information | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001269 | 2025-05-04 | 2025-05-04 | 0 | INF | For Information | 1 | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" |  | 2025-05
001269 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5487 | 0 | 131242-WST02-DR-M-5487 | 2025-05-04 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | Rev 0: For Information Only | 2025-05-30 | 2026-01-30 | 194 | For Information | YES | 2026-02-19 | NO | Resubmitted | 0 |  |  | 001269 | 2025-05-04 | 2025-05-04 | 0 | INF | For Information | 1 | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" |  | 2025-05
001270 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0059 | 0 | 131242-WST02-CD-IM-0059 | 2025-05-09 | Submission of BIM Coordination VCM Model (Apr 2025) | For Information | 2025-06-06 | 2025-05-29 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001270 | 2025-05-09 | 2025-05-09 | 0 | INF | For Information | 1 | "Submission of BIM Coordination VCM Model (Apr 2025) " |  | 2025-05
001271 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0080 | 0 | 131242-WST02-QA-M-0080 | 2025-05-09 | FAT Report for Discharge Transfer Pumps (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-07-01 | 37 | Approved with Comments | YES | 2025-07-21 | NO | Resubmitted | 0 |  |  | 001271 | 2025-05-09 | 2025-05-09 | 0 | AWC | Approved with Comments | 1 | "FAT Report for Discharge Transfer Pumps (KSB)" |  | 2025-05
001272 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0077 | 0 | 131242-WSD11-QA-M-0077 | 2025-05-09 | Final FAT report for THP train 1 & Train 2 Feed pumps | Rev 0: Approved | 2025-06-06 | 2025-07-02 | 38 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001272 | 2025-05-09 | 2025-05-09 | 0 | APP | Approved | 1 | "Final FAT report for THP train 1 & Train 2 Feed pumps" |  | 2025-05
001273 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0075 | 0 | 131242-WSW41-QA-M-0075 | 2025-05-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen) | Rev 0: Approved | 2025-06-06 | 2025-07-14 | 46 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001273 | 2025-05-09 | 2025-05-09 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen)" |  | 2025-05
001274 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0004 | 0 | 131242-WSD11-VI-M-0004 | 2025-05-10 | Preliminary Design and Vendor Approval Document for Steam Equiptment Package | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001274 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" |  | 2025-05
001275 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0016 | 0 | 131242-WSD11-CL-P-0016 | 2025-05-10 | HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard | Rev 0: Approved | 2025-06-06 | 2025-07-04 | 39 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001275 | 2025-05-10 | 2025-05-10 | 0 | APP | Approved | 1 | "HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard" |  | 2025-05
001276 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0040 | 0 | 131242-WSD11-DS-M-0040 | 2025-05-10 | THP HWR Bypass Control Valve | Approved with Comments | 2025-06-06 | 2025-05-21 | 7 | Approved with Comments | YES | 2025-06-10 | NO | Resubmitted | 0 |  |  | 001276 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "THP HWR Bypass Control Valve" |  | 2025-05
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5721 | 0 | 131242-WST02-DS-M-5721 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" |  | 2025-05
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5722 | 0 | 131242-WST02-DS-M-5722 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" |  | 2025-05
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5723 | 0 | 131242-WST02-DS-M-5723 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" |  | 2025-05
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5724 | 0 | 131242-WST02-DS-M-5724 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" |  | 2025-05
001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5725 | 0 | 131242-WST02-DS-M-5725 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | 30 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001277 | 2025-05-10 | 2025-05-10 | 0 | AWC | Approved with Comments | 1 | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" |  | 2025-05
001278 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0032 | 0 | 131242-WSW41-QA-C-0032 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Mar 2024 | For information | 2025-06-10 | 2025-05-20 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001278 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Mar 2024" |  | 2025-05
001279 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0033 | 0 | 131242-WSW41-QA-C-0033 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Apr 2024 | For Information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001279 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" |  | 2025-05
001280 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0034 | 0 | 131242-WSW41-QA-C-0034 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024 | For Information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001280 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" |  | 2025-05
001281 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0082 | 0 | 131242-WSW41-QA-M-0082 | 2025-05-13 | FAT report for THP Sludge cooler D Stage 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 | 2025-07-02 | 36 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001281 | 2025-05-13 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT report for THP Sludge cooler D Stage 2" |  | 2025-05
001281 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0082 | 1 | 131242-WSW41-QA-M-0082 | 2025-12-02 | FAT report for THP Sludge cooler D Stage 2 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001281 | 2025-05-13 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT report for THP Sludge cooler D Stage 2" |  | 2025-12
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620 | E | 131242-WSD11-DR-S-1600_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" |  | 2025-05
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620 | E | 131242-WSD11-DR-S-1601_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" |  | 2025-05
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620 | E | 131242-WSD11-DR-S-5600_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" |  | 2025-05
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620 | E | 131242-WSD11-DR-S-5601_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" |  | 2025-05
001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5602_ST620 | E | 131242-WSD11-DR-S-5602_ST620 | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | 21 | For Information | YES | 2025-07-01 | NO | Resubmitted | 0 |  |  | 001282 | 2025-05-13 | 2025-05-13 | E | INF | For Information | 1 | "ST620 Pipe Supports and Duct Supports Redesign" |  | 2025-05
001283 | 00 | Aaron | CSA | NA | New WD | NA | NA | NA | NA | NA | New WD -NA-NA-NA-NA | 2025-05-13 | NEW WD from BCA for ST618 - THP Train Cambi Structures | For information | 2025-06-10 | 2025-05-21 | 6 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001283 | 2025-05-13 | 2025-05-13 | NA | INF | For Information | 1 | "NEW WD from BCA for ST618 - THP Train Cambi Structures" |  | 2025-05
001284 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011 | E | 131242-WST02-DR-S-1011 | 2025-05-13 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-10 | 2025-06-30 | 34 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001284&&001656 | 2025-05-13 | 2025-09-08 | A.1 | AWC | Not Approved | 2 | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" |  | 2025-05
001284 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004 | E | 131242-WST02-DR-S-7004 | 2025-05-13 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-10 | 2025-06-30 | 34 | Approved with Comments | YES | 2025-07-18 | NO | Resubmitted | 0 |  |  | 001284 | 2025-05-13 | 2025-05-13 | E | AWC | Approved with Comments | 1 | "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1203 | F | 131242-WST02-DR-S-1203 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1204 | F | 131242-WST02-DR-S-1204 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 2202 | F | 131242-WST02-DR-S-2202 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3202 | F | 131242-WST02-DR-S-3202 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5205 | F | 131242-WST02-DR-S-5205 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5206 | F | 131242-WST02-DR-S-5206 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5207 | F | 131242-WST02-DR-S-5207 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5208 | F | 131242-WST02-DR-S-5208 | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | 62 | For Information | YES | 2025-08-27 | NO | Resubmitted | 0 |  |  | 001285 | 2025-05-13 | 2025-05-13 | F | INF | For Information | 1 | "ST608 drawings Connection Details" |  | 2025-05
001286 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0009 | 0 | 131242-WSW41-PO-E-0009 | 2025-05-13 | Unpriced PO for Accessories for Lighting Protection (SkyPRO) | For information | 2025-06-10 | 2025-05-20 | 5 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001286 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" |  | 2025-05
001287 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0017 | 0 | 131242-WSW41-PO-M-0017 | 2025-05-13 | Unpriced LOA for Electric Hoist (Helmsion Engineering) | Rev 0: For Information Only. | 2025-06-10 | 2025-11-21 | 138 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001287 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Unpriced LOA for Electric Hoist (Helmsion Engineering) " |  | 2025-05
001288 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0078 | 0 | 131242-WSW41-QA-M-0078 | 2025-05-13 | Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) | NA | 2025-06-10 | 2025-09-08 | 84 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001288 | 2025-05-13 | 2025-05-13 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) " |  | 2025-05
001289 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0079 | 0 | 131242-WSW41-QA-M-0079 | 2025-05-13 | Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 | 2025-08-01 | 58 | Approved with Comments | YES | 2025-08-21 | NO | Resubmitted | 0 |  |  | 001289 | 2025-05-13 | 2025-05-13 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve" |  | 2025-05
001290 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0022 | 0 | 131242-WSW41-PC-W-0022 | 2025-05-13 | Payment Claim No.22 | Rev (0): Approved. Please refer to S.O. correspondence no. 350 date 16 May 2025. | 2025-06-10 | 2025-08-22 | 73 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001290 | 2025-05-13 | 2025-05-13 | 0 | APP | Approved | 1 | "Payment Claim No.22" |  | 2025-05
001291 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0024 | 0 | 131242-WSW41-RT-PM-0024 | 2025-05-13 | C4B Monthly Progress Report Number No.24 (04 25) | Approved with Comments No resubmission is required | 2025-06-10 | 2025-05-16 | 3 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001291 | 2025-05-13 | 2025-05-13 | 0 | AWC | Approved with Comments | 1 | "C4B Monthly Progress Report Number No.24 (04 25)" |  | 2025-05
001292 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0035 | 0 | 131242-WSW41-QA-C-0035 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 | For information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001292 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " |  | 2025-05
001293 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0036 | 0 | 131242-WSW41-QA-C-0036 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024 | For information | 2025-06-10 | 2025-06-02 | 14 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001293 | 2025-05-13 | 2025-05-13 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024" |  | 2025-05
001294 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0037 | 0 | 131242-WSW41-QA-C-0037 | 2025-05-14 | Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025 | For information | 2025-06-11 | 2025-06-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001294 | 2025-05-14 | 2025-05-14 | 0 | INF | For Information | 1 | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" |  | 2025-05
001295 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0030 | 0 | 131242-WSW41-SP-C-0030 | 2025-05-14 | Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information | 2025-06-11 | 2025-06-02 | 13 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001295 | 2025-05-14 | 2025-05-14 | 0 | INF | For Information | 1 | "Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) " |  | 2025-05
001296 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BS | 0001 | 0 | 131242-WST02-DS-BS-0001 | 2025-05-15 | Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories) | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001296 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" |  | 2025-05
001297 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BF | 0002 | 0 | 131242-WST02-DS-BF-0002 | 2025-05-15 | Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories) | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001297 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" |  | 2025-05
001298 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BF | 0003 | 0 | 131242-WST02-DS-BF-0003 | 2025-05-15 | Data Sheets for Clean Gas System | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001298 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | " Data Sheets for Clean Gas System" |  | 2025-05
001299 | 00 | Karthik | BS | NA | 131242 | WST02 | DR | BF | 5000 | 0 | 131242-WST02-DR-BF-5000 | 2025-05-15 | Typical installation drawing for PA & Fire Alarm System | Approved with Comments | 2025-06-12 | 2025-05-25 | 7 | Approved with Comments | YES | 2025-06-12 | NO | Resubmitted | 0 |  |  | 001299&&001306 | 2025-05-15 | 2025-05-18 | A | AWC | Approved | 2 | "Typical installation drawing for PA & Fire Alarm System" && "Typical Installation drawing For PA & Fire Alarm" |  | 2025-05
001300 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0030 | 0 | 131242-WST02-QA-E-0030 | 2025-05-15 | Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-12 | 2025-06-09 | 17 | Approved with Comments | YES | 2025-06-27 | NO | Resubmitted | 0 |  |  | 001300 | 2025-05-15 | 2025-05-15 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) " |  | 2025-05
001301 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | BS | 1398 | 0 | 131242-WST02-DS-BS-1398 | 2025-05-15 | Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance) | Rev 0: For Information | 2025-06-12 | 2025-06-23 | 27 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001301 | 2025-05-15 | 2025-05-15 | 0 | INF | For Information | 1 | "Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance)" |  | 2025-05
001302 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0038 | 0 | 131242-WSW41-QA-C-0038 | 2025-05-18 | Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025 | For Information | 2025-06-13 | 2025-06-04 | 12 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001302 | 2025-05-18 | 2025-05-18 | 0 | INF | For Information | 1 | "Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025" |  | 2025-05
001303 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0031 | 0 | 131242-WSW41-QA-E-0031 | 2025-05-18 | FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN) | Rev 0: Approved | 2025-06-13 | 2025-05-29 | 8 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001303 | 2025-05-18 | 2025-05-18 | 0 | APP | Approved | 1 | "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" |  | 2025-05
001304 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0012 | 0 | 131242-WSW41-QA-I-0012 | 2025-05-18 | Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-13 | 2025-07-14 | 40 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001304 | 2025-05-18 | 2025-05-18 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" |  | 2025-05
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7001 | A | 131242-WST02-DR-BF-7001 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 41 |  |  | 000190&&001305 | 2023-11-15 | 2025-05-18 | A | AWC | Approved with Comments | 3 | "Hose Reel (SSN Area)" && "Panel GA & Wiring drawing for BS Systems" |  | 2025-05
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-BF-7002 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 000661&&001305 | 2024-08-20 | 2025-06-19 | A.1 | AWC | Approved with Comments | 3 | "SSN External Fire Hydrant Layout & Details " && "Panel GA & Wiring drawing for BS Systems" |  | 2025-05
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7004 | A | 131242-WST02-DR-BF-7004 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001305 | 2025-05-18 | 2025-05-18 | A | AWC | Approved with Comments | 1 | "Panel GA & Wiring drawing for BS Systems" |  | 2025-05
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7005 | A | 131242-WST02-DR-BF-7005 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001305 | 2025-05-18 | 2025-05-18 | A | AWC | Approved with Comments | 1 | "Panel GA & Wiring drawing for BS Systems" |  | 2025-05
001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7104 | A | 131242-WST02-DR-BF-7104 | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | 25 | Approved with Comments | YES | 2025-07-11 | NO | Resubmitted | 0 |  |  | 001305 | 2025-05-18 | 2025-05-18 | A | AWC | Approved with Comments | 1 | "Panel GA & Wiring drawing for BS Systems" |  | 2025-05
001306 | 00 | Karthik | BS | NA | 131242 | WST02 | DR | BF | 5000 | A | 131242-WST02-DR-BF-5000 | 2025-05-18 | Typical Installation drawing For PA & Fire Alarm | Approved | 2025-06-13 | 2025-06-30 | 30 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001299&&001306 | 2025-05-15 | 2025-05-18 | A | APP | Approved | 2 | "Typical installation drawing for PA & Fire Alarm System" && "Typical Installation drawing For PA & Fire Alarm" |  | 2025-05
001307 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | NA | NA | Fabrication drawing-NA-NA-NA-NA | 2025-05-18 | ST609 SSN-PR001 Fabrication Drawing and Model | For information. Subject mentioned 'model' however no models were included in the submittal. Also, all drawings are not as per TWRP standard, including file naming and title block. | 2025-06-13 | 2025-08-05 | 56 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001307&&001364&&001365&&001366 | 2025-05-18 | 2025-06-12 | NA | INF | For Information | 4 | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " |  | 2025-05
001308 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0017 | 0 | 131242-WSD11-CL-P-0017 | 2025-05-19 | G1 Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-07-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001308 | 2025-05-19 | 2025-08-25 | 1 | AWC | Approved with Comments | 2 | "G1 Booster Pump Hydraulics Calculation " |  | 2025-05
001308 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0017 | 1 | 131242-WSD11-CL-P-0017 | 2025-08-25 | G1 Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-12 |  | 155 | Awaiting S.O.'s response | YES | 2025-10-10 | NO | Overdue | 0 |  |  | 001308 | 2025-05-19 | 2025-08-25 | 1 | PEN | Approved with Comments | 2 | "G1 Booster Pump Hydraulics Calculation " |  | 2025-08
001309 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0018 | 0 | 131242-WSD11-CL-P-0018 | 2025-05-19 | G2D Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-07-07 | 35 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001309 | 2025-05-19 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "G2D Booster Pump Hydraulics Calculation " |  | 2025-05
001309 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0018 | 1 | 131242-WSD11-CL-P-0018 | 2025-07-28 | G2D Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-15 |  | 175 | Awaiting S.O.'s response | YES | 2025-09-12 | NO | Overdue | 0 |  |  | 001309 | 2025-05-19 | 2025-07-28 | 1 | PEN | Approved with Comments | 2 | "G2D Booster Pump Hydraulics Calculation " |  | 2025-07
001310 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5711 | 0 | 131242-WST02-DS-M-5711 | 2025-05-19 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-05-30 | 9 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001310 | 2025-05-19 | 2025-07-15 | 1 | AWC | Approved with Comments | 2 | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" |  | 2025-05
001310 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5711 | 1 | 131242-WST02-DS-M-5711 | 2025-07-15 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | 184 | Awaiting S.O.'s response | YES | 2025-09-01 | NO | Overdue | 0 |  |  | 001310 | 2025-05-19 | 2025-07-15 | 1 | PEN | Approved with Comments | 2 | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" |  | 2025-07
001311 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0004 | 0 | 131242-WSD11-RT-P-0004 | 2025-05-19 | H2S Dispersion Simulation And Risk Assessement Report | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-02 | 32 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001311 | 2025-05-19 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "H2S Dispersion Simulation And Risk Assessement Report" |  | 2025-05
001311 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0004 | 1 | 131242-WSD11-RT-P-0004 | 2025-07-28 | H2S Dispersion Simulation And Risk Assessement Report | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-15 | 2025-09-24 | 42 | Approved with Comments | YES | 2025-10-14 | NO | Resubmitted | 0 |  |  | 001311 | 2025-05-19 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "H2S Dispersion Simulation And Risk Assessement Report" |  | 2025-07
001312 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501 | A | 131242-WSD11-DR-S-3501 | 2025-05-19 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-10 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001312&&001363 | 2025-05-19 | 2025-06-12 | F | NAP | Not Approved | 2 | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" |  | 2025-05
001312 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501_Endorsed | - | 131242-WSD11-DR-S-3501_Endorsed | 2025-05-19 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-10 | 38 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001312 | 2025-05-19 | 2025-05-19 | - | NAP | Not Approved | 1 | "Revised Design of THP Steel Structure Plinths" |  | 2025-05
001312 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | Comment reply | NA | 131242-WSD11-DR-S-Comment reply | 2025-08-22 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-09-17 | 18 | For Information | NO |  | YES | Resubmitted | 0 |  |  | 001312 | 2025-08-22 | 2025-08-22 | NA | INF | For Information | 1 | "Revised Design of THP Steel Structure Plinths" |  | 2025-08
001313 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0013 | 0 | 131242-WSW41-QA-I-0013 | 2025-05-20 | Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-17 | 2025-07-14 | 39 | Approved with Comments | YES | 2025-08-01 | NO | Resubmitted | 0 |  |  | 001313 | 2025-05-20 | 2025-05-20 | 0 | AWC | Approved with Comments | 1 | "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" |  | 2025-05
001314 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2008 | 0 | 131242-WSW41-VI-M-2008 | 2025-05-20 | Preliminary Design and Vendor Approval for Solenoid Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-17 | 2025-06-20 | 23 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001314 | 2025-05-20 | 2025-07-28 | 1 | AWC | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Solenoid Valve " |  | 2025-05
001314 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2008 | 1 | 131242-WSW41-VI-M-2008 | 2025-07-28 | Preliminary Design and Vendor Approval for Solenoid Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-15 |  | 175 | Awaiting S.O.'s response | YES | 2025-09-12 | NO | Overdue | 0 |  |  | 001314 | 2025-05-20 | 2025-07-28 | 1 | PEN | Approved with Comments | 2 | "Preliminary Design and Vendor Approval for Solenoid Valve " |  | 2025-07
001315 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0081 | 0 | 131242-WSD11-QA-M-0081 | 2025-05-23 | FAT Report for THP Sludge Cooler C Stage 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-20 | 2025-07-02 | 28 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001315 | 2025-05-23 | 2025-12-02 | 1 | AWC | Approved | 2 | "FAT Report for THP Sludge Cooler C Stage 2" |  | 2025-05
001315 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0081 | 1 | 131242-WSD11-QA-M-0081 | 2025-12-02 | FAT Report for THP Sludge Cooler C Stage 2 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | 15 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001315 | 2025-05-23 | 2025-12-02 | 1 | APP | Approved | 2 | "FAT Report for THP Sludge Cooler C Stage 2" |  | 2025-12
001316 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0074 | 0 | 131242-WSW41-QA-M-0074 | 2025-05-23 | Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson) | NA | 2025-06-20 | 2025-09-02 | 72 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001316 | 2025-05-23 | 2025-05-23 | 0 | APP | Approved | 1 | "Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson)" |  | 2025-05
001317 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0031 | 0 | 131242-WSD11-QA-E-0031 | 2025-05-23 | SAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-20 | 2025-07-23 | 43 | Approved with Comments | YES | 2025-08-12 | NO | Resubmitted | 0 |  |  | 001317 | 2025-05-23 | 2025-05-23 | 0 | AWC | Approved with Comments | 1 | "SAT Report for WSD11-MCC-0101A&B" |  | 2025-05
001318 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0002 | 0 | 131242-WST02-OM-M-0002 | 2025-05-26 | O&M Manual for Aeration Blower | NA | 2025-06-23 |  | 220 | Awaiting S.O.'s response | YES | 2025-07-11 | NO | Overdue | 0 |  |  | 001318 | 2025-05-26 | 2025-05-26 | 0 | PEN | Awaiting S.O.'s response | 1 | "O&M Manual for Aeration Blower" |  | 2025-05
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5624 | A | 131242-WST02-DR-M-5624 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | NAP | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" |  | 2025-05
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5625 | A | 131242-WST02-DR-M-5625 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | NAP | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" |  | 2025-05
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5624 | 0 | 131242-WST02-DS-M-5624 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-05-26 | 0 | NAP | Not Approved | 1 | "Data Sheet and Drawing for Davit Crane" |  | 2025-05
001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5625 | 0 | 131242-WST02-DS-M-5625 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | 86 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001319 | 2025-05-26 | 2025-05-26 | 0 | NAP | Not Approved | 1 | "Data Sheet and Drawing for Davit Crane" |  | 2025-05
001319 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5624 | B | 131242-WST02-DR-M-5624 | 2025-11-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-12-16 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | PEN | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" |  | 2025-11
001319 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5625 | B | 131242-WST02-DR-M-5625 | 2025-11-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-12-16 |  | 88 | Awaiting S.O.'s response | YES | 2026-01-13 | NO | Overdue | 0 |  |  | 001319 | 2025-05-26 | 2025-11-26 | B | PEN | Not Approved | 2 | "Data Sheet and Drawing for Davit Crane" |  | 2025-11
001320 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0083 | 0 | 131242-WSW41-QA-M-0083 | 2025-05-26 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-23 | 2025-07-31 | 48 | Approved with Comments | NO |  | YES | Resubmitted | 0 |  |  | 001320 | 2025-05-26 | 2025-10-01 | 1 | AWC | Approved with Comments | 2 | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " |  | 2025-05
001320 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0083 | 1 | 131242-WSW41-QA-M-0083 | 2025-10-01 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 |  | 128 | Awaiting S.O.'s response | YES | 2025-11-18 | NO | Overdue | 0 |  |  | 001320 | 2025-05-26 | 2025-10-01 | 1 | PEN | Approved with Comments | 2 | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " |  | 2025-10
001321 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0032 | 0 | 131242-WSW41-MS-C-0032 | 2025-05-26 | MSRA and SWP for RC Sub & Super-Structural Work (TechGems) | Rev 0: Approved | 2025-06-23 | 2025-06-20 | 19 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001321 | 2025-05-26 | 2025-05-26 | 0 | APP | Approved | 1 | "MSRA and SWP for RC Sub & Super-Structural Work (TechGems)" |  | 2025-05
001322 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | MS | M | 0008 | 0 | 131242-WSD11-MS-M-0008 | 2025-05-27 | Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building | Rev 0: Approved | 2025-06-24 | 2025-08-11 | 54 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001322 | 2025-05-27 | 2025-05-27 | 0 | APP | Approved | 1 | "Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building " |  | 2025-05
001323 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0084 | 0 | 131242-WST02-QA-M-0084 | 2025-05-28 | FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank) | Rev 0: Approved | 2025-06-25 | 2025-07-02 | 25 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001323 | 2025-05-28 | 2025-05-28 | 0 | APP | Approved | 1 | "FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank)" |  | 2025-05
001324 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0085 | 0 | 131242-WSD11-QA-M-0085 | 2025-05-28 | FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps | Rev 0: Approved | 2025-06-25 | 2025-07-04 | 27 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001324 | 2025-05-28 | 2025-05-28 | 0 | APP | Approved | 1 | "FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps" |  | 2025-05
001325 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-A-0002 | 2025-05-28 | Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. | Approved | 2025-06-25 | 2025-06-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000781&&001325 | 2024-10-26 | 2025-05-28 | 0 | APP | Approved | 2 | "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " |  | 2025-05
001326 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | CL | A | 0002 | 0 | 131242-WST02-CL-A-0002 | 2025-05-28 | Siphonic System Schematic and Calculation | Approved | 2025-06-25 | 2025-07-09 | 30 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 001326 | 2025-05-28 | 2025-05-28 | 0 | APP | Approved | 1 | "Siphonic System Schematic and Calculation" |  | 2025-05
001327 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-A-0004 | 2025-05-28 | Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. | Approved | 2025-06-25 | 2025-06-04 | 5 | Approved | NO |  | YES | Resubmitted | 0 |  |  | 000855&&001327 | 2024-11-28 | 2025-05-28 | 0 | APP | Approved | 2 | "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1541 | A | 131242-WSD11-DR-IP-1541 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1542 | A | 131242-WSD11-DR-IP-1542 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1543 | A | 131242-WSD11-DR-IP-1543 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1544 | A | 131242-WSD11-DR-IP-1544 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1545 | A | 131242-WSD11-DR-IP-1545 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1546 | A | 131242-WSD11-DR-IP-1546 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1547 | A | 131242-WSD11-DR-IP-1547 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1548 | A | 131242-WSD11-DR-IP-1548 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1549 | A | 131242-WSD11-DR-IP-1549 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1550 | A | 131242-WSD11-DR-IP-1550 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1551 | A | 131242-WSD11-DR-IP-1551 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1552 | A | 131242-WSD11-DR-IP-1552 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1553 | A | 131242-WSD11-DR-IP-1553 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1554 | A | 131242-WSD11-DR-IP-1554 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1555 | A | 131242-WSD11-DR-IP-1555 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1556 | A | 131242-WSD11-DR-IP-1556 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1557 | A | 131242-WSD11-DR-IP-1557 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328&&001897 | 2025-05-28 | 2025-12-15 | A | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" && "THP FOIP-0001 GA & Wiring Drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1091 | A | 131242-WSD11-DR-IP-1091 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1092 | A | 131242-WSD11-DR-IP-1092 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1093 | A | 131242-WSD11-DR-IP-1093 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1094 | A | 131242-WSD11-DR-IP-1094 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1095 | A | 131242-WSD11-DR-IP-1095 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1096 | A | 131242-WSD11-DR-IP-1096 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1097 | A | 131242-WSD11-DR-IP-1097 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1098 | A | 131242-WSD11-DR-IP-1098 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1099 | A | 131242-WSD11-DR-IP-1099 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1100 | A | 131242-WSD11-DR-IP-1100 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1101 | A | 131242-WSD11-DR-IP-1101 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1102 | A | 131242-WSD11-DR-IP-1102 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1103 | A | 131242-WSD11-DR-IP-1103 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1104 | A | 131242-WSD11-DR-IP-1104 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1105 | A | 131242-WSD11-DR-IP-1105 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1106 | A | 131242-WSD11-DR-IP-1106 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1107 | A | 131242-WSD11-DR-IP-1107 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1108 | A | 131242-WSD11-DR-IP-1108 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1109 | A | 131242-WSD11-DR-IP-1109 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1110 | A | 131242-WSD11-DR-IP-1110 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1111 | A | 131242-WSD11-DR-IP-1111 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1112 | A | 131242-WSD11-DR-IP-1112 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1113 | A | 131242-WSD11-DR-IP-1113 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1114 | A | 131242-WSD11-DR-IP-1114 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1115 | A | 131242-WSD11-DR-IP-1115 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1116 | A | 131242-WSD11-DR-IP-1116 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1117 | A | 131242-WSD11-DR-IP-1117 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1118 | A | 131242-WSD11-DR-IP-1118 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1119 | A | 131242-WSD11-DR-IP-1119 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1120 | A | 131242-WSD11-DR-IP-1120 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1121 | A | 131242-WSD11-DR-IP-1121 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1122 | A | 131242-WSD11-DR-IP-1122 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1123 | A | 131242-WSD11-DR-IP-1123 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1124 | A | 131242-WSD11-DR-IP-1124 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1125 | A | 131242-WSD11-DR-IP-1125 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1031 | A | 131242-WSD11-DR-IP-1031 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1032 | A | 131242-WSD11-DR-IP-1032 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1033 | A | 131242-WSD11-DR-IP-1033 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1034 | A | 131242-WSD11-DR-IP-1034 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1035 | A | 131242-WSD11-DR-IP-1035 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1036 | A | 131242-WSD11-DR-IP-1036 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1037 | A | 131242-WSD11-DR-IP-1037 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1038 | A | 131242-WSD11-DR-IP-1038 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1039 | A | 131242-WSD11-DR-IP-1039 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1040 | A | 131242-WSD11-DR-IP-1040 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1041 | A | 131242-WSD11-DR-IP-1041 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1042 | A | 131242-WSD11-DR-IP-1042 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1043 | A | 131242-WSD11-DR-IP-1043 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1044 | A | 131242-WSD11-DR-IP-1044 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1045 | A | 131242-WSD11-DR-IP-1045 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1046 | A | 131242-WSD11-DR-IP-1046 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1047 | A | 131242-WSD11-DR-IP-1047 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1048 | A | 131242-WSD11-DR-IP-1048 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1049 | A | 131242-WSD11-DR-IP-1049 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1050 | A | 131242-WSD11-DR-IP-1050 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1051 | A | 131242-WSD11-DR-IP-1051 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1052 | A | 131242-WSD11-DR-IP-1052 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1053 | A | 131242-WSD11-DR-IP-1053 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1054 | A | 131242-WSD11-DR-IP-1054 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1055 | A | 131242-WSD11-DR-IP-1055 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1056 | A | 131242-WSD11-DR-IP-1056 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1057 | A | 131242-WSD11-DR-IP-1057 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1058 | A | 131242-WSD11-DR-IP-1058 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1059 | A | 131242-WSD11-DR-IP-1059 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1060 | A | 131242-WSD11-DR-IP-1060 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1061 | A | 131242-WSD11-DR-IP-1061 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1062 | A | 131242-WSD11-DR-IP-1062 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1063 | A | 131242-WSD11-DR-IP-1063 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1064 | A | 131242-WSD11-DR-IP-1064 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1065 | A | 131242-WSD11-DR-IP-1065 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-05-28 | A | NAP | Not Approved | 1 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1001 | A | 131242-WSD11-DR-IP-1001 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1002 | A | 131242-WSD11-DR-IP-1002 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1003 | A | 131242-WSD11-DR-IP-1003 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1004 | A | 131242-WSD11-DR-IP-1004 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1005 | A | 131242-WSD11-DR-IP-1005 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1006 | A | 131242-WSD11-DR-IP-1006 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1007 | A | 131242-WSD11-DR-IP-1007 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1008 | A | 131242-WSD11-DR-IP-1008 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1009 | A | 131242-WSD11-DR-IP-1009 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1010 | A | 131242-WSD11-DR-IP-1010 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1011 | A | 131242-WSD11-DR-IP-1011 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1012 | A | 131242-WSD11-DR-IP-1012 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1013 | A | 131242-WSD11-DR-IP-1013 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1014 | A | 131242-WSD11-DR-IP-1014 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1015 | A | 131242-WSD11-DR-IP-1015 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1016 | A | 131242-WSD11-DR-IP-1016 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1017 | A | 131242-WSD11-DR-IP-1017 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1018 | A | 131242-WSD11-DR-IP-1018 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1019 | A | 131242-WSD11-DR-IP-1019 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1020 | A | 131242-WSD11-DR-IP-1020 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | NAP | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3001 | A | 131242-WSD11-DR-IP-3001 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3002 | A | 131242-WSD11-DR-IP-3002 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3003 | A | 131242-WSD11-DR-IP-3003 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3004 | A | 131242-WSD11-DR-IP-3004 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3005 | A | 131242-WSD11-DR-IP-3005 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3006 | A | 131242-WSD11-DR-IP-3006 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3007 | A | 131242-WSD11-DR-IP-3007 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3008 | A | 131242-WSD11-DR-IP-3008 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3009 | A | 131242-WSD11-DR-IP-3009 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3010 | A | 131242-WSD11-DR-IP-3010 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3011 | A | 131242-WSD11-DR-IP-3011 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3012 | A | 131242-WSD11-DR-IP-3012 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3013 | A | 131242-WSD11-DR-IP-3013 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3014 | A | 131242-WSD11-DR-IP-3014 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3015 | A | 131242-WSD11-DR-IP-3015 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3016 | A | 131242-WSD11-DR-IP-3016 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3017 | A | 131242-WSD11-DR-IP-3017 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3018 | A | 131242-WSD11-DR-IP-3018 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3019 | A | 131242-WSD11-DR-IP-3019 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3020 | A | 131242-WSD11-DR-IP-3020 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3021 | A | 131242-WSD11-DR-IP-3021 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3022 | A | 131242-WSD11-DR-IP-3022 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3023 | A | 131242-WSD11-DR-IP-3023 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3024 | A | 131242-WSD11-DR-IP-3024 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3025 | A | 131242-WSD11-DR-IP-3025 | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | 69 | Not Approved | NO |  | YES | Resubmitted | 0 |  |  | 001230&&001328 | 2025-05-28 | 2025-11-11 | B | NAP | Approved with Comments | 2 | "THP WAP FFOTP_GA & Wiring Diagram" && "THP ICA GA & Wiring drawings" |  | 2025-05
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1001 | B | 131242-WSD11-DR-IP-1001 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1002 | B | 131242-WSD11-DR-IP-1002 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1003 | B | 131242-WSD11-DR-IP-1003 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1004 | B | 131242-WSD11-DR-IP-1004 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1005 | B | 131242-WSD11-DR-IP-1005 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1006 | B | 131242-WSD11-DR-IP-1006 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1007 | B | 131242-WSD11-DR-IP-1007 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1008 | B | 131242-WSD11-DR-IP-1008 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10
001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1009 | B | 131242-WSD11-DR-IP-1009 | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | 0 | Approved with Comments | YES | 2025-10-30 | NO | Resubmitted | 0 |  |  | 001328 | 2025-05-28 | 2025-10-28 | B | AWC | Approved with Comments | 2 | "THP ICA GA & Wiring drawings" |  | 2025-10